## T1 Project Pivot Table
Phase | (All)
Row Labels | Sum of Total Project Budget | Sum of Leveraging Funds | Sum of T1-Actuals/Project Budget
3 | 32102126.8687 | 8133846 | 23709971.0388
4 | 19745598.3287 | 3063207.6667 | 16682391.3288
2 | 17694383.2638 | 5527807 | 13019617.7737
1 | 17663211.5738 | 6631875 | 12184377.8438
5 | 13457736.8454 | 2992514.6333 | 10553498.0988
8 | 8508766.2854 | 66840.6667 | 8441925.6188
6 | 6533090.5354 | 2219507.3333 | 4259375.6387
7 | 2027087.6187 | 16875 | 2010212.6187
Grand Total | 117732001.32 | 28652473.3 | 90861369.96
Notes:
The total T1 bond program includes $100M in bond sales plus approx $3M in interest, for a total of $103M.
Not shown here is approx. $12.1M in staffing, equipment, supplies, and services.

## T1 Projects
Council District | Phase | Project Code | Project Name | Total Project Budget | T1-Actuals/Project Budget | Leveraging Funds | Project Completed
1 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
2 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
3 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
4 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
5 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
6 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
7 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
8 | 1 | PRWT119010 | Citywide Restroom Assessment | 14754.1875 | 14754.1875 |  | FY21
4 | 1 | PWT1CB1902 | Old City Hall/Vet's Building | 376000 | 376000 |  | FY21
2 | 1 | PRWT119003 | Frances Albrier Community Center | 230281.79 | 230281.79 |  | FY21
1 | 1 | PRWT119014 | Tom Bates Fieldhouse/Restroom | 304293 | 304293 |  | FY21
8 | 1 | PRWT119016 | Willard Clubhouse | 150720.75 | 150720.75 |  | FY21
5 | 1 | PRWT119005 | Live Oak Community Center | 7441689 | 6354689.33 | 1087000 | FY21
4 | 1 | PWT1CB1901/PWENCB1801 | North Berkeley Senior Center | 10823332.46 | 8848332.46 | 1975000 | Still Ongoing
2 | 1 | PRWT119011 | Strawberry Creek Park Restroom | 1057127 | 816126.65 | 241000 | FY21
3 | 1 | PWENCB1405 | Berkeley Mental Health Building | 7793166.25 | 1932611.25 | 5860555 | FY22
2 | 1 | PWT1EL1910 | Corporation Yard (Electrical) | 493588.5 | 493588.5 |  | FY21
1 | 1 | PWT1EL1910 | Marina Corporation Yard (Electrical) | 493588.5 | 493588.5 |  | FY22
2 | 1 | PWT1EL1911 | Berkeley Health Clinic (Electrical) | 7000 | 7000 |  | FY19
4 | 1 | PWT1CB1912 | Public Safety Building (HVAC) | 4620 | 4620 |  | FY20
2 | 1 | PRWT119001 | Aquatic Park Tide Tubes | 780770 | 405770.24 | 375000 | FY21
1 | 1 | PRWT119007 | Municipal Pier | 133421.5 | 236462.77 |  | FY22
2 | 1 | PRWT119007 | Municipal Pier | 133421.5 | 236462.77 |  | FY21
6 | 1 | PWT1GI1905 | Rose Garden Drainage | 189477 | 135270.9 |  | FY20
6 | 1 | PRWT119012 | Rose Garden Tennis, Pathways | 4498902 | 2682901.87 | 1816000 | FY22
1 | 1 | PWENSD1819 | Cordonices Creek Restoration | 1026019 | 23019 | 1003000 | FY20
1 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
2 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
3 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
4 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
5 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
6 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
7 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
8 | 1 | PRWT119002 | Citywide Irrigation System | 66032.6813 | 66032.6813 |  | FY21
3 | 1 | PRWT119004 | Grove Park Fields | 422449 | 164139.17 |  | Still Ongoing
2 | 1 | PRWT119008 | George Florence Play | 606897 | 605897.3 | 1000 | FY21
2 | 1 | PRWT119009 | San Pablo Play and Tennis | 2568325 | 1214325.05 | 1354000 | FY22
1 | 1 | 17WF01 | Tom Bates Field Turf Replacement | 1460220 | 311220 | 1149000 | FY18
1 | 1 | PWT1GI1906 | Green Infrastructure | 35675.75 | 35675.75 |  | FY21
2 | 1 | PWT1GI1906 | Green Infrastructure | 35675.75 | 35675.75 |  | FY21
3 | 1 | PWT1GI1906 | Green Infrastructure | 35675.75 | 35675.75 |  | FY21
7 | 1 | PWT1GI1906 | Green Infrastructure | 35675.75 | 35675.75 |  | FY21
4 | 1 | PWT1ST1907 | Adeline and Hearst | 2085137 | 1942137 | 143000 | FY21
3 | 1 | PWT1ST1907 | Adeline and Hearst | 2085137 | 1942137 | 143000 | FY21
2 | 1 | PWT1ST1908 | Monterey and Ward | 1988605.9 | 1907605.9 | 81000 | FY22
5 | 1 | PWT1ST1908 | Monterey and Ward | 1988605.9 | 1907605.9 | 81000 | FY22
1 | 1 | PRWT119006 | University Ave, Marina Blvd, Spinnaker | 4126846.955 | 1442346.955 | 2684500 | Still Ongoing
2 | 1 | PRWT119006 | University Ave, Marina Blvd, Spinnaker | 4126846.955 | 1442346.955 | 2684500 | Still Ongoing
3 | 2 | PRWT122001 | MLK Jr. Youth Services Center | 7287250 | 7000000 | 287250
3 | 2 | PWT1CB2201 | South Berkeley Senior Center | 3000000 | 3000000
3 | 2 | PRWT122002 | African American Holistic Resource Center | 7169480 | 7000000 | 169480
7 | 2 | PWT1CB2202 | Restrooms in the ROW (2-3)-Telegraph/ Channing | 450000 | 450000
3 | 2 | PWT1CB2202 | Restrooms in the ROW (2-3) Adeline/ Alcatraz | 450000 | 450000
2 | 2 | PWT1CB2202 | Restrooms in the ROW (2-3) San Pablo | 450000 | 450000
1 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
2 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
3 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
4 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
5 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
6 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
7 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
8 | 2 | PRWT122003 | Cazadero Dining Hall & ADA Improvements | 50000 | 50000
8 | 2 | PRWT122004 | Willard Clubhouse/Restroom Replacement | 7000000 | 7000000
1 | 2 | PRWT122005 | Tom Bates Restroom/ Community Space | 3025000 | 2900000 | 125000
1 | 2 | PRWT122006 | Harrison Park - Restroom Renovation | 450000 | 450000
1 | 2 | PRWT122007 | Ohlone Park - New Restroom and Lighting | 1200000 | 1200000
1 | 2 | PRWPK20003 | Ohlone (Milvia) Ages 2-5, 5-12, Garden Mural, Exercise | 1103500 | 500000 | 903500
5 | 2 | PRWPK19004 | John Hinkel Lower Ages 2-12, picnic, parking | 1732732.41 | 400000 | 1332732.41
3 | 2 | PRWT119004 | Grove Park Ages 2-5, 5-12 | 2617557 | 960871 | 1656686
2 | 2 | PRWT122009 | Aquatic Park Tide Tubes Clean out, Phase 1B | 524432 | 500000 | 24432
4 | 2 | PRWPK21008 | Civic Center Park – Turtle Garden | 891666 | 300000 | 591666
5 | 2 | PRWT122011 | King Pool Tile and Plaster Replacement | 350000 | 350000 | 88274.89
1 | 2 | PRWT122012 | Piling Replacements | 600000 | 600000 | 750000
2 | 2 | PRWT122012 | Piling Replacements | 600000 | 600000 | 750000
1 | 2 | PRWT122013 | D and E Dock Replacement | 500000 | 500000
1 | 2 | PRWT122014 | K Dock Restroom Renovation | 400000 | 400000
1 | 2 | PRWT122015 | Cesar Chavez Park - New Restroom (on Spinnaker) | 350000 | 350000
1 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
2 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
3 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
4 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
5 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
6 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
7 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
8 | 2 | PWT1ST2201 | T1 Streets Contribution - Annual Street Paving Impvmnts | 843750 | 843750
1 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
2 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
3 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
4 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
5 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
6 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
7 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
8 | 2 | PWT1ST2202 | Bollard Conversion to Landscaping | 18750 | 18750
1 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
2 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
3 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
4 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
5 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
6 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
7 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
8 | 2 | PWT1SW2201 | Sidewalks Maintenance & Safety Repairs | 248125 | 231250 | 16875
5 | 2 | PWT1SW2202 | Pathway Repairs/Improvements | 116631.6667 | 66666 | 49965.6667
6 | 2 | PWT1SW2202 | Pathway Repairs/Improvements | 116631.6667 | 66666 | 49965.6667
8 | 2 | PWT1SW2202 | Pathway Repairs/Improvements | 116633.6667 | 66668 | 49965.6667
4 | 2 | PWENSD2103 | Storm Drain Impv-Marin, Virginia, and Spruce | 486666 | 150000 | 336666.6667
5 | 2 | PWENSD2103 | Storm Drain Impv-Marin, Virginia, and Spruce | 486666 | 150000 | 336666.6667
6 | 2 | PWENSD2103 | Storm Drain Impv-Marin, Virginia, and Spruce | 486668 | 150000 | 336666.6667
5 | 2 | PWT1SD2101 | John Hinkel Storm Drain Repairs | 100000 | 100000
4 | 2 | PWT1CB2203 | 1947 Center Street Improvements | 1800000 | 1800000
4 | 2 | PWT1CB2204 | Fire Station #2 | 1536765 | 1536765
1 | 2 | PWT1CB2205 | Fire Station #6 | 1213235 | 1213235
2 | 2 | PWT1CB2212 | Corporation Yard-Deferred Mtc - Gate, Paving, Parking, Fuel Island | 350000 | 350000
2 | 2 | PWT1CB2210 | Corporation Yard-Wash Station Compliance | 200000 | 200000
2 | 2 | PWT1CB2209 | Corporation Yard-Green Room Lockers, Bathroom, Training Room, Floor, Cabinets | 1700000 | 1700000
2 | 2 | PWT1CB2211 | Corporation Yard-Storage Room - Roof Repair Bldg H | 600000 | 600000
7 | 2 | PWT1CB2207 | Oxford & Telegraph Channing Garage Restrooms | 300000 | 300000
4 | 2 | PWT1CB2208 | Emergency Power Supply Solar Batteries | 500000 | 500000
Note on F15: Quesada, Christina: Proje ct ongoing
Note on C18: Quesada, Christina: combined projects for Mairna Corpyard and Corporation yard
Note on D18: Quesada, Christina: combined project with Marina Coryard
Note on D67: Quesada, Christina: Merged project with Ohlone Park Lighting PRWT122010, included actuals from FY22