## Ariba On Demand - Known Issues
MyFloridaMarketPlace Known Issues as of Aug. 19, 2022
New? | SIR Number | Master Ticket | Title | Description | Impact to Customers Temporary Fix (if available) | Status | Functional Area
Yes | 3769 | CS0031434 | Encumbrance number and line number are not displayed on an invoice reconciliation when the Exception Handler is also assigned the Invoice Manager group on Invoice Reconciliation | Encumbrance number and line number are not displayed on an invoice reconciliation when the Exception Handler is also assigned the Invoice Manager group on Invoice Reconciliation. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
Yes | 3767 | CS0028663 | User Maintenance eForm Email Address Validation does not allow single quote | UM2470 could not be submitted do to a single quote in the User's Email Address. | Users with a single quote in their Email Address cannot be updated via the User Maintenance eForm. System Administrators should reach out to the Helpdesk in these cases for MFMP to make the desired updates. | Investigation | System Administration
Yes | 3766 | CS0030329 | Agency customer encountered an error on three address maintenance eForm submissions | Address Maintenance eForm encountered issues submitting AM97, AM98, and AM102. The issue is partially due to the new addresses including spaces or parenthesis in the name. | When creating new addresses via the Address Maintenance eForm, do not use spaces or parenthesis in the Address Name. | Investigation | System Administration
Yes | 3765 | CS0030360 | Vendor W9 Status Failed to Update in AOD | A vendor had an updated W9 status of 'Valid W-9 on File' in VIP, while AOD showed a W9 status of 'No W-9 on File'. We expect both systems to be in sync. | The agency customer is able to submit the Purchase Order since the vendor's W9 status is valid in FLAIR. MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
Yes | 3764 | CS0025448 | Accounting Errors when reconciling E-Invoices for Staples Business Advantage | Valid Accounting cannot be selected Staples Business Advantage eInvoices. | Users should create PO-Based Invoices to invoice against Staples Business Advantage | Investigation | Buying and Invoicing
Yes | 3761 | CS0030432 | Encumbrance rollback for PR5629-V2 not triggered after a single line was not successfully encumbered | PR5629-V2 was stuck in Ordering status in AOD. Upon review of change order, one of the encumbrance lines did not successfully update in FLAIR. We expected the encumbrance rollback to occur, did not see the updates in the system. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
Yes | 3760 | CS0031008 | Contract Encumbrance Line field on IRs Allows Greater than 4 Digits | The Contract Encumbrance Line Number field was manually keyed in with the Encumbrance Number (C#####). The Contract Encumbrance Line Number field should only contain 4 digits (####). | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
Yes | 3759 | CS0031005 | Changes to Multiple Split Accounting Percentages causing Encumbrance Lines to not record properly between MFMP AOD and FLAIR | The toggling of percentages between splits 3 & 4 on the change order for C05697 (PR35116-V2) caused Enc Line 0003 to be deleted from AOD (but not communicated to FLAIR) & new Enc line 0007 to be created (with the same percentage as original Enc Line 0003). | Customers should recreate the affected PR with the intended split accounting percentages and cancel the original PR to release the encumbrance for all lines. | Investigation | Integration/Interfaces
Yes | 3758 | CS0030880 | Add Statewide Approvers created via User Maintenance eForm to Statewide purchasing unit | Currently, user profiles created or updated via the User Maintenance eForm to include a Statewide Approver group are only assigned the purchasing unit for the user who submitted the eForm. Given that these users need systemwide visibility, they should also be added to the statewide purchasing unit. | The DMS system Administrator or impacted users with a Statewide Approver group can reach out to the MFMP Help Desk to have the Purchasing Unit for their account updated. | Investigation | Buying and Invoicing
Yes | 3755 | CS0028867 | Migrated DPU requestions with the Advance Payment Indicator set to "Yes" are marked "No" in AOD | Migrated DPU requisitions with the Advanced Payment Indicator checked in the Legacy System are not set to "Yes" in AOD | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
Yes | 3754 | CS0030736 | IR281713119-22377 disbursement not deleted in FLAIR after partial disbursement failure | An IR did not delete it's disbursement in FLAIR after it encountered a partial disbursement failure. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
Yes | 3751 | CS0029360 | PO Number not Generated for Migrated DPU Requisition (PR1080) | A Migrated DPU Requestion did not generate a PO Number in AOD. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
Yes | 3750 | CS0029339 | Encumber Funds defaults to "Yes" on PCard Requisition (PR50114) | Encumbered funds defaults to "Yes" on PCard orders | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
Yes | 3748 | CS0030486 | Encumbrance Rollback for C009E1 not able to release in FLAIR | 1 Encumbrance, C009E1, failed to release in FLAIR after a change order failed to process for accounting reasons. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
Yes | 3746 | CS0030238 | Delete Disbursement for DOT Invoice Failed Due to Incorrect Encumbrance Information | The Delete Disbursement for IR82190341-18193 was processed with the incorrect Prefix and Encumbrance Number causing the Delete Disbursement to be unsuccessful. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Integration/Interfaces
No | 3741 | CS0027832 | Approved Invoice Reconciliations with '/' in the IR# are stuck in Paying | Currently, if an Invoice Reconciliation number contains a forward slash, then once it is approved it will be stuck in Paying and will not receive payment information. | Customers must recreate affected Invoice Reconciliations that contain a forward slash and need to be paid. | Investigation | Integration/Interfaces
No | 3738 | CS0026886 | Fund ID 000319 Not Selectable on PR8233-v2 | Fund ID 000319 did not default as expected when selecting the associated Expansion Option, Organization Code and Budget Entity. Fund ID is derived from the Expansion Option and is not editable by the user. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3737 | CS0026978 | "MOP Must Be Set" Error Message Encountered when Attempting to Apply Discount on PO-Based Invoice | "Method of Procurement must be set" error notification encountered when attempting to apply a discount on a PO-Based Invoice for purchase order C03EA8. | As a workaround, the user should update the amount with the discounted price on the invoice rather than utilizing the discount option. | Investigation | Buying and Invoicing
No | 3735 | CS0027208 | Incorrect Supplier Location exported to FLAIR for C03096 | Purchase order C03096 in AOD is for vendor sequence 002; however, the purchase order in FLAIR is for sequence 001 of the same vendor | The encumbrance recorded in FLAIR may reflect the incorrect vendor sequence ID; however, we have confirmed this issue does not occur on the disbursements, therefore users should still be able to process Invoices despite this issue. | Investigation | Integration/Interfaces
No | 3732 | CS0025974 | DOH MFMP system administrator unable to search for Org Code: 64373312212 in the user maintenance eForm | DOH MFMP system administrator unable to search for Org Code: 64373312212 in the user maintenance eForm because the dropdowns search fields are limited to 5K results on eForms. DOH and other agencies have more than 5K organization codes. | Organization codes beyond the 5K limit are not searchable and cannot be given to user's via User Maintenance eForms. | Investigation | System Administration
No | 3731 | CS0026529 | Sum of Rounded Amounts does not match Total Amount of IR1235-3178 | Customer inquiry regarding a payment voucher that was $0.07 less than the IR total amount. iWay and FLAIR only able to process amounts into the hundredth decimal place. Line item split by percentage causes decimals beyond the hundredth to be truncated | As a workaround, customers can split line items by amount to avoid this issue. | Investigation | Buying and Invoicing
No | 3729 | CS0028510 | Remittance import task extracting IR557212251-4676 with partial payment information | IR in the Central Error report on 08/02 was erroneously picked up by the remittance task on 07/26 before both lines of the IR had their Warrant number. | The issue has impacted one IR to date. The customer's impact was a partially paid IR. | Investigation | Buying and Invoicing
No | 3727 | CS0028149 | FDOT invoice reconciliations fail prevalidation due to an "encumbrance record not on file" FLAIR error | FDOT invoice reconciliations fail prevalidation due to an "encumbrance record not on file" FLAIR error. | MFMP continues its investigation and will provide an update when more information is available. | Open | Integration/Interfaces
No | 3726 | CS0027602 | The Transaction Fee Exemption field defaults to “Yes” for vendor records with a “0” in the Transaction Fee Exempt status field | The Transaction Fee Exemption field defaults to “Yes” for vendor records with a “0” in the Transaction Fee Exempt status field. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3722 | CS0025978 | INV72400077044-3067 stuck in 'CC Invoice to AN' Status | INV72400077044-3067 stuck in 'CC Invoice to AN' Status | The invoice did not generate an invoice reconciliation. The agency may input a new PO-based invoice to process payment to the vendor. | Open | Buying and Invoicing
No | 3721 | CS0025973 | FDC customer receive a system error when attempting to update two user profiles | FDC customer receive a system error when attempting to update two user profiles. | MFMP continues its investigation and will provide an update when more information is available. | Open | System Administration
No | 3720 | CS0024563 | DOH system administrator is unable to search for FLAIR login eForms created by their agency | DOH system administrator is unable to search for FLAIR login eForms created by their agency. | MFMP continues its investigation and will provide an update when more information is available. | Open | System Administration
No | 3719 | CS0026731 | Agency customers are not required to choose a Solicitation Number when selecting MOPs H through J | Agency customers are not required to choose a Solicitation Number when selecting MOPs H through J. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3718 | CS0023001 | The Category 210020 not available for selection on PR7266-V4 | The Category 210020 not available for selection on PR7266-V4. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3715 | CS0023077 | Closed Order preventing edits on PR17454 | Closed Order preventing edits on PR17454. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3714 | CS0024659 | DOH Exception Handler receiving "user name is required" error from FLAIR when reconciling an invoice reconciliation | DOH Exception Handler receiving "user name is required" error from FLAIR when reconciling an invoice reconciliation. | MFMP continues its investigation and will provide an update when more information is available. | Open | Integration/Interfaces
No | 3713 | CS0025391 | When searching for an Address, only line 1 of the address is displayed in the search results | When searching for an Address, only line 1 of the address is displayed in the search results. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3712 | CS0026608 | FLAIR Login Information eForm is not reporting failed validation to customers | FLAIR Login Information eForm is not reporting failed validation to customers. | MFMP continues its investigation and will provide an update when more information is available. | Open | Integration/Interfaces
No | 3711 | CS0026542 | Delete Disbursement request for IRAR-00217036-4701 marked the IR Payment Completed in FLAIR | Delete Disbursement request for IRAR-00217036-4701 marked the IR Payment Completed in FLAIR. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3710 | CS0025671 | Agency customers receiving system-wide notifications for failed and rejected transactions | Agency customers receiving system-wide notifications for failed and rejected transactions. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3708 | CS0025198 | Disable transmission of payment to the Ariba Business Network | Disable transmission of payment to the Ariba Business Network. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3705 | CS0023400 | Integration failure notifications sent to agencies at the entity-level | Integration failure notifications sent to agencies at the entity-level. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3704 | CS0024399 | When a supplier location has a Preferred Ordering Method set to 'Electronic Ordering', but no business network ID, the order will fail to send to the supplier | When a supplier location has a Preferred Ordering Method set to 'Electronic Ordering', but no business network ID, the order will fail to send to the supplier. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3701 | CS0024331 | Duplicative Expansion Option Versions displayed in account selection and view | Duplicative Expansion Option Versions displayed in account selection and view. | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3697 | CS0024288 | The FLAIR Login eForm does not record log in credentials using the Transaction Type dropdown | The FLAIR Login eForm does not record log in credentials using the Transaction Type dropdown | Like the Legacy Buyer system, to update the agency's encumbrance user's FLAIR login information, an agency customer must be assigned to the FLAIR Login Information group (without the Buying Invoice Manager group). To update the disbursement user's FLAIR login information in MFMP, an agency customer must be assigned the FLAIR Login Information and Buying Invoice Manager group. | Investigation | Buying and Invoicing
No | 3696 | CS0022836 | FWC encumber funds checkbox defaults to "unchecked" | FWC encumber funds checkbox defaults to "unchecked". | FWC users must click the encumbered funds checkbox to process encumbered requestions. | Open | Buying and Invoicing
No | 3692 | CS0025885 | AOD purchase orders are not available in the DFS FACTS system | AOD purchase orders are not available in the DFS FACTS system | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3690 | CS0025883 | The transaction date on invoice reconciliations sent to FLAIR is set to the day the invoice reconciliation is integrated with FLAIR | The transaction date on invoice reconciliations sent to FLAIR is set to the day the invoice reconciliation is integrated with FLAIR | MFMP continues its investigation and will provide an update when more information is available. | Third-Party | Buying and Invoicing
No | 3689 | CS0025881 | Delegation of Authority requests submitted via the eForm is working inconsistently | Delegation of Authority requests submitted via the eForm is working inconsistently. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3685 | CS0025874 | FWC expansion option 7Z is not available in AOD | FWC reported an issue where expansion option 7Z is not available in AOD. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3683 | CS0025738 | A delete disbursement request for IR44939403A-4742 was successful; however, the success message did not display in the user interface | A delete disbursement request for IR44939403A-4742 was successful; however, the success message did not display in the user interface | MFMP confirmed that the delete disbursement request was successful and informed the impacted agency. | Investigation | Buying and Invoicing
No | 3682 | CS0025736 | Line 8, split 2 was deleted on C00F27; however, the deletion was not transmitted to FLAIR | Line 8, split 2 was deleted on C00F27; however, the deletion was not transmitted to FLAIR. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3681 | CS0023449 | DOT MFMP Contract C13886 from Legacy Buyer was not migrated to AOD | DOT MFMP Contract C13886 from Legacy Buyer was not migrated to AOD. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Contract Terms
No | 3679 | CS0025734 | The release encumbrance checkbox is editable on unencumbered requestions | The release encumbrance checkbox is editable on unencumbered requestions. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3671 | CS0023309 | The Organization Code, Expansion Option, and Object Code are not displayed in the purchase order print view | Organization Code, Expansion Option, and Object Code are not displayed in the purchase order print view. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3669 | CS0022295 | COA - AOD Expansion Set Not Associated with Agency | COA - AOD Expansion Set Not Associated with Agency | MFMP continues its investigation and will provide an update when more information is available. | Open | Buying and Invoicing
No | 3666 | CS0023906 | Two invoice reconciliations marked "Paid in FLAIR" are stuck in Paying status | Two invoice reconciliations marked "Paid in FLAIR" are stuck in Paying status. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3662 | CS0024466 | Office Depot (ODP) is auto-rejecting purchase orders | Office Depot (ODP) is auto-rejecting purchase orders | The MFMP team is working with ODP to resolve their purchase order processing issues. MFMP will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3661 | CS0022183 | The User and Address Maintenance eForms do not display postal address details | When an MFMP System Admin clicks the "more info" link on an address from the User and Address Maintenance eForms, the postal address field is blank, and an error message is displayed. | System Administrators can access the Address Tableau dashboard to view the postal address for an address, capture the ID, and use the ID to select the desired address on the User and Address Maintenance eForms. | Investigation | System Administration
No | 3656 | CS0023507 | Unable to import an electronic invoice from the Ariba Business Network for a specific vendor | The MFMP system receives an error when attempting to load an invoice from the Ariba Business Network from one of the vendors signed up for electronic invoicing. | This issue has impacted one invoice to date. The vendor can submit a paper invoice to the agency as a temporary workaround. | Investigation | Buying and Invoicing
No | 3745 | CS0027899 | 2 Purchase Orders sent to separate Vendor Registrations belonging to the same owner, contained the same supplier name. | 2 separate suppliers were selected on C0511C & C04E61. However the PO sent to the Supplier referenced a single supplier. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3744 | CS0027072 | Sourcing Vendor Response Email - Click Here link does not allow accepting of quote | The email notification of a vendor response to a solicitation contains a click here link that navigates to a page where no action can be taken by the event owner. The link is designed to allow users to review the vendor response. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing
No | 3743 | CS0027136 | User cannot be found in AOD after creation via User Maintenance eForm | One user record, created via the User Maintenance eForm in AOD was not properly formed, preventing the affected user from using the system. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Buying and Invoicing

## VIP - Known Issues
MyFloridaMarketPlace Known Issues as of Aug. 19, 2022
New? | SIR Number | Master Ticket | Title | Description | Impact to Customers Temporary Fix (if available) | Status | Functional Area
Yes | 3768 | CS0029601 | Invalid VPT Rating link sent to agency customer | An agency customer received a VPT Rating Email, but upon clicking the interactive link they were brought to a VIP landing page for a different procurement account. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
Yes | 3763 | CS0029381 | VIP Terms of Use verbiage in registration confirmation Email requires updates | As part of recent updates implemented to Rule 60A-1.033, F.A.C., the VIP Terms of Use have changed. These updates will need to be reflected within the VIP registration confirmation Email. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Registration
Yes | 3752 | CS0028836 | Advertisement Email Notification Not Sent to All Vendors for IN-02205 | Only a subset of vendors received an email for the opening of IN-02205. | Affected Vendors are not notified of Solicitations opening or changing. | Investigation | Vendor Information Portal
Yes | 3747 | CS0029169 | Updating Remit To or Bill To details generates a new location sequence | When a vendor updates the Remit To or Bill To address of a vendor location, a new location is created after saving the edits. The same location should be updated with the new information, rather than an additional location being created. This does not occur if only the Order From address is updated for a location. | The affected vendor will have an additional vendor location created with their intended details. As a workaround, the vendor could flag the initial location sequence that they updated for deletion, since the new location will include the updated information. | Investigation | Vendor Information Portal
No | 3742 | CS0028087 | Vendor Received an empty Confirmation Code upon registration | 1 vendor registered for VIP, but then received a confirmation email with a no confirmation code for verification. | The affected Vendor is creating a new registration. | Investigation | Vendor Registration
No | 3740 | CS0029871 | Vendors without solicitation contact cannot be added to Sourcing events | Currently, a vendor can click Intends to Participate on an integrated advertisement whether they have a solicitation contact or not. When a vendor without a solicitation contact clicks Intends to Participate, the vendor is unable to be added to the associated Sourcing event. | Vendor can opt-in for solicitations on their vendor registration. Once that is done they can establish a solicitation contact. Once they've established the solicitation contact and let MFMP know, the MFMP team will initiate a process to add the vendor to the sourcing event, resulting in the invitation email being sent. | Investigation | Integration/Interfaces
No | 3623 | CS0018786 | A user is unable to upload a valid advertisement attachment after receiving a "Filename can not exceed 50 characters" error message | A user is unable to upload a valid advertisement attachment after receiving a "Filename can not exceed 50 characters" error message | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3624 | CS0019047 | The VIP expired password notification email verbiage requires updates to provide clearer instructions for resetting expired passwords | The VIP expired password notification email verbiage requires updates to provide clearer instructions for resetting expired passwords. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3625 | CS0018738 | The OSD administrator view of the CBE summary displays the incorrect minority designations | The OSD administrator view of the CBE summary displays the incorrect minority designations | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Supplier Diversity
No | 3626 | CS0019123 | Vendors seeking their first OD recertification in VIP can submit a recertification request without uploading the required attachments | Vendors seeking their first OD recertification in VIP can submit a recertification request without uploading the required attachments. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Supplier Diversity
No | 3628 | CS0019551 | The "Call the Helpdesk" system error displays when viewing Advertisement Notification Log for ITN-01481 | The "Call the Helpdesk" system error displays when viewing Advertisement Notification Log for ITN-01481. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3630 | CS0019244 | Some vendors did not receive an advertisement notification for ITB-01379 | Some vendors did not receive an advertisement notification for ITB-01379. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3641 | CS0021531 | Users are unable to log into VIP 10 minutes after the MFA code is generated | Users are unable to log into VIP 10 minutes after the MFA code is generated. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3673 | CS0021377 | A user received a “Cannot complete this action" system error when submitting an ITN | A user received a “Cannot complete this action" system error when submitting an ITN | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3698 | CS0026021 | The Advertisement Search does not return results when using the Start and End date search fields. | The Advertisement Search does not return results when using the Start and End date search fields. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Advertisement Management
No | 3631 | CS0020684 | Vendor unable to save an uncommon email address domain in VIP | A vendor with an uncommon @domain in their email cannot save the email in their vendor registration. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3632 | CS0020325 | Some emails sent from dms.myflorida.com domain are routed to the recipients junk/SPAM mail folder | Some emails sent from dms.myflorida.com domain are routed to the recipients junk mail | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3634 | CS0022718 | The newsfeed doesn't allow a blank or empty input value | The newsfeed doesn't allow a blank or empty input value. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3620 | CS0018253 | EWA Vendor cannot submit a $0 report | EWA Vendor cannot submit a $0 report | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3619 | CS0016641 | Error Submitting CBE Certification if Recertification Questionnaire comment exceeds 50 characters | Error Submitting CBE Certification if Recertification Questionnaire comment exceeds 50 characters | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3618 | CS0016950 | VIP Registration Not In Sourcing When Solicitation Contact Does Not Have a Username | VIP Registration Not In Sourcing When Solicitation Contact Does Not Have a Username | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3616 | CS0015549 | Vendor Contact - Invalid Characters Failing FLAIR and Buyer Integration | Vendor Contact - Invalid Characters Failing FLAIR and Buyer Integration | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3613 | CS0015518 | Error Exporting Search results for users with 'Vendor Viewer' group | VIP admin users with the Vendor Viewer group are unable to export search results in VIP | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3611 | CS0014034 | Download Certificate' button for Individual Vendor downloads Licensing Documentation | Download Certificate' button for Individual Vendor downloads Licensing Documentation | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3610 | CS0013934 | Address Info in Public Vendor Search Results tied to Inactive Location | Public Vendor search results display location information from an old/inactive location | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3609 | CS0013941 | Unable to send password reset request for username larger than 12 characters | Unable to send password reset request for username larger than 12 characters | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3608 | CS0012718 | "Call the Helpdesk" popup displayed when viewing Advertisement Notification Log for ITB-00202 | "Call the Helpdesk" popup displayed when viewing Advertisement Notification Log for ITB-00202 | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3586 | CS0012616 | Vendor Compliance Percentage displaying over 100% | The percentage on the Vendor Compliance widget is displaying 100.01% | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3566 | CS0010825 | "Contact the Help Desk" popup displayed when vendor audit log contains entries tied to deleted users | "Contact the Help Desk" popup displayed when vendor audit log contains entries tied to deleted users | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal
No | 3565 | CS0011155 | Incorrect overall balance amounts are displayed when a credit is available | The Balance Due does not display correctly when there is a credit balance in VIP | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Vendor Information Portal

## Tableau - Known Issues
MyFloridaMarketPlace Known Issues as of Aug. 19, 2022
New? | SIR Number | Master Ticket | Title | Description | Impact to Customers Temporary Fix (if available) | Status | Functional Area
Yes | 3762 | CS0029273 | Tableau missing invoice payment data | Tableau invoice reports currently do not include details relating to invoice payment data, such as IR Paid Date, Warrant Issue Date, and Statewide Document Number. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Reporting
No | 3674 | CS0025437 | The amount field in the Invoicing dashboard displays incorrect data | The amount field in the Invoicing dashboard displays incorrect data. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Reporting
No | 3686 | CS0025886 | Some user profile information in the User dashboard is incorrect | Confirmed that some users in the Tableau dashboard display inaccurate profile details. However, when you view the user profile in AOD, the profile is correct. | MFMP continues its investigation and will provide an update when more information is available. | Investigation | Reporting

## Resolved Issues
MyFloridaMarketPlace Resolved Issues
New? | SIR Number | Master Ticket | Title | Description | Resolution Date | Resolution Note | Status | Functional Area
No | 3736 | CS0029405 | Invoices Cannot Be Submitted with Punchout Catalog Line Items tied to Segment or Family-level Commodity Codes | Suppliers define the commodity codes for their catalog items. In Ariba on Demand (AOD) a commodity code must be selected at the more specific Class or Commodity levels of the Commodity Code hierarchy for invoicing purposes. Some catalog items were only defined at the broader Segment or Family levels which prevents users to invoice against impacted orders. | Resolved on Aug. 12, 2022. | Agency customers can now submit an invoice reconciliation associated with a segment and family-level commodity code. | Closed | Buying and Invoicing
No | 3688 | CS0025879 | Agency customers are unable to edit the Site Code on invoice reconciliations | Agency customers are unable to edit the Site Code on invoice reconciliations | Resolved on Aug. 12, 2022. | Agency customers can now edit the Site Code on the invoice and invoice reconciliation. | Closed | Buying and Invoicing
No | 3690 | CS0025883 | The transaction date on invoice reconciliations sent to FLAIR is set to the day the invoice reconciliation is integrated with FLAIR | The transaction date on invoice reconciliations sent to FLAIR is set to the day the invoice reconciliation is integrated with FLAIR | Resolved with the 1.2.8 Hotfix on Aug.4, 2022. | Two new date fields have been added on the Invoice eForm; the Transaction Date is now correctly calculated from the Invoice date fields when integrating with FLAIR. | Closed | Buying and Invoicing
No | 3733 | CS0029211 | A Warrant Issue Date Format Update Is Required for Some Invoices Prior to July 2022 CBI Generation | A Warrant Issue Date Format Update Is Required for Some Invoices Prior to July 2022 CBI Generation | Resolved with the 1.2.8 Hotfix on Aug.4, 2022. | The warrant issue date format logic has been corrected for impacted invoices. Warrant Issue Dates will no longer be impacted during the monthly generation of CBIs. | Closed | Integration/Interfaces
No | 3727 | CS0028149 | FDOT invoice reconciliations fail prevalidation due to an "encumbrance record not on file" FLAIR error | FDOT invoice reconciliations fail prevalidation due to an "encumbrance record not on file" FLAIR error. | Resolved on Aug. 2, 2022. | DOT invoice reconciliations impacted by this issue may be resubmitted. | Closed | Integration/Interfaces
No | 3669 | CS0022295 | Some agency customers are unable to submit a requestion due to the "ExpSet_ObjectCode" error message | Multiple agencies reported receiving the ExpSet_ObjectCode has been deleted error, preventing them from submitting requestions. | Resolved on Aug. 1, 2022. | Agency can resubmit transactions affected by this issue. | Closed | Buying and Invoicing
No | 3687 | CS0025877 | The object code search displays the statewide (000000) and agency-specific (##0000) prefix | The object code search displays the statewide (000000) and agency-specific (##0000) prefix | Resolved on July 27, 2022. | Agency-specific object codes no longer appear in the Object Code dropdown. | Closed | Buying and Invoicing
No | 3724 | CS0027455 | Add the master agreement field to middleware | Add the custom Master Agreement field to the payment export. | Resolved with the 1.2.6 Hotfix on July 28, 2022. | N/A | Closed | Integration/Interfaces
No | 3725 | CS0027458 | The CFO received date on IR6011722003832-1728 & IRCS 1122-2188 have an incorrect date | The CFO received date on IR6011722003832-1728 & IRCS 1122-2188 have an incorrect date. | Resolved with the 1.2.6 Hotfix on July 28, 2022. | The CFO Received Date will now display the date an IR successfully prevalidated in FLAIR. | Closed | Integration/Interfaces
No | 3723 | CS0027451 | Four DOT invoices with encumbrance information processed as unencumbered disbursements in FLAIR | Four DOT invoices with encumbrance information processed as unencumbered disbursements in FLAIR | Resolved with the 1.2.6 Hotfix on July 28, 2022. | All DOT invoice reconciliations with encumbrance information will process as an encumbered disbursement FLAIR. | Closed | Integration/Interfaces
No | 3706 | CS0026377 | IR112486-5943 failed integration due to a single quote in the Grouping Character field | IR112486-5943 failed integration due to a single quote in the Grouping Character field. | Resolved with the 1.2.6 Hotfix on July 28, 2022. | IRs with a single quote will no longer fail to integrate with FLAIR. | Closed | Integration/Interfaces
No | 3645 | CS0023512 | Some encumbrances are not released when a requisition with multiple lines or split accounting partially fails FLAIR integration | When requestion with multiple lines or split accounting partially fails FLAIR integration, the MFMP system automatically releases the successful lines and sends the requisition back to the requester for processing. In some cases, the MFMP system's attempts to automatically release the successful lines are unsuccessful. | Resolved with the 1.2.3 Hotfix on July 15, 2022. | Encumbrances are now automatically released when a requisition partially fails FLAIR integration. | Closed | Buying and Invoicing
No | 3633 | CS0022838 | The Chart of Accounting (COA) correlation validation requires some agency customers to choose from correlated values only | The COA correlation validation requires some agency customers to only choose correlated values for the Project and Contract ID fields, preventing some agencies from submitting requisitions using non-correlated Project and Contract ID values. | Resolved on July, 18, 2022. | Agencies impacted by this issue may submit requisitions with non-correlated Project and Contract ID values. | Closed | Buying and Invoicing
No | 3694 | CS0025888 | The service categories for the Financial Performance Audit STC RFQ are incorrect | The service categories for the Financial Performance Audit STC RFQ are incorrect. | Resolved on July 20, 2022. | N/A | Closed | Integration/Interfaces
No | 3677 | CS0025464 | Some agencies are unable to submit invoice reconciliations due to a "password not on file" error | Multiple agencies reported issues with submitting invoice reconciliations due to the "password not on file" error. The agencies confirmed their FLAIR login credentials were properly recorded and valid in MFMP. | Resolved with the 1.2.4 Hotfix on July 21, 2022. | Agencies impacted by this issue may resubmit invoice reconciliations. | Closed | Buying and Invoicing
No | 3676 | CS0025457 | The AOD Sourcing to VIP advertisement integration must ignore updates originating from the robotic processing automation (RPA) application | The AOD Sourcing to VIP advertisement integration must ignore updates originating from the robotic processing automation (RPA) application. | Resolved with the 1.2.4 Hotfix on July 21, 2022. | N/A | Closed | Integration/Interfaces
No | 3675 | CS0025452 | The VIP intent to participate integration was refined to extract additional data for AOD Sourcing integration | The VIP intent to participate integration was refined to extract additional data for AOD Sourcing integration. | Resolved with the 1.2.4 Hotfix on July 21, 2022. | N/A | Closed | Integration/Interfaces
No | 3695 | CS0025889 | PUI name field displayed instead of the PUI number in various areas of AOD | PUI name field displayed instead of the PUI number in various areas of AOD | Resolved on July 21, 2022. | N/A | Closed | Buying and Invoicing
No | 3709 | CS0024492 | Commodity Code 80161508 is available in Expert View but not Guided Buying | Commodity Code 80161508 is available in Expert View but not Guided Buying. | Resolved on July 27, 2022. | The commodity codes in Guided Buying and Expert View are now consistent. | Closed | Buying and Invoicing
No | 3648 | CS0024060 | Some agency workflows did not generate the proper PUI-based user group | Multiple agencies reported that their workflow did not generate with the proper user group when submitting requisitions and invoice reconciliations. | Resolved on July 6, 2022. | Agencies with transactions impacted by this issue submitted before July 6, 2022, can withdraw and resubmit the transactions. The workflow will regenerate with the proper approval nodes. | Closed | Buying and Invoicing
No | 3649 | CS0024065 | Some agency requisition workflows did not generate the supervisor approval chain | Multiple agencies reported that their workflow did not generate with the proper supervisor chain when submitting requisitions. | Resolved on July 7, 2022. | Agencies with transactions impacted by this issue submitted before July 7, 2022, can withdraw and resubmit the transactions. The workflow will regenerate with the proper approval nodes. | Closed | Buying and Invoicing
No | 3650 | CS0024067 | Some agency requisition workflows generate a supervisor whose threshold is below the requestion amount | Multiple agencies reported that their requisition workflow generated a supervisor whose threshold is below the requisition amount when submitting a requisition. | Resolved on July 8, 2022. | Agencies with transactions impacted by this issue submitted before July 8, 2022, can withdraw and resubmit the transactions. The workflow will regenerate with the proper approval nodes. | Closed | Buying and Invoicing
No | 3653 | CS0024079 | Some agency customers can view receipts from other state agencies not associated with their agency | Multiple agencies reported that they could view other agencies' receipts in their "To Do" queues. | Resolved on July 8, 2022. | Impacted agencies can remove unwanted receipts from their "To Do" queue by opening the "To Do" queue and clicking the "Clean Up" button or by Archiving the receipts to their Archive folder. | Closed | Buying and Invoicing
No | 3652 | CS0024072 | Agency customers assigned the Buying Requester group cannot create invoices | DOH reported an issue where their Requesters cannot create invoices in AOD. In Buyer 9r1, the Requester group inherits the PO and Contract-Based Invoice eForms. However, in AOD, access to the PO and Contract-Based Invoice eForms are managed separately via the Buying Invoice Entry User group. Requesters were not granted the new Buying Invoice Entry User group in AOD, thus, preventing those users from creating invoices. | Resolved on July 11, 2022. | MFMP updated the Buying Requester group to inherit access to create PO-Based and Contract-Based Invoices in AOD. | Closed | Buying and Invoicing
No | 3654 | CS0024135 | The requisition workflow adds the On Behalf Of (OBO) user as a Watcher | DEP reported an issue where the requisition workflow added their OBO as a Watcher instead of an Approver in the requisition workflow, preventing DEP from requiring the OBO user to approve requisitions. | Resolved on July 11, 2022. | MFMP updated the OBO approval rule to be consistent with the Buyer 9r1 rule, allowing all agencies to specify whether the requisition workflow adds the OBO as an Approver or Watcher by purchasing unit indicator (PUI). | Closed | Buying and Invoicing
No | 3655 | CS0024146 | Some vendors did not receive all their purchase orders (PO) through the Ariba Business Network | A vendor reported issues receiving some of their POs through the Ariba Business Network, preventing the vendor from fulfilling orders. | Resolved on July 11, 2022. | MFMP re-sent all POs to the vendors impacted by this issue. Some POs were not resent because the agency opted not to send the initial PO to the vendor. | Closed | Buying and Invoicing
No | 3644 | CS0023463 | The Delegation of Authority (DOA) eForm interface saved delegation dates in an improper date format | MFMP identified an issue where the DOA eForm interface saved delegation dates in an improper format from some DOA eForm submissions, causing the DOA eForm dates to display incorrectly in Tableau. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | MFMP updated the DOA Tableau dashboard for impacted DOA eForms to display the correct delegation start and end dates. | Closed | Integration/Interfaces
No | 3643 | CS0023457 | The Central FLAIR payment interface improperly maps the Warrant number | MFMP identified an issue where the Central FLAIR interface improperly mapped the Warrant number, requiring the MFMP to manually load the Central FLAIR payment data into Ariba On Demand. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | The Central FLAIR interface automatically loads Central FLAIR payment data without manual intervention from the MFMP team. | Closed | Integration/Interfaces
No | 3640 | CS0022862 | The Accounting Description interface failed to load due to inactive accounting references | MFMP identified an issue where the Accounting Description interface failed to load due to inactive accounting references in the Central FLAIR Accounting Description file. This issue prevents the interface from loading the complete Accounting Description data into Ariba on Demand and prevents some agency customers from selecting the latest 29-digit Account Code. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | The Accounting Description interface loads the complete Central FLAIR Accounting Description data into Ariba on Demand. | Closed | Integration/Interfaces
No | 3639 | CS0022850 | The Tableau Address interface does not include the agency Entity ID (OLO) | MFMP identified an issue where the Tableau Address interface does not include agency entity IDs, preventing the Tableau address dashboard from displaying entities associated with agency address data. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | The Tableau Address dashboard now displays the Entity IDs associated with agency address data. | Closed | Integration/Interfaces
No | 3637 | CS0022847 | The DFS FACTS reports are not readable on the MFMP Secure Reports website | MFMP identified an issue where the DFS FACTS reports are not readable on the Secure Reports website, preventing DFS FACTS from accessing and loading purchase order data from AOD. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | The DFS FACTS reports are now readable on the Secure Reports website, and DFS FACTS may retrieve the applicable file to load in the DFS FACTS system. | Closed | Integration/Interfaces
No | 3636 | CS0022842 | The VIP to AOD vendor interface does not include the vendor remittance address data | MFMP identified an issue where the VIP to AOD vendor interface doesn't include the vendor remittance address data, preventing new and updated vendor remittance data from loading into AOD. | Resolved with the 1.2.1 Hotfix on July 11, 2022. | The VIP to AOD interface now loads new and updated vendor remittance data into AOD. MFMP recovered and re-loaded vendor records impacted by this issue, ensuring the latest remittance information from the vendor's VIP registration is in AOD. | Closed | Integration/Interfaces
No | 3646 | CS0022591 | Agency customers are unable to submit an STC RFQ to some vendors on the Management Consulting and IT Staff Aug state contracts | Multiple agency Customers have reported receiving an error when attempting to add specific suppliers to an STC RFQ in Guided Buying. | Resolved on July 15, 2022. | MFMP worked with nine impacted vendors and updated their vendor registrations to include a Solicitation Contact to prevent agency customers from receiving the error in Guided Buying. Agencies impacted by this issue can submit new STC RFQs. | Closed | Buying and Invoicing
No | 3606 | CS0012934 | Vendor User unable to log in to Sourcing due to 'Dashboard' is null error | Vendor User unable to log in to Sourcing due to 'Dashboard' is null error | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3605 | CS0012985 | Public vendor search inaccurately displaying solicitation selection due to null EMAIL_SOLICITATION_CONTACT | Public vendor search inaccurately displaying solicitation selection due to null EMAIL_SOLICITATION_CONTACT | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3603 | CS0013041 | VIP User Search - Agency filter cannot handle apostrophe | VIP User Search - Agency filter cannot handle apostrophe | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3602 | CS0012920 | Contacts in deleted status associated to active locations cause locations details to be hidden and not editable | Contacts in deleted status associated to active locations cause locations details to be hidden and not editable | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3601 | CS0012550 | Advertisement Opened and Notification Email sent before Advertisement Open Date | Advertisement status changed to Open and associated notification email sent before Advertisement Open Date | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3598 | CS0012452 | Username is Invalid' error prohibiting a vendor from completing their registration | Username is Invalid' error prohibiting a vendor from completing their registration | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3597 | CS0013417 | Minority Business Designation certification status on Vendor Details and Registration Summary is editable by the vendor | Minority Business Designation certification status on Vendor Details and Registration Summary is editable by the vendor | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3595 | CS0012966 | Vendor Location Sequence Number Defaults to '000' when PS performs Pin Update | When updating the Pin number in VIP, the Sequence number will default to 000 | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3594 | CS0013213 | OSD Vendor Search displays one row per registration contact | OSD Vendor Search displays one row per registration contact | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3593 | CS0012481 | Error Saving CBE Certification in "Awaiting Additional Information" Status | Error received when placing CBE Certification in Awaiting Additional Information status | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3592 | CS0012953 | In-App notifications for monthly BCS CBI tasks not being sent | In-App notifications for monthly BCS CBI tasks not being sent | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3591 | CS0012732 | Vendor Users can save Contacts with invalid Phone Number length or Country Code Selection | Vendor Users can save Contacts with invalid Phone Number length or Country Code Selection | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3590 | CS0012625 | Incorrect attachments displayed on Advertisement Preview page during advertisement edit | Incorrect attachments displayed on Advertisement Preview page during advertisement edit | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3585 | CS0012608 | Prevent inactive user from being prompted to change their password | Inactive users are prompted to change their password upon login. Once updated, they are able to login to VIP | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3584 | CS0012606 | Route user to user management dashboard upon completion of a user edit | User is not routed to the User Management Dashboard upon completion of user edit | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3583 | CS0012601 | "Connected" is misspelled in the vendor resource section | "Connected" is misspelled in the vendor resource section | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3582 | CS0012430 | VIP restricts vendor access to US-based IPs only | VIP restricts vendor access to US-based IPs only | Resolved with the 1.0.2 Hotfix on April 6, 2022. | N/A | Closed | Vendor Information Portal
No | 3580 | CS0010603 | "Call the Helpdesk" pops up when attempting to edit an Advertisement | "Call the Helpdesk" pops up when attempting to edit an Advertisement | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3579 | CS0011885 | Amount Error when Manually Posting Payment across multiple CBIs | An error message is received when posting payments manually across multiple CBIs | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3578 | CS0011598 | 'Submit Self-Report' Buttons on individual CBI Detail links to 'Page Not Found' | 'Submit Self-Report' Buttons on individual CBI Detail links to 'Page Not Found' | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3577 | CS0010997 | Update link to DFS EFT Registration Link in Vendor Registration Confirmation Email | Update link to DFS EFT Registration Link in Vendor Registration Confirmation Email | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3576 | CS0011419 | Error Submitting CBE Certification if Issuing Agency Name of License exceeds 50 characters | Error received when the agency name issuing certification exceeds 50 characters | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3572 | CS0010916 | Error Popup generated when viewing CBI History for Multiple Vendors. | Error Popup generated when viewing CBI History for Multiple Vendors. | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3571 | CS0011811 | "I do not wish to add Commodity Codes" Selection Not Recorded | Once selected, the 'I do not wish to add Commodity Codes' selection does not save. | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3569 | CS0011810 | OSD Admin is receiving the certification related notification intended for the vendor | OSD Admin is receiving the certification related notification intended for the vendor | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3568 | CS0011807 | Minority Designation in Owners table of Vendor CBE Profile includes "Non-Certified" | Minority Designation in Owners table of Vendor CBE Profile includes "Non-Certified" | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3567 | CS0011800 | CBE Certified Vendors by Date Report (In App) including vendors outside of date range | When the CBE Certified Vendors by Date report is run, the report includes vendors outside of the selected date range | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3563 | CS0011605 | Newsfeed hyperlinks open as unsafe URL | Newsfeed hyperlinks open as unsafe URL | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3562 | CS0011602 | Contact information popup is not displayed on public vendor details | When using the public vendor search, no contact information popup appears when clicking a contact name | Resolved with the 1.0.2 Hotfix on April 6, 2022. | N/A | Closed | Vendor Information Portal
No | 3561 | CS0011599 | OSD Certification Assignee dropdown does not contain any results | OSD Certification Assignee dropdown does not contain any results | Resolved with the 1.0.2 Hotfix on April 6, 2022. | N/A | Closed | Vendor Information Portal
No | 3559 | CS0010852 | Invalid Username/Password Popup Displayed for Locked Accounts | Users continue to receive the Invalid/Username Password popup after entering bad credentials 3 times | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3557 | CS0010775 | Vendor Registration completed without locations or solicitations selection | Clicking the Commodity Codes link on the Navigation Bar allows vendors to bypass the location and solicitation areas of the registration | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3555 | CS0011423 | Vendor Records not extracted to FLAIR/Sourcing due to Solicitation Selection updates | Vendor Records not extracted to FLAIR/Sourcing due to Solicitation Selection updates | Resolved with the 1.0.2 Hotfix on April 6, 2022. | N/A | Closed | Vendor Information Portal
No | 3554 | CS0010584 | Issue with NG VIP to 9r1 Sourcing Password Sync | Issue with NG VIP to 9r1 Sourcing Password Sync | Resolved with the 1.0.1 Hotfix on March 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3550 | CS0010437 | Vendor Registrations not appearing in search results if Main Contact is set to user without Portal User record. | Vendor Registrations not appearing in search results if Main Contact is set to user without Portal User record. | Resolved with the 1.0.2 Hotfix on April 6, 2022. | N/A | Closed | Vendor Information Portal
No | 3547 | CS0010375 | Update References to Credit Card Payment Functionality in BCS | the Transaction Fee Payment Methods text incorrectly includes credit/debit card | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3546 | CS0010482 | Legacy Organizations Displayed | Legacy Organizations displayed in VIP Advertisement and User Management | Resolved with the 1.0.1 Hotfix on March 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3545 | CS0010471 | Advertisement Notifications not Generating | A Commodity Code description is preventing advertisement notifications from correctly generating | Resolved with the 1.0.1 Hotfix on March 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3544 | CS0010407 | Test VIP link in temporary password email | The link to VIP within the temporary password reset email is directing vendors to an incorrect site | Resolved with the 1.0.1 Hotfix on March 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3543 | CS0010442 | Cannot edit an Advertisement with an Response Open Date in the past | Customers are unable to edit an advertisement which does not have a current or future Response Open Date | Resolved with the 1.0.1 Hotfix on March 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3589 | CS0012621 | Vendor Compliance widget Missing Reports and Collections counts are swapped | The counts for Missing Reports and Collections are swapped and are displayed under the opposite title in the vendor compliance widget | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3607 | CS0012498 | Reporting period unavailable for a Vendor who received first CBI in NGVIP | Reporting period unavailable for a Vendor who received first CBI in NGVIP | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal
No | 3612 | CS0014708 | FAQ Bot/Virtual agent temporarily disabled by ServiceNow 'San Diego' Upgrade | FAQ Bot/Virtual agent temporarily disabled by ServiceNow 'San Diego' Upgrade | Resolved with the 1.0.2 Hotfix on May 6, 2022. | N/A | Closed | FAQ Bot
No | 3617 | CS0015756 | VPT Rating Notification Email instructs Agency Customers to log into VIP | VPT Rating Notification Email instructs Agency Customers to log into VIP | Resolved with the 1.1.0 Release on May 28, 2022. | N/A | Closed | Vendor Information Portal

## Definitions
Column Header | Definition
New? | Yes: Designates a new issue added to the Known Issues List No: Designates an existing issue recorded on the previous Known Issues List
SIR Number | Unique System Investigation Request (SIR) number assigned to the issue.
Master Ticket | The master or parent Customer Service Desk ticket number assigned to the issue.
Title | Title of the reported issue.
Description | High-level description of the reported issue.
Impact to Customers Temporary Workaround (if available) | High-level summary of the issue's impact to agency customers and details on the temporary workaround, if available.
Status | Investigation: The MFMP team is currently investigating the root cause and resolution. Third-Party: The MFMP team is currently working with SAP Ariba to investigate a root cause and resolution. Closed: The MFMP team has resolved the issue.
Functional Area | The functional area in MFMP associated with the issue, i.e., Vendor Information Portal, Buying and Invoicing, Sourcing & Contracts, Reporting, Tableau, Integration/Interfaces, etc.
Note: New rows added or updated in the Known Issues List are highlighted in yellow.