## July 20
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 3700 | 4199 | Grand Ave | Dead End east of 38th | Cecil Ave | 50.0041 | 1 | Local | [17 empty] | 72590.5765 | [19 empty] | 1711.95 | 27.3563 | 46832.63 | 0.76005
| Hall |  |  |  |  | 2600 | 2999 | Grand Ave | S 26th St | Dead End to west | 61.1995 | 1 | Local | [17 empty] | 64222.824 | [19 empty] | 1255.22 | 33.0094 | 41434.08 | 0.67244
| Hall |  |  |  |  | 3000 | 3699 | Grand Ave | Dead End east of 32nd | Dead End west of Canopy Ct | 64.4573 | 1 | Local | [17 empty] | 131092.8 | [19 empty] | 2917.54 | 32.8616 | 84576 | 1.3726
| Hall |  |  |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | [19 empty] | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  |  |  |  | 3200 | 3699 | Hale Ave | S 32nd St | Dead End to west | 48.0322 | 1 | Local | [17 empty] | 103495.05 | [19 empty] | 2281.7 | 29.2637 | 66771 | 1.0836
| Hall |  |  |  |  | 1904-12-04 | 1919-12-25 | Lower Hunters Trce | Dixie Hwy | Greenbelt Hwy | 65.8978 | 1 | Pri Coll | [17 empty] | 50887.65 | [19 empty] | 1117 | 27.6106 | 30841 | 0.50052
| Hall |  |  |  |  | 6616 | 7299 | Lower Hunters Trce | Greenbelt Hwy | Cane Run Rd | 64.1728 | 1 | Pri Coll | [17 empty] | 116082.681 | [19 empty] | 2705.89 | 26 | 70353.14 | 1.1418
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [13 empty] | 2 |  |  |  | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-255 |  |  | 3400 | 3799 | W Magnolia Ave | Louis Coleman Jr Dr | Gibson Ln | 35 | 1 | Local | [13 empty] | 3 |  |  | 3 | 125495.75 | 1655.73 | July | [16 empty] | Seems to be many Semi Tractor Trailors. May use Fiber | 2381.3351 | 34 | 80965 | 1.314
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hwy | W Hill St | 67 | 1 | Min Art | [17 empty] | 293670 | 242320.52 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 3600 | 3699 | Friar Tuck Ct | Robinhood Ln | Dead End | 41 | 2 | Local | [17 empty] | 13852.35 | [19 empty] | 406 | 22 | 8937 | 0.14504
| Hall |  |  |  |  | 5100 | 5199 | Jefferson Blvd | Poplar Level Rd | Fern Valley Rd | 58.4628 | 2 | Min Art | [17 empty] | 117874.35 | [19 empty] | 1152.2379 | 62.0002 | 71439 | 1.1594
| Hall |  |  |  |  | 3600 | 3699 | Little John Ct | Robinhood Ln | Dead End | 54 | 2 | Local | [17 empty] | 9605.35 | [19 empty] | 258 | 24 | 6197 | 0.10057
| Hall |  |  |  |  | 4600 | 4699 | Oaklawn Ln | Rangeland Rd | Oakdale Ln | 40 | 2 | Local | [17 empty] | 45000 | [19 empty] | 1142 | 22 | 25124 | 0.40774
| Hall |  |  |  |  | 1200 | 1399 | Old Fern Valley Rd | Preston Hwy | Fern Valley Rd | 53 | 2 | Local | [17 empty] | 110589.4 | [19 empty] | 3398 | 21 | 71348 | 1.1579
| Hall |  |  |  |  | 5800 | 6099 | Robinhood Ln | Friar Tuck Ct | Forest Dr | 32.905 | 2 | Local | [17 empty] | 52659.7 | [19 empty] | 1475.2816 | 23.0288 | 33974 | 0.55137
| Hall |  |  |  |  | 4000 | 4099 | Tower Rd | Preston Hwy | Dead End | 46 | 2 | Local | [17 empty] | 96856.4 | [19 empty] | 2604 | 24 | 62488 | 1.0141
| Hall |  |  |  |  | 1600 | 2699 | Dixdale Ave | Wingfield Ave | S 28th St | 55.9513 | 3 | Local | [17 empty] | 170479.85 | [19 empty] | 5770.7465 | 19.0594 | 109987 | 1.785
| Hall |  | 350002-300 |  |  |  |  | Dixie Hwy | W Burnett Ave | Bernheim Ln | 66 | 3 | Min Art | [17 empty] | 254141 | [18 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  |  |  |  | 1600 | 1799 | W Lee St | S 15th St | Dixie Hwy | 47.1551 | 3 | Local | [17 empty] | 107680.05 | [19 empty] | 2701.6913 | 25.7139 | 69471 | 1.1275
| Hall |  |  |  |  | 500 | 799 | Bergman St | Dead End | S Shelby St | 20 | 4 | Local | [17 empty] | 59203.8 | [19 empty] | 1317 | 29 | 38196 | 0.61989
| Hall |  |  |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | [19 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  |  |  |  | 100 | 1299 | E Breckinridge St | S 1st St | Barret Ave | 60.4014 | 4 | Pri Coll | [17 empty] | 402154.632 | [19 empty] | 6770.28 | 36 | 243730.08 | 3.9555
| Hall |  |  |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | [19 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  |  |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | [19 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | [19 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  |  |  |  | 400 | 999 | E Witherspoon St | N Preston St | River Rd | 59.6256 | 4 | Min Art | [13 empty] | 8 |  |  |  | 326255.457 |  | July | [16 empty] | Portion of this may have been paved with bridges project. | 3413.14 | 57.9322 | 197730.58 | 3.209
| Hall |  |  |  |  | 150 | 399 | E Witherspoon St | Bingham Way | N Preston St | 62.9283 | 4 | Min Art | [17 empty] | 95488.8 | [19 empty] | 1425.1269 | 40.6083 | 57872 | 0.93921
| Hall |  |  |  |  | 700 | 799 | Henry Fripo St | S Clay St | S Shelby St | 18 | 4 | Local | [17 empty] | 22452.8 | [19 empty] | 585 | 24 | 14033 | 0.22774
| Hall |  |  |  |  | 400 | 999 | Lampton St | S Preston St | Dead End | 36.2169 | 4 | Local | [17 empty] | 149189.05 | [19 empty] | 3187.4777 | 30.1966 | 96251 | 1.5621
| Hall |  |  |  |  | 500 | 799 | Meriwether Ave | E Burnett Ave | S Shelby St | 62.3338 | 4 | Pri Coll | [17 empty] | 110292.435 | [19 empty] | 2228.13 | 30 | 66843.9 | 1.0848
| Hall |  | 350002-247 |  |  |  |  | N 1st St | W Main St | E Witherspoon St |  | 4 | [17 empty] | 4 | 150000 | 122034.64 | July
| Hall |  |  |  |  | 300 | 1499 | S 15th St | W Jefferson St | W Hill St | 53.5853 | 4 | Min Art | [17 empty] | 687630.9 | [19 empty] | 10228.8508 | 40.7422 | 416746 | 6.7634
| Hall |  |  |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | [19 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 1400 | 1454 | S Preston St | S Jackson St | E Burnett Ave | 54.0007 | 4 | Min Art | [17 empty] | 33037.95 | [19 empty] | 564.7347 | 35.4556 | 20023 | 0.32496
| Hall |  |  |  |  | 300 | 599 | S Wenzel St | E Chestnut St | E Jefferson St | 25.8121 | 4 | Local | [17 empty] | 74648 | [19 empty] | 1387.7936 | 34.7026 | 48160 | 0.78159
| Hall |  |  |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | [19 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  |  |  |  | 850 | 1499 | W Muhammad Ali Blvd | Roy Wilkins Ave | S 15th St | 56.2923 | 4 | Min Art | [17 empty] | 185212.5 | [19 empty] | 2927.305 | 38.3459 | 112250 | 1.8217
| Hall |  |  |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [19 empty] | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 600 | 699 | Hardin St | Bank St | Gilligan St | 2 | 5 | Local | [17 empty] | 19381.2 | [19 empty] | 247 | 25 | 6252 | 0.10146
| Hall |  |  |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | [19 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-277 |  |  | 100 | 299 | N & S 46th St | N Longworth Ave | W Market St | 20.6662 | 5 | Local | [13 empty] | 6 |  |  | 6 | 71380.6 | 5731.19 | [17 empty] | May have been paved into gutter from Longworth to Duncan | 1555.8172 | 29.5999 | 46052 | 0.74738
| Hall |  |  |  |  | 700 | 899 | N 33rd St | Northwestern Pky | Dead End | 54.0197 | 5 | Local | [17 empty] | 56883.45 | [19 empty] | 531.8259 | 69.0057 | 36699 | 0.59559
| Hall |  |  |  |  | 700 | 899 | N 34th St | Northwestern Pky | Dead End | 57.1053 | 5 | Local | [17 empty] | 41126.15 | [19 empty] | 514.4215 | 51.5783 | 26533 | 0.43061
| Hall |  |  |  |  | 700 | 799 | N 36th St | Northwestern Pky | Rudd Ave | 44 | 5 | Local | [17 empty] | 21298.55 | [19 empty] | 529 | 26 | 13741 | 0.223
| Hall |  | 350002-312 |  |  | 3200 | 3299 | Rudd Ave | Dead End (east) | N 34th St | 44.7342 | 5 | Local | [13 empty] | 12 |  |  |  | 87872.6 | 32983.13 | [17 empty] | Brick paver sidewalk NW of 34th, Possible LSR project. | 959.6305 | 59.0769 | 56692 | 0.92006
| Hall |  |  |  |  | 3400 | 3899 | Rudd Ave | N 34th St | Dead End (west) | 56.5344 | 5 | Local | [17 empty] | 107745.15 | [19 empty] | 1259.0092 | 55.2125 | 69513 | 1.1281
| Hall |  |  |  |  | 200 | 399 | Shawnee Dr | W Market St | Southwestern Pky | 20.4991 | 5 | Local | [17 empty] | 86138.15 | [19 empty] | 1543.6989 | 35.9999 | 55573 | 0.9019
| Hall |  |  |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | [19 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  |  |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | [19 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  |  |  |  | 1900-12-15 | 1904-05-17 | Southwestern Pky | S Shawnee Ter | Gibson Ln | 59.2734 | 5 | Min Art | [17 empty] | 598921.95 | [19 empty] | 10181.6927 | 35.6506 | 362983 | 5.8909
| Hall |  |  |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | [19 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  |  |  |  | 1901-05-19 | 1901-08-21 | Colorado Ave | Dead End | Algonquin Pky | 61.8146 | 6 | Maj Art | [17 empty] | 119260.35 | [19 empty] | 2131.5568 | 33.909 | 72279 | 1.173
| Hall |  | 350002-208 |  |  | 800 | 1155 | Dixie Hwy | Maple St | Hale Ave | 59.8113 | 6 | Min Art | [13 empty] | Ramps Complete |  |  |  | 202327.257 | See S 17th St | [18 empty] | 3226.91 | 38 | 122622.58 | 1.9901
| Hall |  | 350002-301 |  |  |  |  | Dumesnil St | Dixie Hwy | S 26th St | 59 | 6 | Min Art | [17 empty] | 125991 |  | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 2400 | 2899 | S Floyd St | Old Eastern Pky | Central Ave | 60.0965 | 6 | Pri Coll | [17 empty] | 29653.8 | [19 empty] | 412 | 43.6214 | 17972 | 0.29167
| Hall |  |  |  |  | 900 | 1499 | W Kentucky St | S 9th St | S 15th St | 52.5746 | 6 | Pri Coll | [17 empty] | 177564.75 | [19 empty] | 2808.5642 | 38.3167 | 107615 | 1.7465
| Hall |  |  |  |  | 1000 | 2399 | W Ormsby Ave | Dead End | S 25th St | 44.9819 | 6 | Local | [17 empty] | 310365.8 | [19 empty] | 7886.4736 | 25.3898 | 200236 | 3.2497
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hey | Catalpa St | 66 | 6 | Min Art | [17 empty] | 137347 | See Wilson Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | [19 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-308 |  |  |  |  | Lime Kiln Ln | US 42 | Brownsboro Rd | 65 | 7 | Pri Coll | [17 empty] | 120650 | 3734.75 | [17 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | [19 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-245 |  |  |  |  | Alta Vista Rd | Beargrass Ave | I-64 overpass | 58 | 8 | Local | [17 empty] | 153131 |  | July | [17 empty] | 4340 | 23 | 98794 | 1.6033
| Hall |  |  |  |  | 1 | 99 | Beverly Rd | Cross Rd | Dead End | 26 | 8 | Local | [17 empty] | 9203.9 | [19 empty] | 330 | 18 | 5938 | 0.096369
| Hall |  |  |  |  | 2300 | 2699 | Brookside Dr | Ingleside Dr | Dead End | 62 | 8 | Local | [13 empty] | 0 |  |  |  | 62048 | [18 empty] | Concrete. Circle of cul-de-sac may have been paved previously. | 646.3277 | 24 | 15512 | 0.25175
| Hall |  |  |  |  | 1 | 1449 | Cross Rd | Castlewood Ave | Eastern Pkwy | 58.4177 | 8 | Local | [17 empty] | 34146.5 | [19 empty] | 1223.9072 | 17.9997 | 22030 | 0.35753
| Hall |  |  |  |  | 2200 | 2549 | Hawthorne Ave | Bon Air Ave | Bardstown Rd | 43.7621 | 8 | Local | [17 empty] | 88168.65 | [19 empty] | 3037.4844 | 18.727 | 56883 | 0.92316
| Hall |  |  |  |  | 2300 | 2399 | Ingleside Dr | Woodbourne Ave | Dead End | 46.0948 | 8 | Local | [13 empty] | 0 |  |  |  | 53432.5 | [18 empty] | Concrete from Brookside to dead end. Watch for asphalt and decorative curb in asphalt section. | 911.9486 | 21.306 | 19430 | 0.31533
| Hall |  |  |  |  | 2860 | 2899 | Lowell Ave | Tyler Ln | Hawthorne Ave | 37 | 8 | Local | [17 empty] | 11778.45 | [19 empty] | 422.1865 | 18 | 7599 | 0.12333
| Hall |  | 350002-262 |  |  | 2400 | 2699 | Ransdell Ave | Grinstead Dr | Bassett Ave | 47.2922 | 8 | Local | [13 empty] | 6 |  |  | 7 | 94001.3 | 15500.75 | [17 empty] | Ray Ave may have been paved which updated ramps at this intersection | 2021.5198 | 30.0002 | 60646 | 0.98423
| Hall |  |  |  |  | 1630 | 1799 | Ruth Ave | Strand Ave | Radnor Ave | 58.6718 | 8 | Local | [17 empty] | 15067.55 | [19 empty] | 486.0341 | 20.0007 | 9721 | 0.15776
| Hall |  |  |  |  | 1617 | 1999 | Speed Ave | Fernwood Ave | Bardstown Rd | 23 | 8 | Local | [17 empty] | 72978.5 | [19 empty] | 1158 | 18 | 20851 | 0.33839
| Hall |  |  |  |  | 1905-06-22 | 1906-03-13 | Speed Ave | Bardstown Rd | Spring Dr | 64.8405 | 8 | Pri Coll | [17 empty] | 68566.905 | [19 empty] | 1385.19 | 30 | 41555.7 | 0.67441
| Hall |  |  |  |  | 2530 | 2599 | Woodbourne Ave | Valletta Ln | Cherosen Rd | 33.6999 | 8 | Local | [13 empty] | 0 |  |  |  | 54761.5 | [18 empty] | Watch for asphalt and decorative curbs | 1662.1826 | 21.2552 | 35330 | 0.57338
| Hall |  | 350002-245 |  |  | 2800 | 2899 | Alta Vista Pl | Alta Vista Ct | Dead End | 4 | 9 | Local | [13 empty] | 0 |  |  |  | 24260 |  | July | [16 empty] | Concrete, then transitions to Asphalt. | 379 | 16 | 6065 | 0.09843
| Hall |  | 350002-245 |  |  | 2800 | 2899 | Alta Vista Way | Alta Vista Rd | Dead End | 36 | 9 | Local | [13 empty] | 0 |  |  |  | 14496 |  | July | [16 empty] | Asphalt | 226 | 16 | 3624 | 0.058814
| Hall |  |  |  |  | 200 | 399 | Coralberry Rd | Dead End | Dead End | 55.9856 | 9 | Local | [17 empty] | 54516.6 | [19 empty] | 1506.6618 | 23.3443 | 35172 | 0.57081
| Hall |  |  |  |  | 200 | 299 | Mockingbird Gardens Dr | Dead End | Winterleaf Dr | 42.5777 | 9 | Local | [17 empty] | 57269.4 | [19 empty] | 1830.1722 | 20.1883 | 36948 | 0.59963
| Hall |  | 350002-290 |  |  | 100 | 299 | N Bayly Ave | Frankfort Ave | Hollywood Ter | 22.525 | 9 | Local | [13 empty] | 11 |  |  |  | 61958.15 | [18 empty] | Several ramps are stairs. Likely technically infeasible. | 1375.1377 | 29.0684 | 39973 | 0.64873
| Hall |  | 350002-290 |  |  | 200 | 299 | N Clifton Ave | Sycamore Ave | Brownsboro Rd | 46.5993 | 9 | Local | [13 empty] | 6 |  |  |  | 53104.55 | [18 empty] | Pave entire triangle area at Sycamore, one set of stairs at sycamore which is likely infeasible | 1285.4381 | 26.6532 | 34261 | 0.55603
| Hall |  | 350002-290 |  |  | 100 | 199 | N Jane St | Frankfort Ave | Brownboro Rd | 47.6659 | 9 | Local | [13 empty] | 8 |  |  |  | 56206.1 | [18 empty] | Need to confirm ADA ramps before RR tracks | 1893.1414 | 19.1544 | 36262 | 0.5885
| Hall |  |  |  |  | 200 | 399 | Pepperbush Rd | Dead End | Dead End | 55.3127 | 9 | Local | [17 empty] | 100709.7 | [19 empty] | 1046.8959 | 62.0635 | 64974 | 1.0545
| Hall |  |  |  |  | 3500 | 3599 | Waterleaf Ct | Waterleaf Way | Dead End | 44 | 9 | Local | [17 empty] | 23628.2 | [19 empty] | 693 | 22 | 15244 | 0.2474
| Hall |  |  |  |  | 200 | 299 | Waterleaf Way | Dead End | Mockingbird Gardens dr | 46.4515 | 9 | Local | [17 empty] | 28020.9 | [19 empty] | 821.7223 | 22.0001 | 18078 | 0.29339
| Hall |  |  |  |  | 3500 | 3599 | Winterberry Cir | Mockingbird Gardens Dr | Mockingbird Gardens Dr | 30 | 9 | Local | [17 empty] | 46517.05 | [19 empty] | 1429 | 21 | 30011 | 0.48705
| Hall |  |  |  |  | 1904-12-04 | 1906-01-07 | Bashford Manor Ln | Newburg Rd | Bardstown Rd | 65.1829 | 10 | Pri Coll | [17 empty] | 274355.5815 | [19 empty] | 5038.67 | 33 | 166276.11 | 2.6985
| Hall |  | 350002-291 |  |  | 1100 | 1299 | Boyle St | Charles St | Goss Ave | 44.0005 | 10 | Local | [13 empty] | 6 |  |  |  | 36327.35 | [18 empty] | LWC work was done in area | 781.2483 | 29.9994 | 23437 | 0.38036
| Hall |  | 350002-291 |  |  | 900 | 1199 | Charles St | Texas Ave | Dandridge Ave | 32.7758 | 10 | Local | [13 empty] | 15 |  |  |  | 106627.6 | [18 empty] | LWC work was done in area | 2456.8468 | 28.0001 | 68792 | 1.1164
| Hall |  |  |  |  | 1000 | 1099 | Dixon Ave | Dead End | Poplar Level Rd | 43 | 10 | Local | [17 empty] | 92589 | [19 empty] | 1102 | 24 | 26454 | 0.42933
| Hall |  |  |  |  | 1000 | 1099 | Eigelbach Ave | Dead End | Poplar Level Rd | 47 | 10 | Local | [17 empty] | 35391.15 | [19 empty] | 951 | 24 | 22833 | 0.37056
| Hall |  |  |  |  | 3100 | 3199 | Harmon Ct | Dead End | Audubon Pky | 0 | 10 | Local | [17 empty] | 35031.5 | [19 empty] | 417 | 24 | 10009 | 0.16244
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Bardstown Rd | Goldsmith Ln |  | 10 | Min Art | [13 empty] | 25 |  |  |  | 511151 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3647 | 62 | 226114 | 3.6696
| Hall |  |  |  |  | 3461 | 3781 | Illinois Ave | Sheridan Ave | 3461 Illinois Ave | 57.9238 | 10 | Local | [17 empty] | 105080.7 | [19 empty] | 3268.3937 | 20.7423 | 67794 | 1.1002
| Hall |  |  |  |  | 3150 | 3199 | Illinois Ave | Osprey Rd | Poplar Level Rd | 21 | 10 | Local | [17 empty] | 8337.45 | [19 empty] | 224.1407 | 24 | 5379 | 0.087296
| Hall |  | 350002-291 |  |  | 1200 | 1299 | Krierger St | Ellison Ave | Goss Ave | 39.3379 | 10 | Local | [13 empty] | 13 |  |  |  | 50722.2 | [18 empty] | Depress sidewalk to be flush with pavement at alleys where possible, LWC work done in area | 1168.7507 | 27.9991 | 32724 | 0.53108
| Hall |  |  |  |  | 1000 | 1099 | Mayer Ave | Dead End | Poplar Level Rd | 37 | 10 | Local | [17 empty] | 66146.5 | [19 empty] | 756 | 25 | 18899 | 0.30671
| Hall |  |  |  |  | 1400 | 1499 | Nightingale Rd | Eagle Pass | Audubon Pky | 39 | 10 | Local | [17 empty] | 58907.75 | [19 empty] | 1727 | 22 | 38005 | 0.61679
| Hall |  |  |  |  | 3100 | 3199 | Osprey Rd | Illinois Ave | Audubon Pky | 50 | 10 | Local | [17 empty] | 24330.35 | [19 empty] | 654 | 24 | 15697 | 0.25475
| Hall |  | 350002-310 |  |  | 2600 | 2899 | Parklawn Dr | Parkway Dr | Dead End | 41.6675 | 10 | Local | [13 empty] | 10 |  |  |  | 56649.4 | 29508.24 | [17 empty] | Pushed back to FY 21 due to virus | 1885.4269 | 19.3845 | 36548 | 0.59314
| Hall |  |  |  |  | 800 | 1699 | Texas Ave | S Shelby St | Wetterau Ave | 48 | 10 | Local | [17 empty] | 271580.15 | [19 empty] | 5300 | 34 | 175213 | 2.8436
| Hall |  | 350002-291 |  |  | 1200 | 1299 | Wetterau Ave | Texas Ave | Dead End | 23.7244 | 10 | Local | [13 empty] | 0 |  |  |  | 16535.4 | [18 empty] | Update ramp on other side of Samuel leading down to shoping center. LWC work done in area | 801.46 | 13.3107 | 10668 | 0.17313
| Hall |  | 350002-291 |  |  | 1000 | 1099 | Wetterau Ave at Ash St | Dead End | Dead End | 21 | 10 | Local | [13 empty] | 6 |  |  |  | 27932.55 | [18 empty] | Pushed back to FY 21 due to virus | 750.84 | 24.0011 | 18021 | 0.29247
| Hall |  |  |  |  | 8000 | 8199 | Amity Ln | Summerfield Dr | Dead End | 55.9519 | 11 | Local | [17 empty] | 31184.45 | [19 empty] | 1000.7746 | 20.1034 | 20119 | 0.32651
| Hall |  |  |  |  | 8000 | 8199 | Cloudcroft Ln | Summerfield Dr | Dead End | 50 | 11 | Local | [17 empty] | 53769.5 | [19 empty] | 1239 | 28 | 34690 | 0.56299
| Hall |  |  |  |  | 3100 | 3199 | Spring Breeze Ct | Amity Ln | Dead End | 55.4007 | 11 | Local | [17 empty] | 28616.1 | [19 empty] | 861.5499 | 21.4288 | 18462 | 0.29962
| Hall |  |  |  |  | 2530 | 2599 | Sunbury Ln | Winterhaven Rd | Winterhaven Rd | 58.8872 | 11 | Local | [17 empty] | 70025.9 | [19 empty] | 1946.0602 | 23.2151 | 45178 | 0.7332
| Hall |  |  |  |  | 8000 | 8099 | Weather Ct | Weather Way | Dead End | 65 | 11 | Local | [17 empty] | 7052.5 | [19 empty] | 253 | 18 | 4550 | 0.073843
| Hall |  |  |  |  | 3000 | 3199 | Weather Way | Summerfield Dr | Dead End | 68.3392 | 11 | Local | [17 empty] | 48962.95 | [19 empty] | 1435.8717 | 21.9999 | 31589 | 0.51266
| Hall |  |  |  |  | 3600 | 3999 | Baymeadow Dr (all) | Brinamwood Dr | Dead End | 72.9415 | 12 | Local | [17 empty] | 71907.6 | [19 empty] | 1973.6702 | 23.6667 | 46392 | 0.7529
| Hall |  |  |  |  | 3600 | 3699 | Birnamwood Ct | Birnamwood Dr | Dead End | 61 | 12 | Local | [17 empty] | 7209.05 | [19 empty] | 258 | 18 | 4651 | 0.075482
| Hall |  |  |  |  | 6900 | 7199 | Birnamwood Dr | St Andrews Church Rd | Baymeadow Dr | 72.8578 | 12 | Local | [17 empty] | 54293.4 | [19 empty] | 1487.6416 | 23.3333 | 35028 | 0.56847
| Hall |  |  |  |  | 3600 | 3699 | Eastmeadow Ct | Birnamwood Dr | Dead End | 56 | 12 | Local | [17 empty] | 6313.15 | [19 empty] | 226 | 18 | 4073 | 0.066101
| Hall |  |  |  |  | 6900 | 6999 | Hyland Hills Ct | Baymeadow Dr | Dead End | 48 | 12 | Local | [17 empty] | 4642.25 | [19 empty] | 150 | 20 | 2995 | 0.048606
| Hall |  |  |  |  | 1905-03-14 | 1906-01-07 | Lower Hunters Trce | Dixie Hwy | Upper Hunters Trce | 63.6414 | 12 | Pri Coll | [17 empty] | 91005 | [19 empty] | 3840.0384 | 29.3265 | 112615 | 1.8276
| Hall |  |  |  |  | 1906-01-08 | 1918-02-09 | Lower Hunters Trce | Upper Hunters Trce | Greenbelt Hwy | 66.9497 | 12 | Pri Coll | [17 empty] | 347664.9 | [19 empty] | 9483.5364 | 25.4712 | 210706 | 3.4196
| Hall |  |  |  |  | 100 | 199 | Mills Dr | Alreva Rd | Blanton Ln | 61.0339 | 12 | Local | [17 empty] | 97908.85 | [19 empty] | 3088.9085 | 20.4496 | 63167 | 1.0251
| LP |  |  |  |  | 1916-06-04 | 1918-08-12 | Sylvania Rd | Memory Ln | Rutledge Rd | 63.5483 | 12 | Sec Coll | [17 empty] | 60800.85 | [19 empty] | 1914.0068 | 19.2523 | 36849 | 0.59803
| Hall |  |  |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | [19 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-281 |  |  | 8000 | 8399 | Afterglow Dr | Dead End | Outer Loop | 49.0349 | 13 | Local | [13 empty] | 4 |  |  | 12 | 175466.2 | 57516 | [17 empty] | May look to add frontage Rd off Outer Loop | 4154.1404 | 27.2509 | 113204 | 1.8372
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | various drainage improvements needed, shoulder | 6261.5 | 19 | 118968.5 | 1.9308
| Hall |  |  |  |  | 800 | 899 | Candleglow Ct | Dead End | Candleglow Ln | 52 | 13 | Local | [17 empty] | 10231.55 | [19 empty] | 367 | 18 | 6601 | 0.10713
| Hall |  |  |  |  | 500 | 899 | Candlelight Ln | New Cut Rd | Dead End | 63.1036 | 13 | Local | [17 empty] | 81216.9 | [19 empty] | 2734.1962 | 19.164 | 52398 | 0.85037
| Hall |  |  |  |  | 400 | 499 | Garrison Ct | Dead End | Garrison Rd | 29 | 13 | Local | [17 empty] | 7745.35 | [19 empty] | 227 | 22 | 4997 | 0.081097
| Hall |  |  |  |  | 7300 | 7699 | Garrison Rd | Dead End | Revolutionary Rd | 53.4225 | 13 | Local | [17 empty] | 69548.5 | [19 empty] | 1908.6386 | 23.5089 | 44870 | 0.7282
| Hall |  |  |  |  | 10600 | 11499 | Harrison Ln | National Tpke | Dead End | 51.4903 | 13 | Local | [17 empty] | 150370.15 | [19 empty] | 5276.3386 | 18.3864 | 97013 | 1.5744
| LP |  |  |  |  | 1929-07-26 | 1935-04-25 | Holsclaw Hill Rd | Mitchell Hill Rd | Dead End | 65.6183 | 13 | Sec Coll | [17 empty] | 351212.4 | [19 empty] | 10567.5567 | 20.1424 | 212856 | 3.4545
| LP |  |  |  |  | 1919-03-01 | 1919-12-25 | Knob Creek Rd | Dead End | Mitchell Hill Rd | 58 | 13 | Sec Coll | [17 empty] | 50631.9 | [19 empty] | 1534.3038 | 20 | 30686 | 0.49801
| Hall |  |  |  |  | 800 | 899 | Taper Ct | Dead End | Candleglow Ln | 67 | 13 | Local | [17 empty] | 6747.15 | [19 empty] | 282 | 16 | 4353 | 0.070645
| Hall |  |  |  |  | 16700 | 17199 | Abbotts Beach Rd | Dixie Hwy | Dead End | 23 | 14 | Local | [17 empty] | 36318.05 | [19 empty] | 2343 | 10 | 23431 | 0.38026
| Hall |  |  |  |  | 5700 | 6099 | Alandale Dr | Dixie Hwy | Omar Khayyam Blvd | 59.1854 | 14 | Local | [17 empty] | 107878.45 | [19 empty] | 2719.5213 | 25.5924 | 69599 | 1.1295
| LP |  | 339051-8 | 2017-07-01 |  |  |  | Bearcamp Rd | Blevins Gap Rd | Wildflower Ln |  | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 287148 |  |  | PW '19 MAP | 8672-410-8210-148451-822702 | [14 empty] | On-hold until culvert replacement complete | 5239 | 18 | 94302 | 1.5304
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | see above | 6261.5 | 19 | 118968.5 | 1.9308
| LP |  |  |  |  | 1909-04-22 | 1915-05-25 | Blevins Gap Rd | Stonestreet Rd | Medora Rd | 70.2148 | 14 | Pri Coll | [17 empty] | 550000 | [19 empty] | 18719.4454 | 20.0252 | 374860 | 6.0837
| Hall |  |  |  |  | 9600 | 9699 | Britannia Ct | Dead End | Scarborough Ave | 61 | 14 | Local | [17 empty] | 23112.05 | [19 empty] | 621 | 24 | 14911 | 0.24199
| Hall |  |  |  |  | 11700 | 11899 | Deering Rd | Flowervale Ln | Dead End | 47 | 14 | Local | [17 empty] | 33464.5 | [19 empty] | 1080 | 20 | 21590 | 0.35039
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65 | 14 | Sec Coll | [17 empty] | 68000.427 | [19 empty] | 1719.962 | 24 | 41212.38 | 0.66884
| Hall |  |  |  |  | 6900 | 7199 | Ethan Allen Way | Kinross Blvd | Bessels Blvd | 42.3493 | 14 | Local | [17 empty] | 85963 | [19 empty] | 2310.8498 | 23.9998 | 55460 | 0.90007
| Hall |  |  |  |  | 6900 | 6999 | Fincastle Trl | Dead End | Lower River Rd | 42 | 14 | Local | [17 empty] | 14022.85 | [19 empty] | 905 | 10 | 9047 | 0.14682
| Hall |  |  |  |  | 2400 | 2499 | Hereford Ct | Scarborough Ave | Dead End | 12 | 14 | Local | [17 empty] | 7548.5 | [19 empty] | 271 | 18 | 4870 | 0.079036
| Hall |  |  |  |  | 2400 | 2499 | Kings Cross Ct | Dead End | Scarborough Ave | 56 | 14 | Local | [17 empty] | 9924.65 | [19 empty] | 291 | 22 | 6403 | 0.10392
| Hall |  |  |  |  | 9700 | 9799 | Leopold Ct | Scarborough Ave | Scarborough Ave | 22 | 14 | Local | [17 empty] | 9689.05 | [19 empty] | 313 | 20 | 6251 | 0.10145
| Hall |  |  |  |  | 9500 | 10099 | Omar Khayyam Blvd | Donau Ln | Count Fleet Dr | 69.6626 | 14 | Local | [17 empty] | 89163.75 | [19 empty] | 2396.8896 | 23.9999 | 57525 | 0.93358
| Hall |  |  |  |  | 2500 | 2505 | Parliament Ct | Scarborough Ave | Scarborough Ave | 55 | 14 | Local | [17 empty] | 9351.15 | [19 empty] | 335 | 18 | 6033 | 0.09791
| Hall |  |  |  |  | 9600 | 9699 | Pembury Ct | Scarborough Ave | Dead End | 23 | 14 | Local | [17 empty] | 7641.5 | [19 empty] | 274 | 18 | 4930 | 0.08001
| Hall |  |  |  |  | 9732 | 9899 | Scarborough Ave | Montpelier Ct | Lamborne Blvd | 65.1377 | 14 | Local | [17 empty] | 21024.2 | [19 empty] | 565.1696 | 23.9999 | 13564 | 0.22013
| Hall |  |  |  |  | 7200 | 7399 | Scenic Trl | Dead End | Lower River Rd | 47 | 14 | Local | [17 empty] | 17859.1 | [19 empty] | 886 | 13 | 11522 | 0.18699
| LP |  |  |  |  | 1935-01-16 | 1938-01-19 | Scotts Gap Rd | Blevins Gap Rd | Dead End | 67.2271 | 14 | Sec Coll | [17 empty] | 224112.9 | [19 empty] | 7455.678 | 18.2178 | 135826 | 2.2043
| LP |  |  |  |  | 1917-10-17 | 1920-07-12 | W Orell Rd | Dixie Hwy | Lower River Rd | 65.5631 | 14 | Pri Coll | [17 empty] | 174266.4 | [19 empty] | 5280.8336 | 19.9999 | 105616 | 1.7141
| Hall |  |  |  |  | 9600 | 9699 | Yarmouth Ct | Scarborough Ave | Dead End | 35 | 14 | Local | [17 empty] | 17054.65 | [19 empty] | 550 | 20 | 11003 | 0.17857
| Hall |  |  |  |  | 4300 | 4399 | Fluhr Dr | Dead End | Anna Ln | 51.7058 | 15 | Local | [17 empty] | 24564.4 | [19 empty] | 660.3467 | 23.9995 | 15848 | 0.2572
| Hall |  |  |  |  | 3500 | 3799 | Georgetown Pl | Berry Blvd | Dead End | 28.4435 | 15 | Local | [17 empty] | 41555.5 | [19 empty] | 1103.1397 | 24.3034 | 26810 | 0.4351
| Hall |  |  |  |  | 300 | 699 | Heywood Ave | S 3rd St | Rodman St | 53.2531 | 15 | Local | [17 empty] | 102665.8 | [19 empty] | 1919.8374 | 34.5008 | 66236 | 1.075
| Hall |  |  |  |  | 1200 | 1320 | Lance Dr | Manslick Rd | Leaf Dr | 59.0188 | 15 | Local | [17 empty] | 30051.4 | [19 empty] | 794.1409 | 24.4138 | 19388 | 0.31465
| Hall |  |  |  |  | 1600 | 1749 | March Blvd | Manslick Rd | Nichols Meadow Cir at school entrance | 71.0419 | 15 | Local | [17 empty] | 80654.25 | [19 empty] | 1224.4896 | 42.4953 | 52035 | 0.84448
| Seven Seas |  | 370579 |  |  |  |  | Rankin St | E Kenton St | E Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 18778.65 |  |  | PW Funds FY 17 | [15 empty] | PCCP - Most panels look ok, I would do select panel replacement - James |  |  | 0 | 0
| Hall |  |  |  |  | 4442 | 4516 | Rear View Dr | Lance Dr | Dead End | 19 | 15 | Local | [17 empty] | 45416 | [19 empty] | 649 | 20 | 12976 | 0.21059
| Hall |  |  |  |  | 2800 | 3099 | S 5th St | M St | Central Ave | 50.6617 | 15 | Local | [17 empty] | 64504.8 | [19 empty] | 1417.7832 | 29.3529 | 41616 | 0.67539
| Hall |  |  |  |  | 1906-07-27 | 1907-12-08 | S Floyd St | Old Eastern Pky | Central Ave | 60 | 15 | Pri Coll | [17 empty] | 214247.55 | [19 empty] | 3290 | 39.4672 | 129847 | 2.1073
| Seven Seas |  | 370579 |  |  |  |  | Tulane Ave | W Kenton St | W Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 14086.05 |  |  | PW Funds FY 17 | [15 empty] | PCCP |  |  | 0 | 0
|  |  | 350002-198 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 |  |  | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1200 | 1499 | Weyler Ave | Arcade Ave | Dead End | 51 | 15 | Local | [17 empty] | 52250.5 | [19 empty] | 1705 | 20 | 33710 | 0.54708
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus. Will be pushed to FY 22
| Hall |  |  |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | [19 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  |  |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | [19 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  |  |  |  | 1920-07-13 | 1921-11-24 | Wolf Pen Branch Rd | Wolf Pen Ln (east of intersection) | Spring Farm Rd | 77.753 | 16 | Sec Coll | [17 empty] | 95670.3 | [19 empty] | 2959.4685 | 19.592 | 57982 | 0.941
| Hall |  | 350002-292 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | [18 empty] | Pushed back to FY 21 due to virus | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-292 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | [18 empty] | Pushed back to FY 21 due to virus | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-292 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | [18 empty] | Pushed back to FY 21 due to virus | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-292 |  |  | 11006 | 11199 | Eagles Cove Dr | Kestrel Ct | Hickory Cove Ct | 61.2884 | 17 | Local | [13 empty] | 5 |  |  |  | 73635.85 | [18 empty] | Pushed back to FY 21 due to virus | 2077.047 | 22.8724 | 47507 | 0.771
| Hall |  | 350002-292 |  |  | 4500 | 4599 | Goshawk Ct | Eagles Cove Dr | Dead End | 66 | 17 | Local | [13 empty] | 2 |  |  |  | 15304.7 | [18 empty] | Pushed back to FY 21 due to virus | 411.4091 | 24 | 9874 | 0.16025
| Hall |  | 350002-292 |  |  | 10700 | 10712 | Hickory Cove Ct | Shenandoah Dr | Eagles Cove Dr | 52 | 17 | Local | [13 empty] | 3 |  |  |  | 26463.15 | [18 empty] | Pushed back to FY 21 due to virus | 656.6535 | 26 | 17073 | 0.27708
| Hall |  |  |  |  | 13600 | 13699 | Sample Ct | Sample Way | Dead End | 67 | 17 | Local | [17 empty] | 11609.5 | [19 empty] | 312.0762 | 24 | 7490 | 0.12156
| Hall |  |  |  |  | 3400 | 3599 | Sample Way | Colonial Springs Rd | Springs Station Rd | 59.8943 | 17 | Local | [17 empty] | 72225.35 | [19 empty] | 2053.5541 | 22.6909 | 46597 | 0.75623
| Hall |  |  |  |  | 13400 | 13499 | Sapling Spring Pl | Dead End | Sample Way | 70 | 17 | Local | [17 empty] | 6300.75 | [19 empty] | 169.381 | 24 | 4065 | 0.065971
| Hall |  |  |  |  | 13500 | 13599 | Squire Springs Ct | Sample Way | Dead End | 66 | 17 | Local | [17 empty] | 15921.6 | [19 empty] | 428.0127 | 24 | 10272 | 0.16671
| Hall |  |  |  |  | 600 | 609 | Dorsey Way | Rymer Way | Elsmere Cir | 87 | 18 | Local | [17 empty] | 19729.95 | [19 empty] | 303 | 42 | 12729 | 0.20658
| Hall |  |  |  |  | 600 | 799 | Elsmere Cir | Dorsey Way | Tamarisk Pkwy | 72.7037 | 18 | Local | [17 empty] | 54589.45 | [19 empty] | 1565.7643 | 22.4932 | 35219 | 0.57157
| Hall |  |  |  |  | 1 | 99 | Hallsdale Dr | Taylorsville Rd | Dead End | 63.1729 | 18 | Local | [17 empty] | 102778.95 | [19 empty] | 2762.8307 | 24.0004 | 66309 | 1.0761
| Hall |  |  |  |  | 600 | 602 | Rymer Way | Winyan Ln | Dorsey Way | 46 | 18 | Local | [17 empty] | 11657.55 | [19 empty] | 341.8596 | 22 | 7521 | 0.12206
| Hall |  |  |  |  | 9900 | 9999 | Spring Ridge Dr | Dead End | Dorsey Way | 49 | 18 | Local | [17 empty] | 30590.8 | [19 empty] | 939.8092 | 21 | 19736 | 0.3203
| Hall |  |  |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 61.7099 | 18 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| Hall |  |  |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | [19 empty] | 1488.0063 | 89 | 132433 | 2.1493
| LP |  | 350002-286 |  |  |  |  | Hagen Rd | Hersfield Rd | dead end |  | 19 | [18 empty] | 12500 |  |  | CIF - *Temp PW '19 Bond | 8138-410-8107-148919-822702 | 12500 |  | 8137-410-8210-148451-822702 | 12500 | [10 empty] | Pushed back to FY 21 due to virus |  |  | 12493 | 0.20275
| Hall |  |  |  |  | 1100 | 1599 | Heafer Rd | N English Station Rd | La Grange Rd | 41 | 19 | Local | [17 empty] | 99816.9 | [19 empty] | 3136 | 21 | 64398 | 1.0451
| Hall |  | 350002-286 |  |  |  |  | Herfield Rd |  |  |  | 19 | Local | [17 empty] | 15000 |  |  | Council | 8138-410-8107-048101-822702 | 15000 | [13 empty] | Pushed back to FY 21 due to virus
| LP |  |  |  |  | 1903-07-23 | 1905-06-21 | N English Station Rd | La Grange Rd | Old Henry Rd | 70.6362 | 19 | Pri Coll | [17 empty] | 190665.75 | [19 empty] | 4744.6459 | 24.3548 | 115555 | 1.8754
| Hall |  |  |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 19 | Pri Coll | [13 empty] | 3 |  |  |  | 34471.7505 | [18 empty] | 0.5 in D 20, need to fix up one radius with potential curba nd gutter. 3 ramps at Urton Ln. | 1160.665 | 18 | 20891.97 | 0.33906
| Hall |  |  |  |  | 12300 | 12499 | Park Field Rd | Heafer Rd | Dead End | 41 | 19 | Local | [17 empty] | CIF | [19 empty] | 711 | 21 | 14643 | 0.23764
| Hall |  | 350002-286 |  |  |  |  | Parkfield Rd |  |  |  | 19 | [18 empty] | 22000 |  |  | Council | 8138-410-8107-048101-822702 | 16000 |  | 8144-410-8107-048101-822702 | 6000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 62 | 19 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  |  |  |  | 1927-12-04 | 1932-04-20 | Easum Rd | Billtown Rd | Old Heady Rd | 65.4048 | 20 | Pri Coll | [17 empty] | 378646.95 | [19 empty] | 12312.9475 | 18.6375 | 229483 | 3.7243
| LP |  | 339051-62 |  |  | 600 | 6499 | Gellhaus Ln | Chenoweth Run Rd | Billtown Rd | 61.166 | 20 | Sec Coll | [13 empty] | 6 |  |  |  | 181381.398 |  | July | [16 empty] | Intersection improvement at Chenoweth Run, possible culverts and Guardrail replacements needed. | 4672.76 | 23.5253 | 109928.12 | 1.784
| LP |  |  |  |  | 9700 | 9299 | Hassy Way | Dry Ridge Rd | Dead End | 84.5338 | 20 | Local | [17 empty] | 189358 | [19 empty] | 1865.9377 | 23.4429 | 43743 | 0.70991
| Hall |  |  |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 20 | Pri Coll | [13 empty] | See N Pope Lick |  |  |  | 34471.7505 | [18 empty] | 0.5 in D 19, see other N Pope Lick | 1160.665 | 18 | 20891.97 | 0.33906
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  |  |  |  | 3500 | 4299 | Old Routt Rd | Dead End | Routt Rd | 45.5989 | 20 | Local | [17 empty] | 224937.55 | [19 empty] | 7256.044 | 20 | 145121 | 2.3552
| LP |  |  |  |  | 15200 | 15299 | Old Taylorsville Rd (near Eastwood Fisherville intersection) | Dead End | Taylorsville Rd | 12 | 20 | Local | [17 empty] | 24133.5 | [19 empty] | 1112.1651 | 14 | 15570 | 0.25269
| LP |  |  |  |  | 14000 | 14199 | Old Taylorsville Rd at Wilderness Trl | Taylorsville Rd | Dead End | 55.6534 | 20 | Local | [17 empty] | 34870.35 | [19 empty] | 1318.8779 | 17.0577 | 22497 | 0.36511
| LP |  |  |  |  | 11800 | 14499 | Rehl Rd | Blankenbaker Pkwy | S Pope Lick Rd | 60.2949 | 20 | Pri Coll | [13 empty] | 0 |  |  |  | 430623.633 |  | July | [16 empty] | Need cores taken, possibly thin asphalt. Possible Fiber project. Check Guardrails. Need to review intersection at Tucker Station Rd | 11862.91 | 22 | 260984.02 | 4.2355
| Hall |  |  |  |  | 3500 | 4299 | S Pope Lick Rd | Old Taylorsville Rd | Dead End | 26 | 20 | Local | [13 empty] | 0 |  |  |  | 183792.8 | [18 empty] | May have been repaved with Parklands project | 6975.0624 | 17 | 118576 | 1.9244
| LP |  |  |  |  | 3400 | 3999 | Wilderness Trl | Old Taylorsville Rd | Dead End | 52 | 20 | Local | [17 empty] | 115172.75 | [19 empty] | 4644.0491 | 16 | 74305 | 1.2059
| LP |  |  |  |  | 16300 | 16399 | Witch Hazel Dr | Hassy Way | Dead End | 90 | 20 | Local | [17 empty] | 66598 | [19 empty] | 610 | 24 | 14639 | 0.23758
| Hall |  |  |  |  | 4400 | 4699 | Allmond Ave | E Woodlawn Ave | Dead End (north) | 54.248 | 21 | Local | [17 empty] | 131756.2 | [19 empty] | 3325.2587 | 25.5631 | 85004 | 1.3795
| Hall |  |  |  |  | 300 | 399 | Chris Dr | Homestead Dr | Dead End | 61 | 21 | Local | [17 empty] | 5054.55 | [19 empty] | 271.7278 | 12 | 3261 | 0.052923
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [19 empty] | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-279 |  |  | 100 | 199 | E Amherst Ave | S 1st St | Wabash Pl | 48.8533 | 21 | Local | [13 empty] | 0 |  |  |  | 50161.1 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 1274.1882 | 25.3981 | 32362 | 0.52521
| Hall |  | 350002-279 |  |  | 100 | 199 | E Tenny Ave | S 1st St | St Leo Pl | 42 | 21 | Local | [13 empty] | 3 |  |  |  | 28551 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 658 | 28 | 18420 | 0.29894
| Hall |  |  |  |  | 200 | 299 | E Woodlawn Ave | Allmond Ave | Nevada Ave | 68 | 21 | Min Art | [17 empty] | 127152.3 | [19 empty] | 1926.5536 | 39.9999 | 77062 | 1.2506
| Hall |  |  |  |  | 5000 | 5199 | Emery Ave | Lyman Ave | W Kenwood Dr | 54 | 21 | Local | [17 empty] | 24539.6 | [19 empty] | 754 | 21 | 15832 | 0.25694
| Hall |  |  |  |  | 5000 | 5199 | Fay Ave | W Kenwood Dr | Alger Ave | 48.6736 | 21 | Local | [17 empty] | 42524.25 | [19 empty] | 1287.734 | 21.3049 | 27435 | 0.44525
| Hall |  |  |  |  | 5900 | 6199 | Gloria Ln | Catheen Way | Dead End | 43.0059 | 21 | Local | [17 empty] | 47087.45 | [19 empty] | 1318.1272 | 23.0471 | 30379 | 0.49302
| Hall |  |  |  |  | 300 | 399 | Hatcher Ave | Southside Dr | Homestead Dr | 39 | 21 | Local | [17 empty] | 15921.6 | [19 empty] | 641.9717 | 16 | 10272 | 0.16671
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
| Hall |  |  |  |  | 300 | 399 | Hillview Dr | Southside Dr | Homestead Dr | 23 | 21 | Local | [17 empty] | 20945.15 | [19 empty] | 750.738 | 18 | 13513 | 0.2193
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-279 |  |  | 4900 | 4999 | Hollins Rd | St Leo Pl | E Amherst Ave | 60 | 21 | Local | [13 empty] | 5 |  |  | 5 | 14066.25 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 303 | 30 | 9075 | 0.14728
| Hall |  |  |  |  | 6800 | 7099 | Homestead Dr | E Kenwood Dr | Dead End | 44.1624 | 21 | Local | [17 empty] | 37426.3 | [19 empty] | 1442.2483 | 16.7419 | 24146 | 0.39187
| Hall |  |  |  |  | 4800 | 5999 | Hood Rd | W Indian Trl | Catheen Way | 14 | 21 | Local | [17 empty] | 30860.5 | [19 empty] | 996 | 20 | 19910 | 0.32312
| Hall |  |  |  |  | 6100 | 6199 | Loretta St | Elam Ct | Whitlock St | 78.4686 | 21 | Local | [17 empty] | 39190.2 | [19 empty] | 1053.4975 | 24.0001 | 25284 | 0.41034
| Hall |  |  |  |  | 500 | 599 | Lyman Ave | Laughlin Ave | Fay Ave | 53 | 21 | Local | [17 empty] | 10696.55 | [19 empty] | 314 | 22 | 6901 | 0.112
| Hall |  |  |  |  | 700 | 799 | Lyman Ave | Reed Ave | Emery Ave | 54 | 21 | Local | [17 empty] | 9114 | [19 empty] | 294 | 20 | 5880 | 0.095427
| Hall |  |  |  |  | 300 | 399 | Meadowood Ct | Southside Dr | Dead End | 29 | 21 | Local | [17 empty] | 7184.25 | [19 empty] | 579.3129 | 8 | 4635 | 0.075222
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 5900 | 6199 | Orville Dr | Gloria Ln | Dead End | 41.6904 | 21 | Local | [17 empty] | 44374.95 | [19 empty] | 1192.8763 | 24 | 28629 | 0.46462
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [19 empty] | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 5000 | 5199 | Reed Ave | W Kenwood Dr | Dead End | 65.1753 | 21 | Local | [17 empty] | 30215.7 | [19 empty] | 935.098 | 20.847 | 19494 | 0.31637
| Hall |  | 350002-279 |  |  | 4800 | 4999 | S 1st St | E Amherst Ave | Dead End to north | 61.3741 | 21 | Local | [13 empty] | 4 |  |  | 4 | 35997.2 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 822.4664 | 28.237 | 23224 | 0.37691
| Hall |  |  |  |  | 2825 | 2899 | Smilax Ave | Loretta St | W Indian Trl | 78 | 21 | Local | [17 empty] | 12877.4 | [19 empty] | 346 | 24 | 8308 | 0.13483
| Hall |  | 350002-279 |  |  | 100 | 114 | W Amherst Ave | Southside Dr | S 1st St | 59 | 21 | Local | [13 empty] | 4 |  |  |  | 16994.2 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 422 | 26 | 10964 | 0.17794
| Hall |  |  |  |  | 900 | 1199 | W Indian Trl | Preston Hwy | Dead End | 52.6638 | 21 | Local | [17 empty] | 116784.75 | [19 empty] | 3947.8218 | 19.0852 | 75345 | 1.2228
| Hall |  | 350002-279 |  |  | 200 | 5799 | W Southland Blvd | Southside Dr | Southern Pkwy | 54.9398 | 21 | Pri Coll | [13 empty] | 15 |  |  | 15 | 256091.9955 | 216139.24 | [17 empty] | 2 speed humps on roadway, need to check ramps at southland Ter. | 5145.34 | 30.1646 | 155207.27 | 2.5189
| Hall |  | 350002-279 |  |  | 100 | 199 | W Tenny Ave | S 1st St | Southside Dr | 35 | 21 | Local | [13 empty] | 8 |  |  |  | 19027.8 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 409 | 30 | 12276 | 0.19923
| Hall |  |  |  |  | 2800 | 2899 | Whitlock St | Norton Ave | Loretta St | 85 | 21 | Local | [17 empty] | 29848.35 | [19 empty] | 837 | 23 | 19257 | 0.31252
| Hall |  |  |  |  | 5400 | 5499 | Winding Rd | Woodmore Ave | Dead End | 47 | 21 | Local | [17 empty] | 46949.5 | [19 empty] | 1121.8398 | 27 | 30290 | 0.49158
| LP |  |  |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [19 empty] | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 1924-08-21 | 1925-03-08 | Fern Creek Rd | Beulah Church Rd | Bardstown Rd | 64.6738 | 22 | Pri Coll | [17 empty] | 139346.2469 | [19 empty] | 4021.5367 | 21 | 84452.2709 | 1.3706
| Hall |  |  |  |  | 8600 | 8609 | Glenhope Dr | Black Iron Rd | break south of Stonebreaker Rd | 56.1215 | 22 | Local | [17 empty] | 25878.8 | [19 empty] | 695.6754 | 23.9997 | 16696 | 0.27096
| Hall |  |  |  |  | 10500 | 10699 | Stonebreaker Rd | Dead End | Dead End | 49.7486 | 22 | Local | [17 empty] | 76402.6 | [19 empty] | 2155.5713 | 22.8673 | 49292 | 0.79997
| Hall |  |  |  |  | 8300 | 8499 | Berea Dr | Damascus Ct | Sardis Way | 44 | 23 | Local | [17 empty] | 46244 | [19 empty] | 1005 | 23 | 23122 | 0.37525
| Hall |  |  |  |  | 6200 | 6399 | Hackberry Way | Maple Rd | Lancewood Rd | 44 | 23 | Local | [17 empty] | 53769.5 | [19 empty] | 1576.8029 | 22 | 34690 | 0.56299
| Hall |  |  |  |  | 9600 | 9899 | Lancewood Rd | Dead End | Price Lane Rd | 46.4626 | 23 | Local | [17 empty] | 50145.6 | [19 empty] | 1516.9546 | 21.3269 | 32352 | 0.52504
| Hall |  | 350002-235 |  |  | 8400 | 9399 | Pennsylvania Run Rd | Vaughn Mill Rd | Cooper Chapel Rd | 60.244 | 23 | Pri Coll | [13 empty] | 0 |  |  |  | 221604.4215 | See Cooper Chapel Rd | [17 empty] | Need to replace 1 culvet for sure, but review others. Update guardrails as necessary. Will avoid sidewalk ramps if possible | 6395.51 | 21 | 134305.71 | 2.1797
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Outer Loop | Pennsylvania Run Rd | 65 | 23 | Pri Coll | [17 empty] | 145558 | 8645.18 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Fegenbush Ln | Outer Loop | 65 | 23 | Pri Coll | [17 empty] | 86290 | See Vaughn Mill Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 9500 | 9599 | Yellow Pine Ct | Dead End | Yellow Pine Dr | 48 | 23 | Local | [17 empty] | 18097.8 | [19 empty] | 486.509 | 24 | 11676 | 0.18949
| Hall |  | 350002-283 |  |  | 3800 | 3899 | Britt Ln | Dead End | Rust Oak Ln | 39.4136 | 24 | Local | [13 empty] | 5 |  |  |  | 47330.8 |  | July | [16 empty] | Pushed back to FY 21 due to virus | 1297.2258 | 23.5395 | 30536 | 0.49557
| Hall |  | 350002-283 |  |  | 8100 | 8199 | Carnes Dr | Dead End | Tuesday Way | 38 | 24 | Local | [13 empty] | 3 |  |  |  | 11198.75 |  | July | [16 empty] | Pushed back to FY 21 due to virus | 301.058 | 24 | 7225 | 0.11726
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  | 350002-283 |  |  | 8000 | 8299 | Horizon Ln | Dead End | Foreman Ln | 48.5169 | 24 | Local | [13 empty] | 2 |  |  |  | 39569.95 |  | July | [16 empty] | Pushed back to FY 21 due to virus | 1088.3103 | 23.4575 | 25529 | 0.41431
| Hall |  |  |  |  | 6000 | 6199 | Ledgerock Cove Pl | Dead End | Dead End | 80.4892 | 24 | Local | [17 empty] | 30097.9 | [19 empty] | 970.9416 | 24 | 19418 | 0.31514
| Hall |  |  |  |  | 6900 | 7099 | Ledgerock Rd | Ledgerock Cove Pl | Moorhaven Dr | 47.5203 | 24 | Local | [17 empty] | 40166.7 | [19 empty] | 1079.7727 | 23.9995 | 25914 | 0.42056
| LP |  |  |  |  | 1901-11-30 | 1903-10-30 | McCawley Rd | Preston Hwy | Jefferson Blvd | 66.4236 | 24 | Pri Coll | [17 empty] | 195165.3 | [19 empty] | 4479.469 | 26.4054 | 118282 | 1.9196
| Hall |  | 350002-237 |  |  |  |  | Monaco Dr | Woodhill Ln | Morningside Way | 48 | 24 | Local | [16 empty] | 3 | 43368 | 4697.21 | July | Council | 8125-410-8107-148385-822702 | 103880.92 |  | 8137-410-8210-148385-822702 | 6320.87 |  | 8101-410-8210-148385-822702 | 61863.6 | [7 empty] | Pushed back to FY 21 due to virus |  |  | 28912 | 0.46922
| Hall |  | 350002-237 |  |  |  |  | Morningside Way | Monaco Dr | Dead End | 20 | 24 | Local | [17 empty] | 27317 |  | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 18211 | 0.29555
| Hall |  | 350002-237 |  |  |  |  | Oaklawn Dr | Preston Hwy | Dead End | 48 | 24 | Local | [17 empty] | 100551 |  | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 67034 | 1.0879
|  |  | 350002-238 |  |  |  |  | Prestonview Ln | Foreman Ln | dead end | 31 | 24 | Local | [13 empty] | 0 |  |  |  | 17791.74 | See Tuesday Way | July | Council | 8133-410-8107-148385-822702 | 17791.74 | [13 empty] | Pushed back to FY 21 due to virus
|  |  | 350002-238 |  |  |  |  | Trio Ave | Preston Hwy | Prestonview Ln | 33 | 24 | Local | [13 empty] | 0 |  |  |  | $17,791,75 | See Tuesday Way | July | Council | 8133-410-8210-148385-822702 | 17791.75 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  | 350002-283 |  |  | 3700 | 3999 | Tuesday Way | Woodbury Dr | Dead End | 42.0113 | 24 | Local | [13 empty] | 7 |  |  |  | 90795.9 | 56577.94 | July | [16 empty] | Pushed back to FY 21 due to virus | 2255.064 | 25.9762 | 58578 | 0.95067
| Hall |  | 350002-283 |  |  | 3700 | 3799 | Wednesday Way | Dead End | Horizon Ln | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 20393.35 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 548.2191 | 24 | 13157 | 0.21353
| Hall |  |  |  |  | 5400 | 5499 | Dannyboy Ln | Ida Way | Dead End | 51 | 25 | Local | [17 empty] | 18463.6 | [19 empty] | 541.4771 | 22 | 11912 | 0.19332
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65.4587 | 25 | Sec Coll | [17 empty] | 272001.708 | [19 empty] | 6879.848 | 23.9612 | 164849.52 | 2.6754
| Hall |  |  |  |  | 5400 | 5499 | Hickory Hill Rd | Park Rd | Southview Rd | 52 | 25 | Local | [17 empty] | 24924 | [19 empty] | 730.9304 | 22 | 16080 | 0.26096
| Hall |  |  |  |  | 900 | 999 | Ida Way | Sunnybrook Dr | Dannyboy Ln | 55 | 25 | Local | [17 empty] | 10510.55 | [19 empty] | 308.2079 | 22 | 6781 | 0.11005
| LP |  | 339051-64 |  |  | 8300 | 8499 | McNair Rd | Manslick Rd | 3rd Street Rd | 62.7373 | 25 | Pri Coll | [13 empty] | 0 |  |  |  | 40944.123 | [18 empty] | Proposed Development may repave McNair. Various base failures, edge of road reconstruction needed. Some sort of shoulder will also be needed. May need to replace driveway on Wisertown Rd with this project, so prioritize for Summer 2019. | 1378.59 | 18 | 24814.62 | 0.40272
| Hall |  |  |  |  | 5300 | 5399 | Southdale Rd | Palatka Rd | Southview Rd | 68.1387 | 25 | Local | [17 empty] | 63858.45 | [19 empty] | 1872.6681 | 22.0002 | 41199 | 0.66862
| Hall |  |  |  |  | 918 | 900 | Southview Rd | Southdale Rd | Palatka Rd | 56.0019 | 25 | Local | [17 empty] | 49846.45 | [19 empty] | 1339.9785 | 23.9996 | 32159 | 0.52191
| LP |  |  |  |  | 9000 | 9302 | Stonestreet Rd | Dixie Hwy | Valley College Dr | 65.9195 | 25 | Min Art | [17 empty] | 296780.55 | [19 empty] | 3575.0904 | 50.3112 | 179867 | 2.9191
| Hall |  |  |  |  | 5400 | 5499 | Sunnybrook Dr | Palatka Rd | Dead End | 55.7993 | 25 | Local | [17 empty] | 33266.1 | [19 empty] | 894.2654 | 23.9996 | 21462 | 0.34831
| Hall |  |  |  |  | 900 | 999 | Westview Dr | New Cut Rd | Dead End | 51 | 25 | Local | [17 empty] | 35299.7 | [19 empty] | 1084.4551 | 21 | 22774 | 0.3696
|  |  | 350002-319 |  |  |  |  | Bashford Manor Ln | Bardstown Rd | Medford Ln |  | 26 | Local | [17 empty] | 42000 |  |  | Council | 8138-105-8107-038226-899998 | 23000 |  | 8138-410-8107-148387-822702 | 19000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 3000 | 3014 | Boaires Ln | Talisman Rd | Rio Rita Ave | 47 | 26 | Local | [17 empty] | 17921.1 | [19 empty] | 481.737 | 24 | 11562 | 0.18764
| Hall |  |  |  |  | 2900 | 3099 | Bowman Ave | Dutchmans Ln | Dead End | 50.8815 | 26 | Local | [17 empty] | 42772.25 | [19 empty] | 1404.5798 | 19.6464 | 27595 | 0.44784
| Hall |  |  |  |  | 2900 | 2999 | Cannons Ln | Dutchmans Ln | Bowman Ave | 35.207 | 26 | Local | [17 empty] | 32943.7 | [19 empty] | 929.1685 | 22.8742 | 21254 | 0.34493
| Hall |  |  |  |  | 6012 | 6399 | Dutchmans Ln | Dutchmans Pky | Dutchmans Pky | 46 | 26 | Local | [17 empty] | 142852.65 | [19 empty] | 2973 | 31 | 92163 | 1.4957
| Hall |  |  |  |  | 3500 | 3599 | Ephraim Mcdowell Dr | Cannons Ln | Abigail Dr | 48.9726 | 26 | Local | [17 empty] | 36181.65 | [19 empty] | 1003.653 | 23.258 | 23343 | 0.37884
| Hall |  |  |  |  | 1908-03-18 | 1909-04-21 | Furman Blvd | Taylorsville Rd | Hikes Ln | 63.8043 | 26 | Pri Coll | [17 empty] | 269468.892 | [19 empty] | 3983.28 | 41 | 163314.48 | 2.6505
| NA |  |  | 2018-07-01 |  | 3000 | 3499 | Hikes Ln | Klondike Ln | Browns Ln | 57.2165 | 26 | Min Art | [13 empty] | 22 |  |  |  | 603010.8 |  |  | PW Funds |  | 603010.8 | [13 empty] | Will try to group with KYTC and bid seperately, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 5316.81 | 60 | 301505.4 | 4.8932
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Klondike Ln | Goldsmith Ln |  | 26 | Min Art | [13 empty] | 20 |  |  |  | 510705 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3483.5026 | 62 | 215977.1635 | 3.5051
| Hall |  | 350002-257 |  |  | 2700 | 3899 | Klondike Ln | Six Mile Ln | Hikes Ln | 61.6177 | 26 | Pri Coll | [13 empty] | 25 |  |  | 12 | 221552.1 | 36215.73 | July | [16 empty] | Look at cross drain near Six Mile Ln, others which may be present. Probable fiber project. | 6394 | 21 | 134274 | 2.1792
| Hall |  |  |  |  | 3000 | 3199 | Talisman Rd | Kings Hwy | Boaires Ln | 47.314 | 26 | Local | [17 empty] | 139885.95 | [19 empty] | 3610.2177 | 24.9982 | 90249 | 1.4647
| QK4 |  | 314578-70 |  |  |  |  | QK4 Density Testing | [22 empty] | 20000 | 33186.51 |  | PW Funds | 8672-410-8210-148929-822703 | 20000 | [17 empty] | 0
| QK4 |  | 314578-78 |  |  |  |  | QK4 supplemental Inspections | [22 empty] | 20000 | 51389 |  | PW Funds | 8672-410-8210-148929-822704 | 20000 | [17 empty] | 0
| QK4 |  | 314578-119 |  |  |  |  | St Anthony Slide | [23 empty] | 3575.74 | [21 empty] | 0

## August 20
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 3700 | 4199 | Grand Ave | Dead End east of 38th | Cecil Ave | 50.0041 | 1 | Local | [17 empty] | 72590.5765 | [19 empty] | 1711.95 | 27.3563 | 46832.63 | 0.76005
| Hall |  |  |  |  | 2600 | 2999 | Grand Ave | S 26th St | Dead End to west | 61.1995 | 1 | Local | [17 empty] | 64222.824 | [19 empty] | 1255.22 | 33.0094 | 41434.08 | 0.67244
| Hall |  |  |  |  | 3000 | 3699 | Grand Ave | Dead End east of 32nd | Dead End west of Canopy Ct | 64.4573 | 1 | Local | [17 empty] | 131092.8 | [19 empty] | 2917.54 | 32.8616 | 84576 | 1.3726
| Hall |  |  |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | [19 empty] | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  |  |  |  | 3200 | 3699 | Hale Ave | S 32nd St | Dead End to west | 48.0322 | 1 | Local | [17 empty] | 103495.05 | [19 empty] | 2281.7 | 29.2637 | 66771 | 1.0836
| Hall |  |  |  |  | 1904-12-04 | 1919-12-25 | Lower Hunters Trce | Dixie Hwy | Greenbelt Hwy | 65.8978 | 1 | Pri Coll | [17 empty] | 50887.65 | [19 empty] | 1117 | 27.6106 | 30841 | 0.50052
| Hall |  |  |  |  | 6616 | 7299 | Lower Hunters Trce | Greenbelt Hwy | Cane Run Rd | 64.1728 | 1 | Pri Coll | [17 empty] | 116082.681 | [19 empty] | 2705.89 | 26 | 70353.14 | 1.1418
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [13 empty] | 2 |  |  |  | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-255 |  |  | 3400 | 3799 | W Magnolia Ave | Louis Coleman Jr Dr | Gibson Ln | 35 | 1 | Local | [13 empty] | 3 |  |  | 3 | 125495.75 | 99645.81 | July | [16 empty] | Seems to be many Semi Tractor Trailors. May use Fiber | 2381.3351 | 34 | 80965 | 1.314
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hwy | W Hill St | 67 | 1 | Min Art | [17 empty] | 293670 | 242320.52 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 3600 | 3699 | Friar Tuck Ct | Robinhood Ln | Dead End | 41 | 2 | Local | [17 empty] | 13852.35 | [19 empty] | 406 | 22 | 8937 | 0.14504
| Hall |  |  |  |  | 5100 | 5199 | Jefferson Blvd | Poplar Level Rd | Fern Valley Rd | 58.4628 | 2 | Min Art | [17 empty] | 117874.35 | [19 empty] | 1152.2379 | 62.0002 | 71439 | 1.1594
| Hall |  |  |  |  | 3600 | 3699 | Little John Ct | Robinhood Ln | Dead End | 54 | 2 | Local | [17 empty] | 9605.35 | [19 empty] | 258 | 24 | 6197 | 0.10057
| Hall |  |  |  |  | 4600 | 4699 | Oaklawn Ln | Rangeland Rd | Oakdale Ln | 40 | 2 | Local | [17 empty] | 45000 | [19 empty] | 1142 | 22 | 25124 | 0.40774
| Hall |  |  |  |  | 1200 | 1399 | Old Fern Valley Rd | Preston Hwy | Fern Valley Rd | 53 | 2 | Local | [17 empty] | 110589.4 | [19 empty] | 3398 | 21 | 71348 | 1.1579
| Hall |  |  |  |  | 5800 | 6099 | Robinhood Ln | Friar Tuck Ct | Forest Dr | 32.905 | 2 | Local | [17 empty] | 52659.7 | [19 empty] | 1475.2816 | 23.0288 | 33974 | 0.55137
| Hall |  |  |  |  | 4000 | 4099 | Tower Rd | Preston Hwy | Dead End | 46 | 2 | Local | [17 empty] | 96856.4 | [19 empty] | 2604 | 24 | 62488 | 1.0141
| Hall |  | 350002-334 |  |  | 1600 | 2699 | Dixdale Ave | Wingfield Ave | S 28th St | 55.9513 | 3 | Local | [17 empty] | 170479.85 |  | August | [17 empty] | 5770.7465 | 19.0594 | 109987 | 1.785
| Hall |  | 350002-334 |  |  |  |  | Dixie Hwy | W Burnett Ave | Bernheim Ln | 66 | 3 | Min Art | [17 empty] | 254141 |  | August | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-334 |  |  | 1600 | 1799 | W Lee St | S 15th St | Dixie Hwy | 47.1551 | 3 | Local | [17 empty] | 107680.05 |  | August | [17 empty] | 2701.6913 | 25.7139 | 69471 | 1.1275
| Hall |  |  |  |  | 500 | 799 | Bergman St | Dead End | S Shelby St | 20 | 4 | Local | [17 empty] | 59203.8 | [19 empty] | 1317 | 29 | 38196 | 0.61989
| Hall |  |  |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | [19 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-338 |  |  | 100 | 1299 | E Breckinridge St | S 1st St | Barret Ave | 60.4014 | 4 | Pri Coll | [17 empty] | 402154.632 | [19 empty] | 6770.28 | 36 | 243730.08 | 3.9555
| Hall |  |  |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | [19 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  |  |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | [19 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | [19 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-247 |  |  | 400 | 999 | E Witherspoon St | N Preston St | River Rd | 59.6256 | 4 | Min Art | [13 empty] | 8 |  |  |  | 326255.457 | See N 1st St | July | [16 empty] | Portion of this may have been paved with bridges project. | 3413.14 | 57.9322 | 197730.58 | 3.209
| Hall |  |  |  |  | 150 | 399 | E Witherspoon St | Bingham Way | N Preston St | 62.9283 | 4 | Min Art | [17 empty] | 95488.8 | [19 empty] | 1425.1269 | 40.6083 | 57872 | 0.93921
| Hall |  |  |  |  | 700 | 799 | Henry Fripo St | S Clay St | S Shelby St | 18 | 4 | Local | [17 empty] | 22452.8 | [19 empty] | 585 | 24 | 14033 | 0.22774
| Hall |  | 350002-339 |  |  | 400 | 999 | Lampton St | S Preston St | Dead End | 36.2169 | 4 | Local | [17 empty] | 149189.05 | [19 empty] | 3187.4777 | 30.1966 | 96251 | 1.5621
| Hall |  |  |  |  | 500 | 799 | Meriwether Ave | E Burnett Ave | S Shelby St | 62.3338 | 4 | Pri Coll | [17 empty] | 110292.435 | [19 empty] | 2228.13 | 30 | 66843.9 | 1.0848
| Hall |  | 350002-247 |  |  |  |  | N 1st St | W Main St | E Witherspoon St |  | 4 | [17 empty] | 4 | 150000 | 383501.48 | July
| Hall |  | 350002-340 |  |  | 300 | 1499 | S 15th St | W Jefferson St | W Hill St | 53.5853 | 4 | Min Art | [17 empty] | 687630.9 | [19 empty] | 10228.8508 | 40.7422 | 416746 | 6.7634
| Hall |  |  |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | [19 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 1400 | 1454 | S Preston St | S Jackson St | E Burnett Ave | 54.0007 | 4 | Min Art | [17 empty] | 33037.95 | [19 empty] | 564.7347 | 35.4556 | 20023 | 0.32496
| Hall |  |  |  |  | 300 | 599 | S Wenzel St | E Chestnut St | E Jefferson St | 25.8121 | 4 | Local | [17 empty] | 74648 | [19 empty] | 1387.7936 | 34.7026 | 48160 | 0.78159
| Hall |  |  |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | [19 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  |  |  |  | 850 | 1499 | W Muhammad Ali Blvd | Roy Wilkins Ave | S 15th St | 56.2923 | 4 | Min Art | [17 empty] | 185212.5 | [19 empty] | 2927.305 | 38.3459 | 112250 | 1.8217
| Hall |  |  |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [19 empty] | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 600 | 699 | Hardin St | Bank St | Gilligan St | 2 | 5 | Local | [17 empty] | 19381.2 | [19 empty] | 247 | 25 | 6252 | 0.10146
| Hall |  |  |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | [19 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-277 |  |  | 100 | 299 | N & S 46th St | N Longworth Ave | W Market St | 20.6662 | 5 | Local | [13 empty] | 6 |  |  | 6 | 71380.6 | 47809.56 | July | [16 empty] | May have been paved into gutter from Longworth to Duncan | 1555.8172 | 29.5999 | 46052 | 0.74738
| Hall |  |  |  |  | 700 | 899 | N 33rd St | Northwestern Pky | Dead End | 54.0197 | 5 | Local | [17 empty] | 56883.45 | [19 empty] | 531.8259 | 69.0057 | 36699 | 0.59559
| Hall |  |  |  |  | 700 | 899 | N 34th St | Northwestern Pky | Dead End | 57.1053 | 5 | Local | [17 empty] | 41126.15 | [19 empty] | 514.4215 | 51.5783 | 26533 | 0.43061
| Hall |  |  |  |  | 700 | 799 | N 36th St | Northwestern Pky | Rudd Ave | 44 | 5 | Local | [17 empty] | 21298.55 | [19 empty] | 529 | 26 | 13741 | 0.223
| Hall |  | 350002-312 |  |  | 3200 | 3299 | Rudd Ave | Dead End (east) | N 34th St | 44.7342 | 5 | Local | [13 empty] | 12 |  |  |  | 87872.6 | 32983.13 | [17 empty] | Brick paver sidewalk NW of 34th, Possible LSR project. | 959.6305 | 59.0769 | 56692 | 0.92006
| Hall |  |  |  |  | 3400 | 3899 | Rudd Ave | N 34th St | Dead End (west) | 56.5344 | 5 | Local | [17 empty] | 107745.15 | [19 empty] | 1259.0092 | 55.2125 | 69513 | 1.1281
| Hall |  |  |  |  | 200 | 399 | Shawnee Dr | W Market St | Southwestern Pky | 20.4991 | 5 | Local | [17 empty] | 86138.15 | [19 empty] | 1543.6989 | 35.9999 | 55573 | 0.9019
| Hall |  |  |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | [19 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  |  |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | [19 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  |  |  |  | 1900-12-15 | 1904-05-17 | Southwestern Pky | S Shawnee Ter | Gibson Ln | 59.2734 | 5 | Min Art | [17 empty] | 598921.95 | [19 empty] | 10181.6927 | 35.6506 | 362983 | 5.8909
| Hall |  |  |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | [19 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  |  |  |  | 1901-05-19 | 1901-08-21 | Colorado Ave | Dead End | Algonquin Pky | 61.8146 | 6 | Maj Art | [17 empty] | 119260.35 | [19 empty] | 2131.5568 | 33.909 | 72279 | 1.173
| Hall |  | 350002-208 |  |  | 800 | 1155 | Dixie Hwy | Maple St | Hale Ave | 59.8113 | 6 | Min Art | [13 empty] | Ramps Complete |  |  |  | 202327.257 | 128033.77 | July | [17 empty] | 3226.91 | 38 | 122622.58 | 1.9901
| Hall |  | 350002-301 |  |  |  |  | Dumesnil St | Dixie Hwy | S 26th St | 59 | 6 | Min Art | [17 empty] | 125991 | 90606.51 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 2400 | 2899 | S Floyd St | Old Eastern Pky | Central Ave | 60.0965 | 6 | Pri Coll | [17 empty] | 29653.8 |  | August | [17 empty] | 412 | 43.6214 | 17972 | 0.29167
| Hall |  |  |  |  | 900 | 1499 | W Kentucky St | S 9th St | S 15th St | 52.5746 | 6 | Pri Coll | [17 empty] | 177564.75 | [19 empty] | 2808.5642 | 38.3167 | 107615 | 1.7465
| Hall |  |  |  |  | 1000 | 2399 | W Ormsby Ave | Dead End | S 25th St | 44.9819 | 6 | Local | [17 empty] | 310365.8 | [19 empty] | 7886.4736 | 25.3898 | 200236 | 3.2497
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hey | Catalpa St | 66 | 6 | Min Art | [17 empty] | 137347 | See Wilson Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | [19 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-308 |  |  |  |  | Lime Kiln Ln | US 42 | Brownsboro Rd | 65 | 7 | Pri Coll | [17 empty] | 120650 | 3734.75 | [17 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | [19 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-245 |  |  |  |  | Alta Vista Rd | Beargrass Ave | I-64 overpass | 58 | 8 | Local | [17 empty] | 153131 | 241570.1 | July | [17 empty] | 4340 | 23 | 98794 | 1.6033
| Hall |  |  |  |  | 1 | 99 | Beverly Rd | Cross Rd | Dead End | 26 | 8 | Local | [17 empty] | 9203.9 | [19 empty] | 330 | 18 | 5938 | 0.096369
| Hall |  | 350002-344 |  |  | 2300 | 2699 | Brookside Dr | Ingleside Dr | Dead End | 62 | 8 | Local | [13 empty] | 0 |  |  |  | 62048 | [18 empty] | Concrete. Circle of cul-de-sac may have been paved previously. | 646.3277 | 24 | 15512 | 0.25175
| Hall |  |  |  |  | 1 | 1449 | Cross Rd | Castlewood Ave | Eastern Pkwy | 58.4177 | 8 | Local | [17 empty] | 34146.5 | [19 empty] | 1223.9072 | 17.9997 | 22030 | 0.35753
| Hall |  | 350002-343 |  |  | 2200 | 2549 | Hawthorne Ave | Bon Air Ave | Bardstown Rd | 43.7621 | 8 | Local | [17 empty] | 88168.65 | 4420.53 | [18 empty] | 3037.4844 | 18.727 | 56883 | 0.92316
| Hall |  | 350002-344 |  |  | 2300 | 2399 | Ingleside Dr | Woodbourne Ave | Dead End | 46.0948 | 8 | Local | [13 empty] | 0 |  |  |  | 53432.5 | [18 empty] | Concrete from Brookside to dead end. Watch for asphalt and decorative curb in asphalt section. | 911.9486 | 21.306 | 19430 | 0.31533
| Hall |  | 350002-345 |  |  | 2860 | 2899 | Lowell Ave | Tyler Ln | Hawthorne Ave | 37 | 8 | Local | [17 empty] | 11778.45 | [19 empty] | 422.1865 | 18 | 7599 | 0.12333
| Hall |  | 350002-262 |  |  | 2400 | 2699 | Ransdell Ave | Grinstead Dr | Bassett Ave | 47.2922 | 8 | Local | [13 empty] | 6 |  |  | 7 | 94001.3 | 15500.75 | August | [16 empty] | Ray Ave may have been paved which updated ramps at this intersection | 2021.5198 | 30.0002 | 60646 | 0.98423
| Hall |  |  |  |  | 1630 | 1799 | Ruth Ave | Strand Ave | Radnor Ave | 58.6718 | 8 | Local | [17 empty] | 15067.55 | [19 empty] | 486.0341 | 20.0007 | 9721 | 0.15776
| Hall |  | 350002-342 |  |  | 1617 | 1999 | Speed Ave | Fernwood Ave | Bardstown Rd | 23 | 8 | Local | [17 empty] | 72978.5 | [19 empty] | 1158 | 18 | 20851 | 0.33839
| Hall |  | 350002-342 |  |  | 1905-06-22 | 1906-03-13 | Speed Ave | Bardstown Rd | Spring Dr | 64.8405 | 8 | Pri Coll | [17 empty] | 68566.905 | [19 empty] | 1385.19 | 30 | 41555.7 | 0.67441
| Hall |  | 350002-344 |  |  | 2530 | 2599 | Woodbourne Ave | Valletta Ln | Cherosen Rd | 33.6999 | 8 | Local | [13 empty] | 0 |  |  |  | 54761.5 | [18 empty] | Watch for asphalt and decorative curbs | 1662.1826 | 21.2552 | 35330 | 0.57338
| Hall |  | 350002-245 |  |  | 2800 | 2899 | Alta Vista Pl | Alta Vista Ct | Dead End | 4 | 9 | Local | [13 empty] | 0 |  |  |  | 24260 | See Alta Vista | July | [16 empty] | Concrete, then transitions to Asphalt. | 379 | 16 | 6065 | 0.09843
| Hall |  | 350002-245 |  |  | 2800 | 2899 | Alta Vista Way | Alta Vista Rd | Dead End | 36 | 9 | Local | [13 empty] | 0 |  |  |  | 14496 | See Alta Vista | July | [16 empty] | Asphalt | 226 | 16 | 3624 | 0.058814
| Hall |  |  |  |  | 200 | 399 | Coralberry Rd | Dead End | Dead End | 55.9856 | 9 | Local | [17 empty] | 54516.6 | [19 empty] | 1506.6618 | 23.3443 | 35172 | 0.57081
| Hall |  |  |  |  | 200 | 299 | Mockingbird Gardens Dr | Dead End | Winterleaf Dr | 42.5777 | 9 | Local | [17 empty] | 57269.4 | [19 empty] | 1830.1722 | 20.1883 | 36948 | 0.59963
| Hall |  | 350002-290 |  |  | 100 | 299 | N Bayly Ave | Frankfort Ave | Hollywood Ter | 22.525 | 9 | Local | [13 empty] | 11 |  |  |  | 61958.15 | [18 empty] | Several ramps are stairs. Likely technically infeasible. | 1375.1377 | 29.0684 | 39973 | 0.64873
| Hall |  | 350002-290 |  |  | 200 | 299 | N Clifton Ave | Sycamore Ave | Brownsboro Rd | 46.5993 | 9 | Local | [13 empty] | 6 |  |  |  | 53104.55 | [18 empty] | Pave entire triangle area at Sycamore, one set of stairs at sycamore which is likely infeasible | 1285.4381 | 26.6532 | 34261 | 0.55603
| Hall |  | 350002-290 |  |  | 100 | 199 | N Jane St | Frankfort Ave | Brownboro Rd | 47.6659 | 9 | Local | [13 empty] | 8 |  |  |  | 56206.1 | [18 empty] | Need to confirm ADA ramps before RR tracks | 1893.1414 | 19.1544 | 36262 | 0.5885
| Hall |  |  |  |  | 200 | 399 | Pepperbush Rd | Dead End | Dead End | 55.3127 | 9 | Local | [17 empty] | 100709.7 | [19 empty] | 1046.8959 | 62.0635 | 64974 | 1.0545
| Hall |  |  |  |  | 3500 | 3599 | Waterleaf Ct | Waterleaf Way | Dead End | 44 | 9 | Local | [17 empty] | 23628.2 | [19 empty] | 693 | 22 | 15244 | 0.2474
| Hall |  |  |  |  | 200 | 299 | Waterleaf Way | Dead End | Mockingbird Gardens dr | 46.4515 | 9 | Local | [17 empty] | 28020.9 | [19 empty] | 821.7223 | 22.0001 | 18078 | 0.29339
| Hall |  |  |  |  | 3500 | 3599 | Winterberry Cir | Mockingbird Gardens Dr | Mockingbird Gardens Dr | 30 | 9 | Local | [17 empty] | 46517.05 | [19 empty] | 1429 | 21 | 30011 | 0.48705
| Hall |  | 350002-341 |  |  | 1904-12-04 | 1906-01-07 | Bashford Manor Ln | Newburg Rd | Bardstown Rd | 65.1829 | 10 | Pri Coll | [17 empty] | 274355.5815 | [19 empty] | 5038.67 | 33 | 166276.11 | 2.6985
| Hall |  | 350002-348 |  |  | 1100 | 1299 | Boyle St | Charles St | Goss Ave | 44.0005 | 10 | Local | [13 empty] | 6 |  |  |  | 36327.35 | See Texas | August | [16 empty] | LWC work was done in area | 781.2483 | 29.9994 | 23437 | 0.38036
| Hall |  | 350002-348 |  |  | 900 | 1199 | Charles St | Texas Ave | Dandridge Ave | 32.7758 | 10 | Local | [13 empty] | 15 |  |  |  | 106627.6 | See Texas | August | [16 empty] | LWC work was done in area | 2456.8468 | 28.0001 | 68792 | 1.1164
| Hall |  |  |  |  | 1000 | 1099 | Dixon Ave | Dead End | Poplar Level Rd | 43 | 10 | Local | [17 empty] | 92589 | [19 empty] | 1102 | 24 | 26454 | 0.42933
| Hall |  |  |  |  | 1000 | 1099 | Eigelbach Ave | Dead End | Poplar Level Rd | 47 | 10 | Local | [17 empty] | 35391.15 | [19 empty] | 951 | 24 | 22833 | 0.37056
| Hall |  |  |  |  | 3100 | 3199 | Harmon Ct | Dead End | Audubon Pky | 0 | 10 | Local | [17 empty] | 35031.5 | [19 empty] | 417 | 24 | 10009 | 0.16244
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Bardstown Rd | Goldsmith Ln |  | 10 | Min Art | [13 empty] | 25 |  |  |  | 511151 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3647 | 62 | 226114 | 3.6696
| Hall |  |  |  |  | 3461 | 3781 | Illinois Ave | Sheridan Ave | 3461 Illinois Ave | 57.9238 | 10 | Local | [17 empty] | 105080.7 | [19 empty] | 3268.3937 | 20.7423 | 67794 | 1.1002
| Hall |  |  |  |  | 3150 | 3199 | Illinois Ave | Osprey Rd | Poplar Level Rd | 21 | 10 | Local | [17 empty] | 8337.45 | [19 empty] | 224.1407 | 24 | 5379 | 0.087296
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Krierger St | Ellison Ave | Goss Ave | 39.3379 | 10 | Local | [13 empty] | 13 |  |  |  | 50722.2 | See Texas | August | [16 empty] | Depress sidewalk to be flush with pavement at alleys where possible, LWC work done in area | 1168.7507 | 27.9991 | 32724 | 0.53108
| Hall |  |  |  |  | 1000 | 1099 | Mayer Ave | Dead End | Poplar Level Rd | 37 | 10 | Local | [17 empty] | 66146.5 | [19 empty] | 756 | 25 | 18899 | 0.30671
| Hall |  |  |  |  | 1400 | 1499 | Nightingale Rd | Eagle Pass | Audubon Pky | 39 | 10 | Local | [17 empty] | 58907.75 | [19 empty] | 1727 | 22 | 38005 | 0.61679
| Hall |  |  |  |  | 3100 | 3199 | Osprey Rd | Illinois Ave | Audubon Pky | 50 | 10 | Local | [17 empty] | 24330.35 | [19 empty] | 654 | 24 | 15697 | 0.25475
| Hall |  | 350002-310 |  |  | 2600 | 2899 | Parklawn Dr | Parkway Dr | Dead End | 41.6675 | 10 | Local | [13 empty] | 10 |  |  |  | 56649.4 | 65090.5 | August | [16 empty] | Pushed back to FY 21 due to virus | 1885.4269 | 19.3845 | 36548 | 0.59314
| Hall |  | 350002-348 |  |  | 800 | 1699 | Texas Ave | S Shelby St | Wetterau Ave | 48 | 10 | Local | [17 empty] | 271580.15 | 296396.19 | August | [17 empty] | 5300 | 34 | 175213 | 2.8436
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Wetterau Ave | Texas Ave | Dead End | 23.7244 | 10 | Local | [13 empty] | 0 |  |  |  | 16535.4 | See Texas | August | [16 empty] | Update ramp on other side of Samuel leading down to shoping center. LWC work done in area | 801.46 | 13.3107 | 10668 | 0.17313
| Hall |  | 350002-348 |  |  | 1000 | 1099 | Wetterau Ave at Ash St | Dead End | Dead End | 21 | 10 | Local | [13 empty] | 6 |  |  |  | 27932.55 | See Texas | August | [16 empty] | Pushed back to FY 21 due to virus | 750.84 | 24.0011 | 18021 | 0.29247
| Hall |  |  |  |  | 8000 | 8199 | Amity Ln | Summerfield Dr | Dead End | 55.9519 | 11 | Local | [17 empty] | 31184.45 | [19 empty] | 1000.7746 | 20.1034 | 20119 | 0.32651
| Hall |  |  |  |  | 8000 | 8199 | Cloudcroft Ln | Summerfield Dr | Dead End | 50 | 11 | Local | [17 empty] | 53769.5 | [19 empty] | 1239 | 28 | 34690 | 0.56299
| Hall |  |  |  |  | 3100 | 3199 | Spring Breeze Ct | Amity Ln | Dead End | 55.4007 | 11 | Local | [17 empty] | 28616.1 | [19 empty] | 861.5499 | 21.4288 | 18462 | 0.29962
| Hall |  |  |  |  | 2530 | 2599 | Sunbury Ln | Winterhaven Rd | Winterhaven Rd | 58.8872 | 11 | Local | [17 empty] | 70025.9 | [19 empty] | 1946.0602 | 23.2151 | 45178 | 0.7332
| Hall |  |  |  |  | 8000 | 8099 | Weather Ct | Weather Way | Dead End | 65 | 11 | Local | [17 empty] | 7052.5 | [19 empty] | 253 | 18 | 4550 | 0.073843
| Hall |  |  |  |  | 3000 | 3199 | Weather Way | Summerfield Dr | Dead End | 68.3392 | 11 | Local | [17 empty] | 48962.95 | [19 empty] | 1435.8717 | 21.9999 | 31589 | 0.51266
| Hall |  |  |  |  | 3600 | 3999 | Baymeadow Dr (all) | Brinamwood Dr | Dead End | 72.9415 | 12 | Local | [17 empty] | 71907.6 | [19 empty] | 1973.6702 | 23.6667 | 46392 | 0.7529
| Hall |  |  |  |  | 3600 | 3699 | Birnamwood Ct | Birnamwood Dr | Dead End | 61 | 12 | Local | [17 empty] | 7209.05 | [19 empty] | 258 | 18 | 4651 | 0.075482
| Hall |  |  |  |  | 6900 | 7199 | Birnamwood Dr | St Andrews Church Rd | Baymeadow Dr | 72.8578 | 12 | Local | [17 empty] | 54293.4 | [19 empty] | 1487.6416 | 23.3333 | 35028 | 0.56847
| Hall |  |  |  |  | 3600 | 3699 | Eastmeadow Ct | Birnamwood Dr | Dead End | 56 | 12 | Local | [17 empty] | 6313.15 | [19 empty] | 226 | 18 | 4073 | 0.066101
| Hall |  |  |  |  | 6900 | 6999 | Hyland Hills Ct | Baymeadow Dr | Dead End | 48 | 12 | Local | [17 empty] | 4642.25 | [19 empty] | 150 | 20 | 2995 | 0.048606
| Hall |  |  |  |  | 1905-03-14 | 1906-01-07 | Lower Hunters Trce | Dixie Hwy | Upper Hunters Trce | 63.6414 | 12 | Pri Coll | [17 empty] | 91005 | [19 empty] | 3840.0384 | 29.3265 | 112615 | 1.8276
| Hall |  |  |  |  | 1906-01-08 | 1918-02-09 | Lower Hunters Trce | Upper Hunters Trce | Greenbelt Hwy | 66.9497 | 12 | Pri Coll | [17 empty] | 347664.9 | [19 empty] | 9483.5364 | 25.4712 | 210706 | 3.4196
| Hall |  |  |  |  | 100 | 199 | Mills Dr | Alreva Rd | Blanton Ln | 61.0339 | 12 | Local | [17 empty] | 97908.85 | [19 empty] | 3088.9085 | 20.4496 | 63167 | 1.0251
| LP |  | 339051-74 |  |  | 1916-06-04 | 1918-08-12 | Sylvania Rd | Memory Ln | Rutledge Rd | 63.5483 | 12 | Sec Coll | [17 empty] | 60800.85 | [19 empty] | 1914.0068 | 19.2523 | 36849 | 0.59803
| Hall |  |  |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | [19 empty] | 208 | 18 | 3742 | 0.060729
[8 empty] | D13 Paving Projects |  |  |  | 13 | [18 empty] | 14000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000
| Hall |  | 350002-281 |  |  | 8000 | 8399 | Afterglow Dr | Dead End | Outer Loop | 49.0349 | 13 | Local | [13 empty] | 4 |  |  | 12 | 175466.2 | 57516 | August | [16 empty] | May look to add frontage Rd off Outer Loop | 4154.1404 | 27.2509 | 113204 | 1.8372
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | various drainage improvements needed, shoulder | 6261.5 | 19 | 118968.5 | 1.9308
| Hall |  | 350002-335 |  |  | 800 | 899 | Candleglow Ct | Dead End | Candleglow Ln | 52 | 13 | Local | [17 empty] | 10231.55 | [19 empty] | 367 | 18 | 6601 | 0.10713
| Hall |  | 350002-335 |  |  | 500 | 899 | Candlelight Ln | New Cut Rd | Dead End | 63.1036 | 13 | Local | [17 empty] | 81216.9 | [19 empty] | 2734.1962 | 19.164 | 52398 | 0.85037
| Hall |  | 350002-336 |  |  | 400 | 499 | Garrison Ct | Dead End | Garrison Rd | 29 | 13 | Local | [17 empty] | 7745.35 | [19 empty] | 227 | 22 | 4997 | 0.081097
| Hall |  | 350002-336 |  |  | 7300 | 7699 | Garrison Rd | Dead End | Revolutionary Rd | 53.4225 | 13 | Local | [17 empty] | 69548.5 | [19 empty] | 1908.6386 | 23.5089 | 44870 | 0.7282
| Hall |  |  |  |  | 10600 | 11499 | Harrison Ln | National Tpke | Dead End | 51.4903 | 13 | Local | [17 empty] | 150370.15 |  | August | [17 empty] | 5276.3386 | 18.3864 | 97013 | 1.5744
| LP |  | 339051-75 |  |  | 1929-07-26 | 1935-04-25 | Holsclaw Hill Rd | Mitchell Hill Rd | Dead End | 65.6183 | 13 | Sec Coll | [17 empty] | 351212.4 | [19 empty] | 10567.5567 | 20.1424 | 212856 | 3.4545
| LP |  | 339051-75 |  |  | 1919-03-01 | 1919-12-25 | Knob Creek Rd | Dead End | Mitchell Hill Rd | 58 | 13 | Sec Coll | [17 empty] | 50631.9 | [19 empty] | 1534.3038 | 20 | 30686 | 0.49801
| Hall |  | 350002-335 |  |  | 800 | 899 | Taper Ct | Dead End | Candleglow Ln | 67 | 13 | Local | [17 empty] | 6747.15 | [19 empty] | 282 | 16 | 4353 | 0.070645
| Hall |  | 350002-347 |  |  | 16700 | 17199 | Abbotts Beach Rd | Dixie Hwy | Dead End | 23 | 14 | Local | [17 empty] | 36318.05 |  | August | [17 empty] | 2343 | 10 | 23431 | 0.38026
| Hall |  |  |  |  | 5700 | 6099 | Alandale Dr | Dixie Hwy | Omar Khayyam Blvd | 59.1854 | 14 | Local | [17 empty] | 107878.45 | [19 empty] | 2719.5213 | 25.5924 | 69599 | 1.1295
| LP |  | 339051-8 | 2017-07-01 |  |  |  | Bearcamp Rd | Blevins Gap Rd | Wildflower Ln |  | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 287148 |  |  | PW '19 MAP | 8672-410-8210-148451-822702 | [14 empty] | On-hold until culvert replacement complete | 5239 | 18 | 94302 | 1.5304
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | see above | 6261.5 | 19 | 118968.5 | 1.9308
| LP |  |  |  |  | 1909-04-22 | 1915-05-25 | Blevins Gap Rd | Stonestreet Rd | Medora Rd | 70.2148 | 14 | Pri Coll | [17 empty] | 550000 | [19 empty] | 18719.4454 | 20.0252 | 374860 | 6.0837
| Hall |  |  |  |  | 9600 | 9699 | Britannia Ct | Dead End | Scarborough Ave | 61 | 14 | Local | [17 empty] | 23112.05 | [19 empty] | 621 | 24 | 14911 | 0.24199
| Hall |  |  |  |  | 11700 | 11899 | Deering Rd | Flowervale Ln | Dead End | 47 | 14 | Local | [17 empty] | 33464.5 | [19 empty] | 1080 | 20 | 21590 | 0.35039
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65 | 14 | Sec Coll | [17 empty] | 68000.427 | [19 empty] | 1719.962 | 24 | 41212.38 | 0.66884
| Hall |  | 350002-337 |  |  | 6900 | 7199 | Ethan Allen Way | Kinross Blvd | Bessels Blvd | 42.3493 | 14 | Local | [17 empty] | 85963 | [19 empty] | 2310.8498 | 23.9998 | 55460 | 0.90007
| Hall |  |  |  |  | 6900 | 6999 | Fincastle Trl | Dead End | Lower River Rd | 42 | 14 | Local | [17 empty] | 14022.85 | [19 empty] | 905 | 10 | 9047 | 0.14682
| Hall |  |  |  |  | 2400 | 2499 | Hereford Ct | Scarborough Ave | Dead End | 12 | 14 | Local | [17 empty] | 7548.5 | [19 empty] | 271 | 18 | 4870 | 0.079036
| Hall |  |  |  |  | 2400 | 2499 | Kings Cross Ct | Dead End | Scarborough Ave | 56 | 14 | Local | [17 empty] | 9924.65 | [19 empty] | 291 | 22 | 6403 | 0.10392
| Hall |  |  |  |  | 9700 | 9799 | Leopold Ct | Scarborough Ave | Scarborough Ave | 22 | 14 | Local | [17 empty] | 9689.05 | [19 empty] | 313 | 20 | 6251 | 0.10145
| Hall |  |  |  |  | 9500 | 10099 | Omar Khayyam Blvd | Donau Ln | Count Fleet Dr | 69.6626 | 14 | Local | [17 empty] | 89163.75 | [19 empty] | 2396.8896 | 23.9999 | 57525 | 0.93358
| Hall |  |  |  |  | 2500 | 2505 | Parliament Ct | Scarborough Ave | Scarborough Ave | 55 | 14 | Local | [17 empty] | 9351.15 | [19 empty] | 335 | 18 | 6033 | 0.09791
| Hall |  |  |  |  | 9600 | 9699 | Pembury Ct | Scarborough Ave | Dead End | 23 | 14 | Local | [17 empty] | 7641.5 | [19 empty] | 274 | 18 | 4930 | 0.08001
| Hall |  |  |  |  | 9732 | 9899 | Scarborough Ave | Montpelier Ct | Lamborne Blvd | 65.1377 | 14 | Local | [17 empty] | 21024.2 | [19 empty] | 565.1696 | 23.9999 | 13564 | 0.22013
| Hall |  |  |  |  | 7200 | 7399 | Scenic Trl | Dead End | Lower River Rd | 47 | 14 | Local | [17 empty] | 17859.1 | [19 empty] | 886 | 13 | 11522 | 0.18699
| LP |  | 339051-76 |  |  | 1935-01-16 | 1938-01-19 | Scotts Gap Rd | Blevins Gap Rd | Dead End | 67.2271 | 14 | Sec Coll | [17 empty] | 224112.9 | [19 empty] | 7455.678 | 18.2178 | 135826 | 2.2043
| LP |  | 339051-77 |  |  | 1917-10-17 | 1920-07-12 | W Orell Rd | Dixie Hwy | Lower River Rd | 65.5631 | 14 | Pri Coll | [17 empty] | 174266.4 | [19 empty] | 5280.8336 | 19.9999 | 105616 | 1.7141
| Hall |  |  |  |  | 9600 | 9699 | Yarmouth Ct | Scarborough Ave | Dead End | 35 | 14 | Local | [17 empty] | 17054.65 | [19 empty] | 550 | 20 | 11003 | 0.17857
| Hall |  |  |  |  | 4300 | 4399 | Fluhr Dr | Dead End | Anna Ln | 51.7058 | 15 | Local | [17 empty] | 24564.4 | [19 empty] | 660.3467 | 23.9995 | 15848 | 0.2572
| Hall |  |  |  |  | 3500 | 3799 | Georgetown Pl | Berry Blvd | Dead End | 28.4435 | 15 | Local | [17 empty] | 41555.5 | [19 empty] | 1103.1397 | 24.3034 | 26810 | 0.4351
| Hall |  |  |  |  | 300 | 699 | Heywood Ave | S 3rd St | Rodman St | 53.2531 | 15 | Local | [17 empty] | 102665.8 | [19 empty] | 1919.8374 | 34.5008 | 66236 | 1.075
| Hall |  |  |  |  | 1200 | 1320 | Lance Dr | Manslick Rd | Leaf Dr | 59.0188 | 15 | Local | [17 empty] | 30051.4 | [19 empty] | 794.1409 | 24.4138 | 19388 | 0.31465
| Hall |  |  |  |  | 1600 | 1749 | March Blvd | Manslick Rd | Nichols Meadow Cir at school entrance | 71.0419 | 15 | Local | [17 empty] | 80654.25 | [19 empty] | 1224.4896 | 42.4953 | 52035 | 0.84448
| Seven Seas |  | 370579 |  |  |  |  | Rankin St | E Kenton St | E Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 18778.65 |  | August | PW Funds FY 17 | [15 empty] | PCCP - Most panels look ok, I would do select panel replacement - James |  |  | 0 | 0
| Hall |  |  |  |  | 4442 | 4516 | Rear View Dr | Lance Dr | Dead End | 19 | 15 | Local | [17 empty] | 45416 | [19 empty] | 649 | 20 | 12976 | 0.21059
| Hall |  |  |  |  | 2800 | 3099 | S 5th St | M St | Central Ave | 50.6617 | 15 | Local | [17 empty] | 64504.8 | [19 empty] | 1417.7832 | 29.3529 | 41616 | 0.67539
| Hall |  |  |  |  | 1906-07-27 | 1907-12-08 | S Floyd St | Old Eastern Pky | Central Ave | 60 | 15 | Pri Coll | [17 empty] | 214247.55 | [19 empty] | 3290 | 39.4672 | 129847 | 2.1073
| Seven Seas |  | 370579 |  |  |  |  | Tulane Ave | W Kenton St | W Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 14086.05 |  | August | PW Funds FY 17 | [15 empty] | PCCP |  |  | 0 | 0
|  |  | 350002-198 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 |  |  | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1200 | 1499 | Weyler Ave | Arcade Ave | Dead End | 51 | 15 | Local | [17 empty] | 52250.5 | [19 empty] | 1705 | 20 | 33710 | 0.54708
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus. Will be pushed to FY 22
| Hall |  |  |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | [19 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  |  |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | [19 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  |  |  |  | 1920-07-13 | 1921-11-24 | Wolf Pen Branch Rd | Wolf Pen Ln (east of intersection) | Spring Farm Rd | 77.753 | 16 | Sec Coll | [17 empty] | 95670.3 | [19 empty] | 2959.4685 | 19.592 | 57982 | 0.941
| Hall |  | 350002-292 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | [18 empty] | Pushed back to FY 21 due to virus | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-292 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | [18 empty] | Pushed back to FY 21 due to virus | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-292 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | [18 empty] | Pushed back to FY 21 due to virus | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-292 |  |  | 11006 | 11199 | Eagles Cove Dr | Kestrel Ct | Hickory Cove Ct | 61.2884 | 17 | Local | [13 empty] | 5 |  |  |  | 73635.85 | [18 empty] | Pushed back to FY 21 due to virus | 2077.047 | 22.8724 | 47507 | 0.771
| Hall |  | 350002-292 |  |  | 4500 | 4599 | Goshawk Ct | Eagles Cove Dr | Dead End | 66 | 17 | Local | [13 empty] | 2 |  |  |  | 15304.7 | [18 empty] | Pushed back to FY 21 due to virus | 411.4091 | 24 | 9874 | 0.16025
| Hall |  | 350002-292 |  |  | 10700 | 10712 | Hickory Cove Ct | Shenandoah Dr | Eagles Cove Dr | 52 | 17 | Local | [13 empty] | 3 |  |  |  | 26463.15 | [18 empty] | Pushed back to FY 21 due to virus | 656.6535 | 26 | 17073 | 0.27708
| Hall |  |  |  |  | 13600 | 13699 | Sample Ct | Sample Way | Dead End | 67 | 17 | Local | [17 empty] | 11609.5 | [19 empty] | 312.0762 | 24 | 7490 | 0.12156
| Hall |  |  |  |  | 3400 | 3599 | Sample Way | Colonial Springs Rd | Springs Station Rd | 59.8943 | 17 | Local | [17 empty] | 72225.35 | [19 empty] | 2053.5541 | 22.6909 | 46597 | 0.75623
| Hall |  |  |  |  | 13400 | 13499 | Sapling Spring Pl | Dead End | Sample Way | 70 | 17 | Local | [17 empty] | 6300.75 | [19 empty] | 169.381 | 24 | 4065 | 0.065971
| Hall |  |  |  |  | 13500 | 13599 | Squire Springs Ct | Sample Way | Dead End | 66 | 17 | Local | [17 empty] | 15921.6 | [19 empty] | 428.0127 | 24 | 10272 | 0.16671
[8 empty] | Ridgeview Ave | N Wood Dr | Lynnbrook Dr |  | 18 | Local | [17 empty] | 42400 |  |  | CIF | 8146-410-8107-148267-822702 | 22500
[8 empty] | Hobbs Station | Old Hobbs Pl | Lodge Hill |  | 18 | Local | [17 empty] | 35000 |  |  | CIF | 8146-410-8107-148267-822702 | 35000
[8 empty] | Quince Ct | Hobbs Station | Dead End |  | 18 | Local | [17 empty] | 2500 |  |  | CIF | 8146-410-8107-148267-822702 | 2500
[8 empty] | Ashbrook Ave | Beechcrest Ave | Brookhaven Ave (concrete panel replacement) |  | 18 | Local | [17 empty] | 15000 |  |  | CIF | 8146-410-8107-148267-822702 | 15000
| Hall |  |  |  |  | 600 | 609 | Dorsey Way | Rymer Way | Elsmere Cir | 87 | 18 | Local | [17 empty] | 19729.95 | [19 empty] | 303 | 42 | 12729 | 0.20658
| Hall |  |  |  |  | 600 | 799 | Elsmere Cir | Dorsey Way | Tamarisk Pkwy | 72.7037 | 18 | Local | [17 empty] | 54589.45 | [19 empty] | 1565.7643 | 22.4932 | 35219 | 0.57157
| Hall |  |  |  |  | 1 | 99 | Hallsdale Dr | Taylorsville Rd | Dead End | 63.1729 | 18 | Local | [17 empty] | 102778.95 |  |  | CIF | [16 empty] | 2762.8307 | 24.0004 | 66309 | 1.0761
| Hall |  |  |  |  | 600 | 602 | Rymer Way | Winyan Ln | Dorsey Way | 46 | 18 | Local | [17 empty] | 11657.55 | [19 empty] | 341.8596 | 22 | 7521 | 0.12206
| Hall |  |  |  |  | 9900 | 9999 | Spring Ridge Dr | Dead End | Dorsey Way | 49 | 18 | Local | [17 empty] | 30590.8 | [19 empty] | 939.8092 | 21 | 19736 | 0.3203
| Hall |  | 350002-350 |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 61.7099 | 18 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| Hall |  |  |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | [19 empty] | 1488.0063 | 89 | 132433 | 2.1493
| LP |  | 350002-286 |  |  |  |  | Hagen Rd | Hersfield Rd | dead end |  | 19 | [18 empty] | 12500 |  |  | CIF - *Temp PW '19 Bond | 8138-410-8107-148919-822702 | 12500 |  | 8137-410-8210-148451-822702 | 12500 | [10 empty] | Pushed back to FY 21 due to virus |  |  | 12493 | 0.20275
| Hall |  |  |  |  | 1100 | 1599 | Heafer Rd | N English Station Rd | La Grange Rd | 41 | 19 | Local | [17 empty] | 99816.9 | [19 empty] | 3136 | 21 | 64398 | 1.0451
| Hall |  | 350002-286 |  |  |  |  | Herfield Rd |  |  |  | 19 | Local | [17 empty] | 15000 |  |  | Council | 8138-410-8107-048101-822702 | 15000 | [13 empty] | Pushed back to FY 21 due to virus
| LP |  | 339051-78 |  |  | 1903-07-23 | 1905-06-21 | N English Station Rd | La Grange Rd | Old Henry Rd | 70.6362 | 19 | Pri Coll | [16 empty] | August | 190665.75 | 118409.25 | August | [17 empty] | 4744.6459 | 24.3548 | 115555 | 1.8754
| Hall |  | 350002-351 |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 19 | Pri Coll | [13 empty] | 3 |  |  | August | 34471.7505 | See N Pope Lick | August | [16 empty] | 0.5 in D 20, need to fix up one radius with potential curba nd gutter. 3 ramps at Urton Ln. | 1160.665 | 18 | 20891.97 | 0.33906
| Hall |  |  |  |  | 12300 | 12499 | Park Field Rd | Heafer Rd | Dead End | 41 | 19 | Local | [17 empty] | CIF | [19 empty] | 711 | 21 | 14643 | 0.23764
| Hall |  | 350002-286 |  |  |  |  | Parkfield Rd |  |  |  | 19 | [18 empty] | 22000 |  |  | Council | 8138-410-8107-048101-822702 | 16000 |  | 8144-410-8107-048101-822702 | 6000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 62 | 19 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  | 339051-72 |  |  | 1927-12-04 | 1932-04-20 | Easum Rd | Billtown Rd | Old Heady Rd | 65.4048 | 20 | Pri Coll | [17 empty] | 378646.95 |  | August | [17 empty] | 12312.9475 | 18.6375 | 229483 | 3.7243
| LP |  | 339051-62 |  |  | 600 | 6499 | Gellhaus Ln | Chenoweth Run Rd | Billtown Rd | 61.166 | 20 | Sec Coll | [13 empty] | 6 |  |  |  | 181381.398 | 189438.65 | July | [16 empty] | Intersection improvement at Chenoweth Run, possible culverts and Guardrail replacements needed. | 4672.76 | 23.5253 | 109928.12 | 1.784
| LP |  | 339051-68 |  |  | 9700 | 9299 | Hassy Way | Dry Ridge Rd | Dead End | 84.5338 | 20 | Local | [17 empty] | 189358 | 62203.16 | August | [17 empty] | 1865.9377 | 23.4429 | 43743 | 0.70991
| Hall |  |  |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 20 | Pri Coll | [13 empty] | See N Pope Lick |  |  | August | 34471.7505 | 89728.41 | August | [16 empty] | 0.5 in D 19, see other N Pope Lick | 1160.665 | 18 | 20891.97 | 0.33906
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  | 339051-71 |  |  | 3500 | 4299 | Old Routt Rd | Dead End | Routt Rd | 45.5989 | 20 | Local | [17 empty] | 224937.55 | 120672.59 | August | [17 empty] | 7256.044 | 20 | 145121 | 2.3552
| LP |  | 339051-70 |  |  | 15200 | 15299 | Old Taylorsville Rd (near Eastwood Fisherville intersection) | Dead End | Taylorsville Rd | 12 | 20 | Local | [17 empty] | 24133.5 | 22842.6 | August | [17 empty] | 1112.1651 | 14 | 15570 | 0.25269
| LP |  | 339051-69 |  |  | 14000 | 14199 | Old Taylorsville Rd at Wilderness Trl | Taylorsville Rd | Dead End | 55.6534 | 20 | Local | [17 empty] | 34870.35 | See Wilderness Trl | August | [17 empty] | 1318.8779 | 17.0577 | 22497 | 0.36511
| LP |  |  |  |  | 11800 | 14499 | Rehl Rd | Blankenbaker Pkwy | S Pope Lick Rd | 60.2949 | 20 | Pri Coll | [13 empty] | 0 |  |  |  | 430623.633 | 351795.21 | July | [16 empty] | Need cores taken, possibly thin asphalt. Possible Fiber project. Check Guardrails. Need to review intersection at Tucker Station Rd | 11862.91 | 22 | 260984.02 | 4.2355
| Hall |  |  |  |  | 3500 | 4299 | S Pope Lick Rd | Old Taylorsville Rd | Dead End | 26 | 20 | Local | [13 empty] | 0 |  |  |  | 183792.8 | [18 empty] | May have been repaved with Parklands project | 6975.0624 | 17 | 118576 | 1.9244
| LP |  | 339051-69 |  |  | 3400 | 3999 | Wilderness Trl | Old Taylorsville Rd | Dead End | 52 | 20 | Local | [17 empty] | 115172.75 | 155661.67 | August | [17 empty] | 4644.0491 | 16 | 74305 | 1.2059
| LP |  | 339051-68 |  |  | 16300 | 16399 | Witch Hazel Dr | Hassy Way | Dead End | 90 | 20 | Local | [17 empty] | 66598 | See Hassy Way | August | [17 empty] | 610 | 24 | 14639 | 0.23758
| Hall |  |  |  |  | 4400 | 4699 | Allmond Ave | E Woodlawn Ave | Dead End (north) | 54.248 | 21 | Local | [17 empty] | 131756.2 | [19 empty] | 3325.2587 | 25.5631 | 85004 | 1.3795
| Hall |  |  |  |  | 300 | 399 | Chris Dr | Homestead Dr | Dead End | 61 | 21 | Local | [17 empty] | 5054.55 | [19 empty] | 271.7278 | 12 | 3261 | 0.052923
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [19 empty] | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-279 |  |  | 100 | 199 | E Amherst Ave | S 1st St | Wabash Pl | 48.8533 | 21 | Local | [13 empty] | 0 |  |  |  | 50161.1 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 1274.1882 | 25.3981 | 32362 | 0.52521
| Hall |  | 350002-279 |  |  | 100 | 199 | E Tenny Ave | S 1st St | St Leo Pl | 42 | 21 | Local | [13 empty] | 3 |  |  |  | 28551 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 658 | 28 | 18420 | 0.29894
| Hall |  |  |  |  | 200 | 299 | E Woodlawn Ave | Allmond Ave | Nevada Ave | 68 | 21 | Min Art | [17 empty] | 127152.3 | [19 empty] | 1926.5536 | 39.9999 | 77062 | 1.2506
| Hall |  |  |  |  | 5000 | 5199 | Emery Ave | Lyman Ave | W Kenwood Dr | 54 | 21 | Local | [17 empty] | 24539.6 | [19 empty] | 754 | 21 | 15832 | 0.25694
| Hall |  |  |  |  | 5000 | 5199 | Fay Ave | W Kenwood Dr | Alger Ave | 48.6736 | 21 | Local | [17 empty] | 42524.25 | [19 empty] | 1287.734 | 21.3049 | 27435 | 0.44525
| Hall |  |  |  |  | 5900 | 6199 | Gloria Ln | Catheen Way | Dead End | 43.0059 | 21 | Local | [17 empty] | 47087.45 | [19 empty] | 1318.1272 | 23.0471 | 30379 | 0.49302
| Hall |  |  |  |  | 300 | 399 | Hatcher Ave | Southside Dr | Homestead Dr | 39 | 21 | Local | [17 empty] | 15921.6 | [19 empty] | 641.9717 | 16 | 10272 | 0.16671
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
| Hall |  |  |  |  | 300 | 399 | Hillview Dr | Southside Dr | Homestead Dr | 23 | 21 | Local | [17 empty] | 20945.15 | [19 empty] | 750.738 | 18 | 13513 | 0.2193
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-279 |  |  | 4900 | 4999 | Hollins Rd | St Leo Pl | E Amherst Ave | 60 | 21 | Local | [13 empty] | 5 |  |  | 5 | 14066.25 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 303 | 30 | 9075 | 0.14728
| Hall |  |  |  |  | 6800 | 7099 | Homestead Dr | E Kenwood Dr | Dead End | 44.1624 | 21 | Local | [17 empty] | 37426.3 | [19 empty] | 1442.2483 | 16.7419 | 24146 | 0.39187
| Hall |  |  |  |  | 4800 | 5999 | Hood Rd | W Indian Trl | Catheen Way | 14 | 21 | Local | [17 empty] | 30860.5 | [19 empty] | 996 | 20 | 19910 | 0.32312
| Hall |  |  |  |  | 6100 | 6199 | Loretta St | Elam Ct | Whitlock St | 78.4686 | 21 | Local | [17 empty] | 39190.2 | [19 empty] | 1053.4975 | 24.0001 | 25284 | 0.41034
| Hall |  |  |  |  | 500 | 599 | Lyman Ave | Laughlin Ave | Fay Ave | 53 | 21 | Local | [17 empty] | 10696.55 | [19 empty] | 314 | 22 | 6901 | 0.112
| Hall |  |  |  |  | 700 | 799 | Lyman Ave | Reed Ave | Emery Ave | 54 | 21 | Local | [17 empty] | 9114 | [19 empty] | 294 | 20 | 5880 | 0.095427
| Hall |  |  |  |  | 300 | 399 | Meadowood Ct | Southside Dr | Dead End | 29 | 21 | Local | [17 empty] | 7184.25 | [19 empty] | 579.3129 | 8 | 4635 | 0.075222
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 5900 | 6199 | Orville Dr | Gloria Ln | Dead End | 41.6904 | 21 | Local | [17 empty] | 44374.95 | [19 empty] | 1192.8763 | 24 | 28629 | 0.46462
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [19 empty] | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 5000 | 5199 | Reed Ave | W Kenwood Dr | Dead End | 65.1753 | 21 | Local | [17 empty] | 30215.7 | [19 empty] | 935.098 | 20.847 | 19494 | 0.31637
| Hall |  | 350002-279 |  |  | 4800 | 4999 | S 1st St | E Amherst Ave | Dead End to north | 61.3741 | 21 | Local | [13 empty] | 4 |  |  | 4 | 35997.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 822.4664 | 28.237 | 23224 | 0.37691
| Hall |  |  |  |  | 2825 | 2899 | Smilax Ave | Loretta St | W Indian Trl | 78 | 21 | Local | [17 empty] | 12877.4 | [19 empty] | 346 | 24 | 8308 | 0.13483
| Hall |  | 350002-279 |  |  | 100 | 114 | W Amherst Ave | Southside Dr | S 1st St | 59 | 21 | Local | [13 empty] | 4 |  |  |  | 16994.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 422 | 26 | 10964 | 0.17794
| Hall |  |  |  |  | 900 | 1199 | W Indian Trl | Preston Hwy | Dead End | 52.6638 | 21 | Local | [17 empty] | 116784.75 | [19 empty] | 3947.8218 | 19.0852 | 75345 | 1.2228
| Hall |  | 350002-279 |  |  | 200 | 5799 | W Southland Blvd | Southside Dr | Southern Pkwy | 54.9398 | 21 | Pri Coll | [13 empty] | 15 |  |  | 15 | 256091.9955 | 269998.86 | [17 empty] | 2 speed humps on roadway, need to check ramps at southland Ter. | 5145.34 | 30.1646 | 155207.27 | 2.5189
| Hall |  | 350002-279 |  |  | 100 | 199 | W Tenny Ave | S 1st St | Southside Dr | 35 | 21 | Local | [13 empty] | 8 |  |  |  | 19027.8 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 409 | 30 | 12276 | 0.19923
| Hall |  |  |  |  | 2800 | 2899 | Whitlock St | Norton Ave | Loretta St | 85 | 21 | Local | [17 empty] | 29848.35 | [19 empty] | 837 | 23 | 19257 | 0.31252
| Hall |  |  |  |  | 5400 | 5499 | Winding Rd | Woodmore Ave | Dead End | 47 | 21 | Local | [17 empty] | 46949.5 | [19 empty] | 1121.8398 | 27 | 30290 | 0.49158
| LP |  |  |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [19 empty] | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 1924-08-21 | 1925-03-08 | Fern Creek Rd | Beulah Church Rd | Bardstown Rd | 64.6738 | 22 | Pri Coll | [17 empty] | 139346.2469 | [19 empty] | 4021.5367 | 21 | 84452.2709 | 1.3706
| Hall |  | 350002-346 |  |  | 8600 | 8609 | Glenhope Dr | Black Iron Rd | break south of Stonebreaker Rd | 56.1215 | 22 | Local | [17 empty] | 25878.8 | [19 empty] | 695.6754 | 23.9997 | 16696 | 0.27096
| Hall |  | 350002-346 |  |  | 10500 | 10699 | Stonebreaker Rd | Dead End | Dead End | 49.7486 | 22 | Local | [17 empty] | 76402.6 | [19 empty] | 2155.5713 | 22.8673 | 49292 | 0.79997
| Hall |  |  |  |  | 8300 | 8499 | Berea Dr | Damascus Ct | Sardis Way | 44 | 23 | Local | [17 empty] | 46244 | [19 empty] | 1005 | 23 | 23122 | 0.37525
| Hall |  |  |  |  | 6200 | 6399 | Hackberry Way | Maple Rd | Lancewood Rd | 44 | 23 | Local | [17 empty] | 53769.5 | [19 empty] | 1576.8029 | 22 | 34690 | 0.56299
| Hall |  |  |  |  | 9600 | 9899 | Lancewood Rd | Dead End | Price Lane Rd | 46.4626 | 23 | Local | [17 empty] | 50145.6 | [19 empty] | 1516.9546 | 21.3269 | 32352 | 0.52504
| Hall |  | 350002-304 |  |  | 8400 | 9399 | Pennsylvania Run Rd | Vaughn Mill Rd | Cooper Chapel Rd | 60.244 | 23 | Pri Coll | [13 empty] | 0 |  |  |  | 221604.4215 | See Vaughn Mill | August | [16 empty] | Need to replace 1 culvet for sure, but review others. Update guardrails as necessary. Will avoid sidewalk ramps if possible | 6395.51 | 21 | 134305.71 | 2.1797
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Outer Loop | Pennsylvania Run Rd | 65 | 23 | Pri Coll | [17 empty] | 145558 | 326973.76 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Fegenbush Ln | Outer Loop | 65 | 23 | Pri Coll | [17 empty] | 86290 | See Vaughn Mill Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 9500 | 9599 | Yellow Pine Ct | Dead End | Yellow Pine Dr | 48 | 23 | Local | [17 empty] | 18097.8 | [19 empty] | 486.509 | 24 | 11676 | 0.18949
| Hall |  | 350002-349 |  |  | 3800 | 3899 | Britt Ln | Dead End | Rust Oak Ln | 39.4136 | 24 | Local | [13 empty] | 5 |  |  |  | 47330.8 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1297.2258 | 23.5395 | 30536 | 0.49557
| Hall |  | 350002-349 |  |  | 8100 | 8199 | Carnes Dr | Dead End | Tuesday Way | 38 | 24 | Local | [13 empty] | 3 |  |  |  | 11198.75 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 301.058 | 24 | 7225 | 0.11726
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  | 350002-349 |  |  | 8000 | 8299 | Horizon Ln | Dead End | Foreman Ln | 48.5169 | 24 | Local | [13 empty] | 2 |  |  |  | 39569.95 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1088.3103 | 23.4575 | 25529 | 0.41431
| Hall |  |  |  |  | 6000 | 6199 | Ledgerock Cove Pl | Dead End | Dead End | 80.4892 | 24 | Local | [17 empty] | 30097.9 | [19 empty] | 970.9416 | 24 | 19418 | 0.31514
| Hall |  |  |  |  | 6900 | 7099 | Ledgerock Rd | Ledgerock Cove Pl | Moorhaven Dr | 47.5203 | 24 | Local | [17 empty] | 40166.7 | [19 empty] | 1079.7727 | 23.9995 | 25914 | 0.42056
| LP |  |  |  |  | 1901-11-30 | 1903-10-30 | McCawley Rd | Preston Hwy | Jefferson Blvd | 66.4236 | 24 | Pri Coll | [17 empty] | 195165.3 | [19 empty] | 4479.469 | 26.4054 | 118282 | 1.9196
| Hall |  | 350002-237 |  |  |  |  | Monaco Dr | Woodhill Ln | Morningside Way | 48 | 24 | Local | [16 empty] | 3 | 43368 | 129859.74 | July | Council | 8125-410-8107-148385-822702 | 103880.92 |  | 8137-410-8210-148385-822702 | 6320.87 |  | 8101-410-8210-148385-822702 | 61863.6 | [7 empty] | Pushed back to FY 21 due to virus |  |  | 28912 | 0.46922
| Hall |  | 350002-237 |  |  |  |  | Morningside Way | Monaco Dr | Dead End | 20 | 24 | Local | [17 empty] | 27317 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 18211 | 0.29555
| Hall |  | 350002-237 |  |  |  |  | Oaklawn Dr | Preston Hwy | Dead End | 48 | 24 | Local | [17 empty] | 100551 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 67034 | 1.0879
|  |  | 350002-238 |  |  |  |  | Prestonview Ln | Foreman Ln | dead end | 31 | 24 | Local | [13 empty] | 0 |  |  |  | 17791.74 | 52304.37 | July | Council | 8133-410-8107-148385-822702 | 17791.74 | [13 empty] | Pushed back to FY 21 due to virus
|  |  | 350002-238 |  |  |  |  | Trio Ave | Preston Hwy | Prestonview Ln | 33 | 24 | Local | [13 empty] | 0 |  |  |  | $17,791,75 | See Prestonview | July | Council | 8133-410-8210-148385-822702 | 17791.75 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  | 350002-349 |  |  | 3700 | 3999 | Tuesday Way | Woodbury Dr | Dead End | 42.0113 | 24 | Local | [13 empty] | 7 |  |  |  | 90795.9 | 205413.81 | July | [16 empty] | Pushed back to FY 21 due to virus | 2255.064 | 25.9762 | 58578 | 0.95067
| Hall |  | 350002-349 |  |  | 3700 | 3799 | Wednesday Way | Dead End | Horizon Ln | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 20393.35 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 548.2191 | 24 | 13157 | 0.21353
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Dannyboy Ln | Ida Way | Dead End | 51 | 25 | Local | [17 empty] | 18463.6 | [19 empty] | 541.4771 | 22 | 11912 | 0.19332
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65.4587 | 25 | Sec Coll | [17 empty] | 272001.708 | [19 empty] | 6879.848 | 23.9612 | 164849.52 | 2.6754
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Hickory Hill Rd | Park Rd | Southview Rd | 52 | 25 | Local | [17 empty] | 24924 | [19 empty] | 730.9304 | 22 | 16080 | 0.26096
| Hall |  | 350002-352 |  |  | 900 | 999 | Ida Way | Sunnybrook Dr | Dannyboy Ln | 55 | 25 | Local | [17 empty] | 10510.55 | [19 empty] | 308.2079 | 22 | 6781 | 0.11005
| LP |  | 339051-64 |  |  | 8300 | 8499 | McNair Rd | Manslick Rd | 3rd Street Rd | 62.7373 | 25 | Pri Coll | [13 empty] | 0 |  |  |  | 40944.123 | [18 empty] | Proposed Development may repave McNair. Various base failures, edge of road reconstruction needed. Some sort of shoulder will also be needed. May need to replace driveway on Wisertown Rd with this project, so prioritize for Summer 2019. | 1378.59 | 18 | 24814.62 | 0.40272
| Hall |  | 350002-352 |  |  | 5300 | 5399 | Southdale Rd | Palatka Rd | Southview Rd | 68.1387 | 25 | Local | [17 empty] | 63858.45 | [19 empty] | 1872.6681 | 22.0002 | 41199 | 0.66862
| Hall |  | 350002-352 |  |  | 918 | 900 | Southview Rd | Southdale Rd | Palatka Rd | 56.0019 | 25 | Local | [17 empty] | 49846.45 | [19 empty] | 1339.9785 | 23.9996 | 32159 | 0.52191
| LP |  | 339051-73 |  |  | 9000 | 9302 | Stonestreet Rd | Dixie Hwy | Valley College Dr | 65.9195 | 25 | Min Art | [17 empty] | 296780.55 | [19 empty] | 3575.0904 | 50.3112 | 179867 | 2.9191
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Sunnybrook Dr | Palatka Rd | Dead End | 55.7993 | 25 | Local | [17 empty] | 33266.1 | [19 empty] | 894.2654 | 23.9996 | 21462 | 0.34831
| Hall |  | 350002-352 |  |  | 900 | 999 | Westview Dr | New Cut Rd | Dead End | 51 | 25 | Local | [17 empty] | 35299.7 | [19 empty] | 1084.4551 | 21 | 22774 | 0.3696
|  |  | 350002-319 |  |  |  |  | Bashford Manor Ln | Bardstown Rd | Medford Ln |  | 26 | Local | [17 empty] | 42000 |  |  | Council | 8138-105-8107-038226-899998 | 23000 |  | 8138-410-8107-148387-822702 | 19000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 3000 | 3014 | Boaires Ln | Talisman Rd | Rio Rita Ave | 47 | 26 | Local | [17 empty] | 17921.1 | [19 empty] | 481.737 | 24 | 11562 | 0.18764
| Hall |  |  |  |  | 2900 | 3099 | Bowman Ave | Dutchmans Ln | Dead End | 50.8815 | 26 | Local | [17 empty] | 42772.25 | [19 empty] | 1404.5798 | 19.6464 | 27595 | 0.44784
| Hall |  |  |  |  | 2900 | 2999 | Cannons Ln | Dutchmans Ln | Bowman Ave | 35.207 | 26 | Local | [17 empty] | 32943.7 | [19 empty] | 929.1685 | 22.8742 | 21254 | 0.34493
| Hall |  |  |  |  | 6012 | 6399 | Dutchmans Ln | Dutchmans Pky | Dutchmans Pky | 46 | 26 | Local | [17 empty] | 142852.65 | [19 empty] | 2973 | 31 | 92163 | 1.4957
| Hall |  |  |  |  | 3500 | 3599 | Ephraim Mcdowell Dr | Cannons Ln | Abigail Dr | 48.9726 | 26 | Local | [17 empty] | 36181.65 | [19 empty] | 1003.653 | 23.258 | 23343 | 0.37884
| Hall |  |  |  |  | 1908-03-18 | 1909-04-21 | Furman Blvd | Taylorsville Rd | Hikes Ln | 63.8043 | 26 | Pri Coll | [17 empty] | 269468.892 | [19 empty] | 3983.28 | 41 | 163314.48 | 2.6505
| NA |  |  | 2018-07-01 |  | 3000 | 3499 | Hikes Ln | Klondike Ln | Browns Ln | 57.2165 | 26 | Min Art | [13 empty] | 22 |  |  |  | 603010.8 |  |  | PW Funds |  | 603010.8 | [13 empty] | Will try to group with KYTC and bid seperately, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 5316.81 | 60 | 301505.4 | 4.8932
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Klondike Ln | Goldsmith Ln |  | 26 | Min Art | [13 empty] | 20 |  |  |  | 510705 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3483.5026 | 62 | 215977.1635 | 3.5051
| Hall |  | 350002-257 |  |  | 2700 | 3899 | Klondike Ln | Six Mile Ln | Hikes Ln | 61.6177 | 26 | Pri Coll | [13 empty] | 25 |  |  | 12 | 221552.1 | 36215.73 | July | [16 empty] | Look at cross drain near Six Mile Ln, others which may be present. Probable fiber project. | 6394 | 21 | 134274 | 2.1792
| Hall |  |  |  |  | 3000 | 3199 | Talisman Rd | Kings Hwy | Boaires Ln | 47.314 | 26 | Local | [17 empty] | 139885.95 | [19 empty] | 3610.2177 | 24.9982 | 90249 | 1.4647
| QK4 |  | 314578-70 |  |  |  |  | QK4 Density Testing | [22 empty] | 20000 | 33186.51 |  | PW Funds | 8672-410-8210-148929-822703 | 20000 | [17 empty] | 0
| QK4 |  | 314578-78 |  |  |  |  | QK4 supplemental Inspections | [22 empty] | 20000 | 51389 |  | PW Funds | 8672-410-8210-148929-822704 | 20000 | [17 empty] | 0
| QK4 |  | 314578-119 |  |  |  |  | St Anthony Slide | [23 empty] | 3575.74 | [21 empty] | 0

## Sept 20
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-255 |  |  | 3400 | 3799 | W Magnolia Ave | Louis Coleman Jr Dr | Gibson Ln | 35 | 1 | Local | [13 empty] | 3 |  |  | 3 | 125495.75 | 99645.81 | July | [16 empty] | Seems to be many Semi Tractor Trailors. May use Fiber | 2381.3351 | 34 | 80965 | 1.314
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hwy | W Hill St | 67 | 1 | Min Art | [17 empty] | 293670 | 242320.52 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 3700 | 4199 | Grand Ave | Dead End east of 38th | Cecil Ave | 50.0041 | 1 | Local | [17 empty] | 72590.5765 | [19 empty] | 1711.95 | 27.3563 | 46832.63 | 0.76005
| Hall |  |  |  |  | 2600 | 2999 | Grand Ave | S 26th St | Dead End to west | 61.1995 | 1 | Local | [17 empty] | 64222.824 | [19 empty] | 1255.22 | 33.0094 | 41434.08 | 0.67244
| Hall |  |  |  |  | 3000 | 3699 | Grand Ave | Dead End east of 32nd | Dead End west of Canopy Ct | 64.4573 | 1 | Local | [17 empty] | 131092.8 | [19 empty] | 2917.54 | 32.8616 | 84576 | 1.3726
| Hall |  |  |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | [19 empty] | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  |  |  |  | 3200 | 3699 | Hale Ave | S 32nd St | Dead End to west | 48.0322 | 1 | Local | [17 empty] | 103495.05 | [19 empty] | 2281.7 | 29.2637 | 66771 | 1.0836
| Hall |  |  |  |  | 1904-12-04 | 1919-12-25 | Lower Hunters Trce | Dixie Hwy | Greenbelt Hwy | 65.8978 | 1 | Pri Coll | [17 empty] | 50887.65 | [19 empty] | 1117 | 27.6106 | 30841 | 0.50052
| Hall |  |  |  |  | 6616 | 7299 | Lower Hunters Trce | Greenbelt Hwy | Cane Run Rd | 64.1728 | 1 | Pri Coll | [17 empty] | 116082.681 | [19 empty] | 2705.89 | 26 | 70353.14 | 1.1418
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 3600 | 3699 | Friar Tuck Ct | Robinhood Ln | Dead End | 41 | 2 | Local | [17 empty] | 13852.35 | [19 empty] | 406 | 22 | 8937 | 0.14504
| Hall |  |  |  |  | 5100 | 5199 | Jefferson Blvd | Poplar Level Rd | Fern Valley Rd | 58.4628 | 2 | Min Art | [17 empty] | 117874.35 | [19 empty] | 1152.2379 | 62.0002 | 71439 | 1.1594
| Hall |  |  |  |  | 3600 | 3699 | Little John Ct | Robinhood Ln | Dead End | 54 | 2 | Local | [17 empty] | 9605.35 | [19 empty] | 258 | 24 | 6197 | 0.10057
| Hall |  |  |  |  | 4600 | 4699 | Oaklawn Ln | Rangeland Rd | Oakdale Ln | 40 | 2 | Local | [17 empty] | 45000 | [19 empty] | 1142 | 22 | 25124 | 0.40774
| Hall |  |  |  |  | 1200 | 1399 | Old Fern Valley Rd | Preston Hwy | Fern Valley Rd | 53 | 2 | Local | [17 empty] | 110589.4 | [19 empty] | 3398 | 21 | 71348 | 1.1579
| Hall |  |  |  |  | 5800 | 6099 | Robinhood Ln | Friar Tuck Ct | Forest Dr | 32.905 | 2 | Local | [17 empty] | 52659.7 | [19 empty] | 1475.2816 | 23.0288 | 33974 | 0.55137
| Hall |  |  |  |  | 4000 | 4099 | Tower Rd | Preston Hwy | Dead End | 46 | 2 | Local | [17 empty] | 96856.4 | [19 empty] | 2604 | 24 | 62488 | 1.0141
| Hall |  | 350002-334 |  |  | 1600 | 2699 | Dixdale Ave | Wingfield Ave | S 28th St | 55.9513 | 3 | Local | [17 empty] | 170479.85 | 527564.94 | August | [17 empty] | 5770.7465 | 19.0594 | 109987 | 1.785
| Hall |  | 350002-334 |  |  |  |  | Dixie Hwy | W Burnett Ave | Bernheim Ln | 66 | 3 | Min Art | [17 empty] | 254141 | See Dixdale | August | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-334 |  |  | 1600 | 1799 | W Lee St | S 15th St | Dixie Hwy | 47.1551 | 3 | Local | [17 empty] | 107680.05 | See Dixdale | August | [17 empty] | 2701.6913 | 25.7139 | 69471 | 1.1275
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-247 |  |  | 400 | 999 | E Witherspoon St | N Preston St | River Rd | 59.6256 | 4 | Min Art | [13 empty] | 8 |  |  |  | 326255.457 | See N 1st St | July | [16 empty] | Portion of this may have been paved with bridges project. | 3413.14 | 57.9322 | 197730.58 | 3.209
| Hall |  | 350002-247 |  |  |  |  | N 1st St | W Main St | E Witherspoon St |  | 4 | [17 empty] | 4 | 150000 | 383501.48 | July
| Hall |  |  |  |  | 500 | 799 | Bergman St | Dead End | S Shelby St | 20 | 4 | Local | [17 empty] | 59203.8 | [19 empty] | 1317 | 29 | 38196 | 0.61989
| Hall |  |  |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | [19 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-338 |  |  | 100 | 1299 | E Breckinridge St | S 1st St | Barret Ave | 60.4014 | 4 | Pri Coll | [17 empty] | 402154.632 | 76026.53 | [18 empty] | 6770.28 | 36 | 243730.08 | 3.9555
| Hall |  |  |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | [19 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  |  |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | [19 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | [19 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  |  |  |  | 150 | 399 | E Witherspoon St | Bingham Way | N Preston St | 62.9283 | 4 | Min Art | [17 empty] | 95488.8 | [19 empty] | 1425.1269 | 40.6083 | 57872 | 0.93921
| Hall |  | 350002-339 |  |  | 700 | 799 | Henry Fripo St | S Clay St | S Shelby St | 18 | 4 | Local | [17 empty] | 22452.8 | [19 empty] | 585 | 24 | 14033 | 0.22774
| Hall |  | 350002-339 |  |  | 400 | 999 | Lampton St | S Preston St | Dead End | 36.2169 | 4 | Local | [17 empty] | 149189.05 | 21648.25 | [18 empty] | 3187.4777 | 30.1966 | 96251 | 1.5621
| Hall |  |  |  |  | 500 | 799 | Meriwether Ave | E Burnett Ave | S Shelby St | 62.3338 | 4 | Pri Coll | [17 empty] | 110292.435 | [19 empty] | 2228.13 | 30 | 66843.9 | 1.0848
| Hall |  | 350002-340 |  |  | 300 | 1499 | S 15th St | W Jefferson St | W Hill St | 53.5853 | 4 | Min Art | [17 empty] | 687630.9 | [19 empty] | 10228.8508 | 40.7422 | 416746 | 6.7634
| Hall |  |  |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | [19 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 1400 | 1454 | S Preston St | S Jackson St | E Burnett Ave | 54.0007 | 4 | Min Art | [17 empty] | 33037.95 | [19 empty] | 564.7347 | 35.4556 | 20023 | 0.32496
| Hall |  |  |  |  | 300 | 599 | S Wenzel St | E Chestnut St | E Jefferson St | 25.8121 | 4 | Local | [17 empty] | 74648 | [19 empty] | 1387.7936 | 34.7026 | 48160 | 0.78159
| Hall |  |  |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | [19 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall | [6 empty] | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 |  |  | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14
| Hall |  |  |  |  | 850 | 1499 | W Muhammad Ali Blvd | Roy Wilkins Ave | S 15th St | 56.2923 | 4 | Min Art | [17 empty] | 185212.5 | [19 empty] | 2927.305 | 38.3459 | 112250 | 1.8217
| Hall |  | 350002-356 |  |  | 100 | 299 | N & S 46th St | N Longworth Ave | W Market St | 20.6662 | 5 | Local | [13 empty] | 6 |  |  | 6 | 71380.6 | 48092.31 | July | [16 empty] | May have been paved into gutter from Longworth to Duncan | 1555.8172 | 29.5999 | 46052 | 0.74738
| Hall |  | 350002-363 |  |  | 1900-12-15 | 1904-05-17 | Southwestern Pky | S Shawnee Ter | Gibson Ln | 59.2734 | 5 | Min Art | [17 empty] | 598921.95 |  | September | [16 empty] | Section from Broadway to Dumesnil was repaved, rest will be completed with KYTC project and other portion of Southwestern. | 10181.6927 | 35.6506 | 362983 | 5.8909
| Hall |  |  |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [19 empty] | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 600 | 699 | Hardin St | Bank St | Gilligan St | 2 | 5 | Local | [17 empty] | 19381.2 | [19 empty] | 247 | 25 | 6252 | 0.10146
| Hall |  |  |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | [19 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  |  |  |  | 700 | 899 | N 33rd St | Northwestern Pky | Dead End | 54.0197 | 5 | Local | [17 empty] | 56883.45 | [19 empty] | 531.8259 | 69.0057 | 36699 | 0.59559
| Hall |  |  |  |  | 700 | 899 | N 34th St | Northwestern Pky | Dead End | 57.1053 | 5 | Local | [17 empty] | 41126.15 | [19 empty] | 514.4215 | 51.5783 | 26533 | 0.43061
| Hall |  |  |  |  | 700 | 799 | N 36th St | Northwestern Pky | Rudd Ave | 44 | 5 | Local | [17 empty] | 21298.55 | [19 empty] | 529 | 26 | 13741 | 0.223
| Hall |  | 350002-312 |  |  | 3200 | 3299 | Rudd Ave | Dead End (east) | N 34th St | 44.7342 | 5 | Local | [13 empty] | 12 |  |  |  | 87872.6 | 32983.13 | [17 empty] | Brick paver sidewalk NW of 34th, Possible LSR project. | 959.6305 | 59.0769 | 56692 | 0.92006
| Hall |  |  |  |  | 3400 | 3899 | Rudd Ave | N 34th St | Dead End (west) | 56.5344 | 5 | Local | [17 empty] | 107745.15 | [19 empty] | 1259.0092 | 55.2125 | 69513 | 1.1281
| Hall |  |  |  |  | 200 | 399 | Shawnee Dr | W Market St | Southwestern Pky | 20.4991 | 5 | Local | [17 empty] | 86138.15 | [19 empty] | 1543.6989 | 35.9999 | 55573 | 0.9019
| Hall |  |  |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | [19 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  |  |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | [19 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  |  |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | [19 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-362 |  |  | 2400 | 2899 | S Floyd St | Old Eastern Pky | Central Ave | 60.0965 | 6 | Pri Coll | [17 empty] | 29653.8 | See S Floyd | August | [17 empty] | 412 | 43.6214 | 17972 | 0.29167
| Hall |  | 350002-208 |  |  | 800 | 1155 | Dixie Hwy | Maple St | Hale Ave | 59.8113 | 6 | Min Art | [13 empty] | Ramps Complete |  |  |  | 202327.257 | 128033.77 | July | [17 empty] | 3226.91 | 38 | 122622.58 | 1.9901
| Hall |  | 350002-301 |  |  |  |  | Dumesnil St | Dixie Hwy | S 26th St | 59 | 6 | Min Art | [17 empty] | 125991 | 96296.13 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hey | Catalpa St | 66 | 6 | Min Art | [17 empty] | 137347 | See Wilson Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 1901-05-19 | 1901-08-21 | Colorado Ave | Dead End | Algonquin Pky | 61.8146 | 6 | Maj Art | [17 empty] | 119260.35 | [19 empty] | 2131.5568 | 33.909 | 72279 | 1.173
| Hall |  |  |  |  | 900 | 1499 | W Kentucky St | S 9th St | S 15th St | 52.5746 | 6 | Pri Coll | [17 empty] | 177564.75 | [19 empty] | 2808.5642 | 38.3167 | 107615 | 1.7465
| Hall |  |  |  |  | 1000 | 2399 | W Ormsby Ave | Dead End | S 25th St | 44.9819 | 6 | Local | [17 empty] | 310365.8 | [19 empty] | 7886.4736 | 25.3898 | 200236 | 3.2497
| Hall |  |  |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | [19 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-308 |  |  |  |  | Lime Kiln Ln | US 42 | Brownsboro Rd | 65 | 7 | Pri Coll | [17 empty] | 120650 | 3734.75 | [17 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | [19 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-262 |  |  | 2400 | 2699 | Ransdell Ave | Grinstead Dr | Bassett Ave | 47.2922 | 8 | Local | [13 empty] | 6 |  |  | 7 | 94001.3 | 59692.96 | August | [16 empty] | Ray Ave may have been paved which updated ramps at this intersection | 2021.5198 | 30.0002 | 60646 | 0.98423
| Hall |  | 350002-357 |  |  |  |  | Alta Vista Rd | Beargrass Ave | I-64 overpass | 58 | 8 | Local | [17 empty] | 153131 | 241570.1 | July | [17 empty] | 4340 | 23 | 98794 | 1.6033
| Hall |  | 350002-358 |  |  | 1 | 99 | Beverly Rd | Cross Rd | Dead End | 26 | 8 | Local | [17 empty] | 9203.9 |  | September | [17 empty] | 330 | 18 | 5938 | 0.096369
| Hall |  | 350002-358 |  |  | 1 | 1449 | Cross Rd | Castlewood Ave | Eastern Pkwy | 58.4177 | 8 | Local | [17 empty] | 34146.5 |  | September | [17 empty] | 1223.9072 | 17.9997 | 22030 | 0.35753
| Hall |  | 350002-344 |  |  | 2530 | 2599 | Woodbourne Ave | Valletta Ln | Cherosen Rd | 33.6999 | 8 | Local | [13 empty] | 0 |  |  |  | 54761.5 |  | September | [16 empty] | Watch for asphalt and decorative curbs | 1662.1826 | 21.2552 | 35330 | 0.57338
| Hall |  | 350002-344 |  |  | 2300 | 2699 | Brookside Dr | Ingleside Dr | Dead End | 62 | 8 | Local | [13 empty] | 0 |  |  |  | 62048 | [18 empty] | Concrete. Circle of cul-de-sac may have been paved previously. | 646.3277 | 24 | 15512 | 0.25175
| Hall |  | 350002-343 |  |  | 2200 | 2549 | Hawthorne Ave | Bon Air Ave | Bardstown Rd | 43.7621 | 8 | Local | [17 empty] | 88168.65 | 4420.53 | [18 empty] | 3037.4844 | 18.727 | 56883 | 0.92316
| Hall |  | 350002-344 |  |  | 2300 | 2399 | Ingleside Dr | Woodbourne Ave | Dead End | 46.0948 | 8 | Local | [13 empty] | 0 |  |  |  | 53432.5 | [18 empty] | Concrete from Brookside to dead end. Watch for asphalt and decorative curb in asphalt section. | 911.9486 | 21.306 | 19430 | 0.31533
| Hall |  | 350002-345 |  |  | 2860 | 2899 | Lowell Ave | Tyler Ln | Hawthorne Ave | 37 | 8 | Local | [17 empty] | 11778.45 | [19 empty] | 422.1865 | 18 | 7599 | 0.12333
| Hall |  |  |  |  | 1630 | 1799 | Ruth Ave | Strand Ave | Radnor Ave | 58.6718 | 8 | Local | [17 empty] | 15067.55 | [19 empty] | 486.0341 | 20.0007 | 9721 | 0.15776
| Hall |  | 350002-342 |  |  | 1617 | 1999 | Speed Ave | Fernwood Ave | Bardstown Rd | 23 | 8 | Local | [17 empty] | 72978.5 | [19 empty] | 1158 | 18 | 20851 | 0.33839
| Hall |  | 350002-342 |  |  | 1905-06-22 | 1906-03-13 | Speed Ave | Bardstown Rd | Spring Dr | 64.8405 | 8 | Pri Coll | [17 empty] | 68566.905 | [19 empty] | 1385.19 | 30 | 41555.7 | 0.67441
| Hall |  | 350002-357 |  |  | 2800 | 2899 | Alta Vista Pl | Alta Vista Ct | Dead End | 4 | 9 | Local | [13 empty] | 0 |  |  |  | 24260 | See Alta Vista | July | [16 empty] | Concrete, then transitions to Asphalt. | 379 | 16 | 6065 | 0.09843
| Hall |  | 350002-357 |  |  | 2800 | 2899 | Alta Vista Way | Alta Vista Rd | Dead End | 36 | 9 | Local | [13 empty] | 0 |  |  |  | 14496 | See Alta Vista | July | [16 empty] | Asphalt | 226 | 16 | 3624 | 0.058814
| Hall |  |  |  |  | 200 | 399 | Coralberry Rd | Dead End | Dead End | 55.9856 | 9 | Local | [17 empty] | 54516.6 | [19 empty] | 1506.6618 | 23.3443 | 35172 | 0.57081
| Hall |  |  |  |  | 200 | 299 | Mockingbird Gardens Dr | Dead End | Winterleaf Dr | 42.5777 | 9 | Local | [17 empty] | 57269.4 | [19 empty] | 1830.1722 | 20.1883 | 36948 | 0.59963
| Hall |  | 350002-353 |  |  | 100 | 299 | N Bayly Ave | Frankfort Ave | Hollywood Ter | 22.525 | 9 | Local | [13 empty] | 11 |  |  |  | 61958.15 | [18 empty] | Several ramps are stairs. Likely technically infeasible. | 1375.1377 | 29.0684 | 39973 | 0.64873
| Hall |  | 350002-353 |  |  | 200 | 299 | N Clifton Ave | Sycamore Ave | Brownsboro Rd | 46.5993 | 9 | Local | [13 empty] | 6 |  |  |  | 53104.55 | [18 empty] | Pave entire triangle area at Sycamore, one set of stairs at sycamore which is likely infeasible | 1285.4381 | 26.6532 | 34261 | 0.55603
| Hall |  | 350002-353 |  |  | 100 | 199 | N Jane St | Frankfort Ave | Brownboro Rd | 47.6659 | 9 | Local | [13 empty] | 8 |  |  |  | 56206.1 | [18 empty] | Need to confirm ADA ramps before RR tracks | 1893.1414 | 19.1544 | 36262 | 0.5885
| Hall |  |  |  |  | 200 | 399 | Pepperbush Rd | Dead End | Dead End | 55.3127 | 9 | Local | [17 empty] | 100709.7 | [19 empty] | 1046.8959 | 62.0635 | 64974 | 1.0545
| Hall |  |  |  |  | 3500 | 3599 | Waterleaf Ct | Waterleaf Way | Dead End | 44 | 9 | Local | [17 empty] | 23628.2 | [19 empty] | 693 | 22 | 15244 | 0.2474
| Hall |  |  |  |  | 200 | 299 | Waterleaf Way | Dead End | Mockingbird Gardens dr | 46.4515 | 9 | Local | [17 empty] | 28020.9 | [19 empty] | 821.7223 | 22.0001 | 18078 | 0.29339
| Hall |  |  |  |  | 3500 | 3599 | Winterberry Cir | Mockingbird Gardens Dr | Mockingbird Gardens Dr | 30 | 9 | Local | [17 empty] | 46517.05 | [19 empty] | 1429 | 21 | 30011 | 0.48705
| Hall |  | 350002-348 |  |  | 1100 | 1299 | Boyle St | Charles St | Goss Ave | 44.0005 | 10 | Local | [13 empty] | 6 |  |  |  | 36327.35 | See Texas | August | [16 empty] | LWC work was done in area | 781.2483 | 29.9994 | 23437 | 0.38036
| Hall |  | 350002-348 |  |  | 900 | 1199 | Charles St | Texas Ave | Dandridge Ave | 32.7758 | 10 | Local | [13 empty] | 15 |  |  |  | 106627.6 | See Texas | August | [16 empty] | LWC work was done in area | 2456.8468 | 28.0001 | 68792 | 1.1164
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Krierger St | Ellison Ave | Goss Ave | 39.3379 | 10 | Local | [13 empty] | 13 |  |  |  | 50722.2 | See Texas | August | [16 empty] | Depress sidewalk to be flush with pavement at alleys where possible, LWC work done in area | 1168.7507 | 27.9991 | 32724 | 0.53108
| Hall |  | 350002-310 |  |  | 2600 | 2899 | Parklawn Dr | Parkway Dr | Dead End | 41.6675 | 10 | Local | [13 empty] | 10 |  |  |  | 56649.4 | 65090.51 | August | [16 empty] | Pushed back to FY 21 due to virus | 1885.4269 | 19.3845 | 36548 | 0.59314
| Hall |  | 350002-348 |  |  | 800 | 1699 | Texas Ave | S Shelby St | Wetterau Ave | 48 | 10 | Local | [17 empty] | 271580.15 | 546407.57 | August | [17 empty] | 5300 | 34 | 175213 | 2.8436
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Wetterau Ave | Texas Ave | Dead End | 23.7244 | 10 | Local | [13 empty] | 0 |  |  |  | 16535.4 | See Texas | August | [16 empty] | Update ramp on other side of Samuel leading down to shoping center. LWC work done in area | 801.46 | 13.3107 | 10668 | 0.17313
| Hall |  | 350002-348 |  |  | 1000 | 1099 | Wetterau Ave at Ash St | Dead End | Dead End | 21 | 10 | Local | [13 empty] | 6 |  |  |  | 27932.55 | See Texas | August | [16 empty] | Pushed back to FY 21 due to virus | 750.84 | 24.0011 | 18021 | 0.29247
| Hall |  | 350002-341 |  |  | 1904-12-04 | 1906-01-07 | Bashford Manor Ln | Newburg Rd | Bardstown Rd | 65.1829 | 10 | Pri Coll | [17 empty] | 274355.5815 |  | September | [17 empty] | 5038.67 | 33 | 166276.11 | 2.6985
| Hall |  | 350002-364 |  |  | 1000 | 1099 | Eigelbach Ave | Dead End | Poplar Level Rd | 47 | 10 | Local | [17 empty] | 35391.15 |  | September | [17 empty] | 951 | 24 | 22833 | 0.37056
| Hall |  |  |  |  | 1000 | 1099 | Dixon Ave | Dead End | Poplar Level Rd | 43 | 10 | Local | [17 empty] | 92589 | [19 empty] | 1102 | 24 | 26454 | 0.42933
| Hall |  |  |  |  | 3100 | 3199 | Harmon Ct | Dead End | Audubon Pky | 0 | 10 | Local | [17 empty] | 35031.5 | [19 empty] | 417 | 24 | 10009 | 0.16244
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Bardstown Rd | Goldsmith Ln |  | 10 | Min Art | [13 empty] | 25 |  |  |  | 511151 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3647 | 62 | 226114 | 3.6696
| Hall |  |  |  |  | 3461 | 3781 | Illinois Ave | Sheridan Ave | 3461 Illinois Ave | 57.9238 | 10 | Local | [17 empty] | 105080.7 | [19 empty] | 3268.3937 | 20.7423 | 67794 | 1.1002
| Hall |  |  |  |  | 3150 | 3199 | Illinois Ave | Osprey Rd | Poplar Level Rd | 21 | 10 | Local | [17 empty] | 8337.45 | [19 empty] | 224.1407 | 24 | 5379 | 0.087296
| Hall |  |  |  |  | 1000 | 1099 | Mayer Ave | Dead End | Poplar Level Rd | 37 | 10 | Local | [17 empty] | 66146.5 | [19 empty] | 756 | 25 | 18899 | 0.30671
| Hall |  |  |  |  | 1400 | 1499 | Nightingale Rd | Eagle Pass | Audubon Pky | 39 | 10 | Local | [17 empty] | 58907.75 | [19 empty] | 1727 | 22 | 38005 | 0.61679
| Hall |  |  |  |  | 3100 | 3199 | Osprey Rd | Illinois Ave | Audubon Pky | 50 | 10 | Local | [17 empty] | 24330.35 | [19 empty] | 654 | 24 | 15697 | 0.25475
| Hall |  |  |  |  | 8000 | 8199 | Amity Ln | Summerfield Dr | Dead End | 55.9519 | 11 | Local | [17 empty] | 31184.45 |  | October | [17 empty] | 1000.7746 | 20.1034 | 20119 | 0.32651
| Hall |  |  |  |  | 8000 | 8199 | Cloudcroft Ln | Summerfield Dr | Dead End | 50 | 11 | Local | [17 empty] | 53769.5 |  | October | [17 empty] | 1239 | 28 | 34690 | 0.56299
| Hall |  |  |  |  | 3100 | 3199 | Spring Breeze Ct | Amity Ln | Dead End | 55.4007 | 11 | Local | [17 empty] | 28616.1 |  | October | [17 empty] | 861.5499 | 21.4288 | 18462 | 0.29962
| Hall |  |  |  |  | 2530 | 2599 | Sunbury Ln | Winterhaven Rd | Winterhaven Rd | 58.8872 | 11 | Local | [17 empty] | 70025.9 |  | October | [17 empty] | 1946.0602 | 23.2151 | 45178 | 0.7332
| Hall |  |  |  |  | 8000 | 8099 | Weather Ct | Weather Way | Dead End | 65 | 11 | Local | [17 empty] | 7052.5 |  | October | [17 empty] | 253 | 18 | 4550 | 0.073843
| Hall |  |  |  |  | 3000 | 3199 | Weather Way | Summerfield Dr | Dead End | 68.3392 | 11 | Local | [17 empty] | 48962.95 |  | October | [17 empty] | 1435.8717 | 21.9999 | 31589 | 0.51266
| LP |  | 339051-74 |  |  | 1916-06-04 | 1918-08-12 | Sylvania Rd | Memory Ln | Rutledge Rd | 63.5483 | 12 | Sec Coll | [17 empty] | 60800.85 |  | September | [17 empty] | 1914.0068 | 19.2523 | 36849 | 0.59803
| Hall |  |  |  |  | 3600 | 3999 | Baymeadow Dr (all) | Brinamwood Dr | Dead End | 72.9415 | 12 | Local | [17 empty] | 71907.6 | [19 empty] | 1973.6702 | 23.6667 | 46392 | 0.7529
| Hall |  |  |  |  | 3600 | 3699 | Birnamwood Ct | Birnamwood Dr | Dead End | 61 | 12 | Local | [17 empty] | 7209.05 | [19 empty] | 258 | 18 | 4651 | 0.075482
| Hall |  |  |  |  | 6900 | 7199 | Birnamwood Dr | St Andrews Church Rd | Baymeadow Dr | 72.8578 | 12 | Local | [17 empty] | 54293.4 | [19 empty] | 1487.6416 | 23.3333 | 35028 | 0.56847
| Hall |  |  |  |  | 3600 | 3699 | Eastmeadow Ct | Birnamwood Dr | Dead End | 56 | 12 | Local | [17 empty] | 6313.15 | [19 empty] | 226 | 18 | 4073 | 0.066101
| Hall |  |  |  |  | 6900 | 6999 | Hyland Hills Ct | Baymeadow Dr | Dead End | 48 | 12 | Local | [17 empty] | 4642.25 | [19 empty] | 150 | 20 | 2995 | 0.048606
| Hall |  |  |  |  | 1905-03-14 | 1906-01-07 | Lower Hunters Trce | Dixie Hwy | Upper Hunters Trce | 63.6414 | 12 | Pri Coll | [17 empty] | 91005 | [19 empty] | 3840.0384 | 29.3265 | 112615 | 1.8276
| Hall |  |  |  |  | 1906-01-08 | 1918-02-09 | Lower Hunters Trce | Upper Hunters Trce | Greenbelt Hwy | 66.9497 | 12 | Pri Coll | [17 empty] | 347664.9 | [19 empty] | 9483.5364 | 25.4712 | 210706 | 3.4196
| Hall |  |  |  |  | 100 | 199 | Mills Dr | Alreva Rd | Blanton Ln | 61.0339 | 12 | Local | [17 empty] | 97908.85 | [19 empty] | 3088.9085 | 20.4496 | 63167 | 1.0251
| Hall |  |  |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | [19 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-281 |  |  | 8000 | 8399 | Afterglow Dr | Dead End | Outer Loop | 49.0349 | 13 | Local | [13 empty] | 4 |  |  | 12 | 175466.2 | 193267.43 | August | [16 empty] | May look to add frontage Rd off Outer Loop | 4154.1404 | 27.2509 | 113204 | 1.8372
| Hall |  | 350002-361 |  |  | 10600 | 11499 | Harrison Ln | National Tpke | Dead End | 51.4903 | 13 | Local | [17 empty] | 150370.15 | 84772.32 | August | [17 empty] | 5276.3386 | 18.3864 | 97013 | 1.5744
| Hall |  | 350002-335 |  |  | 800 | 899 | Candleglow Ct | Dead End | Candleglow Ln | 52 | 13 | Local | [17 empty] | 10231.55 | See Candlelight | September | [17 empty] | 367 | 18 | 6601 | 0.10713
| Hall |  | 350002-335 |  |  | 500 | 899 | Candlelight Ln | New Cut Rd | Dead End | 63.1036 | 13 | Local | [17 empty] | 81216.9 | 15338.99 | September | [17 empty] | 2734.1962 | 19.164 | 52398 | 0.85037
| Hall |  | 350002-336 |  |  | 400 | 499 | Garrison Ct | Dead End | Garrison Rd | 29 | 13 | Local | [17 empty] | 7745.35 | See Garrison Rd | September | [17 empty] | 227 | 22 | 4997 | 0.081097
| Hall |  | 350002-336 |  |  | 7300 | 7699 | Garrison Rd | Dead End | Revolutionary Rd | 53.4225 | 13 | Local | [17 empty] | 69548.5 | 4791.56 | September | [17 empty] | 1908.6386 | 23.5089 | 44870 | 0.7282
| LP |  | 339051-75 |  |  | 1929-07-26 | 1935-04-25 | Holsclaw Hill Rd | Mitchell Hill Rd | Dead End | 65.6183 | 13 | Sec Coll | [17 empty] | 351212.4 |  | September | [17 empty] | 10567.5567 | 20.1424 | 212856 | 3.4545
| LP |  | 339051-75 |  |  | 1919-03-01 | 1919-12-25 | Knob Creek Rd | Dead End | Mitchell Hill Rd | 58 | 13 | Sec Coll | [17 empty] | 50631.9 |  | September | [17 empty] | 1534.3038 | 20 | 30686 | 0.49801
| Hall |  | 350002-335 |  |  | 800 | 899 | Taper Ct | Dead End | Candleglow Ln | 67 | 13 | Local | [17 empty] | 6747.15 | See Cadlelight | September | [17 empty] | 282 | 16 | 4353 | 0.070645
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | various drainage improvements needed, shoulder | 6261.5 | 19 | 118968.5 | 1.9308
[8 empty] | D13 Paving Projects |  |  |  | 13 | [18 empty] | 14000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000
| Hall |  | 350002-347 |  |  | 16700 | 17199 | Abbotts Beach Rd | Dixie Hwy | Dead End | 23 | 14 | Local | [17 empty] | 36318.05 | 27208.43 | August | [17 empty] | 2343 | 10 | 23431 | 0.38026
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Britannia Ct | Dead End | Scarborough Ave | 61 | 14 | Local | [17 empty] | 23112.05 |  | September | [17 empty] | 621 | 24 | 14911 | 0.24199
| Hall |  | 350002-337 |  |  | 6900 | 7199 | Ethan Allen Way | Kinross Blvd | Bessels Blvd | 42.3493 | 14 | Local | [17 empty] | 85963 | 13528.2 | September | [17 empty] | 2310.8498 | 23.9998 | 55460 | 0.90007
| Hall |  | 350002-369 |  |  | 6900 | 6999 | Fincastle Trl | Dead End | Lower River Rd | 42 | 14 | Local | [17 empty] | 14022.85 |  | September | [17 empty] | 905 | 10 | 9047 | 0.14682
| Hall |  | 350002-367 |  |  | 2400 | 2499 | Hereford Ct | Scarborough Ave | Dead End | 12 | 14 | Local | [17 empty] | 7548.5 |  | September | [17 empty] | 271 | 18 | 4870 | 0.079036
| Hall |  | 350002-367 |  |  | 2400 | 2499 | Kings Cross Ct | Dead End | Scarborough Ave | 56 | 14 | Local | [17 empty] | 9924.65 |  | September | [17 empty] | 291 | 22 | 6403 | 0.10392
| Hall |  | 350002-367 |  |  | 9700 | 9799 | Leopold Ct | Scarborough Ave | Scarborough Ave | 22 | 14 | Local | [17 empty] | 9689.05 |  | September | [17 empty] | 313 | 20 | 6251 | 0.10145
| Hall |  | 350002-367 |  |  | 2500 | 2505 | Parliament Ct | Scarborough Ave | Scarborough Ave | 55 | 14 | Local | [17 empty] | 9351.15 |  | September | [17 empty] | 335 | 18 | 6033 | 0.09791
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Pembury Ct | Scarborough Ave | Dead End | 23 | 14 | Local | [17 empty] | 7641.5 |  | September | [17 empty] | 274 | 18 | 4930 | 0.08001
| Hall |  | 350002-367 |  |  | 9732 | 9899 | Scarborough Ave | Montpelier Ct | Lamborne Blvd | 65.1377 | 14 | Local | [17 empty] | 21024.2 |  | September | [17 empty] | 565.1696 | 23.9999 | 13564 | 0.22013
| Hall |  | 350002-369 |  |  | 7200 | 7399 | Scenic Trl | Dead End | Lower River Rd | 47 | 14 | Local | [17 empty] | 17859.1 |  | September | [17 empty] | 886 | 13 | 11522 | 0.18699
| LP |  | 339051-77 |  |  | 1917-10-17 | 1920-07-12 | W Orell Rd | Dixie Hwy | Lower River Rd | 65.5631 | 14 | Pri Coll | [17 empty] | 174266.4 |  | September | [17 empty] | 5280.8336 | 19.9999 | 105616 | 1.7141
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Yarmouth Ct | Scarborough Ave | Dead End | 35 | 14 | Local | [17 empty] | 17054.65 |  | September | [17 empty] | 550 | 20 | 11003 | 0.17857
| Hall |  |  |  |  | 5700 | 6099 | Alandale Dr | Dixie Hwy | Omar Khayyam Blvd | 59.1854 | 14 | Local | [17 empty] | 107878.45 | [19 empty] | 2719.5213 | 25.5924 | 69599 | 1.1295
| LP |  | 339051-8 | 2017-07-01 |  |  |  | Bearcamp Rd | Blevins Gap Rd | Wildflower Ln |  | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 287148 |  |  | PW '19 MAP | 8672-410-8210-148451-822702 | [14 empty] | On-hold until culvert replacement complete | 5239 | 18 | 94302 | 1.5304
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | see above | 6261.5 | 19 | 118968.5 | 1.9308
| LP |  |  |  |  | 1909-04-22 | 1915-05-25 | Blevins Gap Rd | Stonestreet Rd | Medora Rd | 70.2148 | 14 | Pri Coll | [17 empty] | 550000 |  |  | PW, Council | 8146-410-8210-148538-822702 | 25000 |  | 8146-410-8107-148538-822702 | 75000 | [11 empty] | 18719.4454 | 20.0252 | 374860 | 6.0837
| Hall |  |  |  |  | 11700 | 11899 | Deering Rd | Flowervale Ln | Dead End | 47 | 14 | Local | [17 empty] | 33464.5 | [19 empty] | 1080 | 20 | 21590 | 0.35039
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65 | 14 | Sec Coll | [17 empty] | 68000.427 | [19 empty] | 1719.962 | 24 | 41212.38 | 0.66884
| Hall |  |  |  |  | 9500 | 10099 | Omar Khayyam Blvd | Donau Ln | Count Fleet Dr | 69.6626 | 14 | Local | [17 empty] | 89163.75 | [19 empty] | 2396.8896 | 23.9999 | 57525 | 0.93358
| LP |  | 339051-76 |  |  | 1935-01-16 | 1938-01-19 | Scotts Gap Rd | Blevins Gap Rd | Dead End | 67.2271 | 14 | Sec Coll | [17 empty] | 224112.9 | [19 empty] | 7455.678 | 18.2178 | 135826 | 2.2043
| Seven Seas |  | 370579 |  |  |  |  | Rankin St | E Kenton St | E Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 18778.65 | 3348.9 | August | PW Funds FY 17 | [15 empty] | PCCP - Most panels look ok, I would do select panel replacement - James |  |  | 0 | 0
| Hall |  | 350002-362 |  |  | 1906-07-27 | 1907-12-08 | S Floyd St | Old Eastern Pky | Central Ave | 60 | 15 | Pri Coll | [17 empty] | 214247.55 | 228106.33 | August | [17 empty] | 3290 | 39.4672 | 129847 | 2.1073
| Seven Seas |  | 370579 |  |  |  |  | Tulane Ave | W Kenton St | W Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 14086.05 | 13384.51 | August | PW Funds FY 17 | [15 empty] | PCCP |  |  | 0 | 0
| Hall |  |  |  |  | 4300 | 4399 | Fluhr Dr | Dead End | Anna Ln | 51.7058 | 15 | Local | [17 empty] | 24564.4 | [19 empty] | 660.3467 | 23.9995 | 15848 | 0.2572
| Hall |  |  |  |  | 3500 | 3799 | Georgetown Pl | Berry Blvd | Dead End | 28.4435 | 15 | Local | [17 empty] | 41555.5 | [19 empty] | 1103.1397 | 24.3034 | 26810 | 0.4351
| Hall |  |  |  |  | 300 | 699 | Heywood Ave | S 3rd St | Rodman St | 53.2531 | 15 | Local | [17 empty] | 102665.8 | [19 empty] | 1919.8374 | 34.5008 | 66236 | 1.075
| Hall |  |  |  |  | 1200 | 1320 | Lance Dr | Manslick Rd | Leaf Dr | 59.0188 | 15 | Local | [17 empty] | 30051.4 | [19 empty] | 794.1409 | 24.4138 | 19388 | 0.31465
| Hall |  |  |  |  | 1600 | 1749 | March Blvd | Manslick Rd | Nichols Meadow Cir at school entrance | 71.0419 | 15 | Local | [17 empty] | 80654.25 | [19 empty] | 1224.4896 | 42.4953 | 52035 | 0.84448
| Hall |  |  |  |  | 4442 | 4516 | Rear View Dr | Lance Dr | Dead End | 19 | 15 | Local | [17 empty] | 45416 | [19 empty] | 649 | 20 | 12976 | 0.21059
| Hall |  |  |  |  | 2800 | 3099 | S 5th St | M St | Central Ave | 50.6617 | 15 | Local | [17 empty] | 64504.8 | [19 empty] | 1417.7832 | 29.3529 | 41616 | 0.67539
|  |  | 350002-198 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 |  |  | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1200 | 1499 | Weyler Ave | Arcade Ave | Dead End | 51 | 15 | Local | [17 empty] | 52250.5 | [19 empty] | 1705 | 20 | 33710 | 0.54708
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus. Will be pushed to FY 22
| Hall |  |  |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | [19 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  |  |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | [19 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  |  |  |  | 1920-07-13 | 1921-11-24 | Wolf Pen Branch Rd | Wolf Pen Ln (east of intersection) | Spring Farm Rd | 77.753 | 16 | Sec Coll | [17 empty] | 95670.3 | [19 empty] | 2959.4685 | 19.592 | 57982 | 0.941
| Hall |  | 350002-292 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | [18 empty] | Pushed back to FY 21 due to virus | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-292 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | [18 empty] | Pushed back to FY 21 due to virus | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-292 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | [18 empty] | Pushed back to FY 21 due to virus | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-292 |  |  | 11006 | 11199 | Eagles Cove Dr | Kestrel Ct | Hickory Cove Ct | 61.2884 | 17 | Local | [13 empty] | 5 |  |  |  | 73635.85 | [18 empty] | Pushed back to FY 21 due to virus | 2077.047 | 22.8724 | 47507 | 0.771
| Hall |  | 350002-292 |  |  | 4500 | 4599 | Goshawk Ct | Eagles Cove Dr | Dead End | 66 | 17 | Local | [13 empty] | 2 |  |  |  | 15304.7 | [18 empty] | Pushed back to FY 21 due to virus | 411.4091 | 24 | 9874 | 0.16025
| Hall |  | 350002-292 |  |  | 10700 | 10712 | Hickory Cove Ct | Shenandoah Dr | Eagles Cove Dr | 52 | 17 | Local | [13 empty] | 3 |  |  |  | 26463.15 | [18 empty] | Pushed back to FY 21 due to virus | 656.6535 | 26 | 17073 | 0.27708
| Hall |  |  |  |  | 13600 | 13699 | Sample Ct | Sample Way | Dead End | 67 | 17 | Local | [17 empty] | 11609.5 | [19 empty] | 312.0762 | 24 | 7490 | 0.12156
| Hall |  |  |  |  | 3400 | 3599 | Sample Way | Colonial Springs Rd | Springs Station Rd | 59.8943 | 17 | Local | [17 empty] | 72225.35 | [19 empty] | 2053.5541 | 22.6909 | 46597 | 0.75623
| Hall |  |  |  |  | 13400 | 13499 | Sapling Spring Pl | Dead End | Sample Way | 70 | 17 | Local | [17 empty] | 6300.75 | [19 empty] | 169.381 | 24 | 4065 | 0.065971
| Hall |  |  |  |  | 13500 | 13599 | Squire Springs Ct | Sample Way | Dead End | 66 | 17 | Local | [17 empty] | 15921.6 | [19 empty] | 428.0127 | 24 | 10272 | 0.16671
[8 empty] | Ashbrook Ave | Beechcrest Ave | Brookhaven Ave (concrete panel replacement) |  | 18 | Local | [17 empty] | 15000 |  |  | CIF | 8146-410-8107-148267-822702 | 15000
| Hall |  |  |  |  | 600 | 609 | Dorsey Way | Rymer Way | Elsmere Cir | 87 | 18 | Local | [17 empty] | 19729.95 | [19 empty] | 303 | 42 | 12729 | 0.20658
| Hall |  |  |  |  | 600 | 799 | Elsmere Cir | Dorsey Way | Tamarisk Pkwy | 72.7037 | 18 | Local | [17 empty] | 54589.45 | [19 empty] | 1565.7643 | 22.4932 | 35219 | 0.57157
| Hall |  |  |  |  | 1 | 99 | Hallsdale Dr | Taylorsville Rd | Dead End | 63.1729 | 18 | Local | [17 empty] | 102778.95 |  |  | CIF | [16 empty] | 2762.8307 | 24.0004 | 66309 | 1.0761
[8 empty] | Hobbs Station | Old Hobbs Pl | Lodge Hill |  | 18 | Local | [17 empty] | 35000 |  |  | CIF | 8146-410-8107-148267-822702 | 35000
[8 empty] | Quince Ct | Hobbs Station | Dead End |  | 18 | Local | [17 empty] | 2500 |  |  | CIF | 8146-410-8107-148267-822702 | 2500
[8 empty] | Ridgeview Ave | N Wood Dr | Lynnbrook Dr |  | 18 | Local | [17 empty] | 42400 |  |  | CIF | 8146-410-8107-148267-822702 | 22500
| Hall |  |  |  |  | 600 | 602 | Rymer Way | Winyan Ln | Dorsey Way | 46 | 18 | Local | [17 empty] | 11657.55 | [19 empty] | 341.8596 | 22 | 7521 | 0.12206
| Hall |  |  |  |  | 9900 | 9999 | Spring Ridge Dr | Dead End | Dorsey Way | 49 | 18 | Local | [17 empty] | 30590.8 | [19 empty] | 939.8092 | 21 | 19736 | 0.3203
| Hall |  | 350002-350 |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 61.7099 | 18 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  | 339051-78 |  |  | 1903-07-23 | 1905-06-21 | N English Station Rd | La Grange Rd | Old Henry Rd | 70.6362 | 19 | Pri Coll | [16 empty] | August | 190665.75 | 118409.25 | August | [17 empty] | 4744.6459 | 24.3548 | 115555 | 1.8754
| Hall |  | 350002-351 |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 19 | Pri Coll | [13 empty] | 3 |  |  | August | 34471.7505 | See N Pope Lick | August | [16 empty] | 0.5 in D 20, need to fix up one radius with potential curba nd gutter. 3 ramps at Urton Ln. | 1160.665 | 18 | 20891.97 | 0.33906
| Hall |  |  |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | [19 empty] | 1488.0063 | 89 | 132433 | 2.1493
| LP |  | 350002-286 |  |  |  |  | Hagen Rd | Hersfield Rd | dead end |  | 19 | [18 empty] | 12500 |  |  | CIF - *Temp PW '19 Bond | 8138-410-8107-148919-822702 | 12500 |  | 8137-410-8210-148451-822702 | 12500 | [10 empty] | Pushed back to FY 21 due to virus |  |  | 12493 | 0.20275
| Hall |  |  |  |  | 1100 | 1599 | Heafer Rd | N English Station Rd | La Grange Rd | 41 | 19 | Local | [17 empty] | 99816.9 | [19 empty] | 3136 | 21 | 64398 | 1.0451
| Hall |  | 350002-286 |  |  |  |  | Herfield Rd |  |  |  | 19 | Local | [17 empty] | 15000 |  |  | Council | 8138-410-8107-048101-822702 | 15000 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 12300 | 12499 | Park Field Rd | Heafer Rd | Dead End | 41 | 19 | Local | [17 empty] | CIF | [19 empty] | 711 | 21 | 14643 | 0.23764
| Hall |  | 350002-286 |  |  |  |  | Parkfield Rd |  |  |  | 19 | [18 empty] | 22000 |  |  | Council | 8138-410-8107-048101-822702 | 16000 |  | 8144-410-8107-048101-822702 | 6000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 62 | 19 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  | 339051-72 |  |  | 1927-12-04 | 1932-04-20 | Easum Rd | Billtown Rd | Old Heady Rd | 65.4048 | 20 | Pri Coll | [17 empty] | 378646.95 | 360120.27 | August | [17 empty] | 12312.9475 | 18.6375 | 229483 | 3.7243
| LP |  | 339051-68 |  |  | 9700 | 9299 | Hassy Way | Dry Ridge Rd | Dead End | 84.5338 | 20 | Local | [17 empty] | 189358 | 62203.16 | August | [17 empty] | 1865.9377 | 23.4429 | 43743 | 0.70991
| Hall |  |  |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 20 | Pri Coll | [13 empty] | See N Pope Lick |  |  | August | 34471.7505 | 89728.41 | August | [16 empty] | 0.5 in D 19, see other N Pope Lick | 1160.665 | 18 | 20891.97 | 0.33906
| LP |  | 339051-71 |  |  | 3500 | 4299 | Old Routt Rd | Dead End | Routt Rd | 45.5989 | 20 | Local | [17 empty] | 224937.55 | 120672.59 | August | [17 empty] | 7256.044 | 20 | 145121 | 2.3552
| LP |  | 339051-70 |  |  | 15200 | 15299 | Old Taylorsville Rd (near Eastwood Fisherville intersection) | Dead End | Taylorsville Rd | 12 | 20 | Local | [17 empty] | 24133.5 | 22842.6 | August | [17 empty] | 1112.1651 | 14 | 15570 | 0.25269
| LP |  | 339051-69 |  |  | 14000 | 14199 | Old Taylorsville Rd at Wilderness Trl | Taylorsville Rd | Dead End | 55.6534 | 20 | Local | [17 empty] | 34870.35 | See Wilderness Trl | August | [17 empty] | 1318.8779 | 17.0577 | 22497 | 0.36511
| LP |  | 339051-69 |  |  | 3400 | 3999 | Wilderness Trl | Old Taylorsville Rd | Dead End | 52 | 20 | Local | [17 empty] | 115172.75 | 155661.67 | August | [17 empty] | 4644.0491 | 16 | 74305 | 1.2059
| LP |  | 339051-68 |  |  | 16300 | 16399 | Witch Hazel Dr | Hassy Way | Dead End | 90 | 20 | Local | [17 empty] | 66598 | See Hassy Way | August | [17 empty] | 610 | 24 | 14639 | 0.23758
| LP |  | 339051-62 |  |  | 600 | 6499 | Gellhaus Ln | Chenoweth Run Rd | Billtown Rd | 61.166 | 20 | Sec Coll | [13 empty] | 6 |  |  |  | 181381.398 | 189438.65 | July | [16 empty] | Intersection improvement at Chenoweth Run, possible culverts and Guardrail replacements needed. | 4672.76 | 23.5253 | 109928.12 | 1.784
| LP |  |  |  |  | 11800 | 14499 | Rehl Rd | Blankenbaker Pkwy | S Pope Lick Rd | 60.2949 | 20 | Pri Coll | [13 empty] | 0 |  |  |  | 430623.633 | 351795.21 | July | [16 empty] | Need cores taken, possibly thin asphalt. Possible Fiber project. Check Guardrails. Need to review intersection at Tucker Station Rd | 11862.91 | 22 | 260984.02 | 4.2355
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 3500 | 4299 | S Pope Lick Rd | Old Taylorsville Rd | Dead End | 26 | 20 | Local | [13 empty] | 0 |  |  |  | 183792.8 | [18 empty] | May have been repaved with Parklands project | 6975.0624 | 17 | 118576 | 1.9244
| Hall |  | 350002-279 |  |  | 100 | 199 | E Amherst Ave | S 1st St | Wabash Pl | 48.8533 | 21 | Local | [13 empty] | 0 |  |  |  | 50161.1 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 1274.1882 | 25.3981 | 32362 | 0.52521
| Hall |  | 350002-279 |  |  | 4900 | 4999 | Hollins Rd | St Leo Pl | E Amherst Ave | 60 | 21 | Local | [13 empty] | 5 |  |  | 5 | 14066.25 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 303 | 30 | 9075 | 0.14728
| Hall |  | 350002-279 |  |  | 4800 | 4999 | S 1st St | E Amherst Ave | Dead End to north | 61.3741 | 21 | Local | [13 empty] | 4 |  |  | 4 | 35997.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 822.4664 | 28.237 | 23224 | 0.37691
| Hall |  | 350002-279 |  |  | 100 | 114 | W Amherst Ave | Southside Dr | S 1st St | 59 | 21 | Local | [13 empty] | 4 |  |  |  | 16994.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 422 | 26 | 10964 | 0.17794
| Hall |  |  |  |  | 4400 | 4699 | Allmond Ave | E Woodlawn Ave | Dead End (north) | 54.248 | 21 | Local | [17 empty] | 131756.2 | [19 empty] | 3325.2587 | 25.5631 | 85004 | 1.3795
| Hall |  |  |  |  | 300 | 399 | Chris Dr | Homestead Dr | Dead End | 61 | 21 | Local | [17 empty] | 5054.55 | [19 empty] | 271.7278 | 12 | 3261 | 0.052923
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [19 empty] | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-279 |  |  | 100 | 199 | E Tenny Ave | S 1st St | St Leo Pl | 42 | 21 | Local | [13 empty] | 3 |  |  |  | 28551 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 658 | 28 | 18420 | 0.29894
| Hall |  |  |  |  | 200 | 299 | E Woodlawn Ave | Allmond Ave | Nevada Ave | 68 | 21 | Min Art | [17 empty] | 127152.3 | [19 empty] | 1926.5536 | 39.9999 | 77062 | 1.2506
| Hall |  |  |  |  | 5000 | 5199 | Emery Ave | Lyman Ave | W Kenwood Dr | 54 | 21 | Local | [17 empty] | 24539.6 | [19 empty] | 754 | 21 | 15832 | 0.25694
| Hall |  |  |  |  | 5000 | 5199 | Fay Ave | W Kenwood Dr | Alger Ave | 48.6736 | 21 | Local | [17 empty] | 42524.25 | [19 empty] | 1287.734 | 21.3049 | 27435 | 0.44525
| Hall |  |  |  |  | 5900 | 6199 | Gloria Ln | Catheen Way | Dead End | 43.0059 | 21 | Local | [17 empty] | 47087.45 | [19 empty] | 1318.1272 | 23.0471 | 30379 | 0.49302
| Hall |  |  |  |  | 300 | 399 | Hatcher Ave | Southside Dr | Homestead Dr | 39 | 21 | Local | [17 empty] | 15921.6 | [19 empty] | 641.9717 | 16 | 10272 | 0.16671
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
| Hall |  |  |  |  | 300 | 399 | Hillview Dr | Southside Dr | Homestead Dr | 23 | 21 | Local | [17 empty] | 20945.15 | [19 empty] | 750.738 | 18 | 13513 | 0.2193
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  |  |  |  | 6800 | 7099 | Homestead Dr | E Kenwood Dr | Dead End | 44.1624 | 21 | Local | [17 empty] | 37426.3 | [19 empty] | 1442.2483 | 16.7419 | 24146 | 0.39187
| Hall |  |  |  |  | 4800 | 5999 | Hood Rd | W Indian Trl | Catheen Way | 14 | 21 | Local | [17 empty] | 30860.5 | [19 empty] | 996 | 20 | 19910 | 0.32312
| Hall |  |  |  |  | 6100 | 6199 | Loretta St | Elam Ct | Whitlock St | 78.4686 | 21 | Local | [17 empty] | 39190.2 | [19 empty] | 1053.4975 | 24.0001 | 25284 | 0.41034
| Hall |  |  |  |  | 500 | 599 | Lyman Ave | Laughlin Ave | Fay Ave | 53 | 21 | Local | [17 empty] | 10696.55 | [19 empty] | 314 | 22 | 6901 | 0.112
| Hall |  |  |  |  | 700 | 799 | Lyman Ave | Reed Ave | Emery Ave | 54 | 21 | Local | [17 empty] | 9114 | [19 empty] | 294 | 20 | 5880 | 0.095427
| Hall |  |  |  |  | 300 | 399 | Meadowood Ct | Southside Dr | Dead End | 29 | 21 | Local | [17 empty] | 7184.25 | [19 empty] | 579.3129 | 8 | 4635 | 0.075222
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 5900 | 6199 | Orville Dr | Gloria Ln | Dead End | 41.6904 | 21 | Local | [17 empty] | 44374.95 | [19 empty] | 1192.8763 | 24 | 28629 | 0.46462
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [19 empty] | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 5000 | 5199 | Reed Ave | W Kenwood Dr | Dead End | 65.1753 | 21 | Local | [17 empty] | 30215.7 | [19 empty] | 935.098 | 20.847 | 19494 | 0.31637
| Hall |  |  |  |  | 2825 | 2899 | Smilax Ave | Loretta St | W Indian Trl | 78 | 21 | Local | [17 empty] | 12877.4 | [19 empty] | 346 | 24 | 8308 | 0.13483
| Hall |  |  |  |  | 900 | 1199 | W Indian Trl | Preston Hwy | Dead End | 52.6638 | 21 | Local | [17 empty] | 116784.75 | [19 empty] | 3947.8218 | 19.0852 | 75345 | 1.2228
| Hall |  | 350002-279 |  |  | 200 | 5799 | W Southland Blvd | Southside Dr | Southern Pkwy | 54.9398 | 21 | Pri Coll | [13 empty] | 15 |  |  | 15 | 256091.9955 | 269998.86 | [17 empty] | 2 speed humps on roadway, need to check ramps at southland Ter. | 5145.34 | 30.1646 | 155207.27 | 2.5189
| Hall |  | 350002-279 |  |  | 100 | 199 | W Tenny Ave | S 1st St | Southside Dr | 35 | 21 | Local | [13 empty] | 8 |  |  |  | 19027.8 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 409 | 30 | 12276 | 0.19923
| Hall |  |  |  |  | 2800 | 2899 | Whitlock St | Norton Ave | Loretta St | 85 | 21 | Local | [17 empty] | 29848.35 | [19 empty] | 837 | 23 | 19257 | 0.31252
| Hall |  |  |  |  | 5400 | 5499 | Winding Rd | Woodmore Ave | Dead End | 47 | 21 | Local | [17 empty] | 46949.5 | [19 empty] | 1121.8398 | 27 | 30290 | 0.49158
| LP |  |  |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [19 empty] | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 1924-08-21 | 1925-03-08 | Fern Creek Rd | Beulah Church Rd | Bardstown Rd | 64.6738 | 22 | Pri Coll | [17 empty] | 139346.2469 | [19 empty] | 4021.5367 | 21 | 84452.2709 | 1.3706
| Hall |  | 350002-346 |  |  | 8600 | 8609 | Glenhope Dr | Black Iron Rd | break south of Stonebreaker Rd | 56.1215 | 22 | Local | [17 empty] | 25878.8 | [19 empty] | 695.6754 | 23.9997 | 16696 | 0.27096
| Hall |  | 350002-346 |  |  | 10500 | 10699 | Stonebreaker Rd | Dead End | Dead End | 49.7486 | 22 | Local | [17 empty] | 76402.6 | [19 empty] | 2155.5713 | 22.8673 | 49292 | 0.79997
| Hall |  | 350002-304 |  |  | 8400 | 9399 | Pennsylvania Run Rd | Vaughn Mill Rd | Cooper Chapel Rd | 60.244 | 23 | Pri Coll | [13 empty] | 0 |  |  |  | 221604.4215 | See Vaughn Mill | August | [16 empty] | Need to replace 1 culvet for sure, but review others. Update guardrails as necessary. Will avoid sidewalk ramps if possible | 6395.51 | 21 | 134305.71 | 2.1797
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Outer Loop | Pennsylvania Run Rd | 65 | 23 | Pri Coll | [17 empty] | 145558 | 326973.75 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Fegenbush Ln | Outer Loop | 65 | 23 | Pri Coll | [17 empty] | 86290 | See Vaughn Mill Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 8300 | 8499 | Berea Dr | Damascus Ct | Sardis Way | 44 | 23 | Local | [17 empty] | 46244 | [19 empty] | 1005 | 23 | 23122 | 0.37525
| Hall |  |  |  |  | 6200 | 6399 | Hackberry Way | Maple Rd | Lancewood Rd | 44 | 23 | Local | [17 empty] | 53769.5 | [19 empty] | 1576.8029 | 22 | 34690 | 0.56299
| Hall |  |  |  |  | 9600 | 9899 | Lancewood Rd | Dead End | Price Lane Rd | 46.4626 | 23 | Local | [17 empty] | 50145.6 | [19 empty] | 1516.9546 | 21.3269 | 32352 | 0.52504
| Hall |  |  |  |  | 9500 | 9599 | Yellow Pine Ct | Dead End | Yellow Pine Dr | 48 | 23 | Local | [17 empty] | 18097.8 | [19 empty] | 486.509 | 24 | 11676 | 0.18949
| Hall |  | 350002-349 |  |  | 3800 | 3899 | Britt Ln | Dead End | Rust Oak Ln | 39.4136 | 24 | Local | [13 empty] | 5 |  |  |  | 47330.8 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1297.2258 | 23.5395 | 30536 | 0.49557
| Hall |  | 350002-349 |  |  | 8100 | 8199 | Carnes Dr | Dead End | Tuesday Way | 38 | 24 | Local | [13 empty] | 3 |  |  |  | 11198.75 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 301.058 | 24 | 7225 | 0.11726
| Hall |  | 350002-349 |  |  | 8000 | 8299 | Horizon Ln | Dead End | Foreman Ln | 48.5169 | 24 | Local | [13 empty] | 2 |  |  |  | 39569.95 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1088.3103 | 23.4575 | 25529 | 0.41431
| Hall |  | 350002-217 |  |  |  |  | Monaco Dr | Woodhill Ln | Morningside Way | 48 | 24 | Local | [16 empty] | 3 | 43368 | 129859.74 | July | Council | 8125-410-8107-148385-822702 | 103880.92 |  | 8137-410-8210-148385-822702 | 6320.87 |  | 8101-410-8210-148385-822702 | 61863.6 | [7 empty] | Pushed back to FY 21 due to virus |  |  | 28912 | 0.46922
| Hall |  | 350002-217 |  |  |  |  | Morningside Way | Monaco Dr | Dead End | 20 | 24 | Local | [17 empty] | 27317 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 18211 | 0.29555
| Hall |  | 350002-217 |  |  |  |  | Oaklawn Dr | Preston Hwy | Dead End | 48 | 24 | Local | [17 empty] | 100551 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 67034 | 1.0879
|  |  | 350002-238 |  |  |  |  | Prestonview Ln | Foreman Ln | dead end | 31 | 24 | Local | [13 empty] | 0 |  |  |  | 17791.74 | 52304.37 | July | Council | 8133-410-8107-148385-822702 | 17791.74 | [13 empty] | Pushed back to FY 21 due to virus
|  |  | 350002-238 |  |  |  |  | Trio Ave | Preston Hwy | Prestonview Ln | 33 | 24 | Local | [13 empty] | 0 |  |  |  | $17,791,75 | See Prestonview | July | Council | 8133-410-8210-148385-822702 | 17791.75 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  | 350002-349 |  |  | 3700 | 3999 | Tuesday Way | Woodbury Dr | Dead End | 42.0113 | 24 | Local | [13 empty] | 7 |  |  |  | 90795.9 | 205531.3 | July | [16 empty] | Pushed back to FY 21 due to virus | 2255.064 | 25.9762 | 58578 | 0.95067
| Hall |  | 350002-349 |  |  | 3700 | 3799 | Wednesday Way | Dead End | Horizon Ln | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 20393.35 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 548.2191 | 24 | 13157 | 0.21353
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 6000 | 6199 | Ledgerock Cove Pl | Dead End | Dead End | 80.4892 | 24 | Local | [17 empty] | 30097.9 | [19 empty] | 970.9416 | 24 | 19418 | 0.31514
| Hall |  |  |  |  | 6900 | 7099 | Ledgerock Rd | Ledgerock Cove Pl | Moorhaven Dr | 47.5203 | 24 | Local | [17 empty] | 40166.7 | [19 empty] | 1079.7727 | 23.9995 | 25914 | 0.42056
| LP |  |  |  |  | 1901-11-30 | 1903-10-30 | McCawley Rd | Preston Hwy | Jefferson Blvd | 66.4236 | 24 | Pri Coll | [17 empty] | 195165.3 | [19 empty] | 4479.469 | 26.4054 | 118282 | 1.9196
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Dannyboy Ln | Ida Way | Dead End | 51 | 25 | Local | [17 empty] | 18463.6 |  | September | [17 empty] | 541.4771 | 22 | 11912 | 0.19332
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Hickory Hill Rd | Park Rd | Southview Rd | 52 | 25 | Local | [17 empty] | 24924 |  | September | [17 empty] | 730.9304 | 22 | 16080 | 0.26096
| Hall |  | 350002-352 |  |  | 900 | 999 | Ida Way | Sunnybrook Dr | Dannyboy Ln | 55 | 25 | Local | [17 empty] | 10510.55 |  | September | [17 empty] | 308.2079 | 22 | 6781 | 0.11005
| Hall |  | 350002-352 |  |  | 5300 | 5399 | Southdale Rd | Palatka Rd | Southview Rd | 68.1387 | 25 | Local | [17 empty] | 63858.45 |  | September | [17 empty] | 1872.6681 | 22.0002 | 41199 | 0.66862
| Hall |  | 350002-352 |  |  | 918 | 900 | Southview Rd | Southdale Rd | Palatka Rd | 56.0019 | 25 | Local | [17 empty] | 49846.45 |  | September | [17 empty] | 1339.9785 | 23.9996 | 32159 | 0.52191
| LP |  | 339051-73 |  |  | 9000 | 9302 | Stonestreet Rd | Dixie Hwy | Valley College Dr | 65.9195 | 25 | Min Art | [17 empty] | 296780.55 |  | September | [17 empty] | 3575.0904 | 50.3112 | 179867 | 2.9191
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Sunnybrook Dr | Palatka Rd | Dead End | 55.7993 | 25 | Local | [17 empty] | 33266.1 |  | September | [17 empty] | 894.2654 | 23.9996 | 21462 | 0.34831
| Hall |  | 350002-352 |  |  | 900 | 999 | Westview Dr | New Cut Rd | Dead End | 51 | 25 | Local | [17 empty] | 35299.7 |  | September | [17 empty] | 1084.4551 | 21 | 22774 | 0.3696
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65.4587 | 25 | Sec Coll | [17 empty] | 272001.708 | [19 empty] | 6879.848 | 23.9612 | 164849.52 | 2.6754
| LP |  | 339051-64 |  |  | 8300 | 8499 | McNair Rd | Manslick Rd | 3rd Street Rd | 62.7373 | 25 | Pri Coll | [13 empty] | 0 |  |  |  | 40944.123 | [18 empty] | Proposed Development may repave McNair. Various base failures, edge of road reconstruction needed. Some sort of shoulder will also be needed. May need to replace driveway on Wisertown Rd with this project, so prioritize for Summer 2019. | 1378.59 | 18 | 24814.62 | 0.40272
| Hall |  | 350002-257 |  |  | 2700 | 3899 | Klondike Ln | Six Mile Ln | Hikes Ln | 61.6177 | 26 | Pri Coll | [13 empty] | 25 |  |  | 12 | 221552.1 | 322580.56 | July | [16 empty] | Look at cross drain near Six Mile Ln, others which may be present. Probable fiber project. | 6394 | 21 | 134274 | 2.1792
| Hall |  | 350002-368 |  |  | 2900 | 3099 | Bowman Ave | Dutchmans Ln | Dead End | 50.8815 | 26 | Local | [17 empty] | 42772.25 |  | October | [17 empty] | 1404.5798 | 19.6464 | 27595 | 0.44784
| Hall |  | 350002-368 |  |  | 2900 | 2999 | Cannons Ln | Dutchmans Ln | Bowman Ave | 35.207 | 26 | Local | [17 empty] | 32943.7 |  | October | [17 empty] | 929.1685 | 22.8742 | 21254 | 0.34493
| Hall |  | 350002-368 |  |  | 3500 | 3599 | Ephraim Mcdowell Dr | Cannons Ln | Abigail Dr | 48.9726 | 26 | Local | [17 empty] | 36181.65 |  | October | [17 empty] | 1003.653 | 23.258 | 23343 | 0.37884
| Hall |  | 350002-319 |  |  |  |  | Bashford Manor Ln | Bardstown Rd | Medford Ln |  | 26 | Local | [17 empty] | 42000 |  | September | Council | 8138-410-8107-148387-822702 | 42000 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 3000 | 3014 | Boaires Ln | Talisman Rd | Rio Rita Ave | 47 | 26 | Local | [17 empty] | 17921.1 | [19 empty] | 481.737 | 24 | 11562 | 0.18764
| Hall |  |  |  |  | 6012 | 6399 | Dutchmans Ln | Dutchmans Pky | Dutchmans Pky | 46 | 26 | Local | [17 empty] | 142852.65 | [19 empty] | 2973 | 31 | 92163 | 1.4957
| Hall |  |  |  |  | 1908-03-18 | 1909-04-21 | Furman Blvd | Taylorsville Rd | Hikes Ln | 63.8043 | 26 | Pri Coll | [17 empty] | 269468.892 | [19 empty] | 3983.28 | 41 | 163314.48 | 2.6505
| NA |  |  | 2018-07-01 |  | 3000 | 3499 | Hikes Ln | Klondike Ln | Browns Ln | 57.2165 | 26 | Min Art | [13 empty] | 22 |  |  |  | 603010.8 |  |  | PW Funds |  | 603010.8 | [13 empty] | Will try to group with KYTC and bid seperately, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 5316.81 | 60 | 301505.4 | 4.8932
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Klondike Ln | Goldsmith Ln |  | 26 | Min Art | [13 empty] | 20 |  |  |  | 510705 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3483.5026 | 62 | 215977.1635 | 3.5051
| Hall |  |  |  |  | 3000 | 3199 | Talisman Rd | Kings Hwy | Boaires Ln | 47.314 | 26 | Local | [17 empty] | 139885.95 | [19 empty] | 3610.2177 | 24.9982 | 90249 | 1.4647
| Hall | [6 empty] | Mcdeane Base Failure
| QK4 |  | 314578-70 |  |  |  |  | QK4 Density Testing | [22 empty] | 20000 | 33186.51 |  | PW Funds | 8672-410-8210-148929-822703 | 20000 | [17 empty] | 0
| QK4 |  | 314578-78 |  |  |  |  | QK4 supplemental Inspections | [22 empty] | 20000 | 51389 |  | PW Funds | 8672-410-8210-148929-822704 | 20000 | [17 empty] | 0
| QK4 |  | 314578-119 |  |  |  |  | St Anthony Slide | [23 empty] | 3575.74 | [21 empty] | 0

## Oct 20
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-255 |  |  | 3400 | 3799 | W Magnolia Ave | Louis Coleman Jr Dr | Gibson Ln | 35 | 1 | Local | [13 empty] | 3 |  |  | 3 | 125495.75 | 99645.81 | July | [16 empty] | Seems to be many Semi Tractor Trailors. May use Fiber | 2381.3351 | 34 | 80965 | 1.314
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hwy | W Hill St | 67 | 1 | Min Art | [17 empty] | 293670 | 242320.52 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 3700 | 4199 | Grand Ave | Dead End east of 38th | Cecil Ave | 50.0041 | 1 | Local | [17 empty] | 72590.5765 | [19 empty] | 1711.95 | 27.3563 | 46832.63 | 0.76005
| Hall |  |  |  |  | 2600 | 2999 | Grand Ave | S 26th St | Dead End to west | 61.1995 | 1 | Local | [17 empty] | 64222.824 | [19 empty] | 1255.22 | 33.0094 | 41434.08 | 0.67244
| Hall |  |  |  |  | 3000 | 3699 | Grand Ave | Dead End east of 32nd | Dead End west of Canopy Ct | 64.4573 | 1 | Local | [17 empty] | 131092.8 | [19 empty] | 2917.54 | 32.8616 | 84576 | 1.3726
| Hall |  |  |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | [19 empty] | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  |  |  |  | 3200 | 3699 | Hale Ave | S 32nd St | Dead End to west | 48.0322 | 1 | Local | [17 empty] | 103495.05 | [19 empty] | 2281.7 | 29.2637 | 66771 | 1.0836
| Hall |  |  |  |  | 1904-12-04 | 1919-12-25 | Lower Hunters Trce | Dixie Hwy | Greenbelt Hwy | 65.8978 | 1 | Pri Coll | [17 empty] | 50887.65 | [19 empty] | 1117 | 27.6106 | 30841 | 0.50052
| Hall |  |  |  |  | 6616 | 7299 | Lower Hunters Trce | Greenbelt Hwy | Cane Run Rd | 64.1728 | 1 | Pri Coll | [17 empty] | 116082.681 | [19 empty] | 2705.89 | 26 | 70353.14 | 1.1418
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 3600 | 3699 | Friar Tuck Ct | Robinhood Ln | Dead End | 41 | 2 | Local | [17 empty] | 13852.35 | [19 empty] | 406 | 22 | 8937 | 0.14504
| Hall |  |  |  |  | 5100 | 5199 | Jefferson Blvd | Poplar Level Rd | Fern Valley Rd | 58.4628 | 2 | Min Art | [17 empty] | 117874.35 | [19 empty] | 1152.2379 | 62.0002 | 71439 | 1.1594
| Hall |  |  |  |  | 3600 | 3699 | Little John Ct | Robinhood Ln | Dead End | 54 | 2 | Local | [17 empty] | 9605.35 | [19 empty] | 258 | 24 | 6197 | 0.10057
| Hall |  |  |  |  | 4600 | 4699 | Oaklawn Ln | Rangeland Rd | Oakdale Ln | 40 | 2 | Local | [17 empty] | 45000 | [19 empty] | 1142 | 22 | 25124 | 0.40774
| Hall |  |  |  |  | 1200 | 1399 | Old Fern Valley Rd | Preston Hwy | Fern Valley Rd | 53 | 2 | Local | [17 empty] | 110589.4 | [19 empty] | 3398 | 21 | 71348 | 1.1579
| Hall |  |  |  |  | 5800 | 6099 | Robinhood Ln | Friar Tuck Ct | Forest Dr | 32.905 | 2 | Local | [17 empty] | 52659.7 | [19 empty] | 1475.2816 | 23.0288 | 33974 | 0.55137
| Hall |  |  |  |  | 4000 | 4099 | Tower Rd | Preston Hwy | Dead End | 46 | 2 | Local | [17 empty] | 96856.4 | [19 empty] | 2604 | 24 | 62488 | 1.0141
| Hall |  | 350002-334 |  |  | 1600 | 2699 | Dixdale Ave | Wingfield Ave | S 28th St | 55.9513 | 3 | Local | [17 empty] | 170479.85 | 527564.94 | August | [17 empty] | 5770.7465 | 19.0594 | 109987 | 1.785
| Hall |  | 350002-334 |  |  |  |  | Dixie Hwy | W Burnett Ave | Bernheim Ln | 66 | 3 | Min Art | [17 empty] | 254141 | See Dixdale | August | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-334 |  |  | 1600 | 1799 | W Lee St | S 15th St | Dixie Hwy | 47.1551 | 3 | Local | [17 empty] | 107680.05 | See Dixdale | August | [17 empty] | 2701.6913 | 25.7139 | 69471 | 1.1275
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-247 |  |  | 400 | 999 | E Witherspoon St | N Preston St | River Rd | 59.6256 | 4 | Min Art | [13 empty] | 8 |  |  |  | 326255.457 | See N 1st St | July | [16 empty] | Portion of this may have been paved with bridges project. | 3413.14 | 57.9322 | 197730.58 | 3.209
| Hall |  | 350002-247 |  |  |  |  | N 1st St | W Main St | E Witherspoon St |  | 4 | [17 empty] | 4 | 150000 | 383501.48 | July
| Hall |  | 350002-338 |  |  | 100 | 1299 | E Breckinridge St | S 1st St | Barret Ave | 60.4014 | 4 | Pri Coll | [17 empty] | 402154.632 | 290310.74 | October | [17 empty] | 6770.28 | 36 | 243730.08 | 3.9555
| Hall |  | 350002-339 |  |  | 700 | 799 | Henry Fripo St | S Clay St | S Shelby St | 18 | 4 | Local | [17 empty] | 22452.8 | See Lampton | October | [17 empty] | 585 | 24 | 14033 | 0.22774
| Hall |  | 350002-339 |  |  | 400 | 999 | Lampton St | S Preston St | Dead End | 36.2169 | 4 | Local | [17 empty] | 149189.05 | 94574.72 | October | [17 empty] | 3187.4777 | 30.1966 | 96251 | 1.5621
| Hall |  |  |  |  | 500 | 799 | Bergman St | Dead End | S Shelby St | 20 | 4 | Local | [17 empty] | 59203.8 | [19 empty] | 1317 | 29 | 38196 | 0.61989
| Hall |  |  |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | [19 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  |  |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | [19 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  |  |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | [19 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | [19 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  |  |  |  | 150 | 399 | E Witherspoon St | Bingham Way | N Preston St | 62.9283 | 4 | Min Art | [17 empty] | 95488.8 | [19 empty] | 1425.1269 | 40.6083 | 57872 | 0.93921
| Hall |  |  |  |  | 500 | 799 | Meriwether Ave | E Burnett Ave | S Shelby St | 62.3338 | 4 | Pri Coll | [17 empty] | 110292.435 | [19 empty] | 2228.13 | 30 | 66843.9 | 1.0848
| Hall |  | 350002-340 |  |  | 300 | 1499 | S 15th St | W Jefferson St | W Hill St | 53.5853 | 4 | Min Art | [17 empty] | 687630.9 | [19 empty] | 10228.8508 | 40.7422 | 416746 | 6.7634
| Hall |  |  |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | [19 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 1400 | 1454 | S Preston St | S Jackson St | E Burnett Ave | 54.0007 | 4 | Min Art | [17 empty] | 33037.95 | [19 empty] | 564.7347 | 35.4556 | 20023 | 0.32496
| Hall |  |  |  |  | 300 | 599 | S Wenzel St | E Chestnut St | E Jefferson St | 25.8121 | 4 | Local | [17 empty] | 74648 | [19 empty] | 1387.7936 | 34.7026 | 48160 | 0.78159
| Hall |  |  |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | [19 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  |  |  |  | 850 | 1499 | W Muhammad Ali Blvd | Roy Wilkins Ave | S 15th St | 56.2923 | 4 | Min Art | [17 empty] | 185212.5 | [19 empty] | 2927.305 | 38.3459 | 112250 | 1.8217
| Hall | [6 empty] | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 |  |  | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14
| Hall |  | 350002-356 |  |  | 100 | 299 | N & S 46th St | N Longworth Ave | W Market St | 20.6662 | 5 | Local | [13 empty] | 6 |  |  | 6 | 71380.6 | 48092.31 | July | [16 empty] | May have been paved into gutter from Longworth to Duncan | 1555.8172 | 29.5999 | 46052 | 0.74738
| Hall |  | 350002-363 |  |  | 1900-12-15 | 1904-05-17 | Southwestern Pky | S Shawnee Ter | Gibson Ln | 59.2734 | 5 | Min Art | [17 empty] | 598921.95 | 117751.86 | September | [16 empty] | Section from Broadway to Dumesnil was repaved, rest will be completed with KYTC project and other portion of Southwestern. | 10181.6927 | 35.6506 | 362983 | 5.8909
| Hall |  |  |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [19 empty] | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 600 | 699 | Hardin St | Bank St | Gilligan St | 2 | 5 | Local | [17 empty] | 19381.2 | [19 empty] | 247 | 25 | 6252 | 0.10146
| Hall |  |  |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | [19 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  |  |  |  | 700 | 899 | N 33rd St | Northwestern Pky | Dead End | 54.0197 | 5 | Local | [17 empty] | 56883.45 | [19 empty] | 531.8259 | 69.0057 | 36699 | 0.59559
| Hall |  |  |  |  | 700 | 899 | N 34th St | Northwestern Pky | Dead End | 57.1053 | 5 | Local | [17 empty] | 41126.15 | [19 empty] | 514.4215 | 51.5783 | 26533 | 0.43061
| Hall |  |  |  |  | 700 | 799 | N 36th St | Northwestern Pky | Rudd Ave | 44 | 5 | Local | [17 empty] | 21298.55 | [19 empty] | 529 | 26 | 13741 | 0.223
| Hall |  | 350002-312 |  |  | 3200 | 3299 | Rudd Ave | Dead End (east) | N 34th St | 44.7342 | 5 | Local | [13 empty] | 12 |  |  |  | 87872.6 | 32983.13 | [17 empty] | Brick paver sidewalk NW of 34th, Possible LSR project. | 959.6305 | 59.0769 | 56692 | 0.92006
| Hall |  |  |  |  | 3400 | 3899 | Rudd Ave | N 34th St | Dead End (west) | 56.5344 | 5 | Local | [17 empty] | 107745.15 | [19 empty] | 1259.0092 | 55.2125 | 69513 | 1.1281
| Hall |  |  |  |  | 200 | 399 | Shawnee Dr | W Market St | Southwestern Pky | 20.4991 | 5 | Local | [17 empty] | 86138.15 | [19 empty] | 1543.6989 | 35.9999 | 55573 | 0.9019
| Hall |  |  |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | [19 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  |  |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | [19 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  |  |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | [19 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-362 |  |  | 2400 | 2899 | S Floyd St | Old Eastern Pky | Central Ave | 60.0965 | 6 | Pri Coll | [17 empty] | 29653.8 | See S Floyd | August | [17 empty] | 412 | 43.6214 | 17972 | 0.29167
| Hall |  | 350002-208 |  |  | 800 | 1155 | Dixie Hwy | Maple St | Hale Ave | 59.8113 | 6 | Min Art | [13 empty] | Ramps Complete |  |  |  | 202327.257 | 128033.77 | July | [17 empty] | 3226.91 | 38 | 122622.58 | 1.9901
| Hall |  | 350002-301 |  |  |  |  | Dumesnil St | Dixie Hwy | S 26th St | 59 | 6 | Min Art | [17 empty] | 125991 | 96296.13 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-299 |  |  |  |  | Wilson Ave | Dixie Hey | Catalpa St | 66 | 6 | Min Art | [17 empty] | 137347 | See Wilson Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 1901-05-19 | 1901-08-21 | Colorado Ave | Dead End | Algonquin Pky | 61.8146 | 6 | Maj Art | [17 empty] | 119260.35 | [19 empty] | 2131.5568 | 33.909 | 72279 | 1.173
| Hall |  |  |  |  | 900 | 1499 | W Kentucky St | S 9th St | S 15th St | 52.5746 | 6 | Pri Coll | [17 empty] | 177564.75 | [19 empty] | 2808.5642 | 38.3167 | 107615 | 1.7465
| Hall |  |  |  |  | 1000 | 2399 | W Ormsby Ave | Dead End | S 25th St | 44.9819 | 6 | Local | [17 empty] | 310365.8 | [19 empty] | 7886.4736 | 25.3898 | 200236 | 3.2497
| Hall |  |  |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | [19 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-308 |  |  |  |  | Lime Kiln Ln | US 42 | Brownsboro Rd | 65 | 7 | Pri Coll | [17 empty] | 120650 | 3734.75 | [17 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | [19 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-262 |  |  | 2400 | 2699 | Ransdell Ave | Grinstead Dr | Bassett Ave | 47.2922 | 8 | Local | [13 empty] | 6 |  |  | 7 | 94001.3 | 59692.96 | August | [16 empty] | Ray Ave may have been paved which updated ramps at this intersection | 2021.5198 | 30.0002 | 60646 | 0.98423
| Hall |  | 350002-357 |  |  |  |  | Alta Vista Rd | Beargrass Ave | I-64 overpass | 58 | 8 | Local | [17 empty] | 153131 | 241570.1 | July | [17 empty] | 4340 | 23 | 98794 | 1.6033
| Hall |  | 350002-358 |  |  | 1 | 99 | Beverly Rd | Cross Rd | Dead End | 26 | 8 | Local | [17 empty] | 9203.9 | See Cross Rd | September | [17 empty] | 330 | 18 | 5938 | 0.096369
| Hall |  | 350002-358 |  |  | 1 | 1449 | Cross Rd | Castlewood Ave | Eastern Pkwy | 58.4177 | 8 | Local | [17 empty] | 34146.5 | 31446.13 | September | [17 empty] | 1223.9072 | 17.9997 | 22030 | 0.35753
| Hall |  | 350002-344 |  |  | 2530 | 2599 | Woodbourne Ave | Valletta Ln | Cherosen Rd | 33.6999 | 8 | Local | [13 empty] | 0 |  |  |  | 54761.5 |  | September | [16 empty] | Watch for asphalt and decorative curbs | 1662.1826 | 21.2552 | 35330 | 0.57338
| Hall |  | 350002-344 |  |  | 2300 | 2699 | Brookside Dr | Ingleside Dr | Dead End | 62 | 8 | Local | [13 empty] | 0 |  |  |  | 62048 | [18 empty] | Concrete. Circle of cul-de-sac may have been paved previously. | 646.3277 | 24 | 15512 | 0.25175
| Hall |  | 350002-343 |  |  | 2200 | 2549 | Hawthorne Ave | Bon Air Ave | Bardstown Rd | 43.7621 | 8 | Local | [17 empty] | 88168.65 | 4420.53 | [18 empty] | 3037.4844 | 18.727 | 56883 | 0.92316
| Hall |  | 350002-344 |  |  | 2300 | 2399 | Ingleside Dr | Woodbourne Ave | Dead End | 46.0948 | 8 | Local | [13 empty] | 0 |  |  |  | 53432.5 | [18 empty] | Concrete from Brookside to dead end. Watch for asphalt and decorative curb in asphalt section. | 911.9486 | 21.306 | 19430 | 0.31533
| Hall |  | 350002-345 |  |  | 2860 | 2899 | Lowell Ave | Tyler Ln | Hawthorne Ave | 37 | 8 | Local | [17 empty] | 11778.45 | [19 empty] | 422.1865 | 18 | 7599 | 0.12333
| Hall |  |  |  |  | 1630 | 1799 | Ruth Ave | Strand Ave | Radnor Ave | 58.6718 | 8 | Local | [17 empty] | 15067.55 | [19 empty] | 486.0341 | 20.0007 | 9721 | 0.15776
| Hall |  | 350002-342 |  |  | 1617 | 1999 | Speed Ave | Fernwood Ave | Bardstown Rd | 23 | 8 | Local | [17 empty] | 72978.5 | [19 empty] | 1158 | 18 | 20851 | 0.33839
| Hall |  | 350002-342 |  |  | 1905-06-22 | 1906-03-13 | Speed Ave | Bardstown Rd | Spring Dr | 64.8405 | 8 | Pri Coll | [17 empty] | 68566.905 | [19 empty] | 1385.19 | 30 | 41555.7 | 0.67441
| Hall |  | 350002-357 |  |  | 2800 | 2899 | Alta Vista Pl | Alta Vista Ct | Dead End | 4 | 9 | Local | [13 empty] | 0 |  |  |  | 24260 | See Alta Vista | July | [16 empty] | Concrete, then transitions to Asphalt. | 379 | 16 | 6065 | 0.09843
| Hall |  | 350002-357 |  |  | 2800 | 2899 | Alta Vista Way | Alta Vista Rd | Dead End | 36 | 9 | Local | [13 empty] | 0 |  |  |  | 14496 | See Alta Vista | July | [16 empty] | Asphalt | 226 | 16 | 3624 | 0.058814
| Hall |  | 350002-376 |  |  | 200 | 399 | Coralberry Rd | Dead End | Dead End | 55.9856 | 9 | Local | [17 empty] | 54516.6 | [19 empty] | 1506.6618 | 23.3443 | 35172 | 0.57081
| Hall |  | 350002-376 |  |  | 200 | 299 | Mockingbird Gardens Dr | Dead End | Winterleaf Dr | 42.5777 | 9 | Local | [17 empty] | 57269.4 | [19 empty] | 1830.1722 | 20.1883 | 36948 | 0.59963
| Hall |  | 350002-353 |  |  | 100 | 299 | N Bayly Ave | Frankfort Ave | Hollywood Ter | 22.525 | 9 | Local | [13 empty] | 11 |  |  |  | 61958.15 | [18 empty] | Several ramps are stairs. Likely technically infeasible. | 1375.1377 | 29.0684 | 39973 | 0.64873
| Hall |  | 350002-353 |  |  | 200 | 299 | N Clifton Ave | Sycamore Ave | Brownsboro Rd | 46.5993 | 9 | Local | [13 empty] | 6 |  |  |  | 53104.55 | [18 empty] | Pave entire triangle area at Sycamore, one set of stairs at sycamore which is likely infeasible | 1285.4381 | 26.6532 | 34261 | 0.55603
| Hall |  | 350002-353 |  |  | 100 | 199 | N Jane St | Frankfort Ave | Brownboro Rd | 47.6659 | 9 | Local | [13 empty] | 8 |  |  |  | 56206.1 | [18 empty] | Need to confirm ADA ramps before RR tracks | 1893.1414 | 19.1544 | 36262 | 0.5885
| Hall |  | 350002-376 |  |  | 200 | 399 | Pepperbush Rd | Dead End | Dead End | 55.3127 | 9 | Local | [17 empty] | 100709.7 | [19 empty] | 1046.8959 | 62.0635 | 64974 | 1.0545
| Hall |  | 350002-376 |  |  | 3500 | 3599 | Waterleaf Ct | Waterleaf Way | Dead End | 44 | 9 | Local | [17 empty] | 23628.2 | [19 empty] | 693 | 22 | 15244 | 0.2474
| Hall |  | 350002-376 |  |  | 200 | 299 | Waterleaf Way | Dead End | Mockingbird Gardens dr | 46.4515 | 9 | Local | [17 empty] | 28020.9 | [19 empty] | 821.7223 | 22.0001 | 18078 | 0.29339
| Hall |  | 350002-376 |  |  | 3500 | 3599 | Winterberry Cir | Mockingbird Gardens Dr | Mockingbird Gardens Dr | 30 | 9 | Local | [17 empty] | 46517.05 | [19 empty] | 1429 | 21 | 30011 | 0.48705
| Hall |  | 350002-348 |  |  | 1100 | 1299 | Boyle St | Charles St | Goss Ave | 44.0005 | 10 | Local | [13 empty] | 6 |  |  |  | 36327.35 | See Texas | August | [16 empty] | LWC work was done in area | 781.2483 | 29.9994 | 23437 | 0.38036
| Hall |  | 350002-348 |  |  | 900 | 1199 | Charles St | Texas Ave | Dandridge Ave | 32.7758 | 10 | Local | [13 empty] | 15 |  |  |  | 106627.6 | See Texas | August | [16 empty] | LWC work was done in area | 2456.8468 | 28.0001 | 68792 | 1.1164
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Krierger St | Ellison Ave | Goss Ave | 39.3379 | 10 | Local | [13 empty] | 13 |  |  |  | 50722.2 | See Texas | August | [16 empty] | Depress sidewalk to be flush with pavement at alleys where possible, LWC work done in area | 1168.7507 | 27.9991 | 32724 | 0.53108
| Hall |  | 350002-310 |  |  | 2600 | 2899 | Parklawn Dr | Parkway Dr | Dead End | 41.6675 | 10 | Local | [13 empty] | 10 |  |  |  | 56649.4 | 65090.51 | August | [16 empty] | Pushed back to FY 21 due to virus | 1885.4269 | 19.3845 | 36548 | 0.59314
| Hall |  | 350002-348 |  |  | 800 | 1699 | Texas Ave | S Shelby St | Wetterau Ave | 48 | 10 | Local | [17 empty] | 271580.15 | 546407.57 | August | [17 empty] | 5300 | 34 | 175213 | 2.8436
| Hall |  | 350002-348 |  |  | 1200 | 1299 | Wetterau Ave | Texas Ave | Dead End | 23.7244 | 10 | Local | [13 empty] | 0 |  |  |  | 16535.4 | See Texas | August | [16 empty] | Update ramp on other side of Samuel leading down to shoping center. LWC work done in area | 801.46 | 13.3107 | 10668 | 0.17313
| Hall |  | 350002-348 |  |  | 1000 | 1099 | Wetterau Ave at Ash St | Dead End | Dead End | 21 | 10 | Local | [13 empty] | 6 |  |  |  | 27932.55 | See Texas | August | [16 empty] | Pushed back to FY 21 due to virus | 750.84 | 24.0011 | 18021 | 0.29247
| Hall |  | 350002-341 |  |  | 1904-12-04 | 1906-01-07 | Bashford Manor Ln | Newburg Rd | Bardstown Rd | 65.1829 | 10 | Pri Coll | [17 empty] | 274355.5815 | 233839.15 | September | [17 empty] | 5038.67 | 33 | 166276.11 | 2.6985
| Hall |  | 350002-364 |  |  | 1000 | 1099 | Eigelbach Ave | Dead End | Poplar Level Rd | 47 | 10 | Local | [17 empty] | 35391.15 | 13904.98 | September | [17 empty] | 951 | 24 | 22833 | 0.37056
| Hall |  | 350002-374 |  |  | 1000 | 1099 | Dixon Ave | Dead End | Poplar Level Rd | 43 | 10 | Local | [17 empty] | 92589 | [19 empty] | 1102 | 24 | 26454 | 0.42933
| Hall |  | 350002-375 |  |  | 3100 | 3199 | Harmon Ct | Dead End | Audubon Pky | 0 | 10 | Local | [17 empty] | 35031.5 | [19 empty] | 417 | 24 | 10009 | 0.16244
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Bardstown Rd | Goldsmith Ln |  | 10 | Min Art | [13 empty] | 25 |  |  |  | 511151 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3647 | 62 | 226114 | 3.6696
| Hall |  |  |  |  | 3461 | 3781 | Illinois Ave | Sheridan Ave | 3461 Illinois Ave | 57.9238 | 10 | Local | [17 empty] | 105080.7 | [19 empty] | 3268.3937 | 20.7423 | 67794 | 1.1002
| Hall |  |  |  |  | 3150 | 3199 | Illinois Ave | Osprey Rd | Poplar Level Rd | 21 | 10 | Local | [17 empty] | 8337.45 | [19 empty] | 224.1407 | 24 | 5379 | 0.087296
| Hall |  | 350002-374 |  |  | 1000 | 1099 | Mayer Ave | Dead End | Poplar Level Rd | 37 | 10 | Local | [17 empty] | 66146.5 | [19 empty] | 756 | 25 | 18899 | 0.30671
| Hall |  | 350002-375 |  |  | 1400 | 1499 | Nightingale Rd | Eagle Pass | Audubon Pky | 39 | 10 | Local | [17 empty] | 58907.75 | [19 empty] | 1727 | 22 | 38005 | 0.61679
| Hall |  | 350002-375 |  |  | 3100 | 3199 | Osprey Rd | Illinois Ave | Audubon Pky | 50 | 10 | Local | [17 empty] | 24330.35 | [19 empty] | 654 | 24 | 15697 | 0.25475
| Hall |  | 350002-372 |  |  | 8000 | 8199 | Amity Ln | Summerfield Dr | Dead End | 55.9519 | 11 | Local | [17 empty] | 31184.45 |  | October | [17 empty] | 1000.7746 | 20.1034 | 20119 | 0.32651
| Hall |  | 350002-372 |  |  | 8000 | 8199 | Cloudcroft Ln | Summerfield Dr | Dead End | 50 | 11 | Local | [17 empty] | 53769.5 |  | October | [17 empty] | 1239 | 28 | 34690 | 0.56299
| Hall |  | 350002-372 |  |  | 3100 | 3199 | Spring Breeze Ct | Amity Ln | Dead End | 55.4007 | 11 | Local | [17 empty] | 28616.1 |  | October | [17 empty] | 861.5499 | 21.4288 | 18462 | 0.29962
| Hall |  | 350002-372 |  |  | 2530 | 2599 | Sunbury Ln | Winterhaven Rd | Winterhaven Rd | 58.8872 | 11 | Local | [17 empty] | 70025.9 |  | October | [17 empty] | 1946.0602 | 23.2151 | 45178 | 0.7332
| Hall |  | 350002-372 |  |  | 8000 | 8099 | Weather Ct | Weather Way | Dead End | 65 | 11 | Local | [17 empty] | 7052.5 |  | October | [17 empty] | 253 | 18 | 4550 | 0.073843
| Hall |  | 350002-372 |  |  | 3000 | 3199 | Weather Way | Summerfield Dr | Dead End | 68.3392 | 11 | Local | [17 empty] | 48962.95 |  | October | [17 empty] | 1435.8717 | 21.9999 | 31589 | 0.51266
| LP |  | 339051-74 |  |  | 1916-06-04 | 1918-08-12 | Sylvania Rd | Memory Ln | Rutledge Rd | 63.5483 | 12 | Sec Coll | [17 empty] | 60800.85 | 42687.73 | September | [17 empty] | 1914.0068 | 19.2523 | 36849 | 0.59803
| Hall |  |  |  |  | 3600 | 3999 | Baymeadow Dr (all) | Brinamwood Dr | Dead End | 72.9415 | 12 | Local | [17 empty] | 71907.6 | [19 empty] | 1973.6702 | 23.6667 | 46392 | 0.7529
| Hall |  |  |  |  | 3600 | 3699 | Birnamwood Ct | Birnamwood Dr | Dead End | 61 | 12 | Local | [17 empty] | 7209.05 | [19 empty] | 258 | 18 | 4651 | 0.075482
| Hall |  |  |  |  | 6900 | 7199 | Birnamwood Dr | St Andrews Church Rd | Baymeadow Dr | 72.8578 | 12 | Local | [17 empty] | 54293.4 | [19 empty] | 1487.6416 | 23.3333 | 35028 | 0.56847
| Hall |  |  |  |  | 3600 | 3699 | Eastmeadow Ct | Birnamwood Dr | Dead End | 56 | 12 | Local | [17 empty] | 6313.15 | [19 empty] | 226 | 18 | 4073 | 0.066101
| Hall |  |  |  |  | 6900 | 6999 | Hyland Hills Ct | Baymeadow Dr | Dead End | 48 | 12 | Local | [17 empty] | 4642.25 | [19 empty] | 150 | 20 | 2995 | 0.048606
| Hall |  |  |  |  | 1905-03-14 | 1906-01-07 | Lower Hunters Trce | Dixie Hwy | Upper Hunters Trce | 63.6414 | 12 | Pri Coll | [17 empty] | 91005 | [19 empty] | 3840.0384 | 29.3265 | 112615 | 1.8276
| Hall |  |  |  |  | 1906-01-08 | 1918-02-09 | Lower Hunters Trce | Upper Hunters Trce | Greenbelt Hwy | 66.9497 | 12 | Pri Coll | [17 empty] | 347664.9 | [19 empty] | 9483.5364 | 25.4712 | 210706 | 3.4196
| Hall |  |  |  |  | 100 | 199 | Mills Dr | Alreva Rd | Blanton Ln | 61.0339 | 12 | Local | [17 empty] | 97908.85 | [19 empty] | 3088.9085 | 20.4496 | 63167 | 1.0251
| Hall |  |  |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | [19 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-370 |  |  | 8000 | 8399 | Afterglow Dr | Dead End | Outer Loop | 49.0349 | 13 | Local | [13 empty] | 4 |  |  | 12 | 175466.2 | 193267.43 | August | [16 empty] | May look to add frontage Rd off Outer Loop | 4154.1404 | 27.2509 | 113204 | 1.8372
| Hall |  | 350002-361 |  |  | 10600 | 11499 | Harrison Ln | National Tpke | Dead End | 51.4903 | 13 | Local | [17 empty] | 150370.15 | 84772.32 | August | [17 empty] | 5276.3386 | 18.3864 | 97013 | 1.5744
| Hall |  | 350002-335 |  |  | 800 | 899 | Candleglow Ct | Dead End | Candleglow Ln | 52 | 13 | Local | [17 empty] | 10231.55 | See Candlelight | September | [17 empty] | 367 | 18 | 6601 | 0.10713
| Hall |  | 350002-335 |  |  | 500 | 899 | Candlelight Ln | New Cut Rd | Dead End | 63.1036 | 13 | Local | [17 empty] | 81216.9 | 58293.95 | September | [17 empty] | 2734.1962 | 19.164 | 52398 | 0.85037
| Hall |  | 350002-336 |  |  | 400 | 499 | Garrison Ct | Dead End | Garrison Rd | 29 | 13 | Local | [17 empty] | 7745.35 | See Garrison Rd | September | [17 empty] | 227 | 22 | 4997 | 0.081097
| Hall |  | 350002-336 |  |  | 7300 | 7699 | Garrison Rd | Dead End | Revolutionary Rd | 53.4225 | 13 | Local | [17 empty] | 69548.5 | 70894.33 | September | [17 empty] | 1908.6386 | 23.5089 | 44870 | 0.7282
| LP |  | 339051-75 |  |  | 1929-07-26 | 1935-04-25 | Holsclaw Hill Rd | Mitchell Hill Rd | Dead End | 65.6183 | 13 | Sec Coll | [17 empty] | 351212.4 | 377860.73 | September | [17 empty] | 10567.5567 | 20.1424 | 212856 | 3.4545
| LP |  | 339051-75 |  |  | 1919-03-01 | 1919-12-25 | Knob Creek Rd | Dead End | Mitchell Hill Rd | 58 | 13 | Sec Coll | [17 empty] | 50631.9 | See Holsclaw Hill | September | [17 empty] | 1534.3038 | 20 | 30686 | 0.49801
| Hall |  | 350002-335 |  |  | 800 | 899 | Taper Ct | Dead End | Candleglow Ln | 67 | 13 | Local | [17 empty] | 6747.15 | See Cadlelight | September | [17 empty] | 282 | 16 | 4353 | 0.070645
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | various drainage improvements needed, shoulder | 6261.5 | 19 | 118968.5 | 1.9308
[8 empty] | D13 Paving Projects |  |  |  | 13 | [18 empty] | 14000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000
| Hall |  | 350002-347 |  |  | 16700 | 17199 | Abbotts Beach Rd | Dixie Hwy | Dead End | 23 | 14 | Local | [17 empty] | 36318.05 | 27208.43 | August | [17 empty] | 2343 | 10 | 23431 | 0.38026
| LP |  | 339051-80 |  |  | 1909-04-22 | 1915-05-25 | Blevins Gap Rd | Stonestreet Rd | Medora Rd | 70.2148 | 14 | Pri Coll | [17 empty] | 550000 |  | November | PW, Council | 8146-410-8210-148538-822702 | 25000 |  | 8146-410-8107-148538-822702 | 75000 | [11 empty] | 18719.4454 | 20.0252 | 374860 | 6.0837
| Hall |  | 350002-337 |  |  | 6900 | 7199 | Ethan Allen Way | Kinross Blvd | Bessels Blvd | 42.3493 | 14 | Local | [17 empty] | 85963 | 60378.05 | October | [17 empty] | 2310.8498 | 23.9998 | 55460 | 0.90007
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Britannia Ct | Dead End | Scarborough Ave | 61 | 14 | Local | [17 empty] | 23112.05 | See Scarborough Ave | September | [17 empty] | 621 | 24 | 14911 | 0.24199
| Hall |  | 350002-369 |  |  | 6900 | 6999 | Fincastle Trl | Dead End | Lower River Rd | 42 | 14 | Local | [17 empty] | 14022.85 |  | September | [17 empty] | 905 | 10 | 9047 | 0.14682
| Hall |  | 350002-367 |  |  | 2400 | 2499 | Hereford Ct | Scarborough Ave | Dead End | 12 | 14 | Local | [17 empty] | 7548.5 | See Scarborough Ave | September | [17 empty] | 271 | 18 | 4870 | 0.079036
| Hall |  | 350002-367 |  |  | 2400 | 2499 | Kings Cross Ct | Dead End | Scarborough Ave | 56 | 14 | Local | [17 empty] | 9924.65 | See Scarborough Ave | September | [17 empty] | 291 | 22 | 6403 | 0.10392
| Hall |  | 350002-367 |  |  | 9700 | 9799 | Leopold Ct | Scarborough Ave | Scarborough Ave | 22 | 14 | Local | [17 empty] | 9689.05 | See Scarborough Ave | September | [17 empty] | 313 | 20 | 6251 | 0.10145
| Hall |  | 350002-367 |  |  | 2500 | 2505 | Parliament Ct | Scarborough Ave | Scarborough Ave | 55 | 14 | Local | [17 empty] | 9351.15 | See Scarborough Ave | September | [17 empty] | 335 | 18 | 6033 | 0.09791
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Pembury Ct | Scarborough Ave | Dead End | 23 | 14 | Local | [17 empty] | 7641.5 | See Scarborough Ave | September | [17 empty] | 274 | 18 | 4930 | 0.08001
| Hall |  | 350002-367 |  |  | 9732 | 9899 | Scarborough Ave | Montpelier Ct | Lamborne Blvd | 65.1377 | 14 | Local | [17 empty] | 21024.2 | 128664.59 | September | [17 empty] | 565.1696 | 23.9999 | 13564 | 0.22013
| Hall |  | 350002-369 |  |  | 7200 | 7399 | Scenic Trl | Dead End | Lower River Rd | 47 | 14 | Local | [17 empty] | 17859.1 | 8524.18 | September | [17 empty] | 886 | 13 | 11522 | 0.18699
| LP |  | 339051-77 |  |  | 1917-10-17 | 1920-07-12 | W Orell Rd | Dixie Hwy | Lower River Rd | 65.5631 | 14 | Pri Coll | [17 empty] | 174266.4 | 131555.99 | September | [17 empty] | 5280.8336 | 19.9999 | 105616 | 1.7141
| Hall |  | 350002-367 |  |  | 9600 | 9699 | Yarmouth Ct | Scarborough Ave | Dead End | 35 | 14 | Local | [17 empty] | 17054.65 | See Scarborough Ave | September | [17 empty] | 550 | 20 | 11003 | 0.17857
| Hall |  |  |  |  | 5700 | 6099 | Alandale Dr | Dixie Hwy | Omar Khayyam Blvd | 59.1854 | 14 | Local | [17 empty] | 107878.45 | [19 empty] | 2719.5213 | 25.5924 | 69599 | 1.1295
| LP |  | 339051-8 | 2017-07-01 |  |  |  | Bearcamp Rd | Blevins Gap Rd | Wildflower Ln |  | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 287148 |  |  | PW '19 MAP | 8672-410-8210-148451-822702 | [14 empty] | On-hold until culvert replacement complete | 5239 | 18 | 94302 | 1.5304
| LP |  | 339051-8 | 2018-07-01 |  | 11500 | 14699 | Bearcamp Rd | Wildflower Hill Ln | county line | 65 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 178452.75 |  |  | PW Funds |  | 178452.75 | [13 empty] | see above | 6261.5 | 19 | 118968.5 | 1.9308
| Hall |  |  |  |  | 11700 | 11899 | Deering Rd | Flowervale Ln | Dead End | 47 | 14 | Local | [17 empty] | 33464.5 | [19 empty] | 1080 | 20 | 21590 | 0.35039
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65 | 14 | Sec Coll | [17 empty] | 68000.427 | [19 empty] | 1719.962 | 24 | 41212.38 | 0.66884
| Hall |  |  |  |  | 9500 | 10099 | Omar Khayyam Blvd | Donau Ln | Count Fleet Dr | 69.6626 | 14 | Local | [17 empty] | 89163.75 | [19 empty] | 2396.8896 | 23.9999 | 57525 | 0.93358
| LP |  | 339051-76 |  |  | 1935-01-16 | 1938-01-19 | Scotts Gap Rd | Blevins Gap Rd | Dead End | 67.2271 | 14 | Sec Coll | [17 empty] | 224112.9 | [19 empty] | 7455.678 | 18.2178 | 135826 | 2.2043
| Seven Seas |  | 370579 |  |  |  |  | Rankin St | E Kenton St | E Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 18778.65 | 3348.9 | August | PW Funds FY 17 | [15 empty] | PCCP - Most panels look ok, I would do select panel replacement - James |  |  | 0 | 0
| Hall |  | 350002-362 |  |  | 1906-07-27 | 1907-12-08 | S Floyd St | Old Eastern Pky | Central Ave | 60 | 15 | Pri Coll | [17 empty] | 214247.55 | 228106.33 | August | [17 empty] | 3290 | 39.4672 | 129847 | 2.1073
| Seven Seas |  | 370579 |  |  |  |  | Tulane Ave | W Kenton St | W Garrett St |  | 15 | Local | [12 empty] | N | 7 |  |  |  | 14086.05 | 13384.51 | August | PW Funds FY 17 | [15 empty] | PCCP |  |  | 0 | 0
| Hall |  |  |  |  | 4300 | 4399 | Fluhr Dr | Dead End | Anna Ln | 51.7058 | 15 | Local | [17 empty] | 24564.4 | [19 empty] | 660.3467 | 23.9995 | 15848 | 0.2572
| Hall |  |  |  |  | 3500 | 3799 | Georgetown Pl | Berry Blvd | Dead End | 28.4435 | 15 | Local | [17 empty] | 41555.5 | [19 empty] | 1103.1397 | 24.3034 | 26810 | 0.4351
| Hall |  |  |  |  | 300 | 699 | Heywood Ave | S 3rd St | Rodman St | 53.2531 | 15 | Local | [17 empty] | 102665.8 | [19 empty] | 1919.8374 | 34.5008 | 66236 | 1.075
| Hall |  |  |  |  | 1200 | 1320 | Lance Dr | Manslick Rd | Leaf Dr | 59.0188 | 15 | Local | [17 empty] | 30051.4 | [19 empty] | 794.1409 | 24.4138 | 19388 | 0.31465
| Hall |  |  |  |  | 1600 | 1749 | March Blvd | Manslick Rd | Nichols Meadow Cir at school entrance | 71.0419 | 15 | Local | [17 empty] | 80654.25 | [19 empty] | 1224.4896 | 42.4953 | 52035 | 0.84448
| Hall |  |  |  |  | 4442 | 4516 | Rear View Dr | Lance Dr | Dead End | 19 | 15 | Local | [17 empty] | 45416 | [19 empty] | 649 | 20 | 12976 | 0.21059
| Hall |  |  |  |  | 2800 | 3099 | S 5th St | M St | Central Ave | 50.6617 | 15 | Local | [17 empty] | 64504.8 | [19 empty] | 1417.7832 | 29.3529 | 41616 | 0.67539
|  |  | 350002-198 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 |  |  | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1200 | 1499 | Weyler Ave | Arcade Ave | Dead End | 51 | 15 | Local | [17 empty] | 52250.5 | [19 empty] | 1705 | 20 | 33710 | 0.54708
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus. Will be pushed to FY 22
| Hall |  |  |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | [19 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  |  |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | [19 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  |  |  |  | 1920-07-13 | 1921-11-24 | Wolf Pen Branch Rd | Wolf Pen Ln (east of intersection) | Spring Farm Rd | 77.753 | 16 | Sec Coll | [17 empty] | 95670.3 | [19 empty] | 2959.4685 | 19.592 | 57982 | 0.941
| Hall |  | 350002-292 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | [18 empty] | Pushed back to FY 21 due to virus | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-292 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | [18 empty] | Pushed back to FY 21 due to virus | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-292 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | [18 empty] | Pushed back to FY 21 due to virus | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-292 |  |  | 11006 | 11199 | Eagles Cove Dr | Kestrel Ct | Hickory Cove Ct | 61.2884 | 17 | Local | [13 empty] | 5 |  |  |  | 73635.85 | [18 empty] | Pushed back to FY 21 due to virus | 2077.047 | 22.8724 | 47507 | 0.771
| Hall |  | 350002-292 |  |  | 4500 | 4599 | Goshawk Ct | Eagles Cove Dr | Dead End | 66 | 17 | Local | [13 empty] | 2 |  |  |  | 15304.7 | [18 empty] | Pushed back to FY 21 due to virus | 411.4091 | 24 | 9874 | 0.16025
| Hall |  | 350002-292 |  |  | 10700 | 10712 | Hickory Cove Ct | Shenandoah Dr | Eagles Cove Dr | 52 | 17 | Local | [13 empty] | 3 |  |  |  | 26463.15 | [18 empty] | Pushed back to FY 21 due to virus | 656.6535 | 26 | 17073 | 0.27708
| Hall |  |  |  |  | 13600 | 13699 | Sample Ct | Sample Way | Dead End | 67 | 17 | Local | [17 empty] | 11609.5 | [19 empty] | 312.0762 | 24 | 7490 | 0.12156
| Hall |  |  |  |  | 3400 | 3599 | Sample Way | Colonial Springs Rd | Springs Station Rd | 59.8943 | 17 | Local | [17 empty] | 72225.35 | [19 empty] | 2053.5541 | 22.6909 | 46597 | 0.75623
| Hall |  |  |  |  | 13400 | 13499 | Sapling Spring Pl | Dead End | Sample Way | 70 | 17 | Local | [17 empty] | 6300.75 | [19 empty] | 169.381 | 24 | 4065 | 0.065971
| Hall |  |  |  |  | 13500 | 13599 | Squire Springs Ct | Sample Way | Dead End | 66 | 17 | Local | [17 empty] | 15921.6 | [19 empty] | 428.0127 | 24 | 10272 | 0.16671
[8 empty] | Ashbrook Ave | Beechcrest Ave | Brookhaven Ave (concrete panel replacement) |  | 18 | Local | [17 empty] | 15000 |  |  | CIF | 8146-410-8107-148267-822702 | 15000
| Hall |  |  |  |  | 600 | 609 | Dorsey Way | Rymer Way | Elsmere Cir | 87 | 18 | Local | [17 empty] | 19729.95 | [19 empty] | 303 | 42 | 12729 | 0.20658
| Hall |  |  |  |  | 600 | 799 | Elsmere Cir | Dorsey Way | Tamarisk Pkwy | 72.7037 | 18 | Local | [17 empty] | 54589.45 | [19 empty] | 1565.7643 | 22.4932 | 35219 | 0.57157
| Hall |  |  |  |  | 1 | 99 | Hallsdale Dr | Taylorsville Rd | Dead End | 63.1729 | 18 | Local | [17 empty] | 102778.95 | [19 empty] | 2762.8307 | 24.0004 | 66309 | 1.0761
[8 empty] | Hobbs Station | Old Hobbs Pl | Lodge Hill |  | 18 | Local | [17 empty] | 35000 |  |  | CIF | 8146-410-8107-148267-822702 | 35000
[8 empty] | Quince Ct | Hobbs Station | Dead End |  | 18 | Local | [17 empty] | 2500 |  |  | CIF | 8146-410-8107-148267-822702 | 2500
[8 empty] | Ridgeview Ave | N Wood Dr | Lynnbrook Dr |  | 18 | Local | [17 empty] | 42400 |  |  | CIF | 8146-410-8107-148267-822702 | 22500
| Hall |  |  |  |  | 600 | 602 | Rymer Way | Winyan Ln | Dorsey Way | 46 | 18 | Local | [17 empty] | 11657.55 | [19 empty] | 341.8596 | 22 | 7521 | 0.12206
| Hall |  |  |  |  | 9900 | 9999 | Spring Ridge Dr | Dead End | Dorsey Way | 49 | 18 | Local | [17 empty] | 30590.8 | [19 empty] | 939.8092 | 21 | 19736 | 0.3203
| Hall |  | 350002-350 |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 61.7099 | 18 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  | 339051-78 |  |  | 1903-07-23 | 1905-06-21 | N English Station Rd | La Grange Rd | Old Henry Rd | 70.6362 | 19 | Pri Coll | [16 empty] | August | 190665.75 | 118409.25 | August | [17 empty] | 4744.6459 | 24.3548 | 115555 | 1.8754
| Hall |  | 350002-351 |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 19 | Pri Coll | [13 empty] | 3 |  |  | August | 34471.7505 | See N Pope Lick | August | [16 empty] | 0.5 in D 20, need to fix up one radius with potential curba nd gutter. 3 ramps at Urton Ln. | 1160.665 | 18 | 20891.97 | 0.33906
| Hall |  |  |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | [19 empty] | 1488.0063 | 89 | 132433 | 2.1493
| LP |  | 350002-286 |  |  |  |  | Hagen Rd | Hersfield Rd | dead end |  | 19 | [18 empty] | 12500 |  |  | CIF - *Temp PW '19 Bond | 8138-410-8107-148919-822702 | 12500 |  | 8137-410-8210-148451-822702 | 12500 | [10 empty] | Pushed back to FY 21 due to virus |  |  | 12493 | 0.20275
| Hall |  |  |  |  | 1100 | 1599 | Heafer Rd | N English Station Rd | La Grange Rd | 41 | 19 | Local | [17 empty] | 99816.9 | [19 empty] | 3136 | 21 | 64398 | 1.0451
| Hall |  | 350002-286 |  |  |  |  | Herfield Rd |  |  |  | 19 | Local | [17 empty] | 15000 |  |  | Council | 8138-410-8107-048101-822702 | 15000 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 12300 | 12499 | Park Field Rd | Heafer Rd | Dead End | 41 | 19 | Local | [17 empty] | CIF | [19 empty] | 711 | 21 | 14643 | 0.23764
| Hall |  | 350002-286 |  |  |  |  | Parkfield Rd |  |  |  | 19 | [18 empty] | 22000 |  |  | Council | 8138-410-8107-048101-822702 | 16000 |  | 8144-410-8107-048101-822702 | 6000 | [10 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 1929-01-07 | 1930-02-10 | Ward Ave | Dorsey Ln | Old Harrods Creek Rd | 62 | 19 | Pri Coll | [17 empty] | 56424.9015 | [19 empty] | 1554.405 | 22 | 34196.91 | 0.55499
| LP |  | 339051-72 |  |  | 1927-12-04 | 1932-04-20 | Easum Rd | Billtown Rd | Old Heady Rd | 65.4048 | 20 | Pri Coll | [17 empty] | 378646.95 | 360120.27 | August | [17 empty] | 12312.9475 | 18.6375 | 229483 | 3.7243
| LP |  | 339051-68 |  |  | 9700 | 9299 | Hassy Way | Dry Ridge Rd | Dead End | 84.5338 | 20 | Local | [17 empty] | 189358 | 62203.16 | August | [17 empty] | 1865.9377 | 23.4429 | 43743 | 0.70991
| Hall |  |  |  |  | 800 | 848 | N Pope Lick Rd | Tucker Station Rd | Rockbridge Rd | 61.7786 | 20 | Pri Coll | [13 empty] | See N Pope Lick |  |  | August | 34471.7505 | 89728.41 | August | [16 empty] | 0.5 in D 19, see other N Pope Lick | 1160.665 | 18 | 20891.97 | 0.33906
| LP |  | 339051-71 |  |  | 3500 | 4299 | Old Routt Rd | Dead End | Routt Rd | 45.5989 | 20 | Local | [17 empty] | 224937.55 | 120672.59 | August | [17 empty] | 7256.044 | 20 | 145121 | 2.3552
| LP |  | 339051-70 |  |  | 15200 | 15299 | Old Taylorsville Rd (near Eastwood Fisherville intersection) | Dead End | Taylorsville Rd | 12 | 20 | Local | [17 empty] | 24133.5 | 22842.6 | August | [17 empty] | 1112.1651 | 14 | 15570 | 0.25269
| LP |  | 339051-69 |  |  | 14000 | 14199 | Old Taylorsville Rd at Wilderness Trl | Taylorsville Rd | Dead End | 55.6534 | 20 | Local | [17 empty] | 34870.35 | See Wilderness Trl | August | [17 empty] | 1318.8779 | 17.0577 | 22497 | 0.36511
| LP |  | 339051-69 |  |  | 3400 | 3999 | Wilderness Trl | Old Taylorsville Rd | Dead End | 52 | 20 | Local | [17 empty] | 115172.75 | 155661.67 | August | [17 empty] | 4644.0491 | 16 | 74305 | 1.2059
| LP |  | 339051-68 |  |  | 16300 | 16399 | Witch Hazel Dr | Hassy Way | Dead End | 90 | 20 | Local | [17 empty] | 66598 | See Hassy Way | August | [17 empty] | 610 | 24 | 14639 | 0.23758
| LP |  | 339051-62 |  |  | 600 | 6499 | Gellhaus Ln | Chenoweth Run Rd | Billtown Rd | 61.166 | 20 | Sec Coll | [13 empty] | 6 |  |  |  | 181381.398 | 189438.65 | July | [16 empty] | Intersection improvement at Chenoweth Run, possible culverts and Guardrail replacements needed. | 4672.76 | 23.5253 | 109928.12 | 1.784
| LP |  |  |  |  | 11800 | 14499 | Rehl Rd | Blankenbaker Pkwy | S Pope Lick Rd | 60.2949 | 20 | Pri Coll | [13 empty] | 0 |  |  |  | 430623.633 | 351795.21 | July | [16 empty] | Need cores taken, possibly thin asphalt. Possible Fiber project. Check Guardrails. Need to review intersection at Tucker Station Rd | 11862.91 | 22 | 260984.02 | 4.2355
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 3500 | 4299 | S Pope Lick Rd | Old Taylorsville Rd | Dead End | 26 | 20 | Local | [13 empty] | 0 |  |  |  | 183792.8 | [18 empty] | May have been repaved with Parklands project | 6975.0624 | 17 | 118576 | 1.9244
| Hall |  | 350002-279 |  |  | 100 | 199 | E Amherst Ave | S 1st St | Wabash Pl | 48.8533 | 21 | Local | [13 empty] | 0 |  |  |  | 50161.1 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 1274.1882 | 25.3981 | 32362 | 0.52521
| Hall |  | 350002-279 |  |  | 4900 | 4999 | Hollins Rd | St Leo Pl | E Amherst Ave | 60 | 21 | Local | [13 empty] | 5 |  |  | 5 | 14066.25 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 303 | 30 | 9075 | 0.14728
| Hall |  | 350002-279 |  |  | 4800 | 4999 | S 1st St | E Amherst Ave | Dead End to north | 61.3741 | 21 | Local | [13 empty] | 4 |  |  | 4 | 35997.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 822.4664 | 28.237 | 23224 | 0.37691
| Hall |  | 350002-279 |  |  | 100 | 114 | W Amherst Ave | Southside Dr | S 1st St | 59 | 21 | Local | [13 empty] | 4 |  |  |  | 16994.2 | See Southland | August | [16 empty] | Pushed back to FY 21 due to virus | 422 | 26 | 10964 | 0.17794
| Hall |  | 350002-279 |  |  | 200 | 5799 | W Southland Blvd | Southside Dr | Southern Pkwy | 54.9398 | 21 | Pri Coll | [13 empty] | 15 |  |  | 15 | 256091.9955 | 271499.61 | November | [16 empty] | 2 speed humps on roadway, need to check ramps at southland Ter. | 5145.34 | 30.1646 | 155207.27 | 2.5189
| Hall |  | 350002-279 |  |  | 100 | 199 | W Tenny Ave | S 1st St | Southside Dr | 35 | 21 | Local | [13 empty] | 8 |  |  |  | 19027.8 | See Southland | November | [16 empty] | Pushed back to FY 21 due to virus | 409 | 30 | 12276 | 0.19923
| Hall |  |  |  |  | 4400 | 4699 | Allmond Ave | E Woodlawn Ave | Dead End (north) | 54.248 | 21 | Local | [17 empty] | 131756.2 | [19 empty] | 3325.2587 | 25.5631 | 85004 | 1.3795
| Hall |  |  |  |  | 300 | 399 | Chris Dr | Homestead Dr | Dead End | 61 | 21 | Local | [17 empty] | 5054.55 | [19 empty] | 271.7278 | 12 | 3261 | 0.052923
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [19 empty] | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-279 |  |  | 100 | 199 | E Tenny Ave | S 1st St | St Leo Pl | 42 | 21 | Local | [13 empty] | 3 |  |  |  | 28551 | See Southland | [17 empty] | Pushed back to FY 21 due to virus | 658 | 28 | 18420 | 0.29894
| Hall |  |  |  |  | 200 | 299 | E Woodlawn Ave | Allmond Ave | Nevada Ave | 68 | 21 | Min Art | [17 empty] | 127152.3 | [19 empty] | 1926.5536 | 39.9999 | 77062 | 1.2506
| Hall |  |  |  |  | 5000 | 5199 | Emery Ave | Lyman Ave | W Kenwood Dr | 54 | 21 | Local | [17 empty] | 24539.6 | [19 empty] | 754 | 21 | 15832 | 0.25694
| Hall |  |  |  |  | 5000 | 5199 | Fay Ave | W Kenwood Dr | Alger Ave | 48.6736 | 21 | Local | [17 empty] | 42524.25 | [19 empty] | 1287.734 | 21.3049 | 27435 | 0.44525
| Hall |  |  |  |  | 5900 | 6199 | Gloria Ln | Catheen Way | Dead End | 43.0059 | 21 | Local | [17 empty] | 47087.45 | [19 empty] | 1318.1272 | 23.0471 | 30379 | 0.49302
| Hall |  |  |  |  | 300 | 399 | Hatcher Ave | Southside Dr | Homestead Dr | 39 | 21 | Local | [17 empty] | 15921.6 | [19 empty] | 641.9717 | 16 | 10272 | 0.16671
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
| Hall |  |  |  |  | 300 | 399 | Hillview Dr | Southside Dr | Homestead Dr | 23 | 21 | Local | [17 empty] | 20945.15 | [19 empty] | 750.738 | 18 | 13513 | 0.2193
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  |  |  |  | 6800 | 7099 | Homestead Dr | E Kenwood Dr | Dead End | 44.1624 | 21 | Local | [17 empty] | 37426.3 | [19 empty] | 1442.2483 | 16.7419 | 24146 | 0.39187
| Hall |  |  |  |  | 4800 | 5999 | Hood Rd | W Indian Trl | Catheen Way | 14 | 21 | Local | [17 empty] | 30860.5 | [19 empty] | 996 | 20 | 19910 | 0.32312
| Hall |  |  |  |  | 6100 | 6199 | Loretta St | Elam Ct | Whitlock St | 78.4686 | 21 | Local | [17 empty] | 39190.2 | [19 empty] | 1053.4975 | 24.0001 | 25284 | 0.41034
| Hall |  |  |  |  | 500 | 599 | Lyman Ave | Laughlin Ave | Fay Ave | 53 | 21 | Local | [17 empty] | 10696.55 | [19 empty] | 314 | 22 | 6901 | 0.112
| Hall |  |  |  |  | 700 | 799 | Lyman Ave | Reed Ave | Emery Ave | 54 | 21 | Local | [17 empty] | 9114 | [19 empty] | 294 | 20 | 5880 | 0.095427
| Hall |  |  |  |  | 300 | 399 | Meadowood Ct | Southside Dr | Dead End | 29 | 21 | Local | [17 empty] | 7184.25 | [19 empty] | 579.3129 | 8 | 4635 | 0.075222
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 5900 | 6199 | Orville Dr | Gloria Ln | Dead End | 41.6904 | 21 | Local | [17 empty] | 44374.95 | [19 empty] | 1192.8763 | 24 | 28629 | 0.46462
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [19 empty] | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 5000 | 5199 | Reed Ave | W Kenwood Dr | Dead End | 65.1753 | 21 | Local | [17 empty] | 30215.7 | [19 empty] | 935.098 | 20.847 | 19494 | 0.31637
| Hall |  |  |  |  | 2825 | 2899 | Smilax Ave | Loretta St | W Indian Trl | 78 | 21 | Local | [17 empty] | 12877.4 | [19 empty] | 346 | 24 | 8308 | 0.13483
| Hall |  |  |  |  | 900 | 1199 | W Indian Trl | Preston Hwy | Dead End | 52.6638 | 21 | Local | [17 empty] | 116784.75 | [19 empty] | 3947.8218 | 19.0852 | 75345 | 1.2228
| Hall |  |  |  |  | 2800 | 2899 | Whitlock St | Norton Ave | Loretta St | 85 | 21 | Local | [17 empty] | 29848.35 | [19 empty] | 837 | 23 | 19257 | 0.31252
| Hall |  |  |  |  | 5400 | 5499 | Winding Rd | Woodmore Ave | Dead End | 47 | 21 | Local | [17 empty] | 46949.5 | [19 empty] | 1121.8398 | 27 | 30290 | 0.49158
| LP |  |  |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [19 empty] | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-385 |  |  | 1924-08-21 | 1925-03-08 | Fern Creek Rd | Beulah Church Rd | Bardstown Rd | 64.6738 | 22 | Pri Coll | [17 empty] | 139346.2469 | 8629.1 | [18 empty] | 4021.5367 | 21 | 84452.2709 | 1.3706
| Hall |  | 350002-346 |  |  | 8600 | 8609 | Glenhope Dr | Black Iron Rd | break south of Stonebreaker Rd | 56.1215 | 22 | Local | [17 empty] | 25878.8 | See Stonebreaker Rd | [18 empty] | 695.6754 | 23.9997 | 16696 | 0.27096
| Hall |  | 350002-346 |  |  | 10500 | 10699 | Stonebreaker Rd | Dead End | Dead End | 49.7486 | 22 | Local | [17 empty] | 76402.6 | 14543.61 | [18 empty] | 2155.5713 | 22.8673 | 49292 | 0.79997
| Hall |  | 350002-304 |  |  | 8400 | 9399 | Pennsylvania Run Rd | Vaughn Mill Rd | Cooper Chapel Rd | 60.244 | 23 | Pri Coll | [13 empty] | 0 |  |  |  | 221604.4215 | See Vaughn Mill | August | [16 empty] | Need to replace 1 culvet for sure, but review others. Update guardrails as necessary. Will avoid sidewalk ramps if possible | 6395.51 | 21 | 134305.71 | 2.1797
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Outer Loop | Pennsylvania Run Rd | 65 | 23 | Pri Coll | [17 empty] | 145558 | 326973.75 | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  | 350002-304 |  |  |  |  | Vaughn Mill Rd | Fegenbush Ln | Outer Loop | 65 | 23 | Pri Coll | [17 empty] | 86290 | See Vaughn Mill Above | July | [16 empty] | Pulled up from FY 21 to replace FY 20 residential roads due to virus
| Hall |  |  |  |  | 8300 | 8499 | Berea Dr | Damascus Ct | Sardis Way | 44 | 23 | Local | [17 empty] | 46244 | [19 empty] | 1005 | 23 | 23122 | 0.37525
| Hall |  |  |  |  | 6200 | 6399 | Hackberry Way | Maple Rd | Lancewood Rd | 44 | 23 | Local | [17 empty] | 53769.5 | [19 empty] | 1576.8029 | 22 | 34690 | 0.56299
| Hall |  |  |  |  | 9600 | 9899 | Lancewood Rd | Dead End | Price Lane Rd | 46.4626 | 23 | Local | [17 empty] | 50145.6 | [19 empty] | 1516.9546 | 21.3269 | 32352 | 0.52504
| Hall |  |  |  |  | 9500 | 9599 | Yellow Pine Ct | Dead End | Yellow Pine Dr | 48 | 23 | Local | [17 empty] | 18097.8 | [19 empty] | 486.509 | 24 | 11676 | 0.18949
| Hall |  | 350002-349 |  |  | 3800 | 3899 | Britt Ln | Dead End | Rust Oak Ln | 39.4136 | 24 | Local | [13 empty] | 5 |  |  |  | 47330.8 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1297.2258 | 23.5395 | 30536 | 0.49557
| Hall |  | 350002-349 |  |  | 8100 | 8199 | Carnes Dr | Dead End | Tuesday Way | 38 | 24 | Local | [13 empty] | 3 |  |  |  | 11198.75 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 301.058 | 24 | 7225 | 0.11726
| Hall |  | 350002-349 |  |  | 8000 | 8299 | Horizon Ln | Dead End | Foreman Ln | 48.5169 | 24 | Local | [13 empty] | 2 |  |  |  | 39569.95 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 1088.3103 | 23.4575 | 25529 | 0.41431
| Hall |  | 350002-217 |  |  |  |  | Monaco Dr | Woodhill Ln | Morningside Way | 48 | 24 | Local | [16 empty] | 3 | 43368 | 129859.74 | July | Council | 8125-410-8107-148385-822702 | 103880.92 |  | 8137-410-8210-148385-822702 | 6320.87 |  | 8101-410-8210-148385-822702 | 61863.6 | [7 empty] | Pushed back to FY 21 due to virus |  |  | 28912 | 0.46922
| Hall |  | 350002-217 |  |  |  |  | Morningside Way | Monaco Dr | Dead End | 20 | 24 | Local | [17 empty] | 27317 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 18211 | 0.29555
| Hall |  | 350002-217 |  |  |  |  | Oaklawn Dr | Preston Hwy | Dead End | 48 | 24 | Local | [17 empty] | 100551 | See Monaco | July | Council | See Monaco Dr | [14 empty] | Pushed back to FY 21 due to virus |  |  | 67034 | 1.0879
|  |  | 350002-238 |  |  |  |  | Prestonview Ln | Foreman Ln | dead end | 31 | 24 | Local | [13 empty] | 0 |  |  |  | 17791.74 | 52304.37 | July | Council | 8133-410-8107-148385-822702 | 17791.74 | [13 empty] | Pushed back to FY 21 due to virus
|  |  | 350002-238 |  |  |  |  | Trio Ave | Preston Hwy | Prestonview Ln | 33 | 24 | Local | [13 empty] | 0 |  |  |  | $17,791,75 | See Prestonview | July | Council | 8133-410-8210-148385-822702 | 17791.75 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  | 350002-349 |  |  | 3700 | 3999 | Tuesday Way | Woodbury Dr | Dead End | 42.0113 | 24 | Local | [13 empty] | 7 |  |  |  | 90795.9 | 205531.3 | July | [16 empty] | Pushed back to FY 21 due to virus | 2255.064 | 25.9762 | 58578 | 0.95067
| Hall |  | 350002-349 |  |  | 3700 | 3799 | Wednesday Way | Dead End | Horizon Ln | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 20393.35 | See Tuesday Way | July | [16 empty] | Pushed back to FY 21 due to virus | 548.2191 | 24 | 13157 | 0.21353
| LP |  | 339051-79 |  |  | 1901-11-30 | 1903-10-30 | McCawley Rd | Preston Hwy | Jefferson Blvd | 66.4236 | 24 | Pri Coll | [17 empty] | 195165.3 | 189435.19 | October | [17 empty] | 4479.469 | 26.4054 | 118282 | 1.9196
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 6000 | 6199 | Ledgerock Cove Pl | Dead End | Dead End | 80.4892 | 24 | Local | [17 empty] | 30097.9 | [19 empty] | 970.9416 | 24 | 19418 | 0.31514
| Hall |  |  |  |  | 6900 | 7099 | Ledgerock Rd | Ledgerock Cove Pl | Moorhaven Dr | 47.5203 | 24 | Local | [17 empty] | 40166.7 | [19 empty] | 1079.7727 | 23.9995 | 25914 | 0.42056
| LP |  | 339051-64 |  |  | 8300 | 8499 | McNair Rd | Manslick Rd | 3rd Street Rd | 62.7373 | 25 | Pri Coll | [13 empty] | 0 |  |  |  | 40944.123 | 69339.51 | October | [16 empty] | Proposed Development may repave McNair. Various base failures, edge of road reconstruction needed. Some sort of shoulder will also be needed. May need to replace driveway on Wisertown Rd with this project, so prioritize for Summer 2019. | 1378.59 | 18 | 24814.62 | 0.40272
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Dannyboy Ln | Ida Way | Dead End | 51 | 25 | Local | [17 empty] | 18463.6 | 127067.01 | September | [17 empty] | 541.4771 | 22 | 11912 | 0.19332
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Hickory Hill Rd | Park Rd | Southview Rd | 52 | 25 | Local | [17 empty] | 24924 | See Dannyboy Ln | September | [17 empty] | 730.9304 | 22 | 16080 | 0.26096
| Hall |  | 350002-352 |  |  | 900 | 999 | Ida Way | Sunnybrook Dr | Dannyboy Ln | 55 | 25 | Local | [17 empty] | 10510.55 | See Dannyboy Ln | September | [17 empty] | 308.2079 | 22 | 6781 | 0.11005
| Hall |  | 350002-352 |  |  | 5300 | 5399 | Southdale Rd | Palatka Rd | Southview Rd | 68.1387 | 25 | Local | [17 empty] | 63858.45 | See Dannyboy Ln | September | [17 empty] | 1872.6681 | 22.0002 | 41199 | 0.66862
| Hall |  | 350002-352 |  |  | 918 | 900 | Southview Rd | Southdale Rd | Palatka Rd | 56.0019 | 25 | Local | [17 empty] | 49846.45 | See Dannyboy Ln | September | [17 empty] | 1339.9785 | 23.9996 | 32159 | 0.52191
| LP |  | 339051-73 |  |  | 9000 | 9302 | Stonestreet Rd | Dixie Hwy | Valley College Dr | 65.9195 | 25 | Min Art | [17 empty] | 296780.55 | 289261.68 | September | [17 empty] | 3575.0904 | 50.3112 | 179867 | 2.9191
| Hall |  | 350002-352 |  |  | 5400 | 5499 | Sunnybrook Dr | Palatka Rd | Dead End | 55.7993 | 25 | Local | [17 empty] | 33266.1 | See Dannyboy Ln | September | [17 empty] | 894.2654 | 23.9996 | 21462 | 0.34831
| Hall |  | 350002-352 |  |  | 900 | 999 | Westview Dr | New Cut Rd | Dead End | 51 | 25 | Local | [17 empty] | 35299.7 | See Dannyboy Ln | September | [17 empty] | 1084.4551 | 21 | 22774 | 0.3696
| Hall |  |  |  |  | 1928-03-13 | 1932-01-11 | Deering Rd/Woodridge Dr | Valley Station Rd | Flowervale Ln | 65.4587 | 25 | Sec Coll | [17 empty] | 272001.708 | [19 empty] | 6879.848 | 23.9612 | 164849.52 | 2.6754
| Hall |  | 350002-257 |  |  | 2700 | 3899 | Klondike Ln | Six Mile Ln | Hikes Ln | 61.6177 | 26 | Pri Coll | [13 empty] | 25 |  |  | 12 | 221552.1 | 333251.79 | July | [16 empty] | Look at cross drain near Six Mile Ln, others which may be present. Probable fiber project. | 6394 | 21 | 134274 | 2.1792
| Hall |  | 350002-384 |  |  | 6012 | 6399 | Dutchmans Ln | Dutchmans Pky | Dutchmans Pky | 46 | 26 | Local | [17 empty] | 142852.65 |  | November | [17 empty] | 2973 | 31 | 92163 | 1.4957
| Hall |  | 350002-368 |  |  | 2900 | 3099 | Bowman Ave | Dutchmans Ln | Dead End | 50.8815 | 26 | Local | [17 empty] | 42772.25 |  | October | See Cannons Ln | [16 empty] | 1404.5798 | 19.6464 | 27595 | 0.44784
| Hall |  | 350002-368 |  |  | 2900 | 2999 | Cannons Ln | Dutchmans Ln | Bowman Ave | 35.207 | 26 | Local | [17 empty] | 32943.7 |  | October | 65596.53 | [16 empty] | 929.1685 | 22.8742 | 21254 | 0.34493
| Hall |  | 350002-368 |  |  | 3500 | 3599 | Ephraim Mcdowell Dr | Cannons Ln | Abigail Dr | 48.9726 | 26 | Local | [17 empty] | 36181.65 |  | October | See Cannons Ln | [16 empty] | 1003.653 | 23.258 | 23343 | 0.37884
| Hall |  | 350002-319 |  |  |  |  | Bashford Manor Ln | Bardstown Rd | Medford Ln |  | 26 | Local | [17 empty] | 42000 | 44370 | September | Council | 8138-410-8107-148387-822702 | 42000 | [13 empty] | Pushed back to FY 21 due to virus
| Hall |  |  |  |  | 3000 | 3014 | Boaires Ln | Talisman Rd | Rio Rita Ave | 47 | 26 | Local | [17 empty] | 17921.1 | [19 empty] | 481.737 | 24 | 11562 | 0.18764
| Hall |  | 350002-383 |  |  | 1908-03-18 | 1909-04-21 | Furman Blvd | Taylorsville Rd | Hikes Ln | 63.8043 | 26 | Pri Coll | [17 empty] | 269468.892 | 50354.23 | [18 empty] | 3983.28 | 41 | 163314.48 | 2.6505
| NA |  |  | 2018-07-01 |  | 3000 | 3499 | Hikes Ln | Klondike Ln | Browns Ln | 57.2165 | 26 | Min Art | [13 empty] | 22 |  |  |  | 603010.8 |  |  | PW Funds |  | 603010.8 | [13 empty] | Will try to group with KYTC and bid seperately, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 5316.81 | 60 | 301505.4 | 4.8932
|  |  |  | 2017-07-01 |  |  |  | Hikes Ln | Klondike Ln | Goldsmith Ln |  | 26 | Min Art | [13 empty] | 20 |  |  |  | 510705 |  |  | PW FUNDS 18 | [15 empty] | Designed by QK4, design nearly complete - will need to fund in phases with first expected to take place in FY 20 | 3483.5026 | 62 | 215977.1635 | 3.5051
| Hall |  | 350002-383 |  |  | 3000 | 3199 | Talisman Rd | Kings Hwy | Boaires Ln | 47.314 | 26 | Local | [17 empty] | 139885.95 | See Furman Blvd | [18 empty] | 3610.2177 | 24.9982 | 90249 | 1.4647
| Hall |  | 350002-371 |  |  |  |  | Mcdeane Base Failure |  |  |  |  | Local | [17 empty] | 70000 | 71609.36 | October
| QK4 |  | 314578-70 |  |  |  |  | QK4 Density Testing | [22 empty] | 20000 | 33186.51 |  | PW Funds | 8672-410-8210-148929-822703 | 20000 | [17 empty] | 0
| QK4 |  | 314578-78 |  |  |  |  | QK4 supplemental Inspections | [22 empty] | 20000 | 51389 |  | PW Funds | 8672-410-8210-148929-822704 | 20000 | [17 empty] | 0
| QK4 |  | 314578-119 |  |  |  |  | St Anthony Slide | [23 empty] | 3575.74 | [21 empty] | 0

## Alleys
PO # | Contractor | Alley Name | From | To | Parallel To | District | Ramps | Alley Match |  | Council Funds |  | Council Funds |  | Other |  | PW Bond | Total Cost | Actual Cost | 50/50 Split | Notes
350002-284 |  | Russell Alley and Kahn Alley | S Clay St | E Breckenridge St | Lampton and Breckenridge | 4 |  | 12500 | 8137-410-8210-148467-822702 | 12500 | 8138-410-8107-148318-822702 | [5 empty] | 25000
350002-285 |  | Eddy ST (E-W and N) | S 18th St | S 19th St | Cedar St and W Muhammad Ali | 4 |  | 15000 | 8137-410-8210-148467-822702 | 15000 | 8138-410-8107-148318-822702 | [5 empty] | 30000
350002-309 |  | Golden Rule Way Alley | S 4th St | S 5th St | Breckenridge and York | 4 |  | 7500 | 8137-410-8210-148467-822702 | 7500 | 8138-410-8107-148318-822702 | [5 empty] | 15000
350002-318 |  | Green Alley | 19th St | 20th St | Jefferson and Cedar | 4 |  | 7905.2 | 8137-410-8210-148467-822702 | 37500 | 8102-410-8105-148793-822702 |  |  | 2094.8 | 8133-410-8210-148450-822803 |  | 47500 |  |  | Remove brick and replace with 12 inch pavement section with asphalt
350002-377 |  | Caldwell Alley | Caldwell St | Breckenridge St | East Caldwell just south of Coke St | 4 |  | 10000 | 8131-410-8210-148937-822702 | 15000 | 8146-410-8107-148793-822702 | [5 empty] | 25000
350002-378 |  | Coke St and Clay St | Coke St | dead end |  | 4 |  | 3457.65 | 8131-410-8210-148937-822702 | 3750 | 8146-410-8107-148793-822702 |  |  | 292.35 | 8115-410-8210-148937-822702 |  | 7500
|  | Whitmore/Lonsdale Alley |  |  |  | 15 |  | 10000 | 8115-410-8210-148937-822702 | 30000 | 8146-410-8107-148925-822702 | [5 empty] | 40000
350002-380 |  | 1000 Block of 43rd Ave | Greenwood Ave | Sunset Ave |  | 1 |  | 2055.85 | 8115-410-8105-148442-822702 | 886.48 | 8101-410-8105-148391-822702 | 14420.11 | 8138-410-8107-148391-822702 | 1137.56 | 8115-410-8210-148937-822702 |  | 18500
350002-381 |  | 4200 Block of Hale | 42nd St | 43rd St | Hale Ave and Virginia Ave | 1 |  | 7310.47 | 8133-410-8210-148450-822702 | 20000 | 8101-410-8105-148391-822702 | 2093.16 | 8101-410-8210-148937-822702 | 596.37 | 8115-410-8105-148442-822702 |  | 30000
|  | Stevens Ave and Arlington Ave Alley | Clifton park Entrance |  |  | 9 |  | 6250 | 8115-410-8210-148987-822702 | 4250 | 8138-410-8107-148227-822705 | [5 empty] | 10500
PO? |  |  | Start | Balance | Account
PO | SW

## Key
Complete
Utility Conflict
Moved to FY 21 due to virus
Concrete Road
Metro Project Pending
Not completed yet
Distribute report to the following:
Daniel Frockt
Benjamin Tipton
Maxwell Bradley
Kellie Watson
Christy Tapp
Aaron Jackson
LaTonya Bell
CC:
Jeff Brown
Vanessa Burns
John Callihan
Ozzy Gibson
Metro Council Staff

## Rating
86-100 | Good
71-85 | Satisfactory
56-70 | Fair
41-55 | Poor
26-40 | Very Poor
11-25 | Serious
0-10 | Failed