## July 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall | [6 empty] | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | [19 empty] | 654.04 | 22 | 14388.88
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220
| Hall |  |  |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | [19 empty] | 4193.0788 | 22.5011 | 94349
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170
| Hall |  |  |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | [18 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057
| Hall |  |  |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | [19 empty] | 674 | 24 | 14370
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934
| LP |  |  |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | [19 empty] | 3141.3701 | 18.0001 | 56545
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152
| Hall |  |  |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | [19 empty] | 6319.7901 | 64.25 | 390254.7693
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154
| LP |  |  |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 | [19 empty] | 8488.84 | 24.375 | 196198.12
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628
| Hall |  |  |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | [19 empty] | 2879.4147 | 39.4858 | 113696
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 58784.5 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 832.3 | [18 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  |  |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253
| Hall |  |  |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | [19 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143
| Hall |  |  |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181
| Hall |  |  |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715
| Hall | [6 empty] | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 7213.09 |  | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 19797.88 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Additional Sdiewa |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105088.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218
| Hall |  |  |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | [19 empty] | 2502 | 24 | 60236
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189
| Hall |  |  |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | [19 empty] | 1265.37 | 18 | 22776.66
| Hall |  |  |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | [19 empty] | 1631.927 | 21.1946 | 34588
| Hall |  |  |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | [19 empty] | 1743 | 20.9966 | 36597
| Hall | [6 empty] | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | [19 empty] | 209.31 | 12 | 2511.72
| Hall |  |  |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | [19 empty] | 621 | 34.0209 | 21127
| Hall |  |  |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | [19 empty] | 423.4543 | 20.6114 | 8728
| Hall | [6 empty] | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | [19 empty] | 1445.54 | 27.5 | 39545.4
| Hall |  |  |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | [19 empty] | 1457 | 19.9973 | 29136
| Hall |  |  |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797
| Hall |  |  |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | [19 empty] | 1512.9948 | 24.0001 | 36312
| Hall |  |  |  |  | 2900 | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | [19 empty] | 642 | 20 | 12838
| Hall |  |  |  |  | 2700 | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | [19 empty] | 1426.064 | 19.9998 | 28521
| Hall |  |  |  |  | 2516 | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205
| Hall |  |  |  |  | 2600 | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | [19 empty] | 212 | 22 | 4665
| Hall |  |  |  |  | 2900 | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | [19 empty] | 243 | 22 | 5340
| Hall |  |  |  |  | 300 | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | [19 empty] | 1916.6368 | 26.0008 | 49834
| Hall |  |  |  |  | 300 | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | [19 empty] | 754.6547 | 23.1232 | 17450
| Hall |  |  |  |  | 2700 | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | [19 empty] | 3068.9028 | 21.4986 | 65977
| Hall |  |  |  |  | 400 | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | [19 empty] | 1390.1485 | 20.8719 | 29015
| Hall |  |  |  |  | 3000 | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | [19 empty] | 350 | 26 | 9107
| Hall |  |  |  |  | 800 | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | [19 empty] | 4433.884 | 21.5831 | 95697
| Hall |  |  |  |  | 1500 | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | [19 empty] | 1662.8415 | 19.2676 | 32039
| Hall |  |  |  |  | 1100 | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | [19 empty] | 527.1789 | 21.285 | 11221
| Hall |  |  |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | [19 empty] | 1690.9463 | 18.0006 | 30437
| Hall |  |  |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | [19 empty] | 1377.761 | 19.319 | 26617
| Hall |  |  |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | [19 empty] | 1128.8777 | 17.9603 | 20275
| Hall |  |  |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | [19 empty] | 1139.5186 | 17.4302 | 19861
| Hall |  |  |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | [19 empty] | 1146.4449 | 18.0009 | 20637
| Hall |  |  |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | [19 empty] | 3297.0021 | 17.9997 | 59345
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall |  |  |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | [19 empty] | 1847.1254 | 24 | 44331
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall |  |  |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | [19 empty] | 185 | 26 | 4823
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 |  |  | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall |  |  |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | [19 empty] | 2527 | 19 | 48019
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597
| Hall |  |  |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030
| Hall |  |  |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | [19 empty] | 2063 | 18 | 37141
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | See Baymeadow Dr | [18 empty] | 208 | 18 | 3742 | 0.060729
| LP |  |  |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | [19 empty] | 2200.5175 | 19.9998 | 44010
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | [19 empty] | 443 | 24 | 10637
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | [19 empty] | 5127.0331 | 36 | 184573
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787
| LP |  |  |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | [18 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | [18 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | [19 empty] | 592 | 36 | 21302
| LP |  |  |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | [19 empty] | 8596.7384 | 19.4165 | 166919
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | [19 empty] | 740.5 | 24 | 17772
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | [19 empty] | 1385.96 | 24 | 33263.04
| LP |  |  |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | [19 empty] | 7713.7136 | 21.6364 | 163943.8394
| LP |  |  |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | [19 empty] | 3562.8483 | 20 | 71256.9659
| Hall |  |  |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | [19 empty] | 2151.3634 | 22.6596 | 48749
| Hall |  |  |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | [19 empty] | 1327.8536 | 24.0004 | 31868
| Hall |  |  |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | [19 empty] | 1439.3365 | 24.0006 | 34544
| LP |  |  |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | [19 empty] | 4819.9565 | 22.4809 | 108355
| Hall |  |  |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | [19 empty] | 1015.1661 | 24 | 24364
| Hall |  |  |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | [19 empty] | 1322.5463 | 24 | 31741
| Hall |  |  |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | [19 empty] | 2307.7144 | 24.0004 | 55386
| Hall |  |  |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | [19 empty] | 787.2275 | 23.9994 | 18893
| Hall |  | 350002-198 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 8968.35 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | [19 empty] | 3015.23 | 24.3333 | 72903.68
| Hall |  |  |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580
| Hall |  |  |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086
| Hall |  |  |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357
| Hall |  |  |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007
| Hall |  |  |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600
| Hall |  |  |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243
| Hall |  |  |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 |  | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 |  | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 19627.4 |  | Council | 8133 410 8210 048101 822702 | 9500
| Hall |  |  |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | [19 empty] | 2453.0901 | 32.4342 | 79564
| Hall |  |  |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | [19 empty] | 436 | 22 | 9587
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct |  | Council | 8676-410-8106-048101-822702 | 13250
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 8529.38 |  | Council | 8133 410 8210 048101 822702 | 41000
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct |  | Council | 8133 410 8107 048101 822702 | 4500
| LP |  |  |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | [19 empty] | 10499.6325 | 23.1 | 235798.657
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct |  | Council | 8133 410 8210 048101 822702 | 6750
| LP | [6 empty] | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 |  |  | CIF | 8148-410-8107-148576-822702 | 110000
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct |  | Council | 8133 410 8210 048101 822702 | 7000
| Hall | [6 empty] | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local
| Hall |  |  |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | [19 empty] | 1120.6118 | 23.3605 | 26178
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  |  |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314
| Hall |  |  |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388
| Hall |  |  |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | [19 empty] | 5810 | 24 | 126087
| Hall |  |  |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910
| Hall |  |  |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area
| Hall |  |  |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019
| Hall |  |  |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463
| Hall |  |  |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019
| Hall |  |  |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | [19 empty] | 2569.24 | 24 | 61661.76
| Hall |  |  |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | [19 empty] | 2330.1716 | 23.9999 | 55924
| Hall |  |  |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | [19 empty] | 740 | 23 | 17019
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [17 empty] | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 |  | July | Council | 8133 410 8210 048101 822702 | 86472.74
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 |  | July | [17 empty] | 4421 | 44.4627 | 205841
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | [19 empty] | 10927.1148 | 19.8246 | 216626
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | [19 empty] | 20311 | 23 | 447535
| Hall |  |  |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | [19 empty] | 480 | 18 | 8644
| Hall |  |  |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | [19 empty] | 554 | 22 | 12197
| Hall |  |  |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | [19 empty] | 552 | 24 | 13241
| Hall |  |  |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | [19 empty] | 168 | 16 | 2680
| Hall |  |  |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | [19 empty] | 1064 | 23 | 24098
| Hall |  |  |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | [19 empty] | 157 | 18 | 2831
| Hall |  |  |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | [19 empty] | 923 | 34 | 31382
| Hall |  |  |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | [19 empty] | 240 | 22 | 5283
| Hall |  |  |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | [19 empty] | 480 | 18 | 8645
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | [19 empty] | 1674 | 24 | 40175
| Hall |  |  |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | [19 empty] | 2273 | 24 | 54556
| Hall |  |  |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | [19 empty] | 149 | 18 | 2677
| Hall |  |  |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | [19 empty] | 1958 | 23 | 44346
| Hall |  |  |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | [19 empty] | 310 | 22 | 6828
| Hall |  |  |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428
| Hall |  |  |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  |  |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792
| Hall |  |  |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642
| Hall |  |  |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906
| Hall |  |  |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98
| Hall |  |  |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693
| LP |  |  |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [18 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| LP |  |  |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | [18 empty] | may require road widening | 20702.2291 | 18.6818 | 386754
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646
| LP |  |  |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | [19 empty] | 3889.3639 | 15.9998 | 62229
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682
| Hall |  |  |  |  | 5900 | 6099 | Bay Pine Dr | Michael Ray Dr | Acme Way | 45 | 23 | Local | [17 empty] | 58526.45 | [19 empty] | 1573.2882 | 24.0001 | 37759
| Hall |  |  |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | [19 empty] | 1162.89 | 24 | 27909.36
| Hall |  |  |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | [19 empty] | 5482.3638 | 23.4665 | 128652
| Hall |  |  |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | [19 empty] | 1218.9502 | 23.2799 | 28377
| Hall |  |  |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | [19 empty] | 463 | 20 | 9268
| Hall |  |  |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | [19 empty] | 621.3517 | 25.9998 | 16155
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628
| LP |  |  |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 |  | July | [17 empty] | 2814.6936 | 55.794 | 157043
| Hall |  |  |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | [19 empty] | 1128.4374 | 25.9997 | 29339
| Hall | [6 empty] | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall |  |  |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | [19 empty] | 4254 | 23.2972 | 99079
| Hall | [6 empty] | Heavenly Way | Moonlight Way | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall |  |  |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | [18 empty] | verify jurisdiction | 3055.0091 | 14.9466 | 45662
| Hall |  |  |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | [19 empty] | 237.4801 | 22 | 5225
| Hall |  |  |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | [19 empty] | 552.9736 | 21.9992 | 12165
| Hall | [6 empty] | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657
| Hall | [6 empty] | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [21 empty] | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000
| Hall | [6 empty] | Alvarado Way | Woodluck Way | Dead End |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | [17 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649
| Hall |  |  |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | [19 empty] | 351 | 24 | 8419
| Hall | [6 empty] | Garden Way | Almara Cir | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 54103.14 | [18 empty] | 2633.616 | 49.9644 | 131587
| Hall |  |  |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | [19 empty] | 3135.2059 | 23.8364 | 74732
| Hall |  |  |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | [19 empty] | 1433.545 | 23.7844 | 34096
| Hall |  |  |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | [19 empty] | 1339 | 22 | 29454
| Hall | [6 empty] | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [21 empty] | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638
| Hall |  |  |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | [19 empty] | 2287.0094 | 21.9999 | 50314
| Hall | [6 empty] | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln

## August 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall | [6 empty] | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | [19 empty] | 654.04 | 22 | 14388.88
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220
| Hall |  |  |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | [19 empty] | 4193.0788 | 22.5011 | 94349
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 |  | August | [17 empty] | 3141.3701 | 18.0001 | 56545
| Hall |  |  |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | [18 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057
| Hall |  |  |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | [19 empty] | 674 | 24 | 14370
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152
| Hall |  |  |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | [19 empty] | 6319.7901 | 64.25 | 390254.7693
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154
| LP |  |  |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 | [19 empty] | 8488.84 | 24.375 | 196198.12
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 47904.55 | [18 empty] | 2879.4147 | 39.4858 | 113696
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39443.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 267855.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 278756.02 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Additional Sdiewa |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105088.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218
| Hall |  |  |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | [19 empty] | 2502 | 24 | 60236
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 4668.78 | [18 empty] | 1265.37 | 18 | 22776.66
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | [19 empty] | 1631.927 | 21.1946 | 34588
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | [19 empty] | 1743 | 20.9966 | 36597
| Hall | [6 empty] | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | [19 empty] | 209.31 | 12 | 2511.72
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 4700.95 | [18 empty] | 621 | 34.0209 | 21127
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | [19 empty] | 423.4543 | 20.6114 | 8728
| Hall | [6 empty] | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 18706.41 | [18 empty] | 1445.54 | 27.5 | 39545.4
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | [19 empty] | 1457 | 19.9973 | 29136
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | [19 empty] | 1512.9948 | 24.0001 | 36312
| Hall |  |  |  |  | 2900 | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | [19 empty] | 642 | 20 | 12838
| Hall |  |  |  |  | 2700 | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | [19 empty] | 1426.064 | 19.9998 | 28521
| Hall |  |  |  |  | 2516 | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205
| Hall |  |  |  |  | 2600 | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | [19 empty] | 212 | 22 | 4665
| Hall |  |  |  |  | 2900 | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | [19 empty] | 243 | 22 | 5340
| Hall |  |  |  |  | 300 | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | [19 empty] | 1916.6368 | 26.0008 | 49834
| Hall |  |  |  |  | 300 | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | [19 empty] | 754.6547 | 23.1232 | 17450
| Hall |  |  |  |  | 2700 | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | [19 empty] | 3068.9028 | 21.4986 | 65977
| Hall |  | 350002-479 |  |  |  |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 |  | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs.
| Hall |  |  |  |  | 400 | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | [19 empty] | 1390.1485 | 20.8719 | 29015
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | [19 empty] | 350 | 26 | 9107
| Hall |  | 350002-475 |  |  | 800 | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | [19 empty] | 4433.884 | 21.5831 | 95697
| Hall |  | 350002-475 |  |  | 1500 | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | [19 empty] | 1662.8415 | 19.2676 | 32039
| Hall |  | 350002-475 |  |  | 1100 | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | [19 empty] | 527.1789 | 21.285 | 11221
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | [19 empty] | 1690.9463 | 18.0006 | 30437
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | [19 empty] | 1377.761 | 19.319 | 26617
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | [19 empty] | 1128.8777 | 17.9603 | 20275
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | [19 empty] | 1139.5186 | 17.4302 | 19861
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | [19 empty] | 1146.4449 | 18.0009 | 20637
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | [19 empty] | 3297.0021 | 17.9997 | 59345
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 |  | August | [17 empty] | 1847.1254 | 24 | 44331
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 |  | August | [17 empty] | 185 | 26 | 4823
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 |  | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  |  |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | [19 empty] | 2527 | 19 | 48019
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597
| Hall |  |  |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030
| Hall |  |  |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | [19 empty] | 2063 | 18 | 37141
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 473432.84 | August | [17 empty] | 5127.0331 | 36 | 184573
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302
| LP |  |  |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | [19 empty] | 2200.5175 | 19.9998 | 44010
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787
| LP |  |  |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | [18 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756
| LP |  |  |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | [19 empty] | 8596.7384 | 19.4165 | 166919
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 |  | August | [17 empty] | 4819.9565 | 22.4809 | 108355
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | [19 empty] | 740.5 | 24 | 17772
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | [19 empty] | 1385.96 | 24 | 33263.04
| LP |  |  |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | [19 empty] | 7713.7136 | 21.6364 | 163943.8394
| LP |  |  |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | [19 empty] | 3562.8483 | 20 | 71256.9659
| Hall |  |  |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | [19 empty] | 2151.3634 | 22.6596 | 48749
| Hall |  |  |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | [19 empty] | 1327.8536 | 24.0004 | 31868
| Hall |  |  |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | [19 empty] | 1439.3365 | 24.0006 | 34544
| Hall |  |  |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | [19 empty] | 1015.1661 | 24 | 24364
| Hall |  |  |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | [19 empty] | 1322.5463 | 24 | 31741
| Hall |  |  |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | [19 empty] | 2307.7144 | 24.0004 | 55386
| Hall |  |  |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | [19 empty] | 787.2275 | 23.9994 | 18893
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | [19 empty] | 3015.23 | 24.3333 | 72903.68
| Hall |  |  |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580
| Hall |  |  |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086
| Hall |  |  |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357
| Hall |  |  |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007
| Hall |  |  |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600
| Hall |  |  |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243
| Hall |  |  |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 52982.72 | August | Council | 8133 410 8210 048101 822702 | 9500
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | [19 empty] | 2453.0901 | 32.4342 | 79564
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | [19 empty] | 436 | 22 | 9587
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23
| LP |  |  |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | [19 empty] | 10499.6325 | 23.1 | 235798.657
| LP | [6 empty] | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 |  |  | CIF | 8148-410-8107-148576-822702 | 110000
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | [19 empty] | 1120.6118 | 23.3605 | 26178
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  |  |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314
| Hall |  |  |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388
| Hall |  |  |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | [19 empty] | 5810 | 24 | 126087
| Hall |  |  |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910
| Hall |  |  |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area
| Hall |  |  |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019
| Hall |  |  |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463
| Hall |  |  |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 13210.29 | [18 empty] | 2569.24 | 24 | 61661.76
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 34296.11 | [18 empty] | 2330.1716 | 23.9999 | 55924
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Rockwood | [18 empty] | 740 | 23 | 17019
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 |  | August | [17 empty] | 20311 | 23 | 447535
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 305015.16 | July | Council | 8133 410 8210 048101 822702 | 86472.74
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 |  | July | [17 empty] | 4421 | 44.4627 | 205841
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | [19 empty] | 10927.1148 | 19.8246 | 216626
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892
| Hall |  |  |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | [19 empty] | 480 | 18 | 8644
| Hall |  |  |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | [19 empty] | 554 | 22 | 12197
| Hall |  |  |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | [19 empty] | 552 | 24 | 13241
| Hall |  |  |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | [19 empty] | 168 | 16 | 2680
| Hall |  |  |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | [19 empty] | 1064 | 23 | 24098
| Hall |  |  |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | [19 empty] | 157 | 18 | 2831
| Hall |  |  |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | [19 empty] | 923 | 34 | 31382
| Hall |  |  |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | [19 empty] | 240 | 22 | 5283
| Hall |  |  |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | [19 empty] | 480 | 18 | 8645
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | [19 empty] | 1674 | 24 | 40175
| Hall |  |  |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | [19 empty] | 2273 | 24 | 54556
| Hall |  |  |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | [19 empty] | 149 | 18 | 2677
| Hall |  |  |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | [19 empty] | 1958 | 23 | 44346
| Hall |  |  |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | [19 empty] | 310 | 22 | 6828
| Hall |  |  |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428
| Hall |  |  |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  |  |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792
| Hall |  |  |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642
| Hall |  |  |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906
| Hall |  |  |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98
| Hall |  |  |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | [18 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | [18 empty] | may require road widening | 20702.2291 | 18.6818 | 386754
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | [19 empty] | 3889.3639 | 15.9998 | 62229
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682
| Hall | [6 empty] | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local
| Hall | [6 empty] | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local
| Hall |  |  |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | [19 empty] | 1162.89 | 24 | 27909.36
| Hall | [6 empty] | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local
| Hall | [6 empty] | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local
| Hall | [6 empty] | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local
| Hall |  |  |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | [19 empty] | 5482.3638 | 23.4665 | 128652
| Hall | [6 empty] | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local
| Hall |  |  |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | [19 empty] | 1218.9502 | 23.2799 | 28377
| Hall | [6 empty] | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local
| Hall |  |  |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | [19 empty] | 463 | 20 | 9268
| Hall |  |  |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | [19 empty] | 621.3517 | 25.9998 | 16155
| Hall | [6 empty] | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 |  | July | [17 empty] | 2814.6936 | 55.794 | 157043
| Hall |  |  |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | [19 empty] | 1128.4374 | 25.9997 | 29339
| Hall | [6 empty] | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall |  |  |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | [19 empty] | 4254 | 23.2972 | 99079
| Hall | [6 empty] | Heavenly Way | Moonlight Way | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall |  |  |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | [18 empty] | verify jurisdiction | 3055.0091 | 14.9466 | 45662
| Hall |  |  |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | [19 empty] | 237.4801 | 22 | 5225
| Hall |  |  |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | [19 empty] | 552.9736 | 21.9992 | 12165
| Hall | [6 empty] | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [21 empty] | CIF | See Sunlight Ln
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657
| Hall | [6 empty] | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [21 empty] | CIF | See Sunlight Ln
| Hall | [6 empty] | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [21 empty] | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 |  | August | [17 empty] | 351 | 24 | 8419
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 |  | August | [17 empty] | 3135.2059 | 23.8364 | 74732
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 |  | August | [17 empty] | 1433.545 | 23.7844 | 34096
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 |  | August | [17 empty] | 1339 | 22 | 29454
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 |  | August | [17 empty] | 2287.0094 | 21.9999 | 50314
| Hall | [6 empty] | Alvarado Way | Woodluck Way | Dead End |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | [17 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649
| Hall | [6 empty] | Garden Way | Almara Cir | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 54103.14 | [18 empty] | 2633.616 | 49.9644 | 131587
| Hall | [6 empty] | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [21 empty] | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638
| Hall | [6 empty] | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln

## Sept 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall | [6 empty] | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | [19 empty] | 654.04 | 22 | 14388.88
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84
| Flynn |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Flynn |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Flynn |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220
| Hall |  |  |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | [19 empty] | 4193.0788 | 22.5011 | 94349
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545
| Hall |  |  |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | [18 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057
| Hall |  |  |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | [19 empty] | 674 | 24 | 14370
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152
| Hall |  |  |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | [19 empty] | 6319.7901 | 64.25 | 390254.7693
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154
| LP |  |  |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 | [19 empty] | 8488.84 | 24.375 | 196198.12
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 47904.55 | [18 empty] | 2879.4147 | 39.4858 | 113696
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39443.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 293273.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Additional Sdiewa |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105088.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218
| Hall |  |  |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | [19 empty] | 2502 | 24 | 60236
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 4668.78 | September | [17 empty] | 1265.37 | 18 | 22776.66
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | [19 empty] | 1631.927 | 21.1946 | 34588
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | [19 empty] | 1743 | 20.9966 | 36597
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | [19 empty] | 209.31 | 12 | 2511.72
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 4700.95 | [18 empty] | 621 | 34.0209 | 21127
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | [19 empty] | 423.4543 | 20.6114 | 8728
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 18706.41 | [18 empty] | 1445.54 | 27.5 | 39545.4
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | [19 empty] | 1457 | 19.9973 | 29136
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | [19 empty] | 1512.9948 | 24.0001 | 36312
| Hall |  |  |  |  | 2900 | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | [19 empty] | 642 | 20 | 12838
| Hall |  |  |  |  | 2700 | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | [19 empty] | 1426.064 | 19.9998 | 28521
| Hall |  |  |  |  | 2516 | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205
| Hall |  |  |  |  | 2600 | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | [19 empty] | 212 | 22 | 4665
| Hall |  |  |  |  | 2900 | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | [19 empty] | 243 | 22 | 5340
| Hall |  |  |  |  | 300 | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | [19 empty] | 1916.6368 | 26.0008 | 49834
| Hall |  |  |  |  | 300 | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | [19 empty] | 754.6547 | 23.1232 | 17450
| Hall |  |  |  |  | 2700 | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | [19 empty] | 3068.9028 | 21.4986 | 65977
| Hall |  | 350002-480 |  |  |  |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs.
| Hall |  |  |  |  | 400 | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | [19 empty] | 1390.1485 | 20.8719 | 29015
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107
| Hall |  | 350002-475 |  |  | 800 | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 60155.23 | September | [17 empty] | 4433.884 | 21.5831 | 95697
| Hall |  | 350002-475 |  |  | 1500 | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039
| Hall |  | 350002-475 |  |  | 1100 | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51275.01 | August | [17 empty] | 1847.1254 | 24 | 44331
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  |  |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | [19 empty] | 2527 | 19 | 48019
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597
| Hall |  |  |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030
| Hall |  |  |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | [19 empty] | 2063 | 18 | 37141
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 473432.84 | August | [17 empty] | 5127.0331 | 36 | 184573
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302
| LP |  |  |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | [19 empty] | 2200.5175 | 19.9998 | 44010
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787
| LP |  |  |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | [18 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756
| LP |  |  |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | [19 empty] | 8596.7384 | 19.4165 | 166919
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | [19 empty] | 740.5 | 24 | 17772
| Hall |  |  |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | [19 empty] | 1385.96 | 24 | 33263.04
| LP |  |  |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | [19 empty] | 7713.7136 | 21.6364 | 163943.8394
| LP |  |  |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | [19 empty] | 3562.8483 | 20 | 71256.9659
| Hall |  |  |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | [19 empty] | 2151.3634 | 22.6596 | 48749
| Hall |  |  |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | [19 empty] | 1327.8536 | 24.0004 | 31868
| Hall |  |  |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | [19 empty] | 1439.3365 | 24.0006 | 34544
| Hall |  |  |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | [19 empty] | 1015.1661 | 24 | 24364
| Hall |  |  |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | [19 empty] | 1322.5463 | 24 | 31741
| Hall |  |  |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | [19 empty] | 2307.7144 | 24.0004 | 55386
| Hall |  |  |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | [19 empty] | 787.2275 | 23.9994 | 18893
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  |  |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | [19 empty] | 3015.23 | 24.3333 | 72903.68
| Hall |  |  |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580
| Hall |  |  |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086
| Hall |  |  |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357
| Hall |  |  |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007
| Hall |  |  |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600
| Hall |  |  |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243
| Hall |  |  |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23
| LP |  |  |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | [19 empty] | 10499.6325 | 23.1 | 235798.657
| LP | [6 empty] | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 |  |  | CIF | 8148-410-8107-148576-822702 | 110000
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  |  |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314
| Hall |  |  |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388
| Hall |  |  |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | [19 empty] | 5810 | 24 | 126087
| Hall |  |  |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910
| Hall |  |  |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area
| Hall |  |  |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019
| Hall |  |  |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463
| Hall |  |  |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 13210.29 | [18 empty] | 2569.24 | 24 | 61661.76
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 34296.11 | [18 empty] | 2330.1716 | 23.9999 | 55924
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Rockwood | [18 empty] | 740 | 23 | 17019
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 305015.16 | July | Council | 8133 410 8210 048101 822702 | 86472.74
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892
| Hall |  |  |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | [19 empty] | 480 | 18 | 8644
| Hall |  |  |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | [19 empty] | 554 | 22 | 12197
| Hall |  |  |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | [19 empty] | 552 | 24 | 13241
| Hall |  |  |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | [19 empty] | 168 | 16 | 2680
| Hall |  |  |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | [19 empty] | 1064 | 23 | 24098
| Hall |  |  |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | [19 empty] | 157 | 18 | 2831
| Hall |  |  |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | [19 empty] | 923 | 34 | 31382
| Hall |  |  |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | [19 empty] | 240 | 22 | 5283
| Hall |  |  |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | [19 empty] | 480 | 18 | 8645
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | [19 empty] | 1674 | 24 | 40175
| Hall |  |  |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | [19 empty] | 2273 | 24 | 54556
| Hall |  |  |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | [19 empty] | 149 | 18 | 2677
| Hall |  |  |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | [19 empty] | 1958 | 23 | 44346
| Hall |  |  |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | [19 empty] | 310 | 22 | 6828
| Hall |  |  |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428
| Hall |  |  |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034
| Hall |  |  |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  |  |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  |  |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792
| Hall |  |  |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642
| Hall |  |  |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906
| Hall |  |  |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98
| Hall |  |  |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 319266.47 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 25117.69 | [17 empty] | may require road widening | 20702.2291 | 18.6818 | 386754
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 6431.33 | [18 empty] | 3889.3639 | 15.9998 | 62229
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682
| Hall | [6 empty] | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local
| Hall | [6 empty] | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local
| Hall |  |  |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | [19 empty] | 1162.89 | 24 | 27909.36
| Hall | [6 empty] | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local
| Hall | [6 empty] | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local
| Hall | [6 empty] | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local
| Hall |  |  |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | [19 empty] | 5482.3638 | 23.4665 | 128652
| Hall | [6 empty] | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local
| Hall |  |  |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | [19 empty] | 1218.9502 | 23.2799 | 28377
| Hall | [6 empty] | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local
| Hall |  |  |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | [19 empty] | 463 | 20 | 9268
| Hall |  |  |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | [19 empty] | 621.3517 | 25.9998 | 16155
| Hall | [6 empty] | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order
| Flynn |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043
| Hall |  |  |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | [19 empty] | 1128.4374 | 25.9997 | 29339
| Hall | [6 empty] | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall |  |  |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | [19 empty] | 4254 | 23.2972 | 99079
| Hall | [6 empty] | Heavenly Way | Moonlight Way | Dead End |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall | [6 empty] | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall | [6 empty] | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall |  |  |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | [18 empty] | verify jurisdiction | 3055.0091 | 14.9466 | 45662
| Hall |  |  |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | [19 empty] | 237.4801 | 22 | 5225
| Hall |  |  |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | [19 empty] | 552.9736 | 21.9992 | 12165
| Hall | [6 empty] | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall | [6 empty] | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657
| Hall | [6 empty] | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [20 empty] | September | CIF | See Sunlight Ln
| Hall | [6 empty] | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [20 empty] | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 308980.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314
| Hall | [6 empty] | Alvarado Way | Woodluck Way | Dead End |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649
| Hall | [6 empty] | Garden Way | Almara Cir | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 197590.1 | september | [17 empty] | 2633.616 | 49.9644 | 131587
| Hall | [6 empty] | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [21 empty] | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638
| Hall | [6 empty] | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln

## Oct 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall | [6 empty] | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | [19 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  |  |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | [19 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  |  |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | [18 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  |  |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | [19 empty] | 674 | 24 | 14370 | 0.23321
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  |  |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | [19 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| LP |  |  |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 | [19 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 47904.55 | [18 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39443.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July | [20 empty] | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 293273.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105088.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  |  |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | [19 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 |  | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 4700.95 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 18706.41 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | [19 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | [19 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | [19 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | [19 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | [19 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | [19 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | [19 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | [19 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 606247.05 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51275.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 |  | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 |  | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 473432.84 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  |  |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | [19 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000 | [14 empty] | 0
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787 | 0.06146
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | [18 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | [19 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | [19 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | [19 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  |  |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | [19 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | [19 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | [19 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | [19 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | [19 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | [19 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | [19 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | [19 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | [19 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | [19 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  |  |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  |  |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  |  |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  |  |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  |  |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  |  |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | [19 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 |  |  | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  |  |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  |  |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  |  |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | [19 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  |  |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  |  |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  |  |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  |  |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  |  |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 13210.29 | [18 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 34296.11 | [18 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Rockwood | [18 empty] | 740 | 23 | 17019 | 0.2762
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 305015.16 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  |  |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | [19 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  |  |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | [19 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  |  |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | [19 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  |  |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | [19 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  |  |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | [19 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  |  |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | [19 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  |  |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | [19 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  |  |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | [19 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  |  |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | [19 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  |  |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | [19 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  |  |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | [19 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  |  |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | [19 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  |  |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | [19 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  |  |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | [19 empty] | 310 | 22 | 6828 | 0.11081
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 670680.22 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 82752.61 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 319266.47 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 |  |  | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [39 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [39 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | [19 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [39 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [39 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [39 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | [19 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [39 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | [19 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [39 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | [19 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | [19 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [39 empty] | 6309 | 0.10239
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
| Hall |  |  |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | [19 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  |  |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | [19 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  |  |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | [18 empty] | verify jurisdiction | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  |  |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | [19 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  |  |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | [19 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 308980.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 404228.2 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Hall | [6 empty] | Alvarado Way | Woodluck Way | Dead End |  | 26 | [21 empty] | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall | [6 empty] | Garden Way | Almara Cir | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall | [6 empty] | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [21 empty] | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall | [6 empty] | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [21 empty] | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 |  |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds

## Nov 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.47 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 |  | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 161405.24 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| LP |  |  |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 | [19 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July | [20 empty] | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 51129.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | [18 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | [18 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | [18 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | [18 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | [18 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | [18 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 44365.58 | [18 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | [18 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 615620.51 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | [18 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000 | [14 empty] | 0
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787 | 0.06146
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | [17 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | [19 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 |  | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | [18 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 41397.86 | [18 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  |  |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | [19 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | [18 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | [18 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | [18 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | [18 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | [18 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | [18 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | [18 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | [19 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  |  |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  |  |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  |  |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  |  |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  |  |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  |  |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 |  | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 |  | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  |  |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  |  |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 202188.7 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  |  |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  |  |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  |  |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  |  |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  |  |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 13210.29 | [18 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 34296.11 | [18 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Rockwood | [18 empty] | 740 | 23 | 17019 | 0.2762
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | [19 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | [19 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 19877.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | [19 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | [19 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | [19 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 86470.31 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
| Hall |  |  |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | [19 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  |  |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | [19 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  |  |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | [18 empty] | verify jurisdiction | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  |  |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | [19 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  |  |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | [19 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian |  | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian |  | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 6862.7 |  | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian |  | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 |  |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800

## Dec 21
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.48 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 361162.08 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [17 empty] | 323726.898 |  | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 34683.36 | July | [20 empty] | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 275758.76 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 615725.01 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370325.87 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000 | [14 empty] | 0
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 41397.86 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [17 empty] | 270507.3349 | 259345.77 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | [18 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | [19 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | [19 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | [19 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376872.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 202188.7 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [17 empty] | 29443.8 | [19 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | [18 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | [18 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 39104.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | [18 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | [18 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 41474.37 | [18 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  |  |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  |  |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | [19 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  |  |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  |  |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  |  |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  |  |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  |  |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  |  |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  |  |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  |  |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  |  |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | [18 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 23445.81 | [18 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | [18 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | [18 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152.01 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 10000 |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800

## Jan 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  |  |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  |  |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  |  |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.48 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  |  |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 39000 |  |  | CIF | 8146-410-8210-148413-822702 | 14000 |  | 8148-410-8107-148574-822702 | 25000 | [14 empty] | 0
| Hall |  |  |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  |  |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  |  |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  |  |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  |  |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  |  |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  |  |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 339120.82 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | [18 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | [19 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | [19 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | [18 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | [19 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 59095.34 | [18 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | [18 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | [19 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 202188.7 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | 67209.73 | [18 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  |  |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  |  |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  |  |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | [18 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | [18 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 39104.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | [18 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | [18 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 41474.37 | [18 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 79426.35 | [18 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | [18 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 23445.81 | [18 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | [18 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | [18 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 10000 |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800

## Feb 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-554 |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | [19 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  | 350002-554 |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | [19 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  | 350002-554 |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | [19 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-554 |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | [19 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  | 350002-554 |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | [19 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.48 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  | 350002-554 |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | [19 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  |  |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  |  |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall | [6 empty] | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  |  |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  |  |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  |  |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  |  |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  |  |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  |  |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall | [6 empty] | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall | [6 empty] | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall | [6 empty] | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall | [6 empty] | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
[8 empty] | Guthrie St | S 2nd St | S 4th St |  | 4 | Local | [36 empty] | Pave only that which had not been paved previously. No ramps
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [19 empty] | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  |  |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | [18 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  |  |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | [19 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  |  |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | [19 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  |  |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | [18 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall | [6 empty] | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall | [6 empty] | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall | [6 empty] | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall | [6 empty] | Coverbrook Ct | Stonyrun Dr | Dead End |  | 11 | Local
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall | [6 empty] | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall | [6 empty] | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall | [6 empty] | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall | [6 empty] | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall | [6 empty] | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  |  |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall | [6 empty] | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
[8 empty] | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| Hall |  | 350002-553 |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | [19 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | [19 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  | 350002-553 |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | [19 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  | 350002-553 |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | [19 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  | 350002-553 |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | [19 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | [19 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  | 350002-552 |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 339120.82 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | [18 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | See Brentwood | [18 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | 54743.76 | [18 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | [18 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | See Brentwood | [18 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 59095.34 | [18 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | [18 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | See Brentwood | [18 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 202188.7 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | 67209.73 | [18 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  | 350002-551 |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | [19 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  | 350002-551 |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | [19 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  | 350002-551 |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | [19 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
[8 empty] | Foxboro Dr | Vannah Ave | Dorsey Way |  | 18 | Local | [17 empty] | 128000 |  |  | Council | 8148-410-8107-148580-822702
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  |  |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | [18 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | [18 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 39104.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | [18 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | [18 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 41474.37 | [18 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | [19 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | [19 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | [19 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | [19 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | [19 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | [19 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | [19 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | [19 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 79426.35 | [18 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
|  |  | 350002-555 |  |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  |  |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | [19 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  |  |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | [19 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  |  |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | [19 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  |  |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | [19 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  |  |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | [18 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 59691.83 | [18 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | [18 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | [18 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| LP |  |  |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 37585.62 |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800

## March 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-554 |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | 53022.19 | [18 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  | 350002-554 |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | See Cecil Ave | [18 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  | 350002-554 |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | See Cecil Ave | [18 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-554 |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | See Cecil Ave | [18 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  | 350002-554 |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | See Cecil Ave | [18 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.48 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  | 350002-554 |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | See Cecil Ave | [18 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  | 350002-567 |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  | 350002-567 |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall |  | 350002-567 |  |  |  |  | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  | 350002-536 |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  | 350002-567 |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  | 350002-567 |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall |  | 350002-568 |  |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  | 350002-568 |  |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  | 350002-568 |  |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-568 |  |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  | 350002-565 |  |  |  |  | Guthrie St | S 2nd St | S 4th St |  | 4 | Local | [17 empty] | 50000 | [18 empty] | Pave only that which had not been paved previously. No ramps
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-564 |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | 7746.71 | [17 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  | 350002-564 |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | 12122.47 | [18 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  | 350002-564 |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | 4892.93 | [18 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  | 350002-564 |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | See Maricopa Ct | [17 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall |  | 350002-556 |  |  |  |  | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall |  | 350002-556 |  |  |  |  | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall |  | 350002-556 |  |  |  |  | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall | [6 empty] | Coverbrook Ct | Stonyrun Dr | Dead End |  | 11 | Local
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall |  | 350002-557 |  |  |  |  | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall |  | 350002-556 |  |  |  |  | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  | 350002-566 |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall |  | 350002-557 |  |  |  |  | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
|  |  | 350002-560 |  |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| Hall |  | 350002-553 |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | See Southacres Dr | [18 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | See Southacres Dr | [18 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  | 350002-553 |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | See Southacres Dr | [18 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  | 350002-553 |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | See Southacres Dr | [18 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  | 350002-553 |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | See Southacres Dr | [18 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | 101911.72 | [18 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  | 350002-552 |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 339120.82 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | [18 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | See Brentwood | [18 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | 54743.76 | [18 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | [18 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | See Brentwood | [18 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 59095.34 | [18 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | [18 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | See Brentwood | [18 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 208168.14 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | 67209.73 | [18 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  | 350002-551 |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | See Southlake Dr | [18 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  | 350002-551 |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | 16840.92 | [18 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  | 350002-551 |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | See Southlake Dr | [18 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
|  |  | 350002-559 |  |  |  |  | Foxboro Dr | Vannah Ave | Dorsey Way |  | 18 | Local | [17 empty] | 128000 |  |  | Council | 8148-410-8107-148580-822702 | 128000
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  | 350002-559 |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | [18 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | [18 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 39104.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | [18 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | [18 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 41474.37 | [18 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| LP |  | 388368-3 |  |  |  |  | Tucker Station and Rehl Rd |  |  |  | 20 | [18 empty] | 50000
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | See W Kingston Ave | [18 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | See W Kingston Ave | [18 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | See W Kingston Ave | [18 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | See W Kingston Ave | [18 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | See W Kingston Ave | [18 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | See W Kingston Ave | [18 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | See W Kingston Ave | [18 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | 115529.16 | [18 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 79426.35 | [18 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
|  |  | 350002-555 |  |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  | 350002-562 |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | 18931.95 | [18 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  | 350002-563 |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | See Monaco Dr | [18 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  | 350002-563 |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | 9275.65 | [18 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  | 350002-561 |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | See Seebolt Dr | [18 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  | 350002-561 |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | March | [17 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 59691.83 | March | [17 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | March | [17 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | March | [17 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
|  |  | 388368-4 |  |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| LP |  | 388368-1 |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| LP |  | 388368-5 |  |  |  |  | Aiken Rd Base Failure | [22 empty] | 500000
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 37585.62 |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800
| Michael Baker |  | 387658-1 |  |  |  |  | Supplemental Inspections | [22 empty] | 71609

## April 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-572 |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 |  | April | [17 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | April | [17 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 160513.03 | April | [17 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  | 350002-554 |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | 53022.19 | [18 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  | 350002-554 |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | See Cecil Ave | [18 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  | 350002-554 |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | See Cecil Ave | [18 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-554 |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | See Cecil Ave | [18 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  | 350002-554 |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | See Cecil Ave | [18 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-554 |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | See Cecil Ave | [18 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  | 350002-567 |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  | 350002-567 |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall |  | 350002-567 |  |  |  |  | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  | 350002-536 |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  | 350002-567 |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  | 350002-567 |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall |  | 350002-568 |  |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
[8 empty] | Harold Ave | Dixie Hwy | Dead End | 52 | 3 | Local | [17 empty] | 60000 |  |  | PW/Council | [15 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-568 |  |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
[8 empty] | McCloskey Ave | Wilart Dr | Algonquin Pkwy | 27 | 3 | Local | [17 empty] | 50000 |  |  | PW/Council | [15 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-568 |  |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-568 |  |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
[8 empty] | Wallie Ann Ct | Bernheim Ln | Wathen Ln | 39 | 3 | Local | [17 empty] | 67500 |  |  | PW/Council | [15 empty] | Awaiting Account number for 50k from D3
[8 empty] | Wilart Dr | Dixie Hwy | McCloskey Ave | 19 | 3 | Local | [17 empty] | 50000 |  |  | PW/Council | [15 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-565 |  |  |  |  | Guthrie St | S 2nd St | S 4th St |  | 4 | Local | [17 empty] | 50000 | 25769.15 | April | [16 empty] | Pave only that which had not been paved previously. No ramps
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  | 350002-571 |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 20184.13 | [18 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  | 350002-571 |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | [18 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-564 |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | 7746.71 | [17 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  | 350002-564 |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | 12122.47 | [18 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  | 350002-564 |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | 4892.93 | [18 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  | 350002-564 |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | See Maricopa Ct | [17 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  |  |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-566 |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 |  | April | [17 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall |  | 350002-556 |  |  |  |  | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall |  | 350002-556 |  |  |  |  | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall |  | 350002-556 |  |  |  |  | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall | [6 empty] | Coverbrook Ct | Stonyrun Dr | Dead End |  | 11 | Local
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall |  | 350002-557 |  |  |  |  | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall |  | 350002-556 |  |  |  |  | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  | 350002-557 |  |  |  |  | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
|  |  | 350002-560 |  |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| Hall |  | 350002-553 |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | See Southacres Dr | [18 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | See Southacres Dr | [18 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  | 350002-553 |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | See Southacres Dr | [18 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  | 350002-553 |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | See Southacres Dr | [18 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  | 350002-553 |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | See Southacres Dr | [18 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | 101911.72 | [18 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  | 350002-552 |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 339120.82 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | April | [17 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | See Brentwood | [18 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | 54743.76 | [18 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | [18 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | See Brentwood | [18 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 59095.34 | [18 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | [18 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | See Brentwood | [18 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 208168.14 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | 67209.73 | [18 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  | 350002-551 |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | See Southlake Dr | [18 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  | 350002-551 |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | 16840.92 | [18 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  | 350002-551 |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | See Southlake Dr | [18 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
|  |  | 350002-559 |  |  |  |  | Foxboro Dr | Vannah Ave | Dorsey Way |  | 18 | Local | [17 empty] | 128000 |  |  | Council | 8148-410-8107-148580-822702 | 128000
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  | 350002-559 |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | April | [17 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | April | [17 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | April | [17 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | April | [17 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | April | [17 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | April | [17 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 215813.97 | April | [17 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | April | [17 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | April | [17 empty] | 480 | 18 | 8645 | 0.1403
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | April | [17 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 198679.56 | April | [17 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | April | [17 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | April | [17 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | April | [17 empty] | 310 | 22 | 6828 | 0.11081
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  | 388368-3 |  |  |  |  | Tucker Station and Rehl Rd |  |  |  | 20 | [18 empty] | 50000
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | See W Kingston Ave | [18 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | See W Kingston Ave | [18 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | See W Kingston Ave | [18 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
|  |  | 350002-505 |  |  |  |  | Meadowbrook Ct | S 5th St | dead end |  | 21 | Local | [18 empty] | See W Kingston Ave
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | See W Kingston Ave | [18 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | See W Kingston Ave | [18 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | See W Kingston Ave | [18 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | See W Kingston Ave | [18 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | 115529.16 | [18 empty] | 1950 | 30 | 57693 | 0.93631
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | See Dart Dr | April | [17 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 398568.1 | April | [17 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | See Dart Dr | April | [17 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | See Dart Dr | April | [17 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | See Dart Dr | April | [17 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | See Dart Dr | April | [17 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | See Dart Dr | April | [17 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | See Dart Dr | April | [17 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | See Dart Dr | April | [17 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | See Dart Dr | April | [17 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | See Dart Dr | April | [17 empty] | 167.3467 | 22 | 3682 | 0.059756
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
|  |  | 350002-555 |  |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  | 350002-562 |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | 67344.09 | [18 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  | 350002-563 |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | See Monaco Dr | [18 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  | 350002-563 |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | 9275.65 | [18 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  | 350002-561 |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | See Seebolt Dr | [18 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  | 350002-561 |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | March | [17 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 207321.31 | March | [17 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | March | [17 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | March | [17 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
|  |  | 388368-4 |  |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| LP |  | 388368-1 |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
|  |  | 350002-534 |  |  |  |  | Saratoga Ridge Ct | Saratoga Ridge Dr | Dead Ed |  |  | Local | [18 empty] | See Saratoga Woods Dr | April
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 37585.62 | January | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| LP |  | 388368-5 |  |  |  |  | Aiken Rd Base Failure | [22 empty] | 500000 | 347476.1
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800
[8 empty] | Montana Ave | Central Ave | Lillian Ave |  |  | Local | [17 empty] | 35000 |  |  | Council | 8672-410-8106-048203-822702 | 17326.67 |  | 8102-410-8105-148372-822705 | 6838.95 |  | 8672-410-8105-148372-822705 | 6838.95 |  | 8133-410-8111-148222-822705 | 3995.43
| Michael Baker |  | 387658-1 |  |  |  |  | Supplemental Inspections | [22 empty] | 71609

## May 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-572 |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | 36531.8 | April | [17 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | April | [17 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 160513.03 | April | [17 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  | 350002-554 |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | 409366.94 | May | [17 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  | 350002-554 |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | See Cecil Ave | May | [17 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  | 350002-554 |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | See Cecil Ave | May | [17 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | May | [16 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-554 |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | See Cecil Ave | May | [17 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  | 350002-554 |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | See Cecil Ave | May | [17 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-554 |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | See Cecil Ave | May | [17 empty] | 1007 | 24 | 24170 | 0.39226
| Hall |  | 350002-580 |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | 85244.57 | [18 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | LWC main replacement, LPA project | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  | 350002-567 |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  | 350002-567 |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [17 empty] | LWC main replacement, LPA project | 674 | 24 | 14370 | 0.23321
| Hall |  | 350002-567 |  |  |  |  | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  | 350002-536 |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  | 350002-567 |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  | 350002-567 |  |  |  |  | Raceland Ave | Kranet Way | Belrad Rd |  | 2 | Local
| Hall |  | 350002-567 |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
|  |  | 350002-577 |  |  |  |  | Montana Ave | Central Ave | Lillian Ave |  | 3 | Local | [17 empty] | 35000 | 25312 | May | Council | 8672-410-8106-048203-822702 | 17326.67 |  | 8102-410-8105-148372-822705 | 6838.95 |  | 8672-410-8105-148372-822705 | 6838.95 |  | 8133-410-8111-148222-822705 | 3995.43 | [7 empty] | 13109 | 0.21275
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall |  | 350002-568 |  |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
[8 empty] | Harold Ave | Dixie Hwy | Dead End | 52 | 3 | Local | [17 empty] | 60000 |  |  | PW/Council | 8138-410-8107-148222-822705 | 50000 | [13 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-568 |  |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | 37086.15 | [18 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
[8 empty] | McCloskey Ave | Wilart Dr | Algonquin Pkwy | 27 | 3 | Local | [17 empty] | 50000 |  |  | PW/Council | See Harold | [14 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-568 |  |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-568 |  |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
[8 empty] | Wallie Ann Ct | Bernheim Ln | Wathen Ln | 39 | 3 | Local | [17 empty] | 67500 |  |  | PW/Council | See Harold | [14 empty] | Awaiting Account number for 50k from D3
[8 empty] | Wilart Dr | Dixie Hwy | McCloskey Ave | 19 | 3 | Local | [17 empty] | 50000 |  |  | PW/Council | See Harold | [14 empty] | Awaiting Account number for 50k from D3
| Hall |  | 350002-565 |  |  |  |  | Guthrie St | S 2nd St | S 4th St |  | 4 | Local | [17 empty] | 50000 | 25769.15 | April | [16 empty] | Pave only that which had not been paved previously. No ramps |  |  | 34603 | 0.56158
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  | 350002-571 |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 20184.13 | [18 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  | 350002-571 |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | [18 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 388368-9 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall |  | 350002-582 |  |  |  |  | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  | 350002-581 |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | 42386.28 | [18 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  | 350002-579 |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  | 350002-575 |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | 62266.17 | [18 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 80338.45 | May | [17 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  | 350002-564 |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | 7746.71 | [17 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  | 350002-564 |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | 12122.47 | [18 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-564 |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | 4892.93 | [18 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  | 350002-564 |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | See Maricopa Ct | [17 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Louisville Paving |  | 388368-7 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Louisville Paving |  | 388368-8 |  |  |  |  | Cleveland Blvd | University Blvd | Zorn Ave |  | 9 | Local | [17 empty] | 75000 | [18 empty] | Being completed to help with new sidewalk project issues
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-566 |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | 97569.02 | April | [17 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall |  | 350002-556 |  |  |  |  | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall |  | 350002-556 |  |  |  |  | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall |  | 350002-556 |  |  |  |  | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall |  | 350002-556 |  |  |  |  | Coverbrook Ct | Stonyrun Dr | Dead End |  | 11 | Local
| Hall |  | 350002-576 |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall |  | 350002-557 |  |  |  |  | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  | 350002-576 |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  | 350002-576 |  |  |  |  | Ridgehurst Pl Frontage Rd | Fieldside Cir | Brody Ln |  | 11
| Hall |  | 350002-578 |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  | 350002-578 |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  | 350002-576 |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  | 350002-576 |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall |  | 350002-556 |  |  |  |  | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  | 350002-557 |  |  |  |  | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
|  |  | 350002-574 |  |  |  |  | Port Rd | Cane Run Rd | Dead End |  | 12 | Local | [18 empty] | 145991.72 | May | [19 empty] | 50103 | 0.81313
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| Hall |  | 350002-553 |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | See Southacres Dr | May | [17 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | See Southacres Dr | May | [17 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  | 350002-553 |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | See Southacres Dr | May | [17 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  | 350002-553 |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | See Southacres Dr | May | [17 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  | 350002-553 |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | See Southacres Dr | May | [17 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | 256861.04 | May | [17 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
|  |  | 350002-560 |  |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| Hall |  | 350002-552 |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 345244.06 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 131354.48 | April | [17 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | See Brentwood | May | [17 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | 316458.46 | May | [17 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | May | [17 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | See Brentwood | May | [17 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 107838.9 | May | [17 empty] | 394 | 32 | 12600 | 0.20449
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | May | [17 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | See Brentwood | May | [17 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | See Rollington Rd | May | [17 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | See Rollington Rd | May | [17 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | See Rollington Rd | May | [17 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 369526.14 | May | [17 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | See Rollington Rd | May | [17 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | See Rollington Rd | May | [17 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | See Rollington Rd | May | [17 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | 390909.38 | May | [16 empty] | Due to developer project, will need to go back and finish to county line | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | See Rollington Rd | May | [17 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-551 |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | See Southlake Dr | [18 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-551 |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | 16840.92 | [18 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-551 |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | See Southlake Dr | [18 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
|  |  | 350002-559 |  |  |  |  | Foxboro Dr | Vannah Ave | Dorsey Way |  | 18 | Local | [17 empty] | 128000 |  |  | Council | 8148-410-8107-148580-822702 | 128000
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  | 350002-559 |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | April | [17 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | April | [17 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | April | [17 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | April | [17 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | April | [17 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | April | [17 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 217206.57 | April | [17 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | April | [17 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | April | [17 empty] | 480 | 18 | 8645 | 0.1403
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | April | [17 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 198679.56 | April | [17 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | April | [17 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | April | [17 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | April | [17 empty] | 310 | 22 | 6828 | 0.11081
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  | 388368-3 |  |  |  |  | Tucker Station and Rehl Rd |  |  |  | 20 | [18 empty] | 50000
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | See W Kingston Ave | May | [17 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | See W Kingston Ave | May | [17 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | See W Kingston Ave | May | [17 empty] | 1407 | 24 | 33762 | 0.54793
|  |  | 350002-505 |  |  |  |  | Meadowbrook Ct | S 5th St | dead end |  | 21 | Local | [18 empty] | See W Kingston Ave | May | [19 empty] | 5501 | 0.089276
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | See W Kingston Ave | May | [17 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | See W Kingston Ave | May | [17 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | See W Kingston Ave | May | [17 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | 419786.9 | May | [17 empty] | 1950 | 30 | 57693 | 0.93631
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | See W Kingston Ave | [17 empty] | Asphalt done on forum/school Need to make concrete repairs | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | See Dart Dr | April | [17 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 398568.1 | April | [17 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | See Dart Dr | April | [17 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | See Dart Dr | April | [17 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | See Dart Dr | April | [17 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | See Dart Dr | April | [17 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | See Dart Dr | April | [17 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | See Dart Dr | April | [17 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | See Dart Dr | April | [17 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | See Dart Dr | April | [17 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | See Dart Dr | April | [17 empty] | 167.3467 | 22 | 3682 | 0.059756
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete |  |  | 17946 | 0.29125
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
|  |  | 350002-555 |  |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  | 350002-562 |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | 67344.09 | [18 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  | 350002-563 |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | See Monaco Dr | [18 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  | 350002-563 |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | 9275.65 | [18 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  | 350002-561 |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | See Seebolt Dr | [18 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  | 350002-561 |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | March | [17 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 282714.55 | March | [17 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | March | [17 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | March | [17 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
|  |  | 388368-4 |  |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| LP |  | 388368-1 |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
|  |  | 350002-534 |  |  |  |  | Saratoga Ridge Ct | Saratoga Ridge Dr | Dead Ed |  |  | Local | [18 empty] | See Saratoga Woods Dr | April
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 37585.62 | January | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
| LP |  | 388368-5 |  |  |  |  | Aiken Rd Base Failure | [22 empty] | 500000 | 404911.65 | May
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800
| Michael Baker |  | 387658-1 |  |  |  |  | Supplemental Inspections | [22 empty] | 71609 | 17701.73
| Louisville Paving |  | 388368-6 |  |  |  |  | Timberbend Bond Release | [22 empty] | 65025

## Alleys
PO # | Contractor | Alley Name | From | To | Parallel To | District | Ramps | Alley Match |  | Council Funds |  | Council Funds |  | Other |  | PW Bond | Total Cost | Actual Cost | 50/50 Split | Notes
350002-377 |  | Caldwell Alley | Caldwell St | Breckenridge St | East Caldwell just south of Coke St | 4 |  | 10000 | 8131-410-8210-148937-822702 | 15000 | 8146-410-8107-148793-822702 | [5 empty] | 25000 | 24726.56
350002-378 |  | Coke St and Clay St | Coke St | dead end |  | 4 |  | 3457.65 | 8131-410-8210-148937-822702 | 3750 | 8146-410-8107-148793-822702 |  |  | 292.35 | 8115-410-8210-148937-822702 |  | 7500 | 5000.22
350002-437 |  | Whitmore/Lonsdale Alley |  |  |  | 15 |  | 10000 | 8115-410-8210-148937-822702 | 30000 | 8146-410-8107-148925-822702 | [5 empty] | 40000 | 23585.03
350002-380 |  | 1000 Block of 43rd Ave | Greenwood Ave | Sunset Ave |  | 1 |  | 2055.85 | 8115-410-8105-148442-822702 | 886.48 | 8101-410-8105-148391-822702 | 14420.11 | 8138-410-8107-148391-822702 | 1137.56 | 8115-410-8210-148937-822702 |  | 18500 | 25069.29
350002-381 |  | 4200 Block of Hale | 42nd St | 43rd St | Hale Ave and Virginia Ave | 1 |  | 7310.47 | 8133-410-8210-148450-822702 | 20000 | 8101-410-8105-148391-822702 | 2093.16 | 8101-410-8210-148937-822702 | 596.37 | 8115-410-8105-148442-822702 |  | 30000 | 32062.92
388368-10 |  | Ward Alley | S 5th St | S 6th St | Garland and Kentucky | 4 |  | 25000 | 8146-410-8107-148793-822702 | [7 empty] | 25000
350002-483 |  | 2914 S 6th St Alley | Heywood Ave | Iowa Ave | Rodman St & S 6th St | 15 |  | 310.34 | 8137-410-8210-148962-822702 | 5239.79 | 8138-410-8205-148915-822702 | 17704.04 | 8138-410-8107-148962-822702 | 21745.83 | 8101-410-8105-148962-822702 |  | 45000 |  |  | On leg closest to church, last 3 properties are non Metro
PO? |  |  | Start | Balance | Account
PO | SW

## Key
Complete
Utility Conflict
Moved to FY 21 due to virus
Concrete Road
Metro Project Pending
Not completed yet
Distribute report to the following:
Daniel Frockt
Benjamin Tipton
Maxwell Bradley
Kellie Watson
Christy Tapp
Aaron Jackson
LaTonya Bell
CC:
Jeff Brown
Vanessa Burns
John Callihan
Ozzy Gibson
Metro Council Staff

## Rating
86-100 | Good
71-85 | Satisfactory
56-70 | Fair
41-55 | Poor
26-40 | Very Poor
11-25 | Serious
0-10 | Failed