## July 2021
July 2021 Sidewalk Repair Schedule
Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Cost | Funding Accounts | Funding Source
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 22286.52 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Summer 2021 |  | 4302 Winnrose Way | 1 | 4 | 1501.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1213 S 41st St | 1 | 4 | 725.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4112 Winnrose Way | 1 | 5 | 3279.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1162 S 41st St | 1 | 4 | 721.8 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1159 S 41st St | 1 | 4 | 963.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1175 S 41st St | 1 | 4 | 2011.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1101 S 41st St | 1 | 4 | 3885.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1222-1224 Cypress St | 1 | 5 | 7670.93 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4114 WINNROSE WAY | 1 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1700 S 38TH ST | 1 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1156 S 26TH ST | 1 | 5 | 12790.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1152 S 26TH ST | 1 | 5 | 13673.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 371 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1433 HAZEL ST | 1 | 4 | 13953.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 S 42ND ST | 1 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 5023 Broadmoor Blvd | 2 | 4 | 206.4 |  | 8146 410 8211 148487 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 4109 St Charles St | 2 | 5 | 12914 |  | 8133 410 8111 148221 822705 ($673) | District 2
FY19 | Summer 2021 |  | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  | 8137 410 8211 148452 822705 ($180) / 8133 410 8111 148221 822705 ($5,936) | Public Works / District 2
FY19 | Summer 2021 |  | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2021 |  | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2021 |  | 4108 St Charles St | 2 | 5 | 1919.36 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2021 |  | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2021 |  | 4404 E Indian Trl | 2 | 5 | 784 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2021 |  | 4310 E Indian Trl | 2 | 4 | 229.12 |  | 8137 410 8211 148452 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  |  | Public Works
FY21 | Summer 2021 |  | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1403 FOREST DR | 2 | 4 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Summer 2021 |  | 4907 Sunday Dr | 2 | 4 | 251.84 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Fall 2021 |  | 4907 SUNDAY DR | 2 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 5101 MEDITERRANEAN CT | 2 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4310 E INDIAN TRL | 2 | 4 | 299 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4404 E INDIAN TRL | 2 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | BROADMOOR BLVD & ST CHARLES LN | 2 | 5 | 5581.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 55000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | West side of Robinhood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY20 | Summer 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Summer 2021 |  | 2328 W LEE ST | 3 | 5 | 1569.75 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1705 VALLEY FORGE WAY | 3 | 4 | 260 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2322 OREGON AVE | 3 | 5 | 1943.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1725 W GAULBERT AVE | 3 | 5 | 8372 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1728-1734 W HILL ST | 3 | 4 | 3737.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1749 W HILL ST | 3 | 4 | 7325.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2314 WOODLAND AVE | 3 | 4 | 3438.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3303 UTAH AVE | 3 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3304 UTAH AVE | 3 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3315 UTAH AVE | 3 | 5 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2020 |  | 200 S 7TH ST | 4 | 5 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Summer 2020 |  | 833 W MAIN ST | 4 | 4 | 3000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2020 |  | 200 S 5TH ST | 4 | 4 | 6000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2020 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  | 8137 410 8211 148452 822705 | Public Works
FY20 | Summer 2020 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  | 8143 410 8211 148472 822705 | Public Works
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 4 |  | 17180 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 1216 FERN ST | 4 | 5 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 100 E JEFFERSON ST | 4 | 4 | 33189 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 1114 PAYNE ST | 4 | 5 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1612 CEDAR ST | 4 | 4 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 426 E ORMSBY AVE | 4 | 4 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1213 W CHESTUNUT ST | 4 | 5 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1202 LEXINGTON RD | 4 | 4 | 348.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 400 S 6TH ST | 4 | 4 | 1129.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1910 MAGAZINE ST | 4 | 4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 913 E LIBERTY ST | 4 | 5 | 6708.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1017 ST PAUL CT | 4 | 4 | 3363.75 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 841 E WASHINGTON ST | 4 | 5 | 41259.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 550 3RD ST | 4 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 810 GOULLON CT | 4 | 5 | 3759.8611 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S 5TH ST & W JEFFERSON ST | 4 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2020 |  | 312 N 30TH ST | 5 | 5 | 4870 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 311 N 30TH ST | 5 | 4 | 7842 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 474 N 29TH ST | 5 | 4 | 4490 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 464 N 25TH ST | 5 | 4 | 64238 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 109 N 40TH ST | 5 | 4 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 805 S 39TH ST | 5 | 4 | 3250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 804 S 39TH ST | 5 | 5 | 7750 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 237 S 46TH ST | 5 | 4 | 1170 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 2333-231 S 46TH ST | 5 | 4 | 2340 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 235 S 46TH ST | 5 | 5 | 2540 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | S 46TH ST & W MARKET ST | 5 | 4 | 4572 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | HERMAN ST & S 46TH ST(249-251) | 5 | 5 | 4620 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 207 S 42ND ST | 5 | 4 | Not to Exceed $55,164 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 616 N 28TH ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 650 S 31st St | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2146 DUNCAN ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 2711 W JEFFERSON ST | 5 | 5 | 5010 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3028 BANK ST | 5 | 4 | 2093 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4308 VERMONT AVE | 5 | 5 | 5083 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4102 VERMONT AVE | 5 | 4 | 299 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1824 BANK ST | 5 | 5 | 12774.2 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 122 NORTHEWESTERN PKY | 5 | 5 | 2093 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 631 S 42ND ST | 5 | 5 | 3438.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 667 S 39TH ST | 5 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 2725 Northwestern Pky | 5 | 4 | 3776 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2714 Alford Ave | 5 | 4 | 1340.4 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 682 Madelon Ct | 5 | 5 | 248.67 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 662 Cecil Ave | 5 | 4 | 7570.8 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 4509-4515 W Market St | 5 | 5 | 3960.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 123 N 42nd St | 5 | 5 | 1112.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 120 S Shawnee Ter | 5 | 4 | 2694.67 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 351 N 28th St | 5 | 5 | 555.33 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | W MARKET ST & SHAWNEE | 5 | 4 | 2541.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3640 River Park Dr | 5 | 5 | 5916 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Summer 2021 |  | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  | 8138 410 8107 148280 822705 | Council District 5
FY22 | Fall 2021 |  | 207 S 42ND ST | 5 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 616 N 28TH ST | 5 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2403 ROWAN ST | 5 | 4 | 29697.6 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4532 W BROADWAY | 5 | 5 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3500 W MAIN ST | 5 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | ELLIOTT AVE & S 31 ST | 5 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2146 DUNCAN ST | 5 | 5 | 12092.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2714 ALFORD AVE | 5 | 4 | 4235.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 682 MADELON CT | 5 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 351 N 25TH ST | 5 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 662 CECIL AVE | 5 | 5 | 8305.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2934 PORTLAND AVE | 5 | 5 | 2441.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 809 S 38TH ST | 5 | 5 | 4485 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 734 S 38TH ST | 5 | 5 | 6245.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 N 26TH ST | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 813 S 45TH ST | 5 | 5 | 16905 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4517 BREWSTTER AVE | 5 | 5 | 6957.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2814 ROWAN ST | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4629 BREWSTER AVE | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 123 N 42ND ST | 5 | 5 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 808 S 45TH ST | 5 | 5 | 6146.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4325 VERMONT AVE | 5 | 4 | 11627.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2020 |  | 1703 S BROOK ST | 6 | 5 | 6720 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 711 COLORADO AVE | 6 | 5 | 2930 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 821 HUMLER ST | 6 | 5 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  | 8146 410 8107 148225 899998 | District 6
FY20 | Fall 2020 |  | 1408 HOMEVIEW DR | 6 | 5 | 15726.25 |  | 8143 410 8211 148472 822705 | Public Works
FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  | 8143 410 8211 148472 822705 | Public Works
FY18 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 6 |  | 30900.74 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2020 |  | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1815 Hale Ave | 6 | 4 | 822.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 1388 S 6TH ST | 6 | 5 | 20700 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2531 GARLAND AVE | 6 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2328 OSAGE AVE | 6 | 5 | 11063 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1709 HALE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 724 CAWTHON ST | 6 | 5 | 1395.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1734 HALE AVE | 6 | 5 | 1744.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1435 LARCHMONNT AVE | 6 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S 15TH ST & PRENTICE ST | 6 | 5 | 1461.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 HOEVIEW DR | 6 | 4 | 11691.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1440 S FLOYD ST | 6 | 5 | 5612 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2207 W OAK ST | 6 | 5 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3212 UTAH AVE | 6 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3236 UTAH AVE | 6 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1501 EARL AVE | 6 | 4 | 2389.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3237 UTAH AVE | 6 | 4 | 2724.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1503 EARL AVE | 6 | 5 | 3917.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3249 UUTAH AVE | 6 | 4 | 6644.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1424 EARL AVE | 6 | 4 | 7040.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3210 UTAH AVE | 6 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 629 W ORMSBY AVE | 6 | 4 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 635 PARK AVE | 6 | 5 | 2821.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 422 W ORMSBY AVE | 6 | 5 | 8203.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 425 W ORMSBY AVE | 6 | 5 | 16943.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 509 W ORMSBY AVE | 6 | 5 | 20061.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 720 W ST CATHERINE ST | 6 | 5 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1265 S BROOK ST | 6 | 5 | 4784 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1261 S BROOK ST | 6 | 5 | 6210 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1020 S 4TH ST | 6 | 5 | 15678.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2020 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 1840 SHADY LN | 8 | 5 | 3380 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1601 SHADY LN | 8 | 5 | 4634.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2114 DOUGLASS BLVD | 8 | 5 | 7176 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1523 MORTON AVE | 8 | 5 | 5014 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2107 DOUGLASS BLVD | 8 | 4 | 33056.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2143 WOODBOURNE AVE | 8 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1500 EDGEWOOD PL | 8 | 4 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2512 DUNDEE RD | 8 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2313 BOULEVARD NAPOLEON | 8 | 4 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1910 HARVARD DR | 8 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2315 BONNYCASTLE AVE | 8 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  | 8138 410 8107 148227 822705 | Council District 9
FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 1644.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 100 N BAYLY AVE | 9 | 5 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 112 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2423 LINDSAY AVE | 9 | 5 | 2574.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 227 CORNELL PL | 9 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2030 EMERALD AVE | 9 | 5 | 4335.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 102 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2238 SYCAMORE AVE | 9 | 5 | 4451.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4011 RIVULET LN | 11 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2824 SIX MILE LN | 11 | 5 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Rd from Trmpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's | 8500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  | 8138 410 8107 148412 822705 | Council District 12
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 12 |  | 278.8 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY18 | Spring 2021 |  | 9303 Minute Men Ct | 13 | 5 | 1283.84 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Spring 2021 |  | 8114 ATLANTA PKY | 13 | 5 | 140 |  | 8133 410 8211 148396 822705 | Public Works
FY18/21 | Spring 2021 |  | 804 FLICKER RD | 13 | 4 | 1324.72 |  | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
FY21 | Spring 2021 |  | 128 ELK RIVER DR | 13 | 5 | 2239.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 9402 Balance Ln | 13 | 5 | 7456.8 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7327 SOUTHSIDE DR | 13 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 7513 Wimstock Ave | 14 | 5 | 3269.6 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 6223 Bethany Ln | 14 | 4 | 1217.6 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 6222-6224 Bethany Ln | 14 | 5 | 853.84 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 5708 FruitwoodDr | 14 | 5 | 458.24 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 8406 Devonshire Dr | 14 | 5 | 2344 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 6300 W Pages Ln | 14 | 5 | 1328.27 |  | TBD | Council District 14
FY21 | Spring 2021 |  | 6911 Ethan Allen Way | 14 | 4 | 2201.6 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 |  | 8146 410 8107 148279 822705 | Council District 14
FY22 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  |  | Public Works
FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  |  | Public Works
FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04
FY22 | Spring 2021 |  | TBD | 14 | 2's through 5's | 55689.59 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3671 POWELL AVE | 15 | 4 | 1661.1111 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1410 Weyler Ave | 15 | 5 | 676.8
FY21 | Winter 2021 |  | 1409 Southgate Ave | 15 | 4 | 422.4
Fy21 | Spring 2021 |  | 1609 Cherry Way | 15 | 4 | 412.8
FY21 | Summer 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Summer 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Summer 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3703 W WHEATMORE DR | 15 | 5 | 12586.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3613 WOODRUFF AVE | 15 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 626 RAWLINGS ST | 15 | 5 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 542 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 546 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 548 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3416 Powell Ave | 15 | 4 | 151.4 |  |  | Council District 15
FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | 343.68 |  |  | Council District 15
FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | 609 |  |  | Council District 15
FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | TBD |  |  | Council District 15
FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | TBD |  |  | Council District 15
FY22 | Spring 2021 |  | Beecher St from Warren Ave to Taylor Blvd | 15 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11412 Hammond Dr | 16 | 5 | 1761.6 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11505 Fisherman Way | 16 | 5 | 1813.59 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 1140 Kendrick Dr | 16 | 5 | 1369.83 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11414 Kendrick Dr | 16 | 5 | 719.03 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11500 Kendrick Dr | 16 | 5 | 538.06 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11506 Kendrick Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11514 Kendrick Dr | 16 | 5 | 403.7 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11516 Kendrick Dr | 16 | 5 | 210.88 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11415 Kendrick Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5410 Baywood Dr | 16 | 5 | 224.14 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5406 Baywood Dr | 16 | 5 | 1157.62 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5311 Drifton Dr | 16 | 5 | 2473.37 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5308 Drifton Dr | 16 | 5 | 1831.93 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5304 Drifton Dr | 16 | 5 | 888.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Baywood Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11513 Fisherman Way | 16 | 5 | 881.38 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11202 Deham Dr | 16 | 5 | 336.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5412 Lithia Dr | 16 | 5 | 1441.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11306 Deham Dr | 16 | 5 | 1435.24 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11307 Deham Dr | 16 | 5 | 988.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11301 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11215 Deham Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 501 Lithia Dr | 16 | 5 | 2094.49 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 17 | 4's and 5's | 1872 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 18 |  | 4930.4 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Spring 2021 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  | 8146 410 8211 148487 822705 | Public Works
FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Summer 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Summer 2021 |  | 1337 Heafer Rd | 19 | 5 | 1649.82 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Summer 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Summer 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY19 | Summer 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 412 LAKE FOREST PKY | 19 | 4 | 2092.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 505 EDGEFOREST PL | 19 | 4 | 3159 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1337 HEAFER RD | 19 | 4 | 2093 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 4010 Stone Lakes Dr (to start in May) | 20 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Spring 2021 |  | 11109 Little Spring Blvd | 20 | 4 | 3815.69 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 10417 Pinoak View Dr | 20 | 5 | 4024.32 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  | 8137 410 8211 148452 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 20 |  | 209 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 223 Iroquios Ave | 21 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 5803 BUCKS LN | 22 | 4 | 6141 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6016 Mercury Dr | 22 | 5 | 1223.33 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Spring 2021 |  | 3806 GREENWICH RD | 22 | 4 | 1794 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3814 GREENWICH RD | 22 | 5 | 2392 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  | 8102 410 8105 148838 822705 | Council District 22
FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7818 APPLEVIEW LN | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7820 APPLEVIEW LN | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6711 VANDRE AVE | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6707 VANDRE AVE | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 23 |  | 2016 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5204 MONACO DR | 24 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2021 |  | Willowcreek Dr from Old South Park Rd to Maplecreek DR | 24 | 2's through 5's | 75000 |  | 8148 410 8211 148560 822705 | Public Works
|  |  | Sidewalk Repairs by D25 | 25 |  | 625.15 |  | 8101 410 8199 148237 822702 | Council District 25
FY22 | Winter 2021 |  | Stone Wynde Dr fro mValley College Dr to Pages Ln | 25 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 26 |  | 1602 |  | 8137 410 8111 148271 822705 | Council District 26
FY22 | Spring 2021 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr | 26 | 2's through 5's | 80000 |  | 8148 410 8211 148560 822705 | Public Works
[5 empty] | Total | 3058785.32 | 0

## August 2021
August 2021 Sidewalk Repair Schedule
Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Cost | Funding Accounts | Funding Source
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 22286.52 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Summer 2021 |  | 4302 Winnrose Way | 1 | 4 | 1501.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1213 S 41st St | 1 | 4 | 725.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4112 Winnrose Way | 1 | 5 | 3279.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1162 S 41st St | 1 | 4 | 721.8 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1159 S 41st St | 1 | 4 | 963.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1175 S 41st St | 1 | 4 | 2011.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1101 S 41st St | 1 | 4 | 3885.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1222-1224 Cypress St | 1 | 5 | 7670.93 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4114 WINNROSE WAY | 1 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1700 S 38TH ST | 1 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1156 S 26TH ST | 1 | 5 | 12790.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1152 S 26TH ST | 1 | 5 | 13673.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 371 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1433 HAZEL ST | 1 | 4 | 13953.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 S 42ND ST | 1 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 5023 Broadmoor Blvd | 2 | 4 | 206.4 | 25254.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 4109 St Charles St | 2 | 5 | 12914 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2
FY19 | Summer 2021 |  | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2
FY19 | Summer 2021 |  | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4108 St Charles St | 2 | 5 | 1919.36 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4404 E Indian Trl | 2 | 5 | 784 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4310 E Indian Trl | 2 | 4 | 229.12 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 1403 FOREST DR | 2 | 4 | 897 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4907 Sunday Dr | 2 | 4 | 251.84 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY22 | Fall 2021 |  | 5101 MEDITERRANEAN CT | 2 | 4 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
|  |  | VARIOUS SIDEWALK REPAIRS TBD by District 2 Council Office | 2 |  | 6609 |  | 8133 410 8111 148221 822705 | District 2
FY22 | Summer 2021 |  | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 45692 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | West side of Robinhood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's |  |  | 8148 410 8211 148560 822705 | Public Works
FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Summer 2021 |  | 2328 W LEE ST | 3 | 5 | 1569.75 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1705 VALLEY FORGE WAY | 3 | 4 | 260 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2322 OREGON AVE | 3 | 5 | 1943.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1725 W GAULBERT AVE | 3 | 5 | 8372 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1728-1734 W HILL ST | 3 | 4 | 3737.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1749 W HILL ST | 3 | 4 | 7325.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2314 WOODLAND AVE | 3 | 4 | 3438.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3303 UTAH AVE | 3 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3304 UTAH AVE | 3 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3315 UTAH AVE | 3 | 5 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2020 |  | 200 S 7TH ST | 4 | 5 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2020 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Summer 2020 |  | 833 W MAIN ST | 4 | 4 | 3000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2020 |  | 200 S 5TH ST | 4 | 4 | 6000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Summer 2020 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  | 8137 410 8211 148452 822705 | Public Works
FY20 | Summer 2020 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  | 8143 410 8211 148472 822705 | Public Works
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 4 |  | 17180 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1216 FERN ST | 4 | 5 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 100 E JEFFERSON ST | 4 | 4 | 33189 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PAYNE ST | 4 | 5 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1612 CEDAR ST | 4 | 4 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 426 E ORMSBY AVE | 4 | 4 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1213 W CHESTUNUT ST | 4 | 5 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1202 LEXINGTON RD | 4 | 4 | 348.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 400 S 6TH ST | 4 | 4 | 1129.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1910 MAGAZINE ST | 4 | 4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 913 E LIBERTY ST | 4 | 5 | 6708.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1017 ST PAUL CT | 4 | 4 | 3363.75 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 841 E WASHINGTON ST | 4 | 5 | 41259.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 550 3RD ST | 4 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 GOULLON CT | 4 | 5 | 3759.8611 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S 5TH ST & W JEFFERSON ST | 4 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 207 S 42ND ST | 5 | 4 | Not to Exceed $55,164 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 616 N 28TH ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 650 S 31st St | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2146 DUNCAN ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 2711 W JEFFERSON ST | 5 | 5 | 5010 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3028 BANK ST | 5 | 4 | 2093 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4308 VERMONT AVE | 5 | 5 | 5083 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4102 VERMONT AVE | 5 | 4 | 299 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1824 BANK ST | 5 | 5 | 12774.2 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 122 NORTHEWESTERN PKY | 5 | 5 | 2093 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 631 S 42ND ST | 5 | 5 | 3438.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 667 S 39TH ST | 5 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 2725 Northwestern Pky | 5 | 4 | 3776 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2714 Alford Ave | 5 | 4 | 1340.4 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 682 Madelon Ct | 5 | 5 | 248.67 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 662 Cecil Ave | 5 | 4 | 7570.8 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 4509-4515 W Market St | 5 | 5 | 3960.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 123 N 42nd St | 5 | 5 | 1112.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 120 S Shawnee Ter | 5 | 4 | 2694.67 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 351 N 28th St | 5 | 5 | 555.33 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | W MARKET ST & SHAWNEE | 5 | 4 | 2541.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3640 River Park Dr | 5 | 5 | 5916 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Summer 2021 |  | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  | 8138 410 8107 148280 822705 | Council District 5
FY22 | Fall 2021 |  | 207 S 42ND ST | 5 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 616 N 28TH ST | 5 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2403 ROWAN ST | 5 | 4 | 29697.6 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4532 W BROADWAY | 5 | 5 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3500 W MAIN ST | 5 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | ELLIOTT AVE & S 31 ST | 5 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2146 DUNCAN ST | 5 | 5 | 12092.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2714 ALFORD AVE | 5 | 4 | 4235.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 682 MADELON CT | 5 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 351 N 25TH ST | 5 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 662 CECIL AVE | 5 | 5 | 8305.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2934 PORTLAND AVE | 5 | 5 | 2441.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 809 S 38TH ST | 5 | 5 | 4485 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 734 S 38TH ST | 5 | 5 | 6245.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 N 26TH ST | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 813 S 45TH ST | 5 | 5 | 16905 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4517 BREWSTTER AVE | 5 | 5 | 6957.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2814 ROWAN ST | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4629 BREWSTER AVE | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 123 N 42ND ST | 5 | 5 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 808 S 45TH ST | 5 | 5 | 6146.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4325 VERMONT AVE | 5 | 4 | 11627.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2020 |  | 1703 S BROOK ST | 6 | 5 | 6720 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 711 COLORADO AVE | 6 | 5 | 2930 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 821 HUMLER ST | 6 | 5 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  | 8146 410 8107 148225 899998 | District 6
FY20 | Fall 2020 |  | 1408 HOMEVIEW DR | 6 | 5 | 15726.25 |  | 8143 410 8211 148472 822705 | Public Works
FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  | 8143 410 8211 148472 822705 | Public Works
FY18 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 6 |  | 30900.74 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2020 |  | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1815 Hale Ave | 6 | 4 | 822.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 1388 S 6TH ST | 6 | 5 | 20700 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2531 GARLAND AVE | 6 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2328 OSAGE AVE | 6 | 5 | 11063 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1709 HALE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 724 CAWTHON ST | 6 | 5 | 1395.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1734 HALE AVE | 6 | 5 | 1744.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1435 LARCHMONNT AVE | 6 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S 15TH ST & PRENTICE ST | 6 | 5 | 1461.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 HOEVIEW DR | 6 | 4 | 11691.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1440 S FLOYD ST | 6 | 5 | 5612 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2207 W OAK ST | 6 | 5 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3212 UTAH AVE | 6 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3236 UTAH AVE | 6 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1501 EARL AVE | 6 | 4 | 2389.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3237 UTAH AVE | 6 | 4 | 2724.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1503 EARL AVE | 6 | 5 | 3917.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3249 UUTAH AVE | 6 | 4 | 6644.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1424 EARL AVE | 6 | 4 | 7040.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3210 UTAH AVE | 6 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 629 W ORMSBY AVE | 6 | 4 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 635 PARK AVE | 6 | 5 | 2821.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 422 W ORMSBY AVE | 6 | 5 | 8203.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 425 W ORMSBY AVE | 6 | 5 | 16943.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 509 W ORMSBY AVE | 6 | 5 | 20061.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 720 W ST CATHERINE ST | 6 | 5 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1265 S BROOK ST | 6 | 5 | 4784 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1261 S BROOK ST | 6 | 5 | 6210 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1020 S 4TH ST | 6 | 5 | 15678.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 1408-1410 Homeview Dr | 6 | 5 | 20154.93 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1601 SHADY LN | 8 | 5 | 4634.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2114 DOUGLASS BLVD | 8 | 5 | 7176 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1523 MORTON AVE | 8 | 5 | 5014 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2107 DOUGLASS BLVD | 8 | 4 | 33056.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2143 WOODBOURNE AVE | 8 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1500 EDGEWOOD PL | 8 | 4 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2512 DUNDEE RD | 8 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2313 BOULEVARD NAPOLEON | 8 | 4 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1910 HARVARD DR | 8 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2315 BONNYCASTLE AVE | 8 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  | 8138 410 8107 148227 822705 | Council District 9
FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 1644.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 100 N BAYLY AVE | 9 | 5 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 112 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2423 LINDSAY AVE | 9 | 5 | 2574.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 227 CORNELL PL | 9 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2030 EMERALD AVE | 9 | 5 | 4335.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 102 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2238 SYCAMORE AVE | 9 | 5 | 4451.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4011 RIVULET LN | 11 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2824 SIX MILE LN | 11 | 5 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's | 8500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  | 8138 410 8107 148412 822705 | Council District 12
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 12 |  | 278.8 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY18 | Spring 2021 |  | 9303 Minute Men Ct | 13 | 5 | 1283.84 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Spring 2021 |  | 8114 ATLANTA PKY | 13 | 5 | 140 |  | 8133 410 8211 148396 822705 | Public Works
FY18/21 | Spring 2021 |  | 804 FLICKER RD | 13 | 4 | 1324.72 |  | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
FY21 | Spring 2021 |  | 128 ELK RIVER DR | 13 | 5 | 2239.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 9402 Balance Ln | 13 | 5 | 7456.8 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7327 SOUTHSIDE DR | 13 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 7513 Wimstock Ave | 14 | 5 | 3269.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6223 Bethany Ln | 14 | 4 | 1217.6 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6222-6224 Bethany Ln | 14 | 5 | 853.84 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 5708 Fruitwood Dr | 14 | 5 | 458.24 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 8406 Devonshire Dr | 14 | 5 | 2344 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6300 W Pages Ln | 14 | 5 | 1328.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6911 Ethan Allen Way | 14 | 4 | 2201.6 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 40156 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1410 Weyler Ave | 15 | 5 | 676.8 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1409 Southgate Ave | 15 | 4 | 422.4 |  | 8143 410 8211 148472 822705 | Public Works
Fy21 | Spring 2021 |  | 1609 Cherry Way | 15 | 4 | 412.8 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3703 W WHEATMORE DR | 15 | 5 | 12586.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3613 WOODRUFF AVE | 15 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 626 RAWLINGS ST | 15 | 5 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 542 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 546 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 548 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3416 Powell Ave | 15 | 4 | 151.4 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | 343.68 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | 609 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd | 15 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11412 Hammond Dr | 16 | 5 | 1761.6 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11505 Fisherman Way | 16 | 5 | 1813.59 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 1140 Kendrick Dr | 16 | 5 | 1369.83 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11414 Kendrick Dr | 16 | 5 | 719.03 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11500 Kendrick Dr | 16 | 5 | 538.06 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11506 Kendrick Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11514 Kendrick Dr | 16 | 5 | 403.7 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11516 Kendrick Dr | 16 | 5 | 210.88 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11415 Kendrick Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5410 Baywood Dr | 16 | 5 | 224.14 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5406 Baywood Dr | 16 | 5 | 1157.62 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5311 Drifton Dr | 16 | 5 | 2473.37 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5308 Drifton Dr | 16 | 5 | 1831.93 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5304 Drifton Dr | 16 | 5 | 888.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Baywood Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11513 Fisherman Way | 16 | 5 | 881.38 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11202 Deham Dr | 16 | 5 | 336.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5412 Lithia Dr | 16 | 5 | 1441.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11306 Deham Dr | 16 | 5 | 1435.24 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11307 Deham Dr | 16 | 5 | 988.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11301 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11215 Deham Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 501 Lithia Dr | 16 | 5 | 2094.49 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 17 | 4's and 5's | 1872 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Spring 2022 |  | VARIOUS SIDEWALK REPAIRS | 18 |  | 4930.4 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  | 8146 410 8211 148487 822705 | Public Works
FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 1649.82 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 412 LAKE FOREST PKY | 19 | 4 | 2092.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 505 EDGEFOREST PL | 19 | 4 | 3159 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1337 HEAFER RD | 19 | 4 | 2093 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Spring 2021 |  | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  | 8137 410 8211 148452 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 20 |  | 209 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 223 Iroquios Ave | 21 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 5803 BUCKS LN | 22 | 4 | 6141 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6016 Mercury Dr | 22 | 5 | 1223.33 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Spring 2021 |  | 3806 GREENWICH RD | 22 | 4 | 1794 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3812 GREENWICH RD | 22 | 5 | 2392 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  | 8102 410 8105 148838 822705 | Council District 22
FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7818 APPLEVIEW LN | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7820 APPLEVIEW LN | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6711 VANDRE AVE | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6707 VANDRE AVE | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 23 |  | 2016 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5204 MONACO DR | 24 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Willowcreek Dr from Old South Park Rd to Maplecreek DR | 24 | 2's through 5's | 75000 |  | 8148 410 8211 148560 822705 | Public Works
|  |  | Sidewalk Repairs by D25 | 25 |  | 625.15 |  | 8101 410 8199 148237 822702 | Council District 25
FY22 | Winter 2021 |  | Stone Wynde Dr fro mValley College Dr to Pages Ln | 25 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 26 |  | 1602 |  | 8137 410 8111 148271 822705 | Council District 26
FY22 | Spring 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr | 26 | 2's through 5's | 80000 |  | 8148 410 8211 148560 822705 | Public Works
[5 empty] | Total | 3065340.8967 | 76933.68

## September 2021
September 2021 Sidewalk Repair Schedule
Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Cost | Funding Accounts | Funding Source
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Summer 2021 |  | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4114 WINNROSE WAY | 1 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1700 S 38TH ST | 1 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1156 S 26TH ST | 1 | 5 | 12790.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1152 S 26TH ST | 1 | 5 | 13673.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 371 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1433 HAZEL ST | 1 | 4 | 13953.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 S 42ND ST | 1 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 5023 Broadmoor Blvd | 2 | 4 | 206.4 | 25254.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 4109 St Charles St | 2 | 5 | 12914 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2
FY19 | Summer 2021 |  | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2
FY19 | Summer 2021 |  | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4108 St Charles St | 2 | 5 | 1919.36 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4404 E Indian Trl | 2 | 5 | 784 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4310 E Indian Trl | 2 | 4 | 229.12 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 1403 FOREST DR | 2 | 4 | 897 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4907 Sunday Dr | 2 | 4 | 251.84 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY22 | Fall 2021 |  | 5101 MEDITERRANEAN CT | 2 | 4 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
|  |  | VARIOUS SIDEWALK REPAIRS TBD by District 2 Council Office | 2 |  | 6609 |  | 8133 410 8111 148221 822705 | District 2
FY22 | Summer 2021 |  | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 45692 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | West side of Robinhood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's |  |  | 8148 410 8211 148560 822705 | Public Works
FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Summer 2021 |  | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3303 UTAH AVE | 3 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3304 UTAH AVE | 3 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3315 UTAH AVE | 3 | 5 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 200 S 7TH ST | 4 | 5 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Fall 2021 |  | 833 W MAIN ST | 4 | 4 | 3000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Fall 2021 |  | 200 S 5TH ST | 4 | 4 | 6000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Fall 2021 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  | 8137 410 8211 148452 822705 | Public Works
FY20 | Fall 2021 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  | 8143 410 8211 148472 822705 | Public Works
FY19 | Fall 2021 |  | VARIOUS SIDEWALK REPAIRS | 4 |  | 17180 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1216 FERN ST | 4 | 5 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 100 E JEFFERSON ST | 4 | 4 | 33189 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PAYNE ST | 4 | 5 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1612 CEDAR ST | 4 | 4 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 426 E ORMSBY AVE | 4 | 4 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1213 W CHESTUNUT ST | 4 | 5 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1202 LEXINGTON RD | 4 | 4 | 348.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 400 S 6TH ST | 4 | 4 | 1129.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1910 MAGAZINE ST | 4 | 4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 913 E LIBERTY ST | 4 | 5 | 6708.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1017 ST PAUL CT | 4 | 4 | 3363.75 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 841 E WASHINGTON ST | 4 | 5 | 41259.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 550 3RD ST | 4 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 GOULLON CT | 4 | 5 | 3759.8611 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S 5TH ST & W JEFFERSON ST | 4 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 207 S 42ND ST | 5 | 4 | 1777.6 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 123 N 42nd St | 5 | 5 | 1112.6 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY18 | Summer 2021 |  | 616 N 28TH ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 650 S 31st St | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2146 DUNCAN ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 4509-4515 W Market St | 5 | 5 | 3960.6 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 351 N 28th St | 5 | 5 | 555.33 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 3640 River Park Dr | 5 | 5 | 5916 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  | 8138 410 8107 148280 822705 | Council District 5
FY22 | Fall 2021 |  | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4532 W BROADWAY | 5 | 5 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | ELLIOTT AVE & S 31 ST | 5 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 351 N 25TH ST | 5 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2934 PORTLAND AVE | 5 | 5 | 2441.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 809 S 38TH ST | 5 | 5 | 4485 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 734 S 38TH ST | 5 | 5 | 6245.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 N 26TH ST | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 813 S 45TH ST | 5 | 5 | 16905 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4517 BREWSTTER AVE | 5 | 5 | 6957.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2814 ROWAN ST | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4629 BREWSTER AVE | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 808 S 45TH ST | 5 | 5 | 6146.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4325 VERMONT AVE | 5 | 4 | 11627.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2020 |  | 1703 S BROOK ST | 6 | 5 | 6720 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 711 COLORADO AVE | 6 | 5 | 2930 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 821 HUMLER ST | 6 | 5 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  | 8146 410 8107 148225 899998 | District 6
FY20 | Fall 2020 |  | 1408 HOMEVIEW DR | 6 | 5 | 15726.25 |  | 8143 410 8211 148472 822705 | Public Works
FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  | 8143 410 8211 148472 822705 | Public Works
FY18 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 6 |  | 30900.74 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2020 |  | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1815 Hale Ave | 6 | 4 | 822.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 1388 S 6TH ST | 6 | 5 | 20700 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2531 GARLAND AVE | 6 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2328 OSAGE AVE | 6 | 5 | 11063 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1709 HALE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 724 CAWTHON ST | 6 | 5 | 1395.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1734 HALE AVE | 6 | 5 | 1744.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1435 LARCHMONNT AVE | 6 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S 15TH ST & PRENTICE ST | 6 | 5 | 1461.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 HOEVIEW DR | 6 | 4 | 11691.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1440 S FLOYD ST | 6 | 5 | 5612 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2207 W OAK ST | 6 | 5 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3212 UTAH AVE | 6 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3236 UTAH AVE | 6 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1501 EARL AVE | 6 | 4 | 2389.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3237 UTAH AVE | 6 | 4 | 2724.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1503 EARL AVE | 6 | 5 | 3917.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3249 UUTAH AVE | 6 | 4 | 6644.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1424 EARL AVE | 6 | 4 | 7040.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3210 UTAH AVE | 6 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 629 W ORMSBY AVE | 6 | 4 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 635 PARK AVE | 6 | 5 | 2821.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 422 W ORMSBY AVE | 6 | 5 | 8203.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 425 W ORMSBY AVE | 6 | 5 | 16943.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 509 W ORMSBY AVE | 6 | 5 | 20061.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 720 W ST CATHERINE ST | 6 | 5 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1265 S BROOK ST | 6 | 5 | 4784 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1261 S BROOK ST | 6 | 5 | 6210 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1020 S 4TH ST | 6 | 5 | 15678.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 1408-1410 Homeview Dr | 6 | 5 | 20154.93 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1601 SHADY LN | 8 | 5 | 4634.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2114 DOUGLASS BLVD | 8 | 5 | 7176 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1523 MORTON AVE | 8 | 5 | 5014 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2107 DOUGLASS BLVD | 8 | 4 | 33056.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2143 WOODBOURNE AVE | 8 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1500 EDGEWOOD PL | 8 | 4 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2512 DUNDEE RD | 8 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2313 BOULEVARD NAPOLEON | 8 | 4 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1910 HARVARD DR | 8 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2315 BONNYCASTLE AVE | 8 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  | 8138 410 8107 148227 822705 | Council District 9
FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 1644.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 100 N BAYLY AVE | 9 | 5 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 112 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2423 LINDSAY AVE | 9 | 5 | 2574.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 227 CORNELL PL | 9 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2030 EMERALD AVE | 9 | 5 | 4335.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 102 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2238 SYCAMORE AVE | 9 | 5 | 4451.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4011 RIVULET LN | 11 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2824 SIX MILE LN | 11 | 5 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's | 8500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  | 8138 410 8107 148412 822705 | Council District 12
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 12 |  | 278.8 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY18 | Spring 2021 |  | 9303 Minute Men Ct | 13 | 5 | 1283.84 |  | 8133 410 8211 148396 822705 | Public Works
FY18 | Spring 2021 |  | 8114 ATLANTA PKY | 13 | 5 | 140 |  | 8133 410 8211 148396 822705 | Public Works
FY18/21 | Spring 2021 |  | 804 FLICKER RD | 13 | 4 | 1324.72 |  | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
FY21 | Spring 2021 |  | 128 ELK RIVER DR | 13 | 5 | 2239.73 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 9402 Balance Ln | 13 | 5 | 7456.8 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7327 SOUTHSIDE DR | 13 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 7513 Wimstock Ave | 14 | 5 | 3269.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6223 Bethany Ln | 14 | 4 | 1217.6 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6222-6224 Bethany Ln | 14 | 5 | 853.84 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 5708 Fruitwood Dr | 14 | 5 | 458.24 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 8406 Devonshire Dr | 14 | 5 | 2344 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6300 W Pages Ln | 14 | 5 | 1328.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6911 Ethan Allen Way | 14 | 4 | 2201.6 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 9805 Sunway Dr | 14 | 5 | 366.98 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1410 Weyler Ave | 15 | 5 | 676.8 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1409 Southgate Ave | 15 | 4 | 422.4 |  | 8143 410 8211 148472 822705 | Public Works
Fy21 | Spring 2021 |  | 1609 Cherry Way | 15 | 4 | 412.8 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3703 W WHEATMORE DR | 15 | 5 | 12586.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3613 WOODRUFF AVE | 15 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 626 RAWLINGS ST | 15 | 5 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 542 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 546 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 548 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3416 Powell Ave | 15 | 4 | 151.4 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | 343.68 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | 609 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Fall 2021 |  | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd | 15 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11412 Hammond Dr | 16 | 5 | 1761.6 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11505 Fisherman Way | 16 | 5 | 1813.59 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 1140 Kendrick Dr | 16 | 5 | 1369.83 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11414 Kendrick Dr | 16 | 5 | 719.03 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11500 Kendrick Dr | 16 | 5 | 538.06 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11506 Kendrick Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11514 Kendrick Dr | 16 | 5 | 403.7 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11516 Kendrick Dr | 16 | 5 | 210.88 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11415 Kendrick Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5410 Baywood Dr | 16 | 5 | 224.14 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5406 Baywood Dr | 16 | 5 | 1157.62 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5311 Drifton Dr | 16 | 5 | 2473.37 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5308 Drifton Dr | 16 | 5 | 1831.93 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5304 Drifton Dr | 16 | 5 | 888.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Baywood Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11513 Fisherman Way | 16 | 5 | 881.38 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11202 Deham Dr | 16 | 5 | 336.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5412 Lithia Dr | 16 | 5 | 1441.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11306 Deham Dr | 16 | 5 | 1435.24 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11307 Deham Dr | 16 | 5 | 988.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11301 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11215 Deham Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 501 Lithia Dr | 16 | 5 | 2094.49 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 17 | 4's and 5's | 1872 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Spring 2022 |  | VARIOUS SIDEWALK REPAIRS | 18 |  | 4930.4 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  | 8146 410 8211 148487 822705 | Public Works
FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 1649.82 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 412 LAKE FOREST PKY | 19 | 4 | 2092.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 505 EDGEFOREST PL | 19 | 4 | 3159 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1337 HEAFER RD | 19 | 4 | 2093 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Spring 2021 |  | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  | 8137 410 8211 148452 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 20 |  | 209 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY21 | Summer 2021 |  | 223 Iroquios Ave | 21 | 4 | 2323 | 72 | 8146 410 8211 148487 822705 | Public Works
FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 5803 BUCKS LN | 22 | 4 | 6141 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6016 Mercury Dr | 22 | 5 | 1223.33 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Spring 2021 |  | 3806 GREENWICH RD | 22 | 4 | 1794 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3812 GREENWICH RD | 22 | 5 | 2392 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  | 8102 410 8105 148838 822705 | Council District 22
FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7818 APPLEVIEW LN | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7820 APPLEVIEW LN | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6711 VANDRE AVE | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6707 VANDRE AVE | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 23 |  | 2016 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5204 MONACO DR | 24 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Willowcreek Dr from Old South Park Rd to Maplecreek DR | 24 | 2's through 5's | 75000 |  | 8148 410 8211 148560 822705 | Public Works
|  |  | Sidewalk Repairs by D25 | 25 |  | 625.15 |  | 8101 410 8199 148237 822702 | Council District 25
FY22 | Winter 2021 |  | Stone Wynde Dr fro mValley College Dr to Pages Ln | 25 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 26 |  | 1602 |  | 8137 410 8111 148271 822705 | Council District 26
FY22 | Spring 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr | 26 | 2's through 5's | 80000 |  | 8148 410 8211 148560 822705 | Public Works
[5 empty] | Total | 3091847.8189 | 181138.58

## October 2021
October 2021 Sidewalk Repair Schedule
Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Cost | Funding Accounts | Funding Source
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 8672 410 8106 048201 822705 | District 1
FY21 | Summer 2021 |  | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4114 WINNROSE WAY | 1 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1700 S 38TH ST | 1 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1156 S 26TH ST | 1 | 5 | 12790.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1152 S 26TH ST | 1 | 5 | 13673.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 371 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1433 HAZEL ST | 1 | 4 | 13953.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 S 42ND ST | 1 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
Proposed for FY22 | Summer 2021 |  | 5023 Broadmoor Blvd | 2 | 4 | 206.4 | 25254.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 4109 St Charles St | 2 | 5 | 12914 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2
FY19 | Summer 2021 |  | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2
FY19 | Summer 2021 |  | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4108 St Charles St | 2 | 5 | 1919.36 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4404 E Indian Trl | 2 | 5 | 784 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4310 E Indian Trl | 2 | 4 | 229.12 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Proposed for FY22 | Summer 2021 |  | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY21 | Summer 2021 |  | 1403 FOREST DR | 2 | 4 | 897 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY19 | Summer 2021 |  | 4907 Sunday Dr | 2 | 4 | 251.84 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
FY22 | Fall 2021 |  | 5101 MEDITERRANEAN CT | 2 | 4 | 598 |  | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
|  |  | VARIOUS SIDEWALK REPAIRS TBD by District 2 Council Office | 2 |  | 6609 |  | 8133 410 8111 148221 822705 | District 2
FY22 | Summer 2021 |  | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 45692 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | West side of Robinhood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's |  |  | 8148 410 8211 148560 822705 | Public Works
FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Summer 2021 |  | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3303 UTAH AVE | 3 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3304 UTAH AVE | 3 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3315 UTAH AVE | 3 | 5 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 200 S 7TH ST | 4 | 5 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Fall 2021 |  | 833 W MAIN ST | 4 | 4 | 3000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Fall 2021 |  | 200 S 5TH ST | 4 | 4 | 6000 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Fall 2021 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  | 8137 410 8211 148452 822705 | Public Works
FY20 | Fall 2021 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  | 8143 410 8211 148472 822705 | Public Works
FY19 | Fall 2021 |  | VARIOUS SIDEWALK REPAIRS | 4 |  | 17180 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1216 FERN ST | 4 | 5 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 100 E JEFFERSON ST | 4 | 4 | 33189 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PAYNE ST | 4 | 5 | 3070.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1612 CEDAR ST | 4 | 4 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 426 E ORMSBY AVE | 4 | 4 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1213 W CHESTUNUT ST | 4 | 5 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1202 LEXINGTON RD | 4 | 4 | 348.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 400 S 6TH ST | 4 | 4 | 1129.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1910 MAGAZINE ST | 4 | 4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 913 E LIBERTY ST | 4 | 5 | 6708.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1017 ST PAUL CT | 4 | 4 | 3363.75 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 841 E WASHINGTON ST | 4 | 5 | 41259.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 550 3RD ST | 4 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 810 GOULLON CT | 4 | 5 | 3759.8611 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | S 5TH ST & W JEFFERSON ST | 4 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 207 S 42ND ST | 5 | 4 | 1777.6 | 5517.31 | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 123 N 42nd St | 5 | 5 | 1112.6 | 5517.31 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 2673.54 | 8148 410 8211 148560 822705 | Public Works
FY18 | Summer 2021 |  | 616 N 28TH ST | 5 | 5 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 650 S 31st St | 5 | 5 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works
FY18 | Summer 2021 |  | 2146 DUNCAN ST | 5 | 5 |  |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 4509-4515 W Market St | 5 | 5 | 3960.6 | 2743.77 | 8146 410 8211 148487 822705 | Public Works
FY18 | Summer 2021 |  | 351 N 28th St | 5 | 5 | 555.33 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2021 |  | 3640 River Park Dr | 5 | 5 | 5916 | 3008.25 | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  | 8138 410 8107 148280 822705 | Council District 5
FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  | 8138 410 8107 148280 822705 | Council District 5
FY22 | Fall 2021 |  | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4532 W BROADWAY | 5 | 5 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | ELLIOTT AVE & S 31 ST | 5 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 351 N 25TH ST | 5 | 5 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2934 PORTLAND AVE | 5 | 5 | 2441.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 809 S 38TH ST | 5 | 5 | 4485 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 734 S 38TH ST | 5 | 5 | 6245.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 N 26TH ST | 5 | 4 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 813 S 45TH ST | 5 | 5 | 16905 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4517 BREWSTTER AVE | 5 | 5 | 6957.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2814 ROWAN ST | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4629 BREWSTER AVE | 5 | 4 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 808 S 45TH ST | 5 | 5 | 6146.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4325 VERMONT AVE | 5 | 4 | 11627.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2020 |  | 1703 S BROOK ST | 6 | 5 | 6720 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 711 COLORADO AVE | 6 | 5 | 2930 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2020 |  | 821 HUMLER ST | 6 | 5 | 6500 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  | 8146 410 8107 148225 899998 | District 6
FY20 | Fall 2020 |  | 1408 HOMEVIEW DR | 6 | 5 | 15726.25 |  | 8143 410 8211 148472 822705 | Public Works
FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  | 8143 410 8211 148472 822705 | Public Works
FY18 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 6 |  | 30900.74 |  | 8133 410 8211 148396 822705 | Public Works
FY21 | Summer 2020 |  | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 1815 Hale Ave | 6 | 4 | 822.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Summer 2021 |  | 1388 S 6TH ST | 6 | 5 | 20700 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2531 GARLAND AVE | 6 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2328 OSAGE AVE | 6 | 5 | 11063 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1709 HALE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 724 CAWTHON ST | 6 | 5 | 1395.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1734 HALE AVE | 6 | 5 | 1744.1667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1435 LARCHMONNT AVE | 6 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | S 15TH ST & PRENTICE ST | 6 | 5 | 1461.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 HOEVIEW DR | 6 | 4 | 11691.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1440 S FLOYD ST | 6 | 5 | 5612 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2207 W OAK ST | 6 | 5 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3236 UTAH AVE | 6 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3237 UTAH AVE | 6 | 4 | 2724.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1503 EARL AVE | 6 | 5 | 3917.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3212 UTAH AVE | 6 | 5 | 664.4444 | 23535.09 | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1501 EARL AVE | 6 | 4 | 2389.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3249 UUTAH AVE | 6 | 4 | 6644.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1424 EARL AVE | 6 | 4 | 7040.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3210 UTAH AVE | 6 | 5 | 2990 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 629 W ORMSBY AVE | 6 | 4 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 635 PARK AVE | 6 | 5 | 2821.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 422 W ORMSBY AVE | 6 | 5 | 8203.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 425 W ORMSBY AVE | 6 | 5 | 16943.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 509 W ORMSBY AVE | 6 | 5 | 20061.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 720 W ST CATHERINE ST | 6 | 5 | 5813.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1265 S BROOK ST | 6 | 5 | 4784 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1261 S BROOK ST | 6 | 5 | 6210 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 1020 S 4TH ST | 6 | 5 | 15678.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Summer 2021 |  | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 1408-1410 Homeview Dr | 6 | 5 | 20154.93 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1601 SHADY LN | 8 | 5 | 4634.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2114 DOUGLASS BLVD | 8 | 5 | 7176 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1523 MORTON AVE | 8 | 5 | 5014 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2107 DOUGLASS BLVD | 8 | 4 | 33056.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2143 WOODBOURNE AVE | 8 | 4 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1500 EDGEWOOD PL | 8 | 4 | 2906.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2512 DUNDEE RD | 8 | 4 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2313 BOULEVARD NAPOLEON | 8 | 4 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1910 HARVARD DR | 8 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2315 BONNYCASTLE AVE | 8 | 5 | 3322.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  | 8138 410 8107 148227 822705 | Council District 9
FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  | 8138 410 8107 148227 822705 | Council District 9
FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 1644.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 100 N BAYLY AVE | 9 | 5 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 112 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2423 LINDSAY AVE | 9 | 5 | 2574.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 227 CORNELL PL | 9 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2030 EMERALD AVE | 9 | 5 | 4335.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 102 N EWING AVE | 9 | 4 | 3737.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2238 SYCAMORE AVE | 9 | 5 | 4451.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4011 RIVULET LN | 11 | 4 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2824 SIX MILE LN | 11 | 5 | 1196 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's | 8500 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  | 8138 410 8107 148412 822705 | Council District 12
FY19 | Spring 2020 |  | VARIOUS SIDEWALK REPAIRS | 12 |  | 278.8 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | 8148 410 8211 148560 822705 | Public Works
FY18 | Spring 2021 |  | 9303 Minute Men Ct | 13 | 5 | 1283.84 | 1846.55 | 8133 410 8211 148396 822705 | Public Works
FY18 | Spring 2021 |  | 8114 ATLANTA PKY | 13 | 5 | 140 | 1846.55 | 8133 410 8211 148396 822705 | Public Works
FY18/21 | Spring 2021 |  | 804 FLICKER RD | 13 | 4 | 1324.72 | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
FY21 | Spring 2021 |  | 128 ELK RIVER DR | 13 | 5 | 2239.73 | 1846.55 | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 9402 Balance Ln | 13 | 5 | 7456.8 | 1846.55 | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7327 SOUTHSIDE DR | 13 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 7513 Wimstock Ave | 14 | 5 | 3269.6 | 1846.55 | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6223 Bethany Ln | 14 | 4 | 1217.6 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6222-6224 Bethany Ln | 14 | 5 | 853.84 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 5708 Fruitwood Dr | 14 | 5 | 458.24 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 8406 Devonshire Dr | 14 | 5 | 2344 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 6300 W Pages Ln | 14 | 5 | 1328.27 | 1846.55 | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6911 Ethan Allen Way | 14 | 4 | 2201.6 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Spring 2021 |  | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
FY21 | Winter 2021 |  | 7014 Ethan Allen Way | 14 | 4 | 550.08 |  | 8146 410 8107 148279 822705 | Council District 14
FY21 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 9805 Sunway Dr | 14 | 5 | 366.98 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | TBD | 14 | 4's or 5's | 8266.73 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6007, 6010, and 6012 Alanadale Dr | 14 | Curb Repair | 4585.07 |  |  | Council District 14
FY21 | Spring 2021 |  | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Winter 2021 |  | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1410 Weyler Ave | 15 | 5 | 676.8 |  | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 1409 Southgate Ave | 15 | 4 | 422.4 |  | 8143 410 8211 148472 822705 | Public Works
Fy21 | Spring 2021 |  | 1609 Cherry Way | 15 | 4 | 412.8 | 1846.55 | 8143 410 8211 148472 822705 | Public Works
FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3703 W WHEATMORE DR | 15 | 5 | 12586.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3613 WOODRUFF AVE | 15 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 626 RAWLINGS ST | 15 | 5 | 2491.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 542 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 546 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 548 RAWLINGS ST | 15 | 3,4 | 8970 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 664.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Fall 2021 |  | 3416 Powell Ave | 15 | 4 | 151.4 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | 343.68 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | 609 |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | TBD |  | TBD | Council District 15
FY22 | Fall 2021 |  | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd | 15 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 |  | 37259 |  | Waiting on D15 Account / 8148 410 8211 148560 822705 | Public Works / Council District 15
FY21 | Fall 2021 |  | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11412 Hammond Dr | 16 | 5 | 1761.6 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11505 Fisherman Way | 16 | 5 | 1813.59 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 1140 Kendrick Dr | 16 | 5 | 1369.83 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11414 Kendrick Dr | 16 | 5 | 719.03 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11500 Kendrick Dr | 16 | 5 | 538.06 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11506 Kendrick Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11514 Kendrick Dr | 16 | 5 | 403.7 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11516 Kendrick Dr | 16 | 5 | 210.88 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11415 Kendrick Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5410 Baywood Dr | 16 | 5 | 224.14 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5406 Baywood Dr | 16 | 5 | 1157.62 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5311 Drifton Dr | 16 | 5 | 2473.37 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5308 Drifton Dr | 16 | 5 | 1831.93 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5304 Drifton Dr | 16 | 5 | 888.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5204 Baywood Dr | 16 | 5 | 201.85 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11513 Fisherman Way | 16 | 5 | 881.38 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11202 Deham Dr | 16 | 5 | 336.29 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 5412 Lithia Dr | 16 | 5 | 1441.84 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11306 Deham Dr | 16 | 5 | 1435.24 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11307 Deham Dr | 16 | 5 | 988.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11301 Deham Dr | 16 | 5 | 584.53 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 11215 Deham Dr | 16 | 5 | 448.27 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 501 Lithia Dr | 16 | 5 | 2094.49 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  | 8101 410 8105 148234 822705 | Council District 16
FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  | 8101 410 8105 148234 822705 | Council District 16
FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Fall 2020 |  | VARIOUS SIDEWALK REPAIRS | 17 | 4's and 5's | 1872 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  | 8148 410 8211 148560 822705 | Public Works
FY19 | Spring 2022 |  | VARIOUS SIDEWALK REPAIRS | 18 |  | 4930.4 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  | 8146 410 8211 148487 822705 | Public Works
FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 1649.82 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  | 8137 410 8211 148452 822705 | Public Works
FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 412 LAKE FOREST PKY | 19 | 4 | 2092.4 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 | 4177.68 | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 505 EDGEFOREST PL | 19 | 4 | 3159 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 1337 HEAFER RD | 19 | 4 | 2093 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  | 8146 410 8211 148487 822705 | Public Works
FY19 | Spring 2021 |  | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  | 8137 410 8211 148452 822705 | Public Works
FY19 | Spring 2021 |  | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  | 8137 410 8211 148452 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 20 |  | 209 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  | 8102 410 8105 148837 822705 | Council District 20
FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  | 8102 410 8105 148837 822705 | Council District 20
FY21 | Summer 2021 |  | 223 Iroquios Ave | 21 | 4 | 2323 | 72 | 8146 410 8211 148487 822705 | Public Works
FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Spring 2021 |  | 5803 BUCKS LN | 22 | 4 | 6141 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 6016 Mercury Dr | 22 | 5 | 1223.33 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Spring 2021 |  | 3806 GREENWICH RD | 22 | 4 | 1794 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Spring 2021 |  | 3812 GREENWICH RD | 22 | 5 | 2392 |  | 8146 410 8211 148487 822705 | Public Works
FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  | 8102 410 8105 148838 822705 | Council District 22
FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  | 8102 410 8105 148838 822705 | Council District 22
FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Summer 2021 |  | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 | 8146 410 8211 148487 822705 | Public Works
FY21 | Summer 2021 |  | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7818 APPLEVIEW LN | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 7820 APPLEVIEW LN | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6711 VANDRE AVE | 23 | 4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY21 | Summer 2021 |  | 6707 VANDRE AVE | 23 | 3,4 |  |  | 8146 410 8211 143058 899998 | Council District 23
FY22 | Winter 2021 |  | 8214 Happiness Way | 23 | 5 | 5112.44 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 23 |  | 2016 |  | 8137 410 8211 148452 822705 | Public Works
FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  | 8148 410 8211 148560 822705 | Public Works
FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  | 8146 410 8211 148487 822705 | Public Works
FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 5204 MONACO DR | 24 | 5 | 996.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Winter 2021 |  | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  | 8148 410 8211 148560 822705 | Public Works
FY22 | Spring 2022 |  | Willowcreek Dr from Old South Park Rd to Maplecreek DR | 24 | 2's through 5's | 75000 |  | 8148 410 8211 148560 822705 | Public Works
|  |  | Sidewalk Repairs by D25 | 25 |  | 625.15 |  | 8101 410 8199 148237 822702 | Council District 25
FY22 | Winter 2021 |  | Stone Wynde Dr fro mValley College Dr to Pages Ln | 25 | 2's through 5's | 50000 |  | 8148 410 8211 148560 822705 | Public Works
FY19 |  |  | VARIOUS SIDEWALK REPAIRS | 26 |  | 1602 |  | 8137 410 8111 148271 822705 | Council District 26
FY22 | Spring 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr | 26 | 2's through 5's | 80000 |  | 8148 410 8211 148560 822705 | Public Works
[5 empty] | Total | 3147621.1389 | 251830.15

## November 2021
Contractor | PO # | Area | Construciton Status | Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | Invoice #
Precision Concrete Cutting |  | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1 |  |  | 120521
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  |  | 120015M-76
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Inspected | FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1152-1156 S 26TH ST | 1 | 5 | 12790.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 3714 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1433-1451 HAZEL ST | 1 | 4 | 13953.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 808 & 810 S 42ND ST | 1 | 4 | 4983.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 2 | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 2 | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 2 | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 2 | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 2 | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 2 | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 2 | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 45692 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 |  | West side of Robinhood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's |  |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 3 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Inspected | FY22 | Fall 2021 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 | November | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 | November | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 | November | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.28
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 | November | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 59.2
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 | November | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 22.94
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 200 S 7TH ST | 4 | 5 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY19 | Fall 2021 |  | 833 W MAIN ST | 4 | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 2 | Not Inspected | FY19 | Fall 2021 |  | 200 S 5TH ST | 4 | 4 | 6000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 2 | Not Inspected | FY19 | Fall 2021 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 2 | Not Inspected | FY20 | Fall 2021 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 1216 FERN ST | 4 | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 100 E JEFFERSON ST | 4 | 4 | 33189 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD | 368745-10 | 2 | Not Inspected | FY22 | Fall 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD | 368745-10 | 2 | Not Inspected | FY22 | Fall 2021 |  | 1910-1912 MAGAZINE ST | 4 | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD | 368745-10 | 2 | Not Inspected | FY22 | Fall 2021 |  | 550 S 3RD ST (possibility Utilities' fault) | 4 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 1 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 23.25
Seven Seas | 368566-5 | 1 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 5 | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 |  | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  |  | 0 | 8138-410-8107-148280-822705 | Council
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  |  | 0 | 8138 410 8107 148280 822705 | Council District 5
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 809 S 38TH ST | 5 | 5 | 4485 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 734 S 38TH ST | 5 | 5 | 6245.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2814 ROWAN ST | 5 | 4 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 6 | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.67
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 635 PARK AVE | 6 | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | November | 1265 S BROOK ST | 6 | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 | November | 1261 S BROOK ST | 6 | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56
TBD | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 | November | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 6 | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 6 | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works |  | 6.03
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 6 | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 6 | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 13.5
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 6 | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
|  | 2 | Not Inspected | FY21 | Fall 2020 |  | 1703 S BROOK ST | 6 | 5 | 6720 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2020 |  | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2020 |  | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2020 |  | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2020 |  | 821 HUMLER ST | 6 | 5 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
|  | 2 | Not Inspected | FY20 | Fall 2020 |  | 1408 HOMEVIEW DR | 6 | 5 | 15726.25 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works
|  | 2 | Not Inspected | FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Summer 2020 |  | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Summer 2021 |  | 1815 Hale Ave | 6 | 4 | 822.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Summer 2021 |  | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 |  | 509 W ORMSBY AVE (Waiting on tree Inspections) | 6 | 5 | 20061.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 2 | Not Inspected | FY21 | Fall 2021 |  | 1408-1410 Homeview Dr | 6 | 5 | 20154.93 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 8 | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Not Inspected | FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  |  |  | FY22 |  |  | 2219-2221 Talbot Ave | 8 | 5 | 15737 |  |  |  | 8146-410-8107-148903-447001 8102-410-8105-148903-401101 | Council
TBD |  |  |  | FY22 |  |  | 2225 Talbott Ave | 8 | 5 | 2412 |  |  |  | 8102-410-8105-148903-401101 8138-410-8107-148903-447001 | Council
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  |  | Sent to Contractor |  |  |  | 1846 Frankfort Ave | 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Ramps at Pope and State St | 9 |  | 1644.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 5000
TBD |  | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Complete | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 10 | 5 | [7 empty] | 5.73
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 4011 RIVULET LN | 11 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 2824 SIX MILE LN | 11 | 5 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's |  |  |  | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2021-01-3
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 13 | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 13 | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 13 | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 13 | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 13 | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Spring 2022 | September | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 14 | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 14 | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 14 | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 14 | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 8406 Devonshire Dr | 14 | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 14 | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 14 | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
|  | 4 | Not Inspected | FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-01-3
|  | 4 | Not Inspected | FY21 | Winter 2021 |  | 7014 Ethan Allen Way | 14 | 4 | 550.08 |  |  | 0 | 8146 410 8107 148279 822705 | Council District 14
|  | 4 | Not Inspected | FY21 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 4 | Not Inspected | FY21 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 4 | Not Inspected | FY21 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 9805 Sunway Dr | 14 | 5 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 4's or 5's | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 6007, 6010, and 6012 Alanadale Dr | 14 | Curb Repair | 4585.07 |  |  | 0 |  | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 15 | 5 | 676.8 |  |  |  | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 15 | 4 | 422.4 |  |  |  | 8143 410 8211 148472 822705 | Public Works |  |  | 2021-01-3
Riverside Paving | 368756-4 | 4 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 15 | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | September | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-01-1
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Fall 2021 | September | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works
|  | 4 | Not Inspected | FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
|  | 4 | Not Inspected | FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
|  | 4 | Not Inspected | FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3705 W WHEATMORE DR | 15 | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 542-546 RAWLINGS ST | 15 | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | 343.68 |  |  | 0 | TBD | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | 609 |  |  | 0 | TBD | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | TBD |  |  | 0 | TBD | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | TBD |  |  | 0 | TBD | Council District 15
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 15 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 |  | 37259 |  |  | 0 | Waiting on D15 Account / 8148 410 8211 148560 822705 | Public Works / Council District 15
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11412 Hammond Dr | 16 | 5 | 1761.6 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11505-11509 Fisherman Way | 16 | 5 | 1813.59 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11408 Kendrick Dr | 16 | 5 | 1369.83 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11414 Kendrick Dr | 16 | 5 | 719.03 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11500 Kendrick Dr | 16 | 5 | 538.06 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11506 Kendrick Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11514 Kendrick Dr | 16 | 5 | 403.7 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11516 Kendrick Dr | 16 | 5 | 210.88 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11415 Kendrick Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor |  |  |  | 5401 Baywood Dr | 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5410 Baywood Dr | 16 | 5 | 224.14 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5404-5406 Baywood Dr | 16 | 5 | 1157.62 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5311 Drifton Dr | 16 | 5 | 2473.37 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5308 Drifton Dr | 16 | 5 | 1831.93 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5304 Drifton Dr | 16 | 5 | 888.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5204 Baywood Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11513 Fisherman Way | 16 | 5 | 881.38 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11202 Deham Dr | 16 | 5 | 336.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5412 Lithia Dr | 16 | 5 | 1441.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11304-11306 Deham Dr | 16 | 5 | 1435.24 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11307 Deham Dr | 16 | 5 | 988.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11301 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 11215 Deham Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 5501 Lithia Dr | 16 | 5 | 2094.49 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
[7 empty] | 4429 Rockwood Dr | 18 | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148268-822705 | Council District 18
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 505 EDGEFOREST PL | 19 | 4 | 3159 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Not Inspected | FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  |  | 0 | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 2093 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
|  | 5 | Not Inspected | FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 412-414 LAKE FOREST PKY | 19 | 4 | 2092.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 21 | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works
|  | 4 | Not Inspected | FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 22 | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 22 | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 22 | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 22 | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2021-01-5 and 1097 (2nd Invoice was for Triumph)
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 23 | 3,4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 23 | 4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 23 | 4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 23 | 3,4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 8214 Happiness Way | 23 | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | 5204 MONACO DR | 24 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Willowcreek Dr from Old South Park Rd to Maplecreek DR | 24 | 2's through 5's | 75000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 4 | Not Inspected |  |  |  | Sidewalk Repairs by D25 | 25 |  | 625.15 |  |  | 0 | 8101 410 8199 148237 822702 | Council District 25
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | Stone Wynde Dr fro mValley College Dr to Pages Ln | 25 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr | 26 | 2's through 5's | 80000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
[9 empty] | Total | 2648907.9289 | 266046.56
Note on H60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## December 2021
| PO # | Area | Construciton Status | Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | inspection month | inspection notes
Seven Seas | 368566-5 | 1 | Inspected | FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1
Precision Concrete Cutting |  | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 24.39
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1152-1156 S 26TH ST | 1 | 5 | 12790.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 83.33
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 3714 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1433-1451 HAZEL ST | 1 | 4 | 13953.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 808 & 810 S 42ND ST | 1 | 4 | 4983.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.33
|  | 1 | Not Inspected | FY22 |  |  | 1147-1149 S 42nd St | 1 |  | 2137.07 |  |  |  | 8133-410-8107-148283-822705 | Council Funds
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 2 | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 2 | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 2 | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 2 | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 2 | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 2 | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 2 | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | 513.78
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  | 17.15
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.55
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 3 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.88
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.83
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.94
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 42
Seven Seas | 368566-5 | 1 | Inspected | FY22 | Fall 2021 | October | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | See Lacevine Rd | #VALUE! | 8148 410 8211 148560 822705 | Public Works |  | 40
|  | 2 | Complete | FY21 | Fall 2021 | December | 200 S 7TH ST | 4 | 5 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | Inspected | FY21 | Fall 2021 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 35.78 | 2021-12-21 | 23'X14' OF DW
|  | 2 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | Inspected | FY21 | Fall 2021 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6.44 | 2021-12-21 | 5'X2' OF AND 6'X8' OF SW
|  | 2 | Inspected | FY19 | Fall 2021 |  | 833 W MAIN ST | 4 | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0.67 | 2021-12-21 | 2'X3' OF BRICK RESET (RR TRACK)
|  | 2 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 4 | 6000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | Inspected | FY19 | Fall 2021 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  | 2021-12-21 | LWC BORE UNDER THE RR ( MSD PAVED DRIVEWAY ENTRANCE- SW REPAIR AND RAMP IS NOW REQUIRED ) MEASURE QUANTITIES AFTER CONSTRUCTION IS COMPLETE BY OTHERS
|  | 2 | Inspected | FY20 | Fall 2021 |  | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  | 32 | 2021-12-21 | 12'X6' AND 30'X6' AND 6'X6' OF SW
|  | 2 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 4 | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | REPAIRED BY OTHERS
|  | 2 | Inspected | FY21 | Fall 2021 |  | 514 BARRET AVE | 4 | 5 | 10925 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 1 | 39.11 | 2021-12-21 | 17'X6' AND 25'X10' OF SW, 1 WM , 22" TREE
|  | 2 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 4 | 33189 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | SAW CUT AND REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19
TBD | 368745-10 | 2 | Inspected | FY22 | Fall 2021 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 | 2021-12-21 | 8'X6' OF SW AND 8'X6' UTILITY VAULT 2" BELOW SW GRADE
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.91
TBD | 368745-10 | 2 | Inspected | FY22 | Fall 2021 |  | 1910-1912 MAGAZINE ST | 4 | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15 | 2021-12-21 | 15'X9' OF SW AND 14" TREE
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.28
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 59.2
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-10 | 2 | Not Inspected | FY22 | Fall 2021 |  | 550 S 3RD ST (possibility Utilities' fault) | 4 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44 | 2021-12-21 | STREET LIGHT BASE REPAIR BY OTHERS, 1-2'X2' SW SQUARE
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 5 | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas |  | 1 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 23.25
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 5 | 13456 |  |  | 0 | 8138-410-8107-148280-822705 | Council | 2 | 46
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 | December | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  |  | 0 | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
Seven Seas | 368566-5 | 1 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 42.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 | 5 | [5 empty] | Public Works? |  | 50.83
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15.11
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.75
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 35.94
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 5 | 4485 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 5 | 6245.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 37.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2814 ROWAN ST | 5 | 4 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.89
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 21
|  | 2 | Inspected | FY21 | Fall 2020 | December | 1703 S BROOK ST | 6 | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
|  | 2 | Inspected | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | REPAIRED BY OTHERS
|  | 2 | Inspected | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | REPAIRED BY OTHERS
|  | 2 | Inspected | FY21 | Fall 2020 | December | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | 6'X6' OF SW AT 2103 GRAND AVE AND 5'X6' OF SW AT 2100 GRAND AVE (by others)
|  | 2 | Inspected | FY21 | Fall 2020 | December | 821 HUMLER ST | 6 | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
|  | 2 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
|  | 2 | Not Inspected | FY20 | Fall 2020 |  | 1408-1410 HOMEVIEW DR | 6 | 5 | 15726.25 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  |  | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
|  | 2 | Inspected | FY20 | Fall 2020 |  | 1336 S 6TH ST | 6 | 4 | 747.5 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  |  |  | 4'X6' OF SW AND 1 TREE
|  | 2 | Inspected | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  |  | DECEMBER
|  | 2 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 6 | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | 2.7 | 2021-12-28 | 5'X5' OF SW OR RAMP
|  | 2 | Inspected | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | 3.33 |  | 6'X5' OF SW BY OTHERS
TBD | 368745-10 | 2 | Inspected | FY22 | Summer 2021 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17.7 |  | 4'X22' OF DW AND 9'X4' RAMP AND 6'X4' RAMP
TBD | 368745-10 | 2 | Inspected | FY22 | Summer 2021 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 9.33 |  | 3-5'X4' SW PANELS AND 6'X4' RAMP
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 4715 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 5-6'x'6 SW PANELS AND10'x6' AND 12'x6' OF SW AND 3 TREES
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 6 | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67
Joash Construction | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 |  | 1434 THORNBERRY AVE | 6 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 6'X4' SW RAMP AND ? OF SW. Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 6 | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 6 | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 6 | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 6 | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 6 | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 635 PARK AVE | 6 | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 |  | 509 W ORMSBY AVE | 6 | 5 | 20061.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 33 |  | 2-9'x12' sw panels AND 8'X10' OF SW AND 8'X4' OF RESET BRICK (remove and replace public trees, straight cut roots on private property tree)
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 1265 S BROOK ST | 6 | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 | December | 1261 S BROOK ST | 6 | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56
TBD | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81
TBD |  | 3 | Not Inspected | FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 8 | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Not Inspected | FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  |  | Not Inspected | FY22 |  |  | 2219-2221 TALBOTT AVE | 8 |  | 18149 |  |  |  | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 2.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 26.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 3.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 4.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 49.28
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 17.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 20
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 0
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 8.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 5.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.07
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 30.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1860 Frankfort Ave | 9 | 4 | 3484.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 29.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas |  |  | Sent to Contractor |  |  |  | 1846 Frankfort Ave | 9 | [8 empty] | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 24
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 36.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 64.81
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 22.42
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 1 | 18.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 1 | 18.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 1 | 18
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 33.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 1 | 12
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1819 (or 1821) Frankfort Ave | 9 | 4 | 265.07 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 0
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1823 Frankfort Ave | 9 | 3 | 712.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1825 Frankfort Ave | 9 | 4 | 6660 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 1 | 7.5
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 32.47
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 32.03
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Ramps at Pope and State St | 9 |  | 1644.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 5000
TBD |  | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 45
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 10 | 5 |  | 2107.9 | [5 empty] | 5.73
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 28.67
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 17.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.67 |  | 5'X4' AND 4'X4' OF SW AND TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 11.11
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 5'X5' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 4011 RIVULET LN | 11 | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  |  |  | GRINDING BY OTHERS
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 11 | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | 7002 URANAS DR | 12 | 4 | 1196 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Not Inspected | FY21 | Fall 2021 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 | October | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 | October | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 13 | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 13 | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 13 | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 13 | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 13 | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | October | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  |  | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  | See Beecher St | See Beecher St | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 4 | Not Inspected | FY21 | Spring 2021 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 14 | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 14 | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 14 | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 14 | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 8406 Devonshire Dr | 14 | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 14 | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 14 | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14
|  | 4 | Inspected | FY21 | Winter 2021 |  | 7014 Ethan Allen Way | 14 | 4 | 550.08 |  |  | 0 | 8146 410 8107 148279 822705 | Council District 14 |  | 12.44 | 2021-12-21 | 4'X28' OF SW (THE PROPERTY OWNER RESURFACED THE DRIVEWAY CAUSING A 1" VERTICAL DISPLACEMENT)
|  | 4 | Inspected | FY21 | Fall 2021 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6.44 | 2021-12-21 | 5'X7' AND 5'X7' AND 2'X4' AND 4'X7' OF SW
|  | 4 | Inspected | FY21 | Fall 2021 |  | 7902 NANCY LN | 14 | 4 | 3588 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6.33 | 2021-12-21 | 4'X4' AND 7'X4' OF SW AND 8'X4' OF DW AND 19" TREE 10' FROM THE SIDEWALK (ROOTS?)
|  | 4 | Inspected | FY21 | Fall 2021 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5.33 | 2021-12-21 | 11'X4' OF SW
TBD |  | 4 | Not Inspected | FY22 | Fall 2021 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Fall 2021 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Fall 2021 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Fall 2021 |  | 9805 Sunway Dr | 14 | 5 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 4's or 5's | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 6007, 6010, and 6012 Alanadale Dr | 14 | Curb Repair | 4585.07 |  |  | 0 |  | Council District 14
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | September | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 15 | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 15 | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 15 | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works
|  | 4 | Inspected | FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8 | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33 | 2021-12-21 | 12'X4' OF SW AND 11' OF CURB
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67 | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3705 W WHEATMORE DR | 15 | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 542-546 RAWLINGS ST | 15 | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 15 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 |  | 37259 |  |  | 0 | 8138-410-8107-148223-822702 $15920.38 8133-410-8107-148223-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 14.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 8.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 21.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11412 Hammond Dr | 16 | 5 | 1761.6 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 27.11
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 12.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 16 | 5 | 1813.59 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 15.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 16 | 5 | 1369.83 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 16.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 16 | 5 | 719.03 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 16 | 5 | 538.06 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 8
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 16 | 5 | 403.7 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 4
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 16 | 5 | 210.88 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 1.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 9.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 1.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 9.33
Seven Seas |  | 3 | Sent to Contractor |  |  | December | 5401 Baywood Dr | 16 | [8 empty] | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5410 Baywood Dr | 16 | 5 | 224.14 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 16 | 5 | 1157.62 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 7.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5311 Drifton Dr | 16 | 5 | 2473.37 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5308 Drifton Dr | 16 | 5 | 1831.93 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5304 Drifton Dr | 16 | 5 | 888.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Baywood Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11513 Fisherman Way | 16 | 5 | 881.38 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 0
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11202 Deham Dr | 16 | 5 | 336.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5412 Lithia Dr | 16 | 5 | 1441.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 19.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 16 | 5 | 1435.24 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 3.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11307 Deham Dr | 16 | 5 | 988.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11301 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 10.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11215 Deham Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 4.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5501 Lithia Dr | 16 | 5 | 2094.49 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 12.67
|  | 3 | Inspected | FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
TBD | 381611-4 | 3 | Not Inspected | FY22 | Winter 2021 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD | 381611-4 | 3 | Not Inspected | FY22 | Winter 2021 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD | 381611-4 | 3 | Not Inspected | FY22 | Winter 2021 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.11 | 2022-12-21 | 7'X4' OF SW, TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.78 | 2022-12-21 | 5'X4' AND 8'X4' OF SW AND WM
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 6'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 10'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 5'X4' AND 5'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 6'X4' AND 5'X4' OF SW AND TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.5 | 2022-12-21 | 8'X4' OF SW RAMP
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 6'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.89 | 2022-12-21 | 9'X4' AND 9'X4' AND 5'X4' OF SW TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.44 | 2022-12-21 | 9'X4' AND 10'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 | 2022-12-21 | 5'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 | 2022-12-21 | 7'X4' AND 8'X4' AND 9'X4' OF SW TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.22 | 2022-12-21 | 9'X4' AND 9'X4' AND 5'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 | 2022-12-21 | 5'X4' OF SW AND TREE
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 10'X4' AND 9'X4' AND TREE
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 6'X4' AND 4'X4' OF SW
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 10'X4' OF SW AND TREE
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 | 2022-12-21 | 9'X4' OF SW
TBD |  | 3 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  | 12'X4' OF SW BY OTHERS
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
|  |  |  | FY 22 |  |  | 4429 Rockwood Dr | 18 | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148268-822705 | Council District 18
|  |  |  | FY 22 |  |  | 10403 Sterling Springs Rd | 18 |  | 2283.41 |  |  |  | 8102-410-8105-148267-822705
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Not Inspected | FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  |  | 0 | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 2093 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
|  | 5 | Not Inspected | FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  |  |  | FY 22 |  |  | 17106 Mallet Hill Dr | 19 |  | 12079.26 |  |  |  | Awaiting Accounts | Council
[7 empty] | 15109 Abington Ridge Pl | 19 |  | See 17106 Mallet Hill |  |  |  | Awaiting Accounts | Council
[7 empty] | 14313 Micawber Way | 19 |  | See 17106 Mallet Hill |  |  |  | Awaiting Accounts | Council
|  |  |  | FY 22 |  |  | 125 Waterstone Way | 19 |  | See 17106 Mallet Hill |  |  |  | Awaiting Accounts | Council
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 412-414 LAKE FOREST PKY | 19 | 4 | 2092.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 505 EDGEFOREST PL | 19 | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
TBD |  | 5 | Complete | FY22 | Winter 2021 | December | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 6.22 |  | 14'X4' OF SW AND DW
TBD |  | 5 | Complete | FY22 | Winter 2021 | December | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 2-4'X4' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 4'X4' OF SW
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | CONCRETE SPALLING
TBD |  | 5 | Complete | FY22 | Winter 2021 | December | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 8'X4' OF SW
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 21 | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works
|  | 4 | Not Inspected | FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 22 | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 22 | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 22 | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 22 | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
TBD |  | 5 | Complete | FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | LGE MH, 10'X4' OF SW - LGE CREATED LOW SPOT (DRAINAGE ISSUE ) IN THE SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-01-22 | R4 5'X4' AND R5 4'X4' OF SW 1 TREE
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 | 2022-12-21 | 6'x4' of SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 6'X4' AND R5 4'X4' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 | 2022-12-21 | 5'x4' of SW
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 23 | 3,4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 23 | 4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 23 | 4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 23 | 3,4 |  |  |  |  | 8146 410 8211 143058 899998 | Council District 23
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 8214 Happiness Way | 23 | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 29.78 | 2022-12-21 | 14'x4' of dw and 53'x4' of sw
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 24 | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  |  | 2022-12-21 | 21'X4' OF SW
Riverside Paving | 368756-4 | 4 | Inspected | FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5.33 |  | 4'x12' of dw
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.78 |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' and 4'x5' of sw and 25" tree
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 4'x10' of sw and 26" tree
TBD |  | 4 | Inspected | FY22 | Winter 2021 | December | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 21.33 | 2022-12-21 | 48'X4' OF ASPHALT SW (WAITING FOR ARBORIST RECOMMENDATION RE TREE ROOTS)
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 2.22 | 2022-12-21 | 4'X5' OF SW REPAIED BY OTHERS
vault top in sw - contact property owner
Note on H58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## January 2022
| PO # | Area | Construciton Status | Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | inspection month | inspection notes
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | January | 1152-1156 S 26TH ST | 1 | 5 | 12790.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 83.33
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
TBD |  | 1 | Inspected | FY22 | Winter 2022 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 30
TBD |  | 1 | Inspected | FY22 | Winter 2022 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17
|  | 1 | Not Inspected | FY22 |  |  | 1147-1149 S 42nd St | 1 |  | 2137.07 |  |  |  | 8133-410-8107-148283-822705 | Council Funds
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1366 OLIVE ST | 1 | 5 | 16445 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32
TBD |  | 1 | Inspected | FY22 | Winter 2022 |  | 1433-1451 HAZEL ST | 1 | 4 | 13953.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 61.1
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3222 VIRGINA | 1 | 4 | 2541.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12
Seven Seas | 368566-5 | 1 | Inspected | FY21 | Fall 2021 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1
TBD |  | 1 | Inspected | FY22 | Winter 2022 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.3 | 2022-01-01 | 33'x4' of sw and 33' of curb
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3516 COTTER DR | 1 | 5 | 1345.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.67 | 2022-01-01 | 11'x6' of sw
TBD |  | 1 | Inspected | FY22 | Winter 2022 |  | 3714 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.77 | 2022-01-01 | 5'x5' of sw
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4408 JENNYMAC DR | 1 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.33 | 2022-01-01 | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.22 | 2022-01-01 | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 743 S 43RD ST | 1 | 4 | 10695 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 24.39
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 808 & 810 S 42ND ST | 1 | 4 | 4983.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.33
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 2 | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 2 | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 2 | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 |  | 104.9
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 2 | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 2 | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 2 | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 2 | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | 513.78
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 3 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7
Seven Seas | 368566-5 | 1 | Inspected | FY22 | Fall 2021 | October | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | 40
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY20 | Fall 2021 |  | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  | 17.15
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.94
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 42
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2116 OREGON AVE | 3 | 4 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.55
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3312 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.88
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3314 UTAH AVE | 3 | 5 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.83
|  | 2 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 4 | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2022-01-31 | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19 | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works |  | By others | 2022-01-31 | 6'X2' OF OF DW
|  | 2 | Complete | FY21 | Fall 2021 | December | 200 S 7TH ST | 4 | 5 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others | 2021-01-31 | RR track in front of Frasier Museum. Investigate moving trash can to this location.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5 | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others | 2022-01-31 | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | Complete | FY20 | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works |  | By others | 2022-01-31 | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 40 | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.28 | 2022-01-31 | 63'X6' and 6'x4' of SW, 3 utility ajustments WM , 22" tree and 12"tree
|  | 2 | Not Inspected | FY22 | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  | SAW CUT AND REPAIRED BY OTHERS
TBD | 368745-10 | 2 | Inspected | FY22 | Winter 2022 |  | 1910-1912 MAGAZINE ST | 4 | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15
|  | 2 | Inspected | FY22 | Winter 2022 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.11
|  | 2 | Inspected | FY22 | Winter 2022 |  | 514 BARRET AVE | 4 | 5 | 10925 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 1 | 44.6 | 2021-01-31 | 30'X11' OF SW and 30' of curb, 1- 8'X6' utility vault adjustment (next to 537 Breckenridge St)
TBD | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 550 S 3RD ST (possibility Utilities' fault) | 4 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44
|  | 2 | Inspected | FY22 | Winter 2022 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 35.78 | 2021-12-21 | 15'X9' OF SW
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 831 FRANKLIN ST | 4 | 5 | 4861.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 59.2
|  | 2 | Inspected | FY22 | Winter 2022 |  | 833 W MAIN ST | 4 | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-10 | 2 | Inspected | FY22 | Winter 2022 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 | 2022-01-31 | Repaired
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2814 ROWAN ST | 5 | 4 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 7.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 38.56
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? |  | 60
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 2 | 40.69
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 18.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 40.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.77
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 1 | 46.55
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 | December | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  |  | See 3511 Northwestern Pkwy | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
Joash Construction |  | 1 |  | FY21 | Fall 2021 | December | 501 Northwesern Pkwy | 5 |  |  |  |  | See 3511 Northwestern Pkwy |  |  |  | 157
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 35.61
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 17.81
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 42.33
|  |  |  | FY 22 | Fall 2021 | December | Vermont and Southwestern | 5 |  |  | 5289.2 |  | 5289.2 |  |  |  | 75.56
Seven Seas |  | 1 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 23.25
Seven Seas | 368566-5 | 1 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 5 | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works |  | 4.44
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1114 PLATO TER | 5 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.75
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15.11
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 464 N 25TH ST | 5 | 4 | 64238 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 474 N 29TH ST | 5 | 4 | 4490 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 804 S 39TH ST | 5 | 5 | 7750 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 805 S 39TH ST | 5 | 4 | 3250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81 | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1261 S BROOK ST | 6 | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56 | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1265 S BROOK ST | 6 | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5 | 2021-12-21 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42 | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
|  | 2 | Inspected | FY21 | Fall 2020 | December | 1703 S BROOK ST | 6 | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 6 | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67 |  | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22 | DECEMBER
|  | 2 | Inspected | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others | 2021-12-28 | 5'X5' OF SW OR RAMP
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 635 PARK AVE | 6 | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5 |  | 6'X5' OF SW BY OTHERS
|  | 2 | Inspected | FY21 | Fall 2020 | December | 821 HUMLER ST | 6 | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | R3 4'X23' of dw
|  | 2 | Inspected | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
|  | 2 | Inspected | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | Inspected | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | R4 19'X8' OF SW AND 47'X8' OF SW and saw cut along the retaining wall as marked, remove and replace 22" tree, seed and protection (consult w/ arborist to remove and replace tree)
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 | January | 1434 THORNBERRY AVE | 6 | 4 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Joash Construction | 368745-10 | 2 | Complete | FY22 | Winter 2022 | January | 509 W ORMSBY AVE | 6 | 5 | 15200 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3 | 33
|  | 2 | Complete | FY21 | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | 7.33
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 6 | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31 |  | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 6 | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 6 | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 6 | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 6 | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 6 | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-10 | 2 | Not Inspected | FY22 | Summer 2021 |  | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67
Joash Construction |  | 2 | Sent to Contractor | FY20 | Winter 2022 |  | 1336 S 6TH ST | 6 | 4 | 14200 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works | 3
Joash Construction |  | 2 | Sent to Contractor | FY20 | Winter 2022 |  | 1408-1410 HOMEVIEW DR | 6 | 5 | 15726.25 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  |  |  | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 9.33
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 17.7
|  | 2 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 8200 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3
TBD |  | 3 | Not Inspected | FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 8 | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  |  |  | FY22 |  |  | 2219-2221 Talbot Ave | 8 | 5 | 15737 |  |  |  | 8146-410-8107-148903-447001 8102-410-8105-148903-401101 | Council
|  |  | Not Inspected | FY22 |  |  | 2219-2221 TALBOTT AVE | 8 |  | 18149 |  |  |  | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  |  |  | FY22 |  |  | 2225 Talbott Ave | 8 | 5 | 2412 |  |  |  | 8102-410-8105-148903-401101 8138-410-8107-148903-447001 | Council
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Not Inspected | FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1821 Frankfort Ave | 9 | 4 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 5 | 213
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1823 Frankfort Ave | 9 | 3 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1825 Frankfort Ave | 9 | 4 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 |  | Sent to Contractor |  |  | January | 1846 Frankfort Ave | 9 |  |  |  |  | See 1860 Frankfort Ave |  |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1860 Frankfort Ave | 9 | 4 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | Ramps at Pope and State St | 9 |  | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 3.67
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 49.28
TBD |  | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 45
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 64.81
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 33.89
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 24
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 30.22
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.67
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.07
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 5.5
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 4.5
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 8.44
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 5000
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 0
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 20
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 17.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 26.5
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 2.67
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas | 368567-3 | 3 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 10 | 5 |  | 2107.9 |  | 2107.9 |  |  |  | 5.73
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 17.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 11.11
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 28.67 |  | 5'X4' AND 4'X4' OF SW AND TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.67
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 11 | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  | 5'X5' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 4011 RIVULET LN | 11 | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  | GRINDING BY OTHERS
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Fall 2021 | January | 7002 URANAS DR | 12 | 4 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 4'x8' of sw and 4'x12' of dw (by others)
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 | October | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln | 2022-01-01 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 | October | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67 | 2022-01-01 | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 |  | 10.66 | 2022-01-01 | 8'x4' of sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11 | 2022-01-01 | 16'x4' and 12'x4' and 12'x4' of sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 | 2022-01-01 | 8'x4' of sw plus fill in void adjacent to sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-01-01 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.89 | 2022-01-01 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 13 | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 13 | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 13 | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 13 | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 13 | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  | See Beecher St | See Beecher St | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | October | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  |  | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 14 | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct | 2022-01-01 | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 14 | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 14 | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 14 | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 14 | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 14 | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 8406 Devonshire Dr | 14 | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
|  | 4 | Inspected | FY 22 | Winter 2022 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5.33
|  | 4 | Inspected | FY22 | Spring 2022 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 1 | 20.4 | 2021-12-21 | 4'X28' OF SW (THE PROPERTY OWNER RESURFACED THE DRIVEWAY CAUSING A 1" VERTICAL DISPLACEMENT)
TBD |  | 4 | Inspected | FY22 | Winter 2022 |  | 6007, 6010, and 6012 Alanadale Dr | 14 | Curb Repair | 4585.07 |  |  | 0 |  | Council District 14 |  |  | 2021-12-21 | 5'X7' AND 5'X7' AND 2'X4' AND 4'X7' OF SW
TBD |  | 4 | Inspected | FY22 | Winter 2022 |  | 6010 & 6012 Alanadale Dr | 14 | 3, 4 | 1342.88 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.7 | 2021-12-21 | 4'X4' AND 7'X4' OF SW AND 8'X4' OF DW AND 19" TREE 10' FROM THE SIDEWALK (ROOTS?)
TBD |  | 4 | Inspected | FY22 | Winter 2022 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.77 | 2021-12-21 | 11'X4' OF SW
|  | 4 | Inspected | FY 22 | Winter 2022 |  | 7014 Ethan Allen Way | 14 | 4 | 550.08 |  |  | 0 | 8146 410 8107 148279 822705 | Council District 14 |  | 12.44 | 2022-01-01 | 4'x4' of SW
|  | 4 | Inspected | FY 22 | Winter 2022 |  | 7902 NANCY LN | 14 | 4 | 3588 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6.33 | 2022-01-01 | 13'X4' OF SW and 2 tree stumps (measure in the field)
TBD |  | 4 | Not Inspected | FY22 | Winter 2022 |  | 9805 Sunway Dr | 14 | 5 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2022-01-01 | 10'x4' of sw (Tree Roots- contact arborist)
|  | 4 | Inspected | FY 22 | Winter 2022 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6.44 | 2022-01-01 | GPS could not find address
TBD |  | 4 | Not Inspected | FY22 | Winter 2022 |  | Pierce Way | 14 | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 4's or 5's | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 13'X4' OF SW and 2 tree stumps, SEED AND PROTECTION
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 15 | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 15 | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 15 | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | September | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  | 2021-12-21 | 12'X4' OF SW AND 11' OF CURB
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
|  | 4 | Inspected | FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3705 W WHEATMORE DR | 15 | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 542-546 RAWLINGS ST | 15 | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 15 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17
TBD |  | 4 | Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 |  | 37259 |  |  | 0 | 8138-410-8107-148223-822702 $15920.38 8133-410-8107-148223-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11202 Deham Dr | 16 | 5 | 336.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11215 Deham Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 4.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11301 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 10.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 16 | 5 | 1435.24 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 3.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11307 Deham Dr | 16 | 5 | 988.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 27.11
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 16 | 5 | 1369.83 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 16.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11412 Hammond Dr | 16 | 5 | 1761.6 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 16
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 16 | 5 | 719.03 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 16 | 5 | 538.06 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 8
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 16 | 5 | 1813.59 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 15.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 16 | 5 | 448.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11513 Fisherman Way | 16 | 5 | 881.38 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 0
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 16 | 5 | 403.7 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 4
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 16 | 5 | 210.88 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 1.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 12.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Baywood Dr | 16 | 5 | 201.85 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 8.44
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 14.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 16 | 5 | 3467.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 21.78
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5304 Drifton Dr | 16 | 5 | 888.27 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 9.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5308 Drifton Dr | 16 | 5 | 1831.93 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 5.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5311 Drifton Dr | 16 | 5 | 2473.37 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.67
Seven Seas |  | 3 | Sent to Contractor |  |  | December | 5401 Baywood Dr | 16 | [8 empty] | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 16 | 5 | 1157.62 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 7.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 6.89
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 9.33
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5410 Baywood Dr | 16 | 5 | 224.14 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 2.22
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5412 Lithia Dr | 16 | 5 | 1441.84 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 19.56
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5501 Lithia Dr | 16 | 5 | 2094.49 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 12.67
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 1.33
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 248
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
|  | 3 | Inspected | FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
TBD |  | 3 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By Others
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 7'X4' OF SW, Straight cut roots
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 | 2022-12-21 | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 6'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.22 | 2022-12-21 | 6'X4' OF SW
Seven Seas |  | 3 | Sent to Contractor | FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17 |  |  | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 5'X4' AND 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 | 2022-12-21 | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 | 2022-12-21 | 6'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 9'X4' AND 10'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.5 | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.89 | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.78 | 2022-12-21 | 7'X4' AND 5'X4' AND 9'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 | 2022-12-21 | 13'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 | 2022-12-21 | 10'X4'of SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.44 | 2022-12-21 | 10'X4' OF SW and
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 10'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 | 2022-12-21 | 5'X4' OF SW and straight cut roots only as necessary.
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 12'X4' OF SW BY OTHERS
|  |  |  | FY 22 |  |  | 10403 Sterling Springs Rd | 18 |  | 2283.41 |  |  |  | 8102-410-8105-148267-822705
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
|  |  |  | FY 22 |  |  | 4429 Rockwood Dr | 18 | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148268-822705 | Council District 18
Precision Concrete Cutting | 381611-5 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works |  | 14
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | October | 505 EDGEFOREST PL | 19 | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works |  | 6.2222
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 12403 Hersfield Rd | 19 | 4 | 3029 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 |  | 125 Waterstone Way | 19 | 5 | See 17106 Mallet Hill |  |  |  | 8102 105 8105 038219 899998 | Council
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1335 Heafer Rd | 19 | 5 | 1083.37 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1337 Heafer Rd | 19 | 5 | 2093 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 1340 Heafer Rd | 19 | 4 | 6518.89 |  |  | 0 | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 |  | 14313 Micawber Way | 19 | 5 | See 17106 Mallet Hill |  |  |  | 8102 105 8105 038219 899998 | Council |  |  |  | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots (arborist)
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 18'x4' of sw, seed and protection
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 |  | 15109 Abington Ridge Pl | 19 | 5 | See 17106 Mallet Hill |  |  |  | 8102 105 8105 038219 899998 | Council
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 |  | 17106 Mallet Hill Dr | 19 | 5 | 12079.26 |  |  |  | 8102 105 8105 038219 899998 | Council
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17204 MALLET HILL DR | 19 | 4 | 520 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 5 | Not Inspected | FY21 | Fall 2021 |  | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 |  | 311 Lake Forest Pky | 19 | 4 | 1674 |  |  | 0 | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 412-414 LAKE FOREST PKY | 19 | 4 | 2092.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 610 WOODLAKE DR | 19 | 5 | 10437.73 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Not Inspected | FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Precision Concrete Cutting | 381611-6 | 5 | Sent to Contractor | FY22 | Winter 2022 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 2.8889
|  | 5 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 9.3333
|  | 5 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 3.5556
|  | 5 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5
|  | 5 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
TBD |  | 5 | Complete | FY22 | Winter 2021 | December | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
TBD |  | 5 | Complete | FY22 | Winter 2021 | December | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 | 2022-01-22 | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2-4'X4' OF SW
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 4'X4' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | CONCRETE SPALLING
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 8'X4' OF SW
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
Seven Seas |  | 5 | Sent to Contractor | FY22 | Winter 2021 |  | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 24.88
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
Precision Concrete Cutting | 381611-7 | 5 | Sent to Contractor | FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 21 | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works |  | 1
TBD |  | 4 | Not Inspected | FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 4 | Not Inspected | FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
|  | 5 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 22 | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 12
|  | 5 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 22 | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 22 | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 18
|  | 5 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 22 | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 8.22
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 3 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 3816 GREENWICH WAY | 22 | 3,4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67
TBD |  | 5 | Complete | FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7600 Hornbeck Dr | 22 | 3 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 3 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 3 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  |  |  | LGE MH, 10'X4' OF SW - LGE CREATED LOW SPOT (DRAINAGE ISSUE ) IN THE SW
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  |  | 2022-01-22 | R4 5'X4' AND R5 4'X4' OF SW 1 TREE
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  |  | 2022-12-21 | 6'x4' of SW
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  |  | 2022-12-21 | 6'X4' AND R5 4'X4' OF SW
Precision Concrete Cutting | 381611-8 | 5 | Sent to Contractor | FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2022-12-21 | 5'x4' of SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 23 | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 23 | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | 38.99
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 23 | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 23 | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works |  | 47.55
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 8214 Happiness Way | 23 | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 29.78 | 2022-12-21 | 14'x4' of dw and 53'x4' of sw
Precision Concrete Cutting | 381611-9 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 24 | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others | 2022-12-21 | 21'X4' OF SW
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | No R4 or R5 issues observed during the Jan 2022 inspection
Riverside Paving | 368758-1 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
|  | 4 | Inspected | FY21 | Fall 2021 |  | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 4'x11' of sw and remove tree stump
Riverside Paving | 368758-1 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 21.33 | 2022-12-21 | 48'X4' OF Asphalt SW, straight cut roots as needed
Riverside Paving | 368758-1 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.78
Precision Concrete Cutting | 381611-18 | 4 | Sent to Contractor | FY 22 | Winter 2022 |  | WillowCreek Drive from Old South Park Rd to Maplecreek Dr | 24 | 5 | 37500
Precision Concrete Cutting | 381611-11 | 4 | Sent to Contractor | 25 | 5 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 25 | 5 | 25000
Precision Concrete Cutting | 381611-12 | 4 | Sent to Contractor | FY22 |  |  | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 26 | 5 | 40000 | [7 empty] | 2022-12-21 | 4'X5' OF SW REPAIED BY OTHERS
[9 empty] | Total | 2610007.4544 | 408606.38
vault top in sw - contact property owner
Note on H63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## February 2022
| PO # | Area | Construciton Status | Date Appropriated | Start | Finish | Project Name | District | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | Invoice # | inspection month | inspection notes
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | February | 1300 S 32ND ST | 1 | 4 | 1146.1667 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2022 | February | 1366 OLIVE ST | 1 | 5 | 16445 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 2 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | February | 3222 VIRGINA | 1 | 4 | 2541.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | February | 3516 COTTER DR | 1 | 5 | 1345.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 11'x6' of sw
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 4408 JENNYMAC DR | 1 | 4 | 1196 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-01-01 | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 4807 HUNTERS POINT CIR | 1 | 4 | 1727.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | February | 5616 CHRISTIAN RIDGE CT | 1 | 4 | 3070.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2022 | February | 743 S 43RD ST | 1 | 4 | 10695 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  |  | 14'x6' of sw and 33'x6' of sw
Joash Construction | 368745-10 | 1 | Complete | FY22 | Winter 2022 | February | 808 & 810 S 42ND ST | 1 | 4 | 4983.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | 11.33
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | January | 1152-1156 S 26TH ST | 1 | 5 | 12790.5556 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 83.33
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 1 | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 1 | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 1 | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 1 | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 1 | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 1 | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1 |  |  | 120521
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 1 | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 1 | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4 | 120015M-76
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 1 | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 1050 S 32ND ST | 1 | 4 | 24817.6389 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.7 |  | 2022-02-22 | 30'x5' of sw and 9' curb
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 1112 S 26TH ST | 1 | 4 | 5813.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 18.3 |  | 2022-02-22 | 33'x5' of sw and 4 utiliy adj
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 1147-1149 S 42nd St | 1 |  | 2137.07 |  |  |  | 8133-410-8107-148283-822705 | Council Funds |  | 9.3 |  |  | 14'x6' of sw, remove stump, s/p
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 1433-1451 HAZEL ST | 1 | 4 | 13953.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 61.1 |  | 2022-02-22 | 40'x6' and 37'x6' and 31x6 of sw and 4 utility adjustments
TBD | 368566-21 | 1 | Complete | FY21 | Winter 2022 |  | 3500 Block of Algonquin Pkwy | 1 | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1 |  |  |  | 2022-02-22 | 3519 9x4 of sw, 3513 5x5 0f sw, 3509 5x4 of sw, 3500 5x4 of sw, 3506 11x6 of dw and 4x4 of sw, 3508 10x10 of dw, 3512 6x5 of sw, 3516 11x8 of dw and 5x4 of sw, 3518 17x4 of dw, 3520 9x4 of sw and 1 utilty adj, 3528 5x4 of sw and 6x4 of sw, 3530 10x4 of dw, 3536 11x4 of sw and 1 tree, 3542 4x4 of sw, 3544 6x4 of dw, 3546 4x4 of sw, 3908 38'x4 of sw and 8' of curb and 1 big tree sent to arborist
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 3511 W KENTUCKY ST | 1 | 4 | 12857 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.3 |  | 2022-02-22 | 6'x12' of sw and 2 utility adjustments
Seven Seas | 368566-23 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 3714 CHAUNCEY AVE | 1 | 5 | 5877.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.77 |  | 2022-01-01 | 5'x5' of sw (snow and ice covered -could not inspect on Feb 22 site visit)
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2 | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2 | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 2 | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 2 | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 2 | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 2 | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 |  | 104.9
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 2 | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 2 | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 2 | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 2 | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 2 | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 2 | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 2 | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 2 | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 2 | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 2 | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | 513.78
Riverside Paving | 368756-4 | 4 | Complete | FY22 | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest
[7 empty] | Various Sidewalk Repairs | 2 |  | 6609 |  |  |  | 8133 410 8111 148221 822705 | Council funds |  |  |  |  | D2 needs to identify projects with this funding.
Joash Construction | 368745-10 | 1 | Complete | FY20 | Fall 2021 | february | 1413 OLEANDA AVE | 3 | 5 | 4651.1111 | 48026.16 |  | 48026.16 | 8143 410 8211 148472 822705 | Public Works |  | 287.74
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 1472 DIXIE HWY | 3 | 4 | 830.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 1505 OLEANDA AVE | 3 | 4 | 1993.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 1509 OLEANDA AVE | 3 | 4 | 6043.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 |  | February | 2116 OREGON AVE | 3 | 4 | 2242.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | February | 2313 ALLSTON AVE | 3 | 5 | 448.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 3312 UTAH AVE | 3 | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 3314 UTAH AVE | 3 | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | february | 3319 UTAH AVE | 3 | 4 | 1063.1111 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 3 | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction |  | 1 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 3 | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction | 368745-10 | 1 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 3 | 4 | 1328.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Seven Seas | 368566-5 | 1 | Inspected | FY22 | Fall 2021 | October | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 2's through 5's | 10760 |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | 40
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 3 | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 3 | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 3 | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 3 | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 3 | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 3 | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 3 | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 3 | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
TBD |  | 1 | Not Inspected | FY22 | Fall 2021 |  | 1634 BEECH ST | 3 | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | bring shovel
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.56
|  | 2 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 4 | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-01-31 | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 4 | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19 |  | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works |  | By others |  | 2022-01-31 | 6'X2' OF OF DW
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 4 | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5 |  | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | Complete | FY21 | Fall 2021 | December | 829 W. Main St. | 4 | 5 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | RR track in front of Frasier Museum. Investigate moving trash can to this location.
|  | 2 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2022-01-31 | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | Complete | FY20 | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 5 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works |  | By others |  | 2022-01-31 | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 40 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 1076 E WASHINGTON ST | 4 | 4 | 9449.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.28 |  | 2022-01-31
[7 empty] | 1115 E Oak St | 4 | 5 | 14455.5556
|  | 2 | Not Inspected | FY22 | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  | 2021-01-31 | Snow and ice on the sw prohibited the site inspection. The sidewalk is within the floodwall right of way and is R1-R5. Set up meeting with MSD to confirm the permitting requirement or closing the gates to block off access since a new sidewalk was constructed in 2021 across from 1224 Franklin St as an altermate ADA comatible sw.
TBD | 368745-22 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 1910-1912 MAGAZINE ST | 4 | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 15 |  | 2021-01-31 | 15'X9' OF SW
| 368745-22 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 237 E Breckinridge St | 4 | 4 | 27864 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.11 |  | 2021-01-31 | R4 6'X2' of dw
| 368745-22 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 514 BARRET AVE | 4 | 5 | 10925 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 2 | 44.6 |  | 2021-01-31 | R5 63'X6' and 6'x4' of sw, 3 utility adjustments, 22" tree and 12" tree
[7 empty] | 530 Barret Ave | 4 | 4 | 4628.8889
TBD | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 550 S 3RD ST (possibility Utilities' fault) | 4 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0 | 0.44 |  | 2021-01-31 | No issue observed during the 1/31/22 sw inspection
[7 empty] | 725 ROSELANE ST | 4 | 5 | 18277.7778
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | 741 FRANKLIN ST | 4 | 5 | 4861.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 63.2
| 368745-22 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 747 E JEFFERSON ST | 4 | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 35.78 |  | 2021-01-31 | R4 23'X14' OF DW
|  | 2 | Inspected | FY22 | Winter 2022 |  | 833 W MAIN ST | 4 | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0 |  | 2021-01-31 | Pw operations is placing trash can on top of displaced rr track to mitigate
[7 empty] | Barret Ave & Baxter Ave | 4 | 5 | 27608.8889
Joash Construction | 368745-10 | 2 | Complete | FY22 | Fall 2021 |  | N SHELBY ST & FRANKLIN ST | 4 | 4,5 | 11553.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-22 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 5 | 4069.7222 |  |  | 0 |  | Public Works |  | 10.67 |  | 2022-01-31 | 30'x11' of sw and 30' of curb and 1 utility adjustment.
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2814 ROWAN ST | 5 | 4 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 7.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 38.56
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? |  | 60
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 1 | 40.69
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 5 | 4 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 18.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 5 | 4 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 40.22
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 5 | 4 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.77
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 1 | 46.55
Joash Construction |  | 1 |  | FY21 | Fall 2021 | December | 501 Northwesern Pkwy | 5 |  |  |  |  | See 3511 Northwestern Pkwy |  |  |  | 157
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 35.61
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 5 | 4 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 17.81
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 5 | 4 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 42.33
|  |  |  | FY 22 | Fall 2021 | December | Vermont and Southwestern | 5 |  |  | 5289.2 |  | 5289.2 |  |  |  | 75.56
Joash Construction | 368745-10 | 1 | Complete | FY22 | Winter 2022 | February | 1114 PLATO TER | 5 | 4 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368745-10 | 1 | Complete | FY22 | Winter 2022 | February | 1501 LYTLE ST | 5 | 4 | 4252.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Seven Seas |  | 1 | Complete | FY22 | Winter 2022 | February | 4501 GREENWOOD AVE #1 | 5 | 5 | 6250 |  |  | Completed by others | 8146 410 8211 148487 822705 | Public Works |  | Completed by others |  | 2022-02-22 | No R4 or R5 observed
Seven Seas |  | 1 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 23.25
Seven Seas | 368566-5 | 1 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 5 | 4 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 5 | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 5 | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 5 | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 5 | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 5 | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 5 | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 5 | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 5 | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works |  | 4.44
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 5 | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | 1 | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 5 | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 5 | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 5 | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
|  | 1 | Not Inspected | FY21 | Winter 2021 |  | 109 N 40TH ST | 5 | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 1 | Complete | FY21 | Winter 2021 |  | 200 Block of Southwestern Pky | 5 | 4 | 15242 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 167.2 |  | 2022-02-22 | 201 -205 SW Parkway, 56’x6’ and 10’x6’ and 16’x6’ of sw, 227 SW Parkway 37’x6’ of sw, and 1 tree, 231 SW Parkway23’x6’ of sw and 1 tree, 235 - 237 SW Parkway 10’x6’ of sw and 14’x6’ of sw and 1 tree, 239 SW Parkway 29’x6’ of sw , 245 SW Parkway 5’x6’ of sw , 249-251 SW Parkway 45’x6’ and 4’x5’ and 3’x5’ of sw
Seven Seas |  | 1 | Inspected | FY22 | Winter 2021 |  | 311 N 30TH ST | 5 | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley- future paving project
Seven Seas |  | 1 | Inspected | FY22 | Winter 2021 |  | 312 N 30TH ST | 5 | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley - future paving project
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 464 N 25TH ST | 5 | 4 | 64238 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 9.3 |  | 2022-02-22 | 25' of curb and 12x7 of sw
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 472 TO 468 N 29TH ST | 5 | 4 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 45 |  | 2022-02-22 | 67x6 of sw and 3 utility adjustments
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 474 N 29TH ST | 5 | 4 | 4490 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 13.3 |  | 2022-02-22 | 20x6 of sw and 1 tree
Joash Construction | 368745-10 | 1 | Sent to Contractor | FY21 | Fall 2021 |  | 501 N 21st St | 5 | 4's and 5's | 22525.8 |  |  |  | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 804 S 39TH ST | 5 | 5 | 7750 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 17 |  | 2022-02-22 | 6'x6' of dw and 7'x6' of dw and 9'x6' of dw and 7'x3' of dw and 1 utility adjustment
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | 805 S 39TH ST | 5 | 4 | 3250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 21.3 |  | 2022-02-22 | 6’x10’ of sw and 6’x22’ of sw, and 4’x4’ of sw
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | N 29TH ST & BANK ST | 5 | 4 | 12000 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 123 |  | 2022-02-22 | 10’x5’ of sw and 15’ of curb, 100’x5’ of sw and 5’x25’ of dw and 91’x5’ of sw and 2 trees
Seven Seas | 368566-24 | 1 | Sent to Contractor | FY22 | Winter 2022 |  | S 28TH ST & W JEFFERSON ST | 5 | 5 | 2210 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 100.8 |  | 2022-02-22 | 43’x8’ of sw at 2732 W. Jeffreson St, 8’x6’ of sw at 2729 W. Jefferson St, 86’x6’of sw at 234 S 28th St.
TBD | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 6 | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81 |  | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1261 S BROOK ST | 6 | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1265 S BROOK ST | 6 | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1317 S 6TH ST | 6 | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5 |  | 2021-12-21 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 6 | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42 |  | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
|  | 2 | Complete | FY21 | Fall 2020 | December | 1703 S BROOK ST | 6 | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 6 | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 6 | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67 |  |  | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 6 | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22 |  | DECEMBER
|  | 2 | Complete | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 6 | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-28 | 5'X5' OF SW OR RAMP
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | December | 635 PARK AVE | 6 | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5 |  |  | 6'X5' OF SW BY OTHERS
|  | 2 | Complete | FY21 | Fall 2020 | December | 821 HUMLER ST | 6 | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | R3 4'X23' of dw
|  | 2 | Complete | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 6 | 5 |  |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  |  | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
|  | 2 | Complete | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 6 | 5 | 4933.5 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | Complete | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 6 | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction | 368745-21 | 2 | Sent to Contractor | FY22 | Winter 2022 | February | 1423 ARCADE AVE | 6 | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | No R4 or R5 present
Joash Construction | 368745-10 | 2 | Inspected | FY22 | Summer 2021 | February | 1330 W BRECKINRIDGE ST | 6 | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67 |  |  | 60'x6' of sw
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 | January | 1434 THORNBERRY AVE | 6 | 4 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 15.5 |  |  | 35'x4' of historic sw and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | Sent to Contractor | FY22 | Winter 2022 | January | 509 W ORMSBY AVE | 6 | 5 | 15200 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3 | 33 |  |  | 10'X18' and 17'x10' and 9'x10' of historic sw and 6'x10' of historic dw and 1 utility gas meter. (remove 1-22", 1-25" and 1-27" tree as marked) seed and protection. Straight cut bricks to tie into sw.
|  | 2 | Complete | FY21 | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 6 | 5 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | 7.33
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 6 | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31 |  |  | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 6 | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 6 | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 6 | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 6 | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 6 | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 6 | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 6 | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 6 | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 6 | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 6 | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 6 | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67
[7 empty] | 1152 Garvin Pl | 6 | 5 | 20946.6667
[7 empty] | 1157 LINCOLN AVE | 6 | 5 | 4675
Joash Construction | 368745-21 | 2 | Sent to Contractor | FY20 | Winter 2022 |  | 1336 S 6TH ST | 6 | 4 | 14200 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works | 3 | 47 |  |  | 12'x7.5' of historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 15.5' x7.5' of historic sw and 15' of historic curb historic (remove 1-31" and 2-17" trees)
[7 empty] | 1364 Lillian Ave | 6 | 5 | 5977.7778
Joash Construction | 368745-21 | 2 | Sent to Contractor | FY20 | Winter 2022 |  | 1408-1410 HOMEVIEW DR | 6 | 5 | 15726.25 |  |  | 0 | 8143 410 8211 148472 822705 | Public Works |  | 55.5 |  |  | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-21 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | 1410 ARCADE AVE | 6 | 4 | 2657.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 9.33 |  |  | 12'x4' of historic sw and curb, 39'x4' of historic sw, and 5'x4' of historic sw, seed and protection
[7 empty] | 1605 DUMESNIL ST | 6 | 5 | 2966.6667
[7 empty] | 1775 Wilson Ave | 6 | 4 | 7028.8889
[7 empty] | 2214 Hale Ave | 6 | 4 | 3553.3333
[7 empty] | 907 Burton Ave | 6 | 5 | 3700
|  | 2 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD | 6 |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
Joash Construction | 368745-21 | 2 | Sent to Contractor | FY22 | Winter 2022 |  | W ORMSBY AVE & S 6TH ST | 6 | 5 | 8200 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 58.6 |  |  | R4 19'X8' OF SW AND 47'X8' OF historic sw and saw cut along the retaining wall as marked, remove two 18" and one 23" tree as marked, seed and protection
[7 empty] | WINKLER AVE & S 5TH ST | 6 | 5 | 5533.3333
TBD |  | 3 | Not Inspected | FY22 | Fall 2021 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-3 | 3 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 8 | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1418 MORTON AVE | 8 | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1522 Rosewood Ave | 8 | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 1819 Harvard Dr | 8 | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 1840 SHADY LN | 8 | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1875 RUTHERFORD AVE | 8 | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1895 RUTHERFORD AVE | 8 | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1900 ROANOKE AVE | 8 | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1902 Deerwood Ave | 8 | 4 | 5556.6 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HAMPDEN CT | 8 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1912 HARVARD DR | 8 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1920 BONNYCASTLE AVE | 8 | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2018 BOULEVARD NAPOLEON | 8 | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2023 Woodbourne Ave | 8 | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2082 Douglass Blvd | 8 | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2105 DOUGLASS BLVD | 8 | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2115 Woodbourne Ave | 8 | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2137 ALTA AVE | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2139 WOODBOURNE AVE | 8 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2208 LAUDERDALE RD | 8 | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2218 WOODBOURNE AVE | 8 | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  |  | Not Inspected | FY22 |  |  | 2219-2221 TALBOTT AVE | 8 |  | 18149 |  |  |  | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2224 Dundee Rd | 8 | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Inspected | FY21 | Winter 2021 |  | 2246 BOULEVARD NAPOLEON | 8 | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2300 MEADOW RD | 8 | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2310 BOULEVARD NAPOLEON | 8 | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2420 LONGEST AVE | 8 | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 3 | Inspected | FY21 | Fall 2021 |  | 2541 Cherokee Pky | 8 | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas |  | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2809 Montrose Ave | 8 | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
|  | 3 | Not Inspected | FY21 | Winter 2021 |  | 701 BAXTER AVE | 8 | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1821 Frankfort Ave | 9 | 4 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1801 Frankfort Ave | 9 | 4 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 5 | 213
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1805 Frankfort Ave | 9 | 4 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1807 Frankfort Ave | 9 | 4 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1809-1811 Frankfort Ave | 9 | 4 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1817 Frankfort Ave | 9 | 5 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1823 Frankfort Ave | 9 | 3 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1825 Frankfort Ave | 9 | 4 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1832-1830 Frankfort Ave | 9 | 4 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 |  | Sent to Contractor |  |  | January | 1846 Frankfort Ave | 9 |  |  |  |  | See 1860 Frankfort Ave |  |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 1860 Frankfort Ave | 9 | 4 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 2039 Frankfort Ave | 9 | 3, damaged detectable warnings | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | 2101 Frankfort Ave | 9 | ramp is out of compliance | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 | January | Ramps at Pope and State St | 9 |  | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1 Eastover Ct | 9 | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 3.67
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 102 Crescent Ct | 9 | 4 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 49.28
TBD |  | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 118 N EWING AVE | 9 | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 45
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 122 N BAYLY AVE | 9 | 5 | 2555.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 148 VERNON AVE | 9 | 4 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1808-1800 Frankfort Ave | 9 | 4 | 15975.52 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 64.81
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1813-1815 Frankfort Ave | 9 | 3, crumbling | 7731.9 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 33.89
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1838 Frankfort Ave | 9 | 5 | 6019.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 24
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1854 Frankfort Ave | 9 | 3, spalling | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1870-1874 Frankfort Ave | 9 | 3, sidewalk is breaking up | 3468.23 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 30.22
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1880 Frankfort Ave | 9 | 3, badly spalling | 792 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.67
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1882 Frankfort Ave | 9 | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1900 MELLWOOD AVE | 9 | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1910 Frankfort Ave | 9 | holding water | 699.87 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 6.07
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 1928 Frankfort Ave | 9 | drainage issues with ramp | 3400.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 5.5
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2 Eastover Ct | 9 | 4 | 1182.6 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 4.5
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 201 S PETERSON AVE | 9 | 5 | 9370.9667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2035 EMERALD AVE | 9 | 4 | 2392 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2040 Frankfort Ave | 9 | 4 | 4884 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2138 New Main St | 9 | damaged detectable warnings | 3480 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 8.44
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2140 SYCAMORE AVE | 9 | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2144 Frankfort Ave | 9 | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 217 MCCREADY AVE | 9 | 4 | 5000
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2334-2336 Frankfort Ave | 9 | 4 | 113.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 0
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2368 Frankfort Ave | 9 | 4 | 2376 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 20
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2400 Frankfort Ave | 9 | 4 | 2059.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 17.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 2608 Frankfort Ave | 9 | 4 | 1428.24 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 13.33
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3210 Frankfort Ave | 9 | 4 | 5467.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 26.5
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3220 MARION CT | 9 | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 3230 Frankfort Ave | 9 | 4 | 275.2 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 2.67
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3410 INGLE AVE | 9 | 4 | 1162.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 3547 NANZ AVE | 9 | 5 | 2788.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | 405 UNIVERSITY AVE | 9 | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Sent to Contractor | FY21 | Fall 2021 |  | Frankfort & Haldeman | 9 | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas | 368567-3 | 3 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 10 | 5 |  | 2107.9 |  | 2107.9 |  |  |  | 5.73
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1014 WAGNER ST | 10 | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1031 WETTERAU AVE | 10 | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1107 E BURNETT AVE | 10 | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 17.33
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 1131 MULBERRY ST | 10 | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 11.11
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 2029 ALEXANDER AVE | 10 | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 28.67 |  |  | 5'X4' AND 4'X4' OF SW AND TREE ROOTS
TBD |  | 3 | Inspected | FY22 | Winter 2021 |  | 220 DERBY AVE | 10 | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.67
TBD |  | 3 | Not Inspected | FY22 | Spring 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 11 | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | 5'X5' OF SW
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 4011 RIVULET LN | 11 | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | GRINDING BY OTHERS
TBD |  | 5 | Inspected | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 11 | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Fall 2021 | January | 7002 URANAS DR | 12 | 4 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | 4'x8' of sw and 4'x12' of dw (by others)
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 | October | Deady Dr from Dead End to Dead End | 12 | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln | 2021-01-3 | 2022-01-01 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 | October | Rebecca Ln from Deady Dr to Dead End | 12 | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67 |  | 2022-01-01 | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 5032 Hunters Point Cir | 12 | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 |  | 10.66 |  | 2022-01-01 | 8'x4' of sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 6208 MOUNT EVEREST DR | 12 | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11 |  | 2022-01-01 | 16'x4' and 12'x4' and 12'x4' of sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 7015 BIRNAMWOOD DR | 12 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 |  | 2022-01-01 | 8'x4' of sw plus fill in void adjacent to sw
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 9612 BROOKS BEND RD | 12 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-01-01 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Riverside Paving | 387121-3 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 12 | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.89 |  | 2022-01-01 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 13 | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 13 | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 13 | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 13 | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 13 | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 2's through 4's | 10138.5 |  | See Beecher St | See Beecher St | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks from New Cut Rd to Dead | 13 | 2's through 5's | 32000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 | October | Glengarry Dr from National Turnpike to Gary Way | 13 | 2's through 5's | 19500 |  |  | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 200 ELK RIVER DR | 13 | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 211 APPOMATTOX RD | 13 | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 6013 LARKGROVE DR | 13 | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 14 | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct |  | 2022-01-01 | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 14 | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 14 | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 14 | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 14 | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 14 | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 14 | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | July | 8405 Devonshire Dr | 14 | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
TBD | 368756-16 | 4 | Inspected | FY21 | Winter 2022 |  | 11802 Pierce Way | 14 | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12 |  | 2022-02-25 | 27'x4' of sw and 2 utility adj, s/p
Riverside Paving | 368756-16 | 4 | Inspected | FY 22 | Winter 2022 |  | 13413 HINCHBROOK BLVD | 14 | 4 | 1328.8889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5.78 |  | 2022-02-25 | 13'x4' of sw, s/p
|  | 4 | Inspected | FY22 | Spring 2022 |  | 13417 Kinross Blvd | 14 | 5 | 3327.92 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 20.44 |  | 2022-02-25 | 46'x4' of sw, 1 utility adjustment, trim tree roots if needed, s/p
TBD |  | 4 | Inspected | FY22 | Winter 2022 |  | 6007 Alanadale Dr | 14 | Curb Repair | 4585.07 |  |  | 0 | 8142-410-8107-148279-821344 | Council District 14 |  |  |  | 2022-02-25 | 33' of curb replacement, s/p
Riverside Paving | 368756-16 | 4 | Inspected | FY22 | Winter 2022 |  | 6012 Alanadale Dr | 14 | 4 | 1342.88 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  | 2022-02-25 | 12'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | Inspected | FY22 | Winter 2022 |  | 7002 Nathan Hale Way | 14 | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 23.11 |  | 2022-02-25 | 52'x4' of sw, raise the sw to eliminate 2" ponding water at the low spot
Riverside Paving | 368756-16 | 4 | Inspected | FY 22 | Winter 2021 |  | 7014 Ethan Allen Way | 14 | 4 | 550.08 |  |  | 0 | 8146 410 8107 148279 822705 | Council District 14 |  | 20.89 |  | 2022-02-25 | 5'x4' and 42x4' of sw, s/p
| 368756-16 | 4 | Inspected | FY 22 | Winter 2022 |  | 7902 NANCY LN | 14 | 4 | 3588 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 8.9 |  | 2022-02-25 | 6'X4' and 6'x4' and 8'x4' of sw and and 9'x5' of dw, s/p
TBD | 368756-16 | 4 | Inspected | FY22 | Winter 2022 |  | 9805 Sun Way Dr | 14 | 5 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.67 |  | 2022-02-25 | 15'x4' of sw, call msd to investigate drainage issues (2 holes in the yard next to the catch basin)
| 368756-16 | 4 | Inspected | FY 22 | Winter 2022 |  | 9900 SUNKIST WAY | 14 | 4 | 2325.5556 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 27.11 |  | 2022-02-25 | 27'x4' and 25'x4' and 9'x4' of sw, s/p
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 4's or 5's | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | TBD | 14 | 2's through 5's | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 15 | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell | 2021-01-3
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 15 | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 15 | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 15 | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 15 | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 15 | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 15 | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 15 | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 15 | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 15 | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | Not Inspected | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Spring 2021 | September | 2431 EMIL AVE | 15 | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1020 Berry Blvd | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  | 2021-12-21 | 12'X4' OF SW AND 11' OF CURB
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1031 NAVAHO PL | 15 | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1496 CLARA AVE | 15 | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1500 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1503-1505 Paula Ct | 15 | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 1506 Hobart Ct | 15 | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
|  | 4 | Inspected | FY21 | Winter 2021 |  | 221 W ADAIR ST (Next to I-264) | 15 | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3418 POWELL AVE | 15 | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3515 HENRY AVE | 15 | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 3705 W WHEATMORE DR | 15 | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 4035 WOODRUFF AVE | 15 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4328 S 2nd St | 15 | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67
|  | 4 | Inspected | FY21 | Fall 2021 |  | 4400 S 2nd St | 15 | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 542-546 RAWLINGS ST | 15 | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 608 RAWLINGS ST | 15 | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 611 MERWIN AVE | 15 | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 631 DUVALL ST | 15 | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 654 N BARBEE WAY | 15 | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | 664 ATWOOD ST | 15 | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4
TBD |  | 4 | Not Inspected | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 15 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Inspected | FY22 | Fall 2021 |  | MERHOFF ST & DUVALL ST | 15 | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17
TBD |  | 4 | Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 |  | 37259 |  |  | 0 | 8138-410-8107-148223-822702 $15920.38 8133-410-8107-148223-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11202 Deham Dr | 16 | 5 | 336.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11215 Deham Dr | 16 | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11301 Deham Dr | 16 | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 16 | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 16 | 5 | 1435.24 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11307 Deham Dr | 16 | 5 | 988.23 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 16 | 5 | 4940.17 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 16 | 5 | 1369.83 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11412 Hammond Dr | 16 | 5 | 1761.6 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 16 | 5 | 719.03 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 16 | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 16 | 5 | 538.06 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 16 | 5 | 1309.75 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 16 | 5 | 1813.59 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 16 | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11513 Fisherman Way | 16 | 5 | 881.38 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 16 | 5 | 403.7 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 16 | 5 | 210.88 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 16 | 5 | 1429.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Baywood Dr | 16 | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 16 | 5 | 929.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | See |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 16 | 5 | 3393.1 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 16 | 5 | 3467.27 | 49112.92 |  | 49112.92 | 8101 410 8105 148234 822705 | Council District 16 |  | 332.23
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5304 Drifton Dr | 16 | 5 | 888.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 16 | 5 | 627.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5308 Drifton Dr | 16 | 5 | 1831.93 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5311 Drifton Dr | 16 | 5 | 2473.37 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5401 Baywood Dr | 16 | 5 |  |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 16 | 5 | 1114.94 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 16 | 5 | 1157.62 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 16 | 5 | 695.96 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 16 | 5 | 1726.32 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 16 | 5 | 973.89 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5410 Baywood Dr | 16 | 5 | 224.14 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5412 Lithia Dr | 16 | 5 | 1441.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5501 Lithia Dr | 16 | 5 | 2094.49 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 16 | 5 | 134.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 248
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 2's through 5's | 7500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Precision Concrete Cutting | 381611-4 | 3 | Inspected | FY22 | Winter 2022 | January | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 2's through 5's | 22500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
|  | 3 | Inspected | FY21 | Fall 2021 |  | 10630 Meeting St | 16 | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4003 Deer Creek Dr | 16 | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
|  | 3 | Inspected | FY21 | Fall 2021 |  | 4230 Ashleywood Ct | 16 | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16
TBD |  | 3 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 17 | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By Others
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13408 FOREST SPRINGS DR | 17 | 5 | 2057.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2022-12-21 | 7'X4' OF SW, Straight cut roots
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13415 FOREST SPRINGS DR | 17 | 5 | 3718.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 |  | 2022-12-21 | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13419 FOREST SPRINGS DR | 17 | 5 | 3552.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 6'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13430 FOREST SPRINGS DR | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.22 |  | 2022-12-21 | 6'X4' OF SW
Seven Seas |  | 3 | Sent to Contractor | FY21 | Summer 2021 |  | 13508 Springs Station Rd | 17 | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17 |  |  |  | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13510 BROKEN BRANCH WAY | 17 | 5 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-12-21 | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13512 BROKEN BRANCH WAY | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 5'X4' AND 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13520 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13606 BROKEN BRANCH WAY | 17 | 5 | 2524.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10.67 |  | 2022-12-21 | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13607 BROKEN BRANCH WAY | 17 | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 13700 BROKEN BRANCH WAY | 17 | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2022-12-21 | 6'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3610 ROCK BAY DR | 17 | 4 | 1245.8333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-12-21 | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3700 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 9'X4' AND 10'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3700 WOODED SPRINGS CT | 17 | 5 | 930.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.5 |  | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3707 ROCK BAY DR | 17 | 4 | 3386.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3710 CYPRESS SPRINGS PL | 17 | 5 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.89 |  | 2022-12-21 | 4'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3724 CYPRESS SPRINGS PL | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.78 |  | 2022-12-21 | 7'X4' AND 5'X4' AND 9'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3801 BUGLEWOOD PL | 17 | 5 | 3136.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  | 2022-12-21 | 13'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3809 ROCK BAY DR | 17 | 4 | 581.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-12-21 | 5'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3814 ROCK BAY DR | 17 | 4 | 1827.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.22 |  | 2022-12-21 | 10'X4'of SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 3915 ROCK BAY DR | 17 | 5 | 1661.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.44 |  | 2022-12-21 | 10'X4' OF SW and
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 4002 ROCK BAY DR | 17 | 5 | 913.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 10'X4' OF SW
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 4010 ROCK BAY DR | 17 | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-12-21 | 5'X4' OF SW and straight cut roots only as necessary.
TBD | 368758-1 | 3 | Sent to Contractor | FY22 | Winter 2021 |  | 9603 MOORFIELD CIR | 17 | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  |  | 12'X4' OF SW BY OTHERS
|  |  |  | FY 22 |  |  | 10403 Sterling Springs Rd | 18 |  | 2283.41 |  |  |  | 8102-410-8105-148267-822705
TBD |  | 3 | Not Inspected | FY22 | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
|  |  |  | FY 22 |  |  | 4429 Rockwood Dr | 18 | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148267-822705 | Council District 18
Precision Concrete Cutting | 381611-5 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 2's through 5's | 30000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 12403 Hersfield Rd | 19 | 4 | 3029 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 | February | 125 Waterstone Way | 19 | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 1335 Heafer Rd | 19 | 5 | 1083.37 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 1337 Heafer Rd | 19 | 5 | 2093 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 1340 Heafer Rd | 19 | 4 | 6518.89 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 14008 CROSSBRANCH CT | 19 | 4 | 1702.27 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 14202 LAKE FOREST DR | 19 | 4 | 764.53 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 14306 LAKE FOREST DR | 19 | 4 | 1085.15 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 | February | 14313 Micawber Way | 19 | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr |  |  | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots tripstop
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 | February | 15109 Abington Ridge Pl | 19 | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368567-7 |  | Sent to Contractor | FY 22 | Spring 2022 | February | 17106 Mallet Hill Dr | 19 | 5 | 12079.26 |  |  | 15681.79 | 8102 410 8105 148963 822702 | Council |  | 69.31
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 17204 MALLET HILL DR | 19 | 4 | 520 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
|  | 5 | Not Inspected | FY21 | Fall 2021 | February | 2213 ARNOLD PALMER BLVD | 19 | 4 | 4422.13 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 | February | 311 Lake Forest Pky | 19 | 4 | 1674 |  |  | See 610 Woodlake | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | February | 504-506 EDGEFOREST PL | 19 | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works |  | 14
Seven Seas |  | 5 | Complete | FY21 | Fall 2021 | February | 505 EDGEFOREST PL | 19 | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works |  | 6.2222
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 610 WOODLAKE DR | 19 | 5 | 10437.73 | 26594.64 |  | 26594.64 | 8146 410 8211 148487 822705 | Public Works |  | 192
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 | February | 612 WOODLAKE DR | 19 | 5 | 9381.95 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | Inspected | FY22 | Winter 2021 | February | STURBRIDGE PL & STURBRIDGE CIR | 19 | 5 | 747.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 11007 FOX MOORE PL | 19 | 5,2 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 10*4
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 14611 LAKE BLUFF PL | 19 | 4 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 18'x4' of sw, seed and protection
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 15105 MEADOW FARMS CT | 19 | 4 | 730.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 17108 MALLET HILL DR | 19 | 5 | 1202.57 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 412-414 LAKE FOREST PKY | 19 | 4 | 2092.4 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 509 EDGEFOREST PL | 19 | 4 | 233.33 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 803 FOXGATE RD | 19 | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 836 LAKE FOREST PKY | 19 | 4 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Not Inspected | FY19 | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 2's through 5's | 15840 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Precision Concrete Cutting | 381611-6 | 5 | Sent to Contractor | FY22 | Winter 2022 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 2's through 5's | 15000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 5 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 20 | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 20 | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 2.8889
|  | 5 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 20 | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 9.3333
|  | 5 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 20 | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 3.5556
|  | 5 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 20 | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | 20 | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5
|  | 5 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 20 | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
Seven Seas |  | 5 | Sent to Contractor | FY22 | Winter 2022 | February | 14304 MICAWBER WAY | 20 | 5 | 2127.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 4 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  |  | 2-4'X4' OF SW
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 114 Wickfield Dr | 20 | 5 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  | 2022-02-22 |  | 5'X4' and 15''x4' of SW, 1 tree
TBD |  | 5 | Complete | FY22 | Winter 2021 |  | 11804 LONGVIEW FARM DR | 20 | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | 11906 LONGVIEW FARM DR | 20 | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | CONCRETE SPALLING
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 12000 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 8'X4' OF SW
TBD |  | 5 | Complete | FY22 | Winter 2021 |  | 12004 LONGVIEW FARM DR | 20 | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 2022-01-22 | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 5 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 3 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 4 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 5 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 5 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 4 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 5 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 5 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13809 Round Top Pl | 20 | 4 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 13811 lakemont Ct | 20 | 4 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14107 Glendower Dr | 20 | 4 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 14'x4' and 12'x4' of sw and 3 trees
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 5 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 200 Wickfield DR | 20 | 5 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 18'x4' and 18'x4' and 6'x4' of sw and 3 trees
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 303 Wickfield Dr | 20 | 4 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 20'x4' of sw and 1 tree
TBD |  | 5 | Not Inspected | FY22 | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 4 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 4 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 5 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 4 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 505 Wickfield Dr | 20 | 5 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 4'x6' and 4'x11' of sw and 1 tree
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 615 Wickfield DR | 20 | 4 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 4'x4' and 4'x18' and 1- 20" tree
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6515 Calm River Way | 20 | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | no issue observed
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6530 Calm River Way | 20 | 4 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 5'x4' and 11'x4' of sw
TBD |  | 5 | Not Inspected | FY22 | Spring 2022 |  | 6726 Calm River Way | 20 | 4 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | 14'x4' of sw
Precision Concrete Cutting | 381611-7 | 5 | Sent to Contractor | FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 2's through 5's | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 21 | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works |  | 1
Precision Concrete Cutting | 381611-13 | 4 | Not Inspected | FY22 | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 2's through 5's | 85000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
|  | 4 | Not Inspected | FY18 | Spring 2021 |  | TBD | 21 |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
|  | 5 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 22 | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 12
|  | 5 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 22 | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 22 | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 22 | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 18
|  | 5 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 22 | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 8.22
TBD |  | 5 | Inspected | FY22 | Winter 2022 |  | 10104 RIMFIRE RD | 22 | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  | 2022-02-23 | 12’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.44 |  | 2022-02-23 | 10’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 11410 Wind Haven Way | 22 | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 1.78 |  | 2022-02-23 | 4’x4’ of sw
TBD |  | 5 | Inspected | FY22 | Winter 2022 |  | 3816 GREENWICH WAY | 22 | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-02-23 | 6'x4' of sw
TBD |  | 5 | Complete | FY22 | Winter 2021 |  | 5807 BUCKS LN | 22 | 4 | 1860.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-01-22 | Addressed by lge
TBD |  | 5 | Inspected | FY22 | Winter 2022 |  | 6217 HINES MILL WAY | 22 | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 |  | 2022-02-23 | 8'x4' of sw
TBD |  | 5 | Inspected | FY22 | Winter 2022 |  | 6416 MOSSY OAKS DR | 22 | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.89 |  | 2022-02-23 | 11'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 5.33 |  | 2022-02-23 | 12’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7600 Hornbeck Farm Rd | 22 | 5 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 7.56 |  | 2022-02-23 | 17’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7802 Windgate Dr | 22 | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 9.78 |  | 2022-02-23 | 4’x4’ of sw & 18’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7804 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.89 |  | 2022-02-23 | 5’x4’ of sw & 6’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7812 Windgate Dr | 22 | 5 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 2.22 |  | 2022-02-23 | 5’x4’ of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7821 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4 |  | 2022-02-23 | 9'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7901 Windgate Dr | 22 | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.44 |  | 2022-02-23 | 10'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7907 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.44 |  | 2022-02-23 | 10'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Niemann Dr | 22 | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.44 |  | 2022-02-23 | 10'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7909 Windgate Dr | 22 | 4 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 5.33 |  | 2022-02-23 | 12'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7912 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 4.44 |  | 2022-02-23 | 10x4 of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7913 Windgate Dr | 22 | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 7.55 |  | 2022-02-23 | 12'x4' of sw and 5'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7916 Windgate Dr | 22 | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  |  |  | 2022-02-23 | No R4 or R5 issues observed during the February 2022 inspection
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7917 Windgate Dr | 22 | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 5.33 |  | 2022-02-23 | 12'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7919 Windgate Dr | 22 | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 6.67 |  | 2022-02-23 | 15'x4' of sw
|  | 5 | Inspected | FY21 | Fall 2021 |  | 7920 Windgate Dr | 22 | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 2.67 |  | 2022-02-23 | 6'x4' of SW
Precision Concrete Cutting | 381611-8 | 5 | Sent to Contractor | FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 2's through 5's | 45000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  | 2021-01-5 and 1097 (2nd Invoice was for Triumph) | 2022-12-21
TBD |  | 5 | Inspected | FY22 | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 23 | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 23 | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 23 | 5 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | 38.99
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 23 | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 23 | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 23 | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works |  | 47.55
TBD |  | 4 | Inspected | FY22 | Winter 2021 |  | 8214 Happiness Way | 23 | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 29.78 |  | 2022-12-21 | 14'x4' of dw and 53'x4' of sw
Precision Concrete Cutting | 381611-9 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 2's through 5's | 55000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 24 | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | 2022-12-21 | 21'X4' OF SW
TBD |  | 4 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  |  | No R4 or R5 issues observed during the Jan 2022 inspection
Riverside Paving | 368758-1 | 4 | Complete | FY22 | Winter 2022 | February | 7832 BRIDLEWOOD PL | 24 | 4 | 1328.8889 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | 37.32 |  |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
Riverside Paving | 368758-1 | 4 | Complete | FY21 | Fall 2021 | February | 8603 Timber Hollow Ct | 24 | 4 | 1727.56 |  |  | See 8918 Elmcreek | 8146 410 8211 148487 822705 | Public Works |  | See 7832 Bridlewood PL |  |  | 4'x11' of sw and remove tree stump
Riverside Paving | 368758-1 | 4 | Complete | FY22 | Winter 2022 | February | 8708 SHEPHERDSVILLE RD | 24 | 4 | 3189.3333 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL |  | 2022-12-21 | 48'X4' OF Asphalt SW, straight cut roots as needed
Riverside Paving | 368758-1 | 4 | Complete | FY22 | Winter 2022 | February | 8918 ELMCREEK DR | 24 | 4 | 3053.8889 | 3824 |  | 3824 | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL
Precision Concrete Cutting | 381611-18 | 4 | Sent to Contractor | FY 22 | Winter 2022 |  | WillowCreek Drive from Old South Park Rd to Maplecreek Dr | 24 | 5 | 37500
Precision Concrete Cutting | 381611-11 | 4 | Sent to Contractor | FY 22 | Winter 2022 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 25 | 5 | 25000
Precision Concrete Cutting | 381611-12 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 26 | 5 | 40000 | [8 empty] | 2022-12-21 | 4'X5' OF SW REPAIED BY OTHERS
|  | 2 | Not Inspected |  |  |  | 731 FRANKLIN ST
[9 empty] | Total | 2646302.5056 | 524454.64
vault top in sw - contact property owner
Note on H69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## March 2022
Contractor | PO # | Area | Construciton Status | Start | Finish | Project Name | District | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Repair SY | inspection notes
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 1300 S 32ND ST | 1 | 1146.1667 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2022 | February | 1366 OLIVE ST | 1 | 16445 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 3222 VIRGINA | 1 | 2541.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 3516 COTTER DR | 1 | 1345.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave | 11'x6' of sw
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 4408 JENNYMAC DR | 1 | 1196 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 4807 HUNTERS POINT CIR | 1 | 1727.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 5616 CHRISTIAN RIDGE CT | 1 | 3070.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2022 | February | 743 S 43RD ST | 1 | 10695 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave | 14'x6' of sw and 33'x6' of sw
Joash Construction | 368746-1 | 1 | Complete | Winter 2022 | February | 808 & 810 S 42ND ST | 1 | 4983.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 11.33
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | January | 1152-1156 S 26TH ST | 1 | 12790.5556 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 83.33
TBD | 368566-21 | 1 | Complete | Winter 2022 | March | 3500 Block of Algonquin Pkwy | 1 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1101 S 41st St | 1 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1159 S 41st St | 1 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1162 S 41st St | 1 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1175 S 41st St | 1 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1213 S 41st St | 1 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1222-1224 Cypress St | 1 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | Complete | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 1 | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 4112 Winnrose Way | 1 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 4302 Winnrose Way | 1 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | 776.4
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 6519 Hunters Creek Blvd | 1 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose | 30'x5' of sw and 9' curb
Seven Seas | 368566-23 | 1 | Sent to Contractor | Winter 2022 |  | 1050 S 32ND ST | 1 | 24817.6389 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 16.7 | 33'x5' of sw and 4 utiliy adj
Seven Seas | 368566-23 | 1 | Sent to Contractor | Winter 2022 |  | 1112 S 26TH ST | 1 | 5813.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 18.3 | 14'x6' of sw, remove stump, s/p
Seven Seas | 368566-25 | 1 | Sent to Contractor | Winter 2022 |  | 1147-1149 S 42nd St | 1 | 2137.07 |  |  |  | 8133-410-8107-148283-822705 | Council Funds | 9.3 | 40'x6' and 37'x6' and 31x6 of sw and 4 utility adjustments
Seven Seas | 368566-23 | 1 | Sent to Contractor | Winter 2022 |  | 1433-1451 HAZEL ST | 1 | 13953.3333 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 61.1 | 3519 9x4 of sw, 3513 5x5 0f sw, 3509 5x4 of sw, 3500 5x4 of sw, 3506 11x6 of dw and 4x4 of sw, 3508 10x10 of dw, 3512 6x5 of sw, 3516 11x8 of dw and 5x4 of sw, 3518 17x4 of dw, 3520 9x4 of sw and 1 utilty adj, 3528 5x4 of sw and 6x4 of sw, 3530 10x4 of dw, 3536 11x4 of sw and 1 tree, 3542 4x4 of sw, 3544 6x4 of dw, 3546 4x4 of sw, 3908 38'x4 of sw and 8' of curb and 1 big tree sent to arborist
Seven Seas | 368566-23 | 1 | Sent to Contractor | Winter 2022 |  | 3511 W KENTUCKY ST | 1 | 12857 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 7.3 | 6'x12' of sw and 2 utility adjustments
Seven Seas | 368566-23 | 1 | Sent to Contractor | Winter 2022 |  | 3714 CHAUNCEY AVE | 1 | 5877.7778 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 2.77 | 5'x5' of sw (snow and ice covered -could not inspect on Feb 22 site visit)
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | Concrete Beveling Poject | 2 | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | Sidewalk Leveling Project | 2 | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 1403 FOREST DR | 2 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 3613-3615 E Indian Trl | 2 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 4108 St Charles St | 2 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 4109 St Charles St | 2 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 | 104.9
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 4310 E Indian Trl | 2 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 4404 E Indian Trl | 2 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 4907 Sunday Dr | 2 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5009 ROY WILLIAMS PL | 2 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5020 Broadmoor Blvd | 2 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5023 Broadmoor Blvd | 2 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5101 Mediterranean Ct | 2 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5105 Broadmoor Blvd | 2 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5107 Broadmoor Blvd | 2 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 5301 GARDEN GREEN WAY | 2 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works | See 4109 Charles
Riverside Paving | 368756-4 | 4 | Complete | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2 | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works | 513.78
Riverside Paving | 368756-4 | 4 | Complete | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2 | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works | See Ridgecrest
[6 empty] | Various Sidewalk Repairs | 2 | 6609 |  |  |  | 8133 410 8111 148221 822705 | Council funds |  | D2 needs to identify projects with this funding.
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 1413 OLEANDA AVE | 3 | 4651.1111 | 48026.16 |  | 48026.16 | 8143 410 8211 148472 822705 | Public Works | 287.74
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 1472 DIXIE HWY | 3 | 830.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 1505 OLEANDA AVE | 3 | 1993.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 1509 OLEANDA AVE | 3 | 6043.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 2116 OREGON AVE | 3 | 2242.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | February | 2313 ALLSTON AVE | 3 | 448.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 3312 UTAH AVE | 3 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 3314 UTAH AVE | 3 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Fall 2021 | february | 3319 UTAH AVE | 3 | 1063.1111 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction |  | 1 | Complete | Fall 2021 | November | 3301 UTAH AVE | 3 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.44
Joash Construction |  | 1 | Complete | Fall 2021 | November | 3303 UTAH AVE | 3 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.44
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | October | 1503 OLEANDA AVE | 3 | 1328.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Seven Seas | 368566-5 | 1 | Not Inspected | Fall 2021 | October | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 3 | 10760 |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works | 40
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1705 VALLEY FORGE WAY | 3 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1709 VALLEY FORGE WAY | 3 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1725 W GAULBERT AVE | 3 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1728-1734 W HILL ST | 3 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1749 W HILL ST | 3 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2314 WOODLAND AVE | 3 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2322 OREGON AVE | 3 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2328 W LEE ST | 3 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
TBD |  | 1 | Not Inspected | Fall 2021 |  | 1634 BEECH ST | 3 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | bring shovel
Joash Construction | 368745-10 | 1 | Not Inspected | Fall 2021 |  | 2616 ALLSTON AVE | 3 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 13.56
|  | 2 | Complete | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works | By others | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | Complete | Fall 2021 | December | 1216 FERN ST | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | December | 1718 MAGAZINE ST | 4 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 14.19 | BRICK SW HAS BEEN REPAIRED
|  | 2 | Inspected | Fall 2021 | December | 200 S 5TH ST | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works | By others | 6'X2' OF OF DW
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | December | 2329 W CHESTNUT ST | 4 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.5 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | Complete | Fall 2021 | December | 829 W. Main St. | 4 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | RR track in front of Frasier Museum. Investigate moving trash can to this location.
|  | 2 | Complete | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By others | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | Complete | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 4 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works | By others | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | March | 1076 E WASHINGTON ST | 4 | 9449.1667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works | 5.28 | REPAIRED BY OTHERS
Joash Construction | 368745-22 | 2 | Complete | Winter 2022 | March | 1910-1912 MAGAZINE ST | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 15
Joash Construction | 368745-22 | 2 | Complete | Winter 2022 | March | 237 E Breckinridge St | 4 | 27864 |  |  |  | 8146 410 8211 148487 822705 | Public Works | see 514 BARRET AVE
Joash Construction | 368745-22 | 2 | Complete | Winter 2022 | March | 514 BARRET AVE | 4 | 10925 | 14104.1 |  | 14104.1 | 8146 410 8211 148487 822705 | Public Works | 101.91 | Snow and ice on the sw prohibited the site inspection. The sidewalk is within the floodwall right of way and is R1-R5. Set up meeting with MSD to confirm the permitting requirement or closing the gates to block off access since a new sidewalk was constructed in 2021 across from 1224 Franklin St as an altermate ADA comatible sw.
TBD | 368745-10 | 2 | Complete | Fall 2021 | March | 550 S 3RD ST (possibility Utilities' fault) | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0.44 | 15'X9' OF SW
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | March | 741 FRANKLIN ST | 4 | 4861.9444 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works | 63.2 | R4 6'X2' of dw
| 368745-22 | 2 | Complete | Winter 2022 | March | 747 E JEFFERSON ST | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | see 514 BARRET AVE | R5 63'X6' and 6'x4' of sw, 3 utility adjustments, 22" tree and 12" tree
|  | 2 | Complete | Winter 2022 | March | 833 W MAIN ST | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 0
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | March | N SHELBY ST & FRANKLIN ST | 4 | 11553.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works | 22.94 | No issue observed during the 1/31/22 sw inspection
TBD | 368745-22 | 2 | Complete | Winter 2022 | March | S HANCOCK ST & E BRECKINRIDGE ST | 4 | 4069.7222 |  |  | 0 |  | Public Works | see 514 BARRET AVE
Joash Construction | 368745-10 | 2 | Complete | Fall 2021 | September | 400 S 6TH ST | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 40 | complete
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 1115 E Oak St | 4 | 14455.5556 | [5 empty] | 55.56 | R4 23'X14' OF DW
|  | 2 | Not Inspected | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | Pw operations is placing trash can on top of displaced rr track to mitigate
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 530 Barret Ave/Lexington Rd | 4 | 4628.8889 | [5 empty] | 36.67
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 725 ROSELANE ST | 4 | 18277.7778 | [5 empty] | 92.22
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | Barret Ave & Baxter Ave | 4 | 27608.8889 | [5 empty] | 55.56 | 30'x11' of sw and 30' of curb and 1 utility adjustment.
|  | 2 | Not Inspected |  |  | 731 FRANKLIN ST | 4
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | W. Jefferson St & S. 4th St | 4 | 4669.4444
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 217 S 5th St | 4 | 2256.6667
| 368745-24 |  |  |  |  | 1120 E. Breckinridge St | 4 | 3455.5556
| 368745-24 |  |  |  |  | 512 Barret Ave | 4 | 15540
| 368745-24 |  |  |  |  | 130 S 3rd St | 4 | 7945
| 368745-24 |  |  |  |  | 4TH ST and LIBERTY ST | 4 | 4000
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 315 E Main St | 4 | 9191.6667
| 368745-24 |  |  |  |  | 721 4th St | 4 | 4000
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 721 S. 4th St | 4 | 5478.8889
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 2814 ROWAN ST | 5 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 7.67
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 38.56
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 2934 Portland Ave | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? | 60
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 40.69
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 355 SOUTHWESTERN PKY | 5 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 18.22
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 361 SOUTHWESTERN PKY | 5 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 40.22
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 4138 LARKWOOD AVE | 5 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 22.77
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 4303 VERMONT AVE | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 46.55 | No R4 or R5 observed
Joash Construction |  | 1 | Complete | Fall 2021 | December | 501 Northwesern Pkwy | 5 |  |  |  | See 3511 Northwestern Pkwy |  |  | 157
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 35.61
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 654 EASTLAWN AVE | 5 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 22.78
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 734 S 38TH ST | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 30.67
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 809 S 38TH ST | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 17.81
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | 814 DEARBORN AVE | 5 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 42.33
Joash Construction | 368745-10 | 1 | Complete | Fall 2021 | December | Vermont and Southwestern | 5 |  | 5289.2 |  | 5289.2 |  |  | 75.56
Joash Construction | 368745-10 | 1 | Complete | Winter 2022 | February | 1114 PLATO TER | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | Complete | Winter 2022 | February | 1501 LYTLE ST | 5 | 4252.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | See 1413 Oleanda Ave
Seven Seas | 368746-1 | 1 | Complete | Winter 2022 | February | 4501 GREENWOOD AVE #1 | 5 | 6250 |  |  | Completed by others | 8146 410 8211 148487 822705 | Public Works | Completed by others
Seven Seas | 368566-5 | 1 | Complete | Winter 2022 | March | 109 N 40TH ST | 5 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 6
Precision Concrete Cutting |  | 1 | Complete | Winter 2021 | March | 200 Block of Southwestern Pky | 5 | 15242 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 167.2
Seven Seas |  | 1 | Complete | Summer 2021 | November | 2146 DUNCAN ST | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works | 80.34
Seven Seas | 368566-5 | 1 | Complete | Fall 2021 | November | 743 DEARBORN AVE | 5 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | October | 616 N 28TH ST | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 120 S Shawnee Ter | 5 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 123 N 42nd St | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 1824 BANK ST | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 207 S 42ND ST | 5 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works | 84.28
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2403 ROWAN ST | 5 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2714 Alford Ave | 5 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 2725 NORTHWESTERN PKY | 5 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 5 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 5 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 3500 W MAIN ST | 5 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works | See 4302 Winnrose | repaird by LWC, a new water meter was installed in the verge next to the new 9'x6' sw,
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 351 N 28th St | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works | 4.44 | 201 -205 SW Parkway, 56’x6’ and 10’x6’ and 16’x6’ of sw, 227 SW Parkway 37’x6’ of sw, and 1 tree, 231 SW Parkway23’x6’ of sw and 1 tree, 235 - 237 SW Parkway 10’x6’ of sw and 14’x6’ of sw and 1 tree, 239 SW Parkway 29’x6’ of sw , 245 SW Parkway 5’x6’ of sw , 249-251 SW Parkway 45’x6’ and 4’x5’ and 3’x5’ of sw
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 3640 River Park Dr | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 | 29 | Curb ramp and alley- future paving project
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 4102 VERMONT AVE | 5 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose | Curb ramp and alley - future paving project
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 5 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose | 25' of curb and 12x7 of sw
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose | 67x6 of sw and 3 utility adjustments
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 4509-4515 W Market St | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works | See 207 S 42nd St | 20x6 of sw and 1 tree
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 631 S 42ND ST | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 650 S 31st St | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works | See 207 S 42nd St | 6'x6' of dw and 7'x6' of dw and 9'x6' of dw and 7'x3' of dw and 1 utility adjustment
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 662 Cecil Ave | 5 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works | See 4302 Winnrose | 6’x10’ of sw and 6’x22’ of sw, and 4’x4’ of sw
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 667 S 39TH ST | 5 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | See 4302 Winnrose | 10’x5’ of sw and 15’ of curb, 100’x5’ of sw and 5’x25’ of dw and 91’x5’ of sw and 2 trees
Seven Seas | 368566-5 | 1 | Complete | Summer 2021 | September | 682 Madelon Ct | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works | See 4302 Winnrose | 43’x8’ of sw at 2732 W. Jeffreson St, 8’x6’ of sw at 2729 W. Jefferson St, 86’x6’of sw at 234 S 28th St.
Seven Seas |  | 1 | Inspected | Winter 2021 |  | 311 N 30TH ST | 5 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Seven Seas |  | 1 | Inspected | Winter 2021 |  | 312 N 30TH ST | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | REPAIRED BY OTHERS
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | 464 N 25TH ST | 5 | 64238 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 9.3 | REPAIRED BY OTHERS
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | 472 TO 468 N 29TH ST | 5 | 6500 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 45 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | 474 N 29TH ST | 5 | 4490 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 13.3 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
Joash Construction | 368745-10 | 1 | Sent to Contractor | Fall 2021 |  | 501 N 21st St | 5 | 22525.8 |  |  |  | 8138 410 8107 148280 822705 | Council District 5 | 140.56
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | 804 S 39TH ST | 5 | 7750 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 17 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | 805 S 39TH ST | 5 | 3250 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 21.3 | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | N 29TH ST & BANK ST | 5 | 12000 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 123
Seven Seas | 368566-24 | 1 | Sent to Contractor | Winter 2022 |  | S 28TH ST & W JEFFERSON ST | 5 | 2210 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 100.8 | 5'X5' OF SW OR RAMP
TBD | 368745-10 | 2 | Complete | Summer 2021 | December | 112 E ST CATHERINE ST | 6 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.81 | 6'X5' OF SW BY OTHERS
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 1261 S BROOK ST | 6 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 16.56 | R3 4'X23' of dw
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 1265 S BROOK ST | 6 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1.78 | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 1317 S 6TH ST | 6 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 11.5
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 1638 W KENTUCKY ST | 6 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 25.42
|  | 2 | Complete | Fall 2020 | December | 1703 S BROOK ST | 6 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others | No R4 or R5 present
|  | 2 | Complete | Summer 2021 | December | 1815 Hale Ave | 6 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others | 60'x6' of sw
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 2623 GREENWOOD AVE | 6 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 5.67 | 35'x4' of historic sw and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 3014 MONTANA AVE | 6 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 14.22 | 10'X18' and 17'x10' and 9'x10' of historic sw and 6'x10' of historic dw and 1 utility gas meter. (remove 1-22", 1-25" and 1-27" tree as marked) seed and protection. Straight cut bricks to tie into sw.
|  | 2 | Complete | Summer 2021 | December | 610 W Magnolia Ave | 6 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others | 7'x6'of sw at 2100 Grand Ave and 6'x6' of sw at 2103 Grand Ave.
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | December | 635 PARK AVE | 6 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 5 | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
|  | 2 | Complete | Fall 2020 | December | 821 HUMLER ST | 6 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By others
|  | 2 | Complete | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 6 |  | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others
|  | 2 | Complete | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 6 | 4933.5 | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others
|  | 2 | Complete | Fall 2020 | December | WILSON AVE & S 23RD ST | 6 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By Others
Joash Construction | 368745-21 | 2 | Inspected | Winter 2022 | February | 1423 ARCADE AVE | 6 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | By others
Joash Construction | 368745-10 | 2 | Inspected | Summer 2021 | February | 1330 W BRECKINRIDGE ST | 6 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 32.67
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | January | 1434 THORNBERRY AVE | 6 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 15.5
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | January | 509 W ORMSBY AVE | 6 | 15200 | 52211.13 |  | 52211.13 | 8148 410 8211 148560 822705 | Public Works | 89.58
|  | 2 | Complete | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 6 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works | 8.67
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | March | 1336 S 6TH ST | 6 | 14200 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works | see 509 W ORMSBY AVE
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | March | 1408-1410 HOMEVIEW DR | 6 | 15726.25 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works | see 509 W ORMSBY AVE
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | March | 1410 ARCADE AVE | 6 | 2657.7778 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works | see 509 W ORMSBY AVE
Joash Construction | 368745-21 | 2 | Complete | Winter 2022 | March | W ORMSBY AVE & S 6TH ST (1338 s 6 th St.) | 6 | 8200 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works | see 509 W ORMSBY AVE
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | November | 1503 EARL AVE | 6 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 3.31 | 12'x7.5' of historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 15.5' x7.5' of historic sw and 15' of historic curb historic (remove 1-31" and 2-17" trees)
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | November | 3221 UTAH AVE | 6 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 9.92
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 1424 EARL AVE | 6 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 13.5 | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 1501 EARL AVE | 6 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 2.92 | 12'x4' of historic sw and curb, 39'x4' of historic sw, and 5'x4' of historic sw, seed and protection
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 1502 PHYLLIS AVE | 6 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 6.03
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3210 UTAH AVE | 6 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 8.7
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3212 UTAH AVE | 6 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 8.05
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3223 UTAH AVE | 6 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 4.47
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3234 UTAH AVE | 6 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 29.27
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3238 UTAH AVE | 6 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 2.72 | R4 19'X8' OF SW AND 47'X8' OF historic sw and saw cut along the retaining wall as marked, remove two 18" and one 23" tree as marked, seed and protection
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3240 UTAH AVE | 6 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 10.11
Joash Construction | 368745-10 | 2 | Complete | Summer 2021 | October | 3249 UTAH AVE | 6 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 4.67 | 7310 Wesboro Rd 16x4 of dw, 7314 Wesboro Rd 16x4 of sw and 1 lge mh adj, 7316 Wesboro Rd 10x4 of sw and 1 lge mh adj, 7322 Wesboro Rd 11x4 and 5x4 and 6x4 of sw and 1 lge mh adj, 7324 10x4 of sw and 1 lge mh adj, 7326 Wesboro Rd 6x4 of sw and one tree inspection. Contacted James Tipton at LGE regarding the 3 transfomers in sidewalk. | (Jason Tipton w LGE 3/18/22)
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 1152 Garvin Pl | 6 | 20946.6667 | [5 empty] | 98.66
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 1157 LINCOLN AVE | 6 | 4675 | [5 empty] | 11
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 1364 Lillian Ave | 6 | 5977.7778 | [5 empty] | 9.78
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 1605 DUMESNIL ST | 6 | 2966.6667 | [5 empty] | 10 | 5'x9' of sw & 5’x5’ of dw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 1775 Wilson Ave | 6 | 7028.8889 | [5 empty] | 18.44 | 4.5'x30' of sw; 1 utility adj., seed and protection.
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 2214 Hale Ave | 6 | 3553.3333 | [5 empty] | 12 | 4'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | 907 Burton Ave | 6 | 3700 | [5 empty] | 17.33 | 4'x37' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist. Upon receiving these recommendations could one of you please reach out the Larry and inform him.
|  | 2 | Not Inspected | TBD |  | Sidewalk Reparis TBD | 6 | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6 |  | 5'x10' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 | 2 | Sent to Contractor | Winter 2022 |  | WINKLER AVE & S 5TH ST | 6 | 5533.3333 | [5 empty] | 30
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 2309 Date St | 6 | 3626.6667 | [6 empty] | 5'x25' of sw & 5’x5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 1400 S. Floyd St | 6 | 9291.6667 | [6 empty] | 5’x12.5’ of sw, seed and protection.
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 121 W Oak St | 6 | See 123 W Oak St | [6 empty] | 6'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 123 W Oak St | 6 | 11433.3333 | [6 empty] | 5'x15' of sw & 5'x55' of sw & 5'x10' of sw & 5'x36.5' of sw & 5'x17' of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
| 368745-24 |  |  |  |  | 1701 Gallagher St | 6 | 9726.6667
| 368745-24 |  | Sent to Contractor | Winter 2022 |  | 1217 S 26th St | 6 | 4433.3333
| 368745-24 |  |  |  |  | 1635 Wilsion Ave | 6 | 5166.6667
| 368745-24 |  |  |  |  | 1429 Homevied Dr | 6 | 3694.4444
| 368745-24 |  |  |  |  | Intersection of 8th & Cawthon | 6 | 11277.7778 | [6 empty] | 5’x14’ of sw, seed and protection.
TBD |  | 3 | Inspected | Winter 2022 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 7 | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5’x43’ of sw & 4’x5.5’ of sw, seed and protection.
| 368569-6 | 3 | Complete | Winter 2021 | March | 1418 MORTON AVE | 8 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 1902 Deerwood Ave | 8 | 5556.6 | 32964.32 |  | 32964.32 | 8146 410 8211 148487 822705 | Public Works | 228.66 | 4'x25' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 2023 Woodbourne Ave | 8 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave | 5’x50’ of sw; 10’x11’ of dw; 3.5'x4.5' of courtesy pad & 3.5'x4.5' of courtesy pad, seed and protection. 2 large trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 2082 Douglass Blvd | 8 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave
TBD | 368569-6 | 3 | Complete | Winter 2021 | March | 2105 DOUGLASS BLVD | 8 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 2115 Woodbourne Ave | 8 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave
TBD | 368569-6 | 3 | Complete | Winter 2021 | March | 2208 LAUDERDALE RD | 8 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5'x13.5' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 2224 Dundee Rd | 8 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave | Historic conc. 6'x54' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
| 368569-6 | 3 | Complete | Winter 2021 | March | 2246 BOULEVARD NAPOLEON | 8 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | Historic conc. 6’x15’ of sw; 3.5'x3.5' of courtesy pad, seed and protection.
TBD | 368569-6 | 3 | Complete | Winter 2021 | March | 2300 MEADOW RD | 8 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | March | 2809 Montrose Ave | 8 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave | 8'x10.5' of sw & 8'x5' of sw & 8'x25' of sw & 8'x15' of sw & 8'x20' of sw & 8'x16.5' of sw & 10'x21' of sw; 1 manhole adj., seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-3 | 3 | Complete | Fall 2021 | November | 2303 Meadow Rd | 8 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 | 27.63
Seven Seas | 368569-6 | 3 | Complete | Fall 2021 | November | 1522 Rosewood Ave | 8 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1819 Harvard Dr | 8 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 5
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1840 SHADY LN | 8 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 15
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1875 RUTHERFORD AVE | 8 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1895 RUTHERFORD AVE | 8 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 16.44
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1900 ROANOKE AVE | 8 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 5.56
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1912 HAMPDEN CT | 8 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 16.67
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1912 HARVARD DR | 8 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 6.94
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 1920 BONNYCASTLE AVE | 8 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 6
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2018 BOULEVARD NAPOLEON | 8 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 74.17
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2137 ALTA AVE | 8 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 7.78
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2139 WOODBOURNE AVE | 8 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 26.33
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2218 WOODBOURNE AVE | 8 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 7.5
Seven Seas | 368569-5 |  | Inspected | Winter 2022 |  | 2219-2221 TALBOTT AVE | 8 | 18149 |  |  |  | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council District 8 | 30.42
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2310 BOULEVARD NAPOLEON | 8 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 7.5
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2420 LONGEST AVE | 8 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 35.33
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 2541 Cherokee Pkwy | 8 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 11.36 | 4'x8' of sw & 5'x26’ of sw, seed and protection, Mr. Ed Bowling His number is (502) 494-9569.once arborist reports back. He wants to save the tree
Seven Seas | 368569-6 | 3 | Inspected | Winter 2022 |  | 701 BAXTER AVE | 8 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 105.11 | Historic Conc. 3'x8' of sw, seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1821 Frankfort Ave | 9 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1801 Frankfort Ave | 9 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 213
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1805 Frankfort Ave | 9 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1807 Frankfort Ave | 9 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | Historic Conc. 3'x10' of curtesy pad, seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1809-1811 Frankfort Ave | 9 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1817 Frankfort Ave | 9 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1823 Frankfort Ave | 9 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1825 Frankfort Ave | 9 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1832-1830 Frankfort Ave | 9 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 |  | Complete |  | January | 1846 Frankfort Ave | 9 |  |  |  | See 1860 Frankfort Ave |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1860 Frankfort Ave | 9 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 2039 Frankfort Ave | 9 | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | 6'x13.5' of sw; and 1 utility adj, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 2101 Frankfort Ave | 9 | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | Historic Conc. 4.5'x36' of sw, seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | Ramps at Pope and State St | 9 | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | January | 1 Eastover Ct | 9 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1808-1800 Frankfort Ave | 9 | 15975.52 |  |  | 75718 | 8138 410 8107 148227 822705 | Council District 9 | 321.65
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1813-1815 Frankfort Ave | 9 | 7731.9 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1838 Frankfort Ave | 9 | 6019.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 3.5'x4' of sw & 5’x30’ of sw & 4’x14’ of sw & 4’x5’ of sw; 2’x5’ of ADA pad; 26’ of curb, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1870-1874 Frankfort Ave | 9 | 3468.23 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1880 Frankfort Ave | 9 | 792 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1882 Frankfort Ave | 9 | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1900 MELLWOOD AVE | 9 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1910 Frankfort Ave | 9 | 699.87 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 1928 Frankfort Ave | 9 | 3400.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2 Eastover Ct | 9 | 1182.6 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Sent to Contractor | Fall 2021 | March | 2040 Frankfort Ave | 9 | 4884 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 5'x14' of sw, seed and protection
Seven Seas | 368567-5 | 3 | Sent to Contractor | Fall 2021 | March | 2138 New Main St | 9 | 3480 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 4'x28' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2140 SYCAMORE AVE | 9 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2334-2336 Frankfort Ave | 9 | 113.4 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2368 Frankfort Ave | 9 | 2376 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2400 Frankfort Ave | 9 | 2059.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 5’x35’ of sw; 1 utility adj., seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 2608 Frankfort Ave | 9 | 1428.24 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 6’x16’ of sw, seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 3210 Frankfort Ave | 9 | 5467.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 6’x31’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 3220 MARION CT | 9 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6’x9’ of sw & 3’x10.5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 3230 Frankfort Ave | 9 | 275.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1808--1800 Frankfort Ave | 5.5’x9’ of sw, seed and protection
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | 405 UNIVERSITY AVE | 9 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | See 1902 Deerwood Ave | 4’x14’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 | March | Frankfort & Haldeman | 9 | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 62 | Full depth repairs to be done by Seven Seas and charged to 368569-7
Seven Seas | 368567-5 | 3 | Sent to Contractor | Fall 2021 |  | 102 Crescent Ct | 9 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 49.28 | 5'X5' OF SW
Seven Seas | 368567-9 | 3 | Complete | Winter 2021 |  | 118 N EWING AVE | 9 | 3588 | 13919 |  | 13919 | 8148 410 8211 148560 822705 | Public Works | 45.6 | GRINDING BY OTHERS
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 122 N BAYLY AVE | 9 | 2555.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 19
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 148 VERNON AVE | 9 | 398.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.67
Seven Seas | 368567-5 | 3 | Sent to Contractor | Fall 2021 |  | 1854 Frankfort Ave | 9 | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 | 3.33
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 201 S PETERSON AVE | 9 | 9370.9667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 9 | 4'x8' of sw and 4'x12' of dw (by others)
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 2035 EMERALD AVE | 9 | 2392 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 18 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Seven Seas | 368567-5 | 3 | Complete | Fall 2021 |  | 2144 Frankfort Ave | 9 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2022 |  | 217 MCCREADY AVE | 9 | 5000 |  |  |  |  | Public Works | 27.78 | 8'x4' of sw
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 3410 INGLE AVE | 9 | 1162.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 7.78 | 16'x4' and 12'x4' and 12'x4' of sw
Seven Seas | 368569-8 | 3 | Sent to Contractor | Winter 2021 |  | 3547 NANZ AVE | 9 | 2788.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 12.44 | 8'x4' of sw plus fill in void adjacent to sw
Seven Seas | 368567-3 | 3 | Unsure | Fall 2021 | November | 1137 Reutlinger Ave | 10 |  | 2107.9 |  | 2107.9 |  |  | 5.73 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 1014 WAGNER ST | 10 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 13.33 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 1031 WETTERAU AVE | 10 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 12
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 1107 E BURNETT AVE | 10 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 17.33
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 1131 MULBERRY ST | 10 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 11.11
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 2029 ALEXANDER AVE | 10 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 28.67
Seven Seas | 368569-7 | 3 | Inspected | Winter 2022 |  | 220 DERBY AVE | 10 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 26.67
TBD |  | 3 | Not Inspected | Winter 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 10 | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 5 | Inspected | Winter 2021 | December | 2824 SIX MILE LN | 11 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works | By others
TBD |  | 5 | Inspected | Winter 2021 | December | 4011 RIVULET LN | 11 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works | By others
TBD |  | 5 | Inspected | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 11 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works | By others | 4’x15’ of sw & 4’x17’ of sw, seed and protection
TBD |  | 5 | Not Inspected | Winter 2021 | November | Lacevine Ct from Lacevine Rd to Lacevine Pl | 11 |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works | See Lacevine Rd | 4’x26’ of sw, seed and protection.
TBD |  | 5 | Not Inspected | Winter 2021 | November | Lacevine Rd from Trumpetvine Rd to Dead End | 11 | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works | 191.11 | 4'x9’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | Complete | Fall 2021 | January | 7002 URANAS DR | 12 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works | By others | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 387121-3 | 4 | Complete | Winter 2022 | October | Deady Dr from Dead End to Dead End | 12 | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works | See Rebecca Ln
Riverside Paving | 387121-3 | 4 | Complete | Winter 2022 | October | Rebecca Ln from Deady Dr to Dead End | 12 | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works | 142.67
Riverside Paving | 387121-3 | 4 | Sent to Contractor | Winter 2022 |  | 5032 Hunters Point Cir | 12 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 | 10.66
Riverside Paving | 387121-3 | 4 | Sent to Contractor | Winter 2022 |  | 6208 MOUNT EVEREST DR | 12 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 11
Riverside Paving | 387121-3 | 4 | Sent to Contractor | Winter 2022 |  | 7015 BIRNAMWOOD DR | 12 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3.56
Riverside Paving | 387121-3 | 4 | Sent to Contractor | Winter 2022 |  | 9612 BROOKS BEND RD | 12 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.44
Riverside Paving | 387121-3 | 4 | Sent to Contractor | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 12 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 1.89
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 128 ELK RIVER DR | 13 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works | See 9303 Minute Men Ct | 27'x4' of sw and 2 utility adj, s/p
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 804 FLICKER RD | 13 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works | See 9303 Minute Men Ct | 13'x4' of sw, s/p
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 8114 ATLANTA PKY | 13 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works | See 9303 Minute Men Ct | 46'x4' of sw, 1 utility adjustment, trim tree roots if needed, s/p
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 9303 Minute Men Ct | 13 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works | 162.85 | 33' of curb replacement, s/p
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 9402 Balance Ln | 13 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works | See 9303 Minute Men Ct | 12'x4' of sw, s/p
TBD | 368756-17 | 4 | Not Inspected | Spring 2022 | November | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 13 | 10138.5 |  | See Beecher St |  | 8148 410 8211 148560 822705 | Public Works | See Beecher St | 52'x4' of sw, raise the sw to eliminate 2" ponding water at the low spot
TBD | 368756-17 | 4 | Not Inspected | Spring 2022 | November | Auburn Oaks from New Cut Rd to Dead | 13 | 32000 |  | See Beecher St |  | 8148 410 8211 148560 822705 | Public Works | See Beecher St | 5'x4' and 42x4' of sw, s/p
TBD | 368756-17 | 4 | Not Inspected | Spring 2022 | October | Glengarry Dr from National Turnpike to Gary Way | 13 | 19500 |  | See Rebecca Ln |  | 8148 410 8211 148560 822705 | Public Works | See Rebecca Ln | 6'X4' and 6'x4' and 8'x4' of sw and and 9'x5' of dw, s/p
Riverside Paving | 368756-17 | 4 | Sent to Contractor | Winter 2022 |  | 200 ELK RIVER DR | 13 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 11.56 | 15'x4' of sw, call msd to investigate drainage issues (2 holes in the yard next to the catch basin) msd sr# 5415608
Riverside Paving | 368756-17 | 4 | Sent to Contractor | Winter 2022 |  | 211 APPOMATTOX RD | 13 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 11.56 | 27'x4' and 25'x4' and 9'x4' of sw, s/p
Riverside Paving | 368756-17 | 4 | Sent to Contractor | Winter 2022 |  | 6013 LARKGROVE DR | 13 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3.78
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 5708 Fruitwood Dr | 14 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 6222-6224 Bethany Ln | 14 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 6223 Bethany Ln | 14 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 6300 W Pages Ln | 14 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 6911 Ethan Allen Way | 14 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 7301-7303 Ethan Allen Way | 14 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 7513 Wimstock Ave | 14 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 8405 Devonshire Dr | 14 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 | See 9303 Minute Men Ct
TBD | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 11802 Pierce Way | 14 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 12
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 13413 HINCHBROOK BLVD | 14 | 1328.8889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 5.78
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Wnter 2022 |  | 13417 Kinross Blvd | 14 | 3327.92 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 20.44
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 6007 Alanadale Dr | 14 | 4585.07 |  |  | 0 | 8142-410-8107-148279-821344 | Council District 14 | 12.42
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 6012 Alanadale Dr | 14 | 1342.88 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 5.33
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 7002 Nathan Hale Way | 14 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 23.11 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2021 |  | 7014 Ethan Allen Way | 14 | 550.08 |  |  | 0 | 8146 410 8107 148279 822705 | Council District 14 | 20.89 | 5’x16’ of sw; 8’x8’ of dw & 14’ of curb, seed and protection
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 7902 NANCY LN | 14 | 3588 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 8.9 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 9805 Sun Way Dr | 14 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 6.67 | 5’x15’ of sw, seed and protection
Riverside Paving | 368756-16 | 4 | Sent to Contractor | Winter 2022 |  | 9900 SUNKIST WAY | 14 | 2325.5556 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 27.11 | 21’x5’ of dw, seed and protection.
TBD |  | 4 | Not Inspected | Spring 2022 |  | TBD | 14 | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 21’x5’of sw & 16’x5’ of sw, seed and protection
TBD |  | 4 | Not Inspected | Spring 2022 |  | TBD | 14 | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25’x5’of sw & 10’x5’ of dw, seed and protection
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 1409 Southgate Ave | 15 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 4'x14' of sw & 4'x10' of dw
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 1410 Weyler Ave | 15 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 5’x6’ of sw & 5’x6’ of sw & 2’x6’ of sw, seed and protection
Riverside Paving | 368756-4 | 4 | Complete | Spring 2021 | July | 1609 Cherry Way | 15 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works | See 9303 Minute Men Ct | 16’x5’of sw & 15’x5’ of sw, seed and protection
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3605 POWELL AVE | 15 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 5’x15’ of sw; 5’x45’ of sw; 5’x10’ of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3606 WHEELER AVE | 15 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 5'x6' of sw; 5'x6' of sw; 5'x13’ of sw, seed and protection. 1 tree stump removal & 1 Magnolia tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3612 WHEELER AVE | 15 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 5'x6' of sw & 5'x6' of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3671 POWELL AVE | 15 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works | 162.85 | 4’x20’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3703 KAHLERT AVE | 15 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 10’ of paved over curb & Gutter, seed and protection
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3710-3712 WHEELER AVE | 15 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 6’x90’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 3724 WHEELER AVE | 15 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 6'x25’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-4 | 4 | Complete | Winter 2021 | July | 530 DRESDEN AVE | 15 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works | See 3671 Powell | 5'x15' of sw; 5'x5' of dw & 5'x10' of dw; 7'x10' of apron, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
TBD | 368756-20 | 4 | Complete | Fall 2021 | March | 1031 NAVAHO PL | 15 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5’x40’ of sw; 5’x10’ of dw, seed and protection.
Riverside Paving | 368756-4 | 4 | Complete | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 15 | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works | 333.78 | 4’x21’ of sw; 4’x9’ of sw; 4’x40’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 | September | 2431 EMIL AVE | 15 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6’x36’ of sw, seed and protection.
Riverside Paving | 368756-18 | 4 | Sent to Contractor | Winter 2022 |  | 1020 Berry Blvd | 15 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 1496 CLARA AVE | 15 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.78 | 5'x35' of sw; 5'x30' of sw (along Merhoof St side of 619 Duvall St), seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-18 | 4 | Sent to Contractor | Winter 2022 |  | 1500 Hobart Ct | 15 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
Riverside Paving | 368756-18 | 4 | Sent to Contractor | Winter 2022 |  | 1503-1505 Paula Ct | 15 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
Riverside Paving | 368756-18 | 4 | Sent to Contractor | Winter 2022 |  | 1506 Hobart Ct | 15 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15
Riverside Paving | 368756-18 |  | Sent to Contractor | Winter 2022 |  | 1421 Anna Lane | 15 | 981.79 |  |  |  | See 3418 Powell | Council District 15 | 6.22
Riverside Paving | 368756-19 | 4 | Sent to Contractor | Winter 2022 |  | 221 W ADAIR ST (Next to I-264) | 15 | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 | 8
Riverside Paving | 368756-18 | 4 | Sent to Contractor | Winter 2022 |  | 3418 POWELL AVE | 15 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 | 7.22
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 3515 HENRY AVE | 15 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 8.33
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 3705 W WHEATMORE DR | 15 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3.33
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 4035 WOODRUFF AVE | 15 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4
Riverside Paving | 368756-19 | 4 | Sent to Contractor | Winter 2022 |  | 4328 S 2nd St | 15 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 | 6.67
Riverside Paving | 368756-19 | 4 | Sent to Contractor | Winter 2022 |  | 4400 S 2nd St | 15 | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 | 5.33
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 542-546 RAWLINGS ST | 15 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 19.56
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 608 RAWLINGS ST | 15 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 15
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 611 MERWIN AVE | 15 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0.44
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 613 DUVALL ST | 15 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 8.5
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 654 N BARBEE WAY | 15 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 12.88
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | 664 ATWOOD ST | 15 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4
TBD | 368756-20 | 4 | Not Inspected | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 15 | 50000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-20 | 4 | Sent to Contractor | Winter 2022 |  | MERHOFF ST & DUVALL ST | 15 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 32.17
TBD |  | 4 | Not Inspected | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr | 15 | 37259 |  |  | 0 | 8138-410-8107-148233-822702 $15920.38 8133-410-8107-148233-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11202 Deham Dr | 16 | 336.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11215 Deham Dr | 16 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11301 Deham Dr | 16 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11303-11305 Deham Dr | 16 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11304-11306 Deham Dr | 16 | 1435.24 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11307 Deham Dr | 16 | 988.23 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11406 Kendrick Dr | 16 | 4940.17 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11408 Kendrick Dr | 16 | 1369.83 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11412 Hammond Dr | 16 | 1761.6 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11414 Kendrick Dr | 16 | 719.03 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11415 Kendrick Dr | 16 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11500 Kendrick Dr | 16 | 538.06 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11504 Kendrick Dr | 16 | 1309.75 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11505-11509 Fisherman Way | 16 | 1813.59 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11506 Kendrick Dr | 16 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11513 Fisherman Way | 16 | 881.38 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11514 Kendrick Dr | 16 | 403.7 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 11516 Kendrick Dr | 16 | 210.88 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5110 Windy Willow Dr | 16 | 1429.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5204 Baywood Dr | 16 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5204 Windy Willow Dr | 16 | 929.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | See | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5207 Windy Willow Dr | 16 | 3393.1 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 6.5'x7.5' of sw, seed and protection.
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5211 Windy Willow Dr | 16 | 3467.27 | 49112.92 |  | 49112.92 | 8101 410 8105 148234 822705 | Council District 16 | 332.23 | 4'x12' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5304 Drifton Dr | 16 | 888.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 4'x12' of sw; 4'x12' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5305-5307 Baywood Dr | 16 | 627.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5308 Drifton Dr | 16 | 1831.93 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 7'X4' OF SW, Straight cut roots
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5311 Drifton Dr | 16 | 2473.37 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5401 Baywood Dr | 16 |  |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 6'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5403 Windy Willow Dr | 16 | 1114.94 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 6'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5404-5406 Baywood Dr | 16 | 1157.62 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 5'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5405 Windy Willow Dr | 16 | 695.96 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5407 Windy Willow Dr | 16 | 1726.32 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 5'X4' AND 5'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5408-5410 Windy Willow Dr | 16 | 973.89 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 5'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5410 Baywood Dr | 16 | 224.14 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5412 Lithia Dr | 16 | 1441.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 4'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5501 Lithia Dr | 16 | 2094.49 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 6'X4' OF SW
Seven Seas | 368567-8 | 3 | Sent to Contractor | Fall 2021 | December | 5505 Windy Willow Dr | 16 | 134.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 | See 5211 Windy Willow Dr | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
Seven Seas | PO applied for | 3 | Inspected | Winter 2022 | January | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 16 | 15000 |  | 10048 | 10048 | 8148 410 8211 148560 822705 | Public Works | 310 | 9'X4' AND 10'X4' OF SW
Seven Seas | PO applied for | 3 | Inspected | Winter 2022 | January | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 16 | 7500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works | See Chamberlan Way | 5'X4' OF SW
Seven Seas | PO applied for | 3 | Inspected | Winter 2022 | January | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 16 | 22500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works | See Chamberlan Way | 4'X4' OF SW
Seven Seas | 368567-8 | 3 | Inspected | Winter 2022 |  | 10630 Meeting St | 16 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 4'X4' OF SW
Seven Seas | 368567-8 | 3 | Inspected | Winter 2022 |  | 4003 Deer Creek Dr | 16 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 7'X4' AND 5'X4' AND 9'X4' OF SW
Seven Seas | 368567-8 | 3 | Inspected | Winter 2022 |  | 4230 Ashleywood Ct | 16 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  | 13'X4' OF SW
TBD |  | 3 | Complete | Winter 2021 | December | 3219 WYNBROOKE CIR | 17 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works | By Others | 5'X4' OF SW
Seven Seas | 368758-1 | 3 | Complete | Winter 2021 | March | 13415 FOREST SPRINGS DR | 17 | 3718.3333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 10'X4'of SW
Seven Seas | 368758-1 | 3 | Complete | Winter 2021 | March | 13419 FOREST SPRINGS DR | 17 | 3552.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 10'X4' OF SW and
Seven Seas | 368758-1 | 3 | Complete | Winter 2021 | March | 13430 FOREST SPRINGS DR | 17 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 10'X4' OF SW
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13510 BROKEN BRANCH WAY | 17 | 398.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 5'X4' OF SW and straight cut roots only as necessary.
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13512 BROKEN BRANCH WAY | 17 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 12'X4' OF SW BY OTHERS
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13520 BROKEN BRANCH WAY | 17 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 4’x8.5' of sw, seed and protection.
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13606 BROKEN BRANCH WAY | 17 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13607 BROKEN BRANCH WAY | 17 | 996.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 2.5'x4.5' of sw; 9'x9.5' of dw, seed and protection.
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 13700 BROKEN BRANCH WAY | 17 | 830.5556 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3610 ROCK BAY DR | 17 | 1245.8333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3700 ROCK BAY DR | 17 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3700 WOODED SPRINGS CT | 17 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3707 ROCK BAY DR | 17 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3710 CYPRESS SPRINGS PL | 17 | 1528.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3724 CYPRESS SPRINGS PL | 17 | 332.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3801 BUGLEWOOD PL | 17 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3809 ROCK BAY DR | 17 | 581.3889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3814 ROCK BAY DR | 17 | 1827.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots tripstop
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 3915 ROCK BAY DR | 17 | 1661.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 4002 ROCK BAY DR | 17 | 913.6111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 4010 ROCK BAY DR | 17 | 747.5 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas | 368758-1 | 3 | Complete | Winter 2022 | March | 9603 MOORFIELD CIR | 17 | 332.2222 | 19391.51 |  | 19391.51 | 8148 410 8211 148560 822705 | Public Works | 105.67
Seven Seas | 368758-1 | 3 | Complete | Winter 2021 | March | 13408 FOREST SPRINGS DR | 17 | 2057.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works | See 9603 MOORFIELD CIR
Seven Seas |  | 3 | Not Inspected | Summer 2021 |  | 13508 Springs Station Rd | 17 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17
Seven Seas | Applied for | 3 | Inspected | Winter 2022 |  | 10403 Sterling Springs Rd | 18 | 2283.41 |  |  |  | 8102-410-8105-148267-822705 | Council District 18
TBD |  | 3 | Complete | Winter 2021 |  | 2817 ENGLEWOOD AVE | 18 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.44
Seven Seas | Applied for | 3 | Inspected | Winter 2022 |  | 4429 Rockwood Dr | 18 | 1359.6 |  |  |  | 8102-410-8105-148267-822705 | Council District 18
Seven Seas | PO applied for | 3 | Inspected | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 18 | 30000 |  | 7375 | 7375 | 8148 410 8211 148560 822705 | Public Works | 227
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 12403 Hersfield Rd | 19 | 3029 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 | See 610 Woodlake | 4’x6’ of sw, seed and protection
Seven Seas | 368567-7 |  | Sent to Contractor | Spring 2022 | February | 125 Waterstone Way | 19 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council | See 17106 Mallet Hill Dr | 4’x4’ of sw, seed and protection
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 1335 Heafer Rd | 19 | 1083.37 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 | See 610 Woodlake
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 1337 Heafer Rd | 19 | 2093 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 | See 610 Woodlake
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 1340 Heafer Rd | 19 | 6518.89 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 | See 610 Woodlake
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 14008 CROSSBRANCH CT | 19 | 1702.27 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 14202 LAKE FOREST DR | 19 | 764.53 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake | 4’x8’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 14306 LAKE FOREST DR | 19 | 1085.15 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake | 4’x18’ of sw, seed and protection
Seven Seas | 368567-7 | 5 | Sent to Contractor | Spring 2022 | February | 14313 Micawber Way | 19 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council | See 17106 Mallet Hill Dr | This was completed in 2019
Seven Seas | 368567-7 | 5 | Sent to Contractor | Spring 2022 | February | 15109 Abington Ridge Pl | 19 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council | See 17106 Mallet Hill Dr | 6'x4' of sw across from 315 Evergreen Rd, replace 10'x4' ramp, and 7' of curb and replace 2-4'x4' sections of sw on Evergreen Rd. side of 12017 Shelbyville Rd.
Seven Seas | 368567-7 | 5 | Sent to Contractor | Spring 2022 | February | 17106 Mallet Hill Dr | 19 | 12079.26 |  |  | 15681.79 | 8102 410 8105 148963 822702 | Council | 106.09
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 17204 MALLET HILL DR | 19 | 520 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake
| 368569-4 | 5 | Not Inspected | Fall 2021 | February | 2213 ARNOLD PALMER BLVD | 19 | 4422.13 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 311 Lake Forest Pky | 19 | 1674 |  |  | See 610 Woodlake | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works | See 610 Woodlake
Seven Seas |  | 5 | Complete | Fall 2021 | February | 504-506 EDGEFOREST PL | 19 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works | 14
Seven Seas |  | 5 | Complete | Fall 2021 | February | 505 EDGEFOREST PL | 19 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works | 6.2222
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 610 WOODLAKE DR | 19 | 10437.73 | 27130.14 |  | 27130.14 | 8146 410 8211 148487 822705 | Public Works | 192
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | February | 612 WOODLAKE DR | 19 | 9381.95 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake
TBD | 368569-4 | 5 | Inspected | Winter 2021 | February | STURBRIDGE PL & STURBRIDGE CIR | 19 | 747.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works | See 610 Woodlake
TBD |  | 5 | Complete | Winter 2021 | March | 15105 MEADOW FARMS CT | 19 | 730.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 4.5’x4’ of sw & 4’x4’ of sw, seed and protection
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | March | 17108 MALLET HILL DR | 19 | 1202.57 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake | 5’x4’ of sw & 15’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | March | 412-414 LAKE FOREST PKY | 19 | 2092.4 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake | Completed
Seven Seas | 368569-4 | 5 | Sent to Contractor | Fall 2021 | March | 509 EDGEFOREST PL | 19 | 233.33 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works | See 610 Woodlake | CONCRETE SPALLING
Seven Seas | 368569-11 | 5 | Sent to Contractor | Winter 2022 |  | 11007 FOX MOORE PL | 19 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8'X4' OF SW
Seven Seas | 368569-11 | 5 | Sent to Contractor | Winter 2022 |  | 14611 LAKE BLUFF PL | 19 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
Seven Seas | 368569-11 | 5 | Sent to Contractor | Winter 2022 |  | 803 FOXGATE RD | 19 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 10’x4’of sw, seed and protection
Seven Seas | 368569-11 | 5 | Sent to Contractor | Winter 2022 |  | 836 LAKE FOREST PKWY | 19 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.5’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Fall 2021 |  | D19 Berrytown Rd Sidewalk Repair Project | 19 | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 12’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | PO applied for | 5 | Sent to Contractor | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 19 | 15840 |  | 8986 | 8986 | 8148 410 8211 148560 822705 | Public Works | 277 | 17’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | PO applied for | 5 | Inspected | Winter 2022 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 19 | 15000 |  | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | #VALUE! | 8148 410 8211 148560 822705 | Public Works | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 15.5’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Spring 2021 | August | 10417-10419 Pinoak View Dr | 20 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 5.3333 | 5’x4’of sw & 10’x4’ of sw; 1 utility adj., seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Spring 2021 | August | 11109-11111 Little Spring Blvd | 20 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 2.8889 | 14’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Spring 2021 | August | 13909-13911 Laclara Way | 20 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 9.3333 | 8’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Spring 2021 | August | 4010 Stone Lakes Dr | 20 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 3.5556 | 9.5’x4’of sw, seed and protection
|  | 5 | Complete | Spring 2021 | August | 4015 Stone Lakes Dr | 20 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 5.3333 | 9’x4’ of sw, seed and protection
|  | 5 | Complete | Spring 2021 | August | 8800 Sanctuary Ln | 20 |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 5 | 14’x4’ of sw & 12’x4’ of sw, seed and protection. 3 trees need to be inspected; we are awaiting recommendations from the arborist.
|  | 5 | Complete | Spring 2021 | August | 9818 Stanalouise Dr | 20 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works | 5.3333 | 4’x4’ of sw & 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-4 | 5 | Complete | Winter 2022 | February | 14304 MICAWBER WAY | 20 | 2127.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works | See 610 Woodlake | 18’x4’ of sw & 21’x4’ of sw & 5’x4’ of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 5 | Complete | Winter 2021 | March | 11804 LONGVIEW FARM DR | 20 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.44 | 20’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 5 | Complete | Winter 2021 | March | 11906 LONGVIEW FARM DR | 20 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.67 | Completed
TBD |  | 5 | Complete | Winter 2021 | March | 12000 LONGVIEW FARM DR | 20 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15’x4’ of sw, seed and protection
TBD |  | 5 | Complete | Winter 2021 | March | 12004 LONGVIEW FARM DR | 20 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works | 3.11 | 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 11012 Perwinkle Ln | 20 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 3.78 | 17.5’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 114 Wickfield Dr | 20 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 8.89 | 16’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13602 Meadow Vista Ct | 20 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 4.44 | 4’x6’ of sw & 4’x11’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13604 Meadow Vista Ct | 20 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 2 | 4’x4’ of sw & 4’x18’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13608 Meadow Vista Ct | 20 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 5.33 | no issue observed
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13610 Meadow Vista Ct | 20 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 7.56 | 6’x4’ of sw & 11’x4 of sw, seed and protection
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13615 Meadow Vista Ct | 20 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 6.89 | 14’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13700-13701 Willow Reed Dr | 20 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 6.67 | The LWC SR # is 1786143959 at 9704 Mary Dell Lane. The MSD SR # is 5415539 at 9920 Mary Dell Lane. I contacted Jason Tipton about the LGE transformer adj. at 9814 Mary Dell Lane.
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13702 Willow Reed Dr | 20 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 6.22
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13705 Willow Reed Dr | 20 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 3.56
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13809 Round Top Pl | 20 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 4.22
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 13811 lakemont Ct | 20 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 4
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 14107 Glendower Dr | 20 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 44.56
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 14601 Landis Lakes Dr | 20 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 5.78
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 200 Wickfield DR | 20 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 1956
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 303 Wickfield Dr | 20 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 8.89
TBD |  | 5 | Complete | Winter 2021 |  | 3106 SHADY SPRINGS DR | 20 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.67 | 12’x4’ of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 4004 Saratoga Woods Dr | 20 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 6.67 | 10’x4’ of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 4026 Pleasant Glen Dr | 20 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 4 | 4’x4’ of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 4504 Stone Lakes Dr | 20 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 7.78 | 6'x4' of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 4517 Saratoga Woods Dr | 20 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 7.11 | Addressed by lge
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 505 Wickfield Dr | 20 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 7.56 | 8'x4' of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 615 Wickfield DR | 20 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 9.78 | 11'x4' of sw
TBD |  | 5 | Complete | Spring 2022 |  | 6515 Calm River Way | 20 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 12’x4’ of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 6530 Calm River Way | 20 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 7.56 | 17’x4’ of sw
Seven Seas | 368569-10 | 5 | Sent to Contractor | Spring 2022 |  | 6726 Calm River Way | 20 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 | 6.22 | 4’x4’ of sw & 18’x4’ of sw
Precision Concrete Cutting | 381611-7 | 5 | Sent to Contractor | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 20 | 50000 |  | 12181.5 | 12181.5 | 8148 410 8211 148560 822705 | Public Works | 417 | 5’x4’ of sw & 6’x4’ of sw
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | July | 223 Iroquios Ave | 21 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works | 1 | 5’x4’ of sw
Precision Concrete Cutting | 381611-13 | 4 | Not Inspected | Winter 2021 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 21 | 85000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 9'x4' of sw
|  | 4 | Not Inspected | Spring 2021 |  | TBD | 21 | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21 |  | 10'x4' of sw
|  | 5 | Complete | Spring 2021 | August | 3806 GREENWICH RD | 22 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 12 | 10'x4' of sw
|  | 5 | Complete | Spring 2021 | August | 3811 GREENWICH RD | 22 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 4 | 10'x4' of sw
|  | 5 | Complete | Spring 2021 | August | 3812 GREENWICH RD | 22 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 4 | 12'x4' of sw
|  | 5 | Complete | Spring 2021 | August | 5803 BUCKS LN | 22 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works | 18 | 10x4 of sw
|  | 5 | Complete | Spring 2021 | August | 6016 Mercury Dr | 22 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 8.22 | 12'x4' of sw and 5'x4' of sw
Seven Seas | 368569-9 | 5 | Sent to Contractor | Winter 2022 |  | 10104 RIMFIRE RD | 22 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 5.33 | No R4 or R5 issues observed during the February 2022 inspection
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 11201 Meadow Breeze Ln | 22 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.44 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 11410 Wind Haven Way | 22 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 1.78 | 15'x4' of sw
Seven Seas | 368569-9 | 5 | Sent to Contractor | Winter 2022 |  | 3816 GREENWICH WAY | 22 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.67 | 6'x4' of SW
|  | 5 | Complete | Winter 2021 |  | 5807 BUCKS LN | 22 | By others |  |  | By others | 8148 410 8211 148560 822705 | Public Works | 4.44
Seven Seas | 368569-9 | 5 | Sent to Contractor | Winter 2022 |  | 6217 HINES MILL WAY | 22 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 3.56 | No R4 or R5 issues observed during the March 2022 inspection
Seven Seas | 368569-9 | 5 | Sent to Contractor | Winter 2022 |  | 6416 MOSSY OAKS DR | 22 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 4.89
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7507 Kendrick Crossing Ln | 22 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 5.33
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7600 Hornbeck Farm Rd | 22 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 7.56
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7802 Windgate Dr | 22 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 9.78
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7804 Windgate Dr | 22 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.89
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7812 Windgate Dr | 22 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 2.22
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7821 Windgate Dr | 22 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4 | 4’x17’ of sw, seed and protection
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7901 Windgate Dr | 22 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.44 | 4’x11’ of sw, seed and protection.
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7907 Windgate Dr | 22 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.44 | 4'x8’ of sw, seed and protection.
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7909 Niemann Dr | 22 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.44 | 4'x54’ of sw & 4'x14’ of sw, seed and protection.
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7909 Windgate Dr | 22 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 5.33
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7912 Windgate Dr | 22 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 4.44 | 21'X4' OF SW
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7913 Windgate Dr | 22 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 7.55 | No R4 or R5 issues observed during the Jan 2022 inspection
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7916 Windgate Dr | 22 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 6.58 | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7917 Windgate Dr | 22 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 5.33 | 4'x11' of sw and remove tree stump
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7919 Windgate Dr | 22 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 6.67 | 48'X4' OF Asphalt SW, straight cut roots as needed
Seven Seas | 368569-9 | 5 | Sent to Contractor | Fall 2021 |  | 7920 Windgate Dr | 22 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 | 2.67
Precision Concrete Cutting | 381611-8 | 5 | Complete | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 22 | 45000 |  | 4729.5 | 4729.5 | 8148 410 8211 148560 822705 | Public Works | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 8902 Willowcreek Drive- Property owner stopped Precision Concrete from completing the beveling work along the sidewalk in front of the house.
TBD |  | 5 | Complete | Winter 2021 |  | MAJOR LN & GLENWAY PL | 22 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2.67
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 6707 VANDRE AVE | 23 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 | See 7802 Appleview | 4'X5' OF SW REPAIED BY OTHERS
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 6711 VANDRE AVE | 23 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 7802 APPLEVIEW LN | 23 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 | 38.99
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 7818 APPLEVIEW LN | 23 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 7820 APPLEVIEW LN | 23 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | Complete | Summer 2021 | August | 8218 VAUGHN MILL RD | 23 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works | 47.55
Riverside Paving | 368756-21 | 4 | Sent to Contractor | Winter 2022 |  | 7208-7210 Quindero Run Rd | 23 | 733.76 |  |  |  | 8137-410-8211-148560-822705 | Public Works | 7.56
Riverside Paving | 368756-21 | 4 | Sent to Contractor | Winter 2022 |  | 7213 Quindero Run Rd | 23 | 550.4 |  |  |  | 8137-410-8211-148560-822705 | public Works | 4.89
Riverside Paving | 368756-21 | 4 | Sent to Contractor | Winter 2022 |  | 7226-7228 Quindero Run Rd | 23 | 917.33 |  |  |  | 8137-410-8211-148560-822705 | Public Works | 3.56
Riverside Paving | 368756-21 | 4 | Sent to Contractor | Winter 2022 |  | 8214 Happiness Way | 23 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 30.22
Precision Concrete Cutting | 381611-9 | 4 | Sent to Contractor | Winter 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 23 | 55000 |  | 4171 | 4171 | 8148 410 8211 148560 822705 | Public Works | 102
TBD |  | 4 | Complete | Winter 2021 | December | 5204 MONACO DR | 24 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works | By Others
TBD |  | 4 | Complete | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 24 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works | By Others
Riverside Paving | 368758-1 | 4 | Complete | Winter 2022 | February | 7832 BRIDLEWOOD PL | 24 | 1328.8889 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works | 37.32
Riverside Paving | 368758-1 | 4 | Complete | Fall 2021 | February | 8603 Timber Hollow Ct | 24 | 1727.56 |  |  | See 8918 Elmcreek | 8146 410 8211 148487 822705 | Public Works | See 7832 Bridlewood PL
Riverside Paving | 368758-1 | 4 | Complete | Winter 2022 | February | 8708 SHEPHERDSVILLE RD | 24 | 3189.3333 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works | See 7832 Bridlewood PL
Riverside Paving | 368758-1 | 4 | Complete | Winter 2022 | February | 8918 ELMCREEK DR | 24 | 3053.8889 | 3824 |  | 3824 | 8148 410 8211 148560 822705 | Public Works | See 7832 Bridlewood PL
Precision Concrete Cutting | 381611-18 | 4 | Sent to Contractor | Winter 2022 |  | WillowCreek Drive from Old South Park Rd to Maplecreek Dr | 24 | 37500 |  | 15831 | 15831 |  |  | 390
Precision Concrete Cutting | 381611-11 | 4 | Sent to Contractor | Winter 2022 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 25 | 25000 |  | 6691.5 | 6691.5
Precision Concrete Cutting | 381611-12 | 4 | Sent to Contractor | Winter 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 26 | 40000
[8 empty] | 2951529.1233 | 657580.2
| 381611-14 |  |  |  |  | CBD Beveling project |  | 250000
vault top in sw - contact property owner
Note on G69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## April 2022
| PO # | Area | District | Construciton Status | Date Appropriated | Start | Finish | F | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | Invoice # | inspection month | inspection notes
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1050 S 32ND ST | 4 | 24817.6389 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 30'x5' of sw and 9' curb
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1112 S 26TH ST | 4 | 5813.8889 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 33'x5' of sw and 4 utiliy adj
Seven Seas | 368566-25 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1147-1149 S 42nd St |  | 2137.07 | 4459.34 |  | 4459.34 | 8133-410-8107-148283-822705 | Council Funds |  | 9.44 | 120015M-91 |  | 14'x6' of sw, remove stump, s/p
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1433-1451 HAZEL ST | 4 | 13953.3333 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 40'x6' and 37'x6' and 31x6 of sw and 4 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3511 W KENTUCKY ST | 4 | 12857 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 6'x12' of sw and 2 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3714 CHAUNCEY AVE | 5 | 5877.7778 | 22589 |  | 22589 | 8148 410 8211 148560 822705 | Public Works |  | 132.64 | 120015M-90 | 2022-01-01 | 5'x5' of sw (snow and ice covered -could not inspect on Feb 22 site visit)
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 1300 S 32ND ST | 4 | 1146.1667 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 1366 OLIVE ST | 5 | 16445 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 2 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3222 VIRGINA | 4 | 2541.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3516 COTTER DR | 5 | 1345.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 11'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4408 JENNYMAC DR | 4 | 1196 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-01-01 | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4807 HUNTERS POINT CIR | 4 | 1727.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 5616 CHRISTIAN RIDGE CT | 4 | 3070.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 743 S 43RD ST | 4 | 10695 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  |  | 14'x6' of sw and 33'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Winter 2022 | February | 808 & 810 S 42ND ST | 4 | 4983.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | 11.33
Joash Construction | 368745-10 | 1 | 1 | Complete | FY22 | Fall 2021 | January | 1152-1156 S 26TH ST | 5 | 12790.5556 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 83.33
Seven Seas | 368566-21 | 1 | 1 | Complete | FY21 | Winter 2022 | March | 3500 Block of Algonquin Pkwy | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1 |  |  |  | 2022-02-22 | 3519 9x4 of sw, 3513 5x5 0f sw, 3509 5x4 of sw, 3500 5x4 of sw, 3506 11x6 of dw and 4x4 of sw, 3508 10x10 of dw, 3512 6x5 of sw, 3516 11x8 of dw and 5x4 of sw, 3518 17x4 of dw, 3520 9x4 of sw and 1 utilty adj, 3528 5x4 of sw and 6x4 of sw, 3530 10x4 of dw, 3536 11x4 of sw and 1 tree, 3542 4x4 of sw, 3544 6x4 of dw, 3546 4x4 of sw, 3908 38'x4 of sw and 8' of curb and 1 big tree sent to arborist
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1 |  |  | 120521
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4 | 120015M-76
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 |  | 104.9
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | 513.78
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest
|  |  | 2 |  |  |  |  | Various Sidewalk Repairs |  | 6609 |  |  |  | 8133 410 8111 148221 822705 | Council funds |  |  |  |  | D2 needs to identify projects with this funding.
Joash Construction | 368746-1 | 1 | 3 | Complete | FY20 | Fall 2021 | February | 1413 OLEANDA AVE | 5 | 4651.1111 | 48026.16 |  | 48026.16 | 8143 410 8211 148472 822705 | Public Works |  | 287.74
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1472 DIXIE HWY | 4 | 830.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1505 OLEANDA AVE | 4 | 1993.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1509 OLEANDA AVE | 4 | 6043.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2116 OREGON AVE | 4 | 2242.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2313 ALLSTON AVE | 5 | 448.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3312 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3314 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3319 UTAH AVE | 4 | 1063.1111 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction | 368745-10 | 1 | 3 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 4 | 1328.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Seven Seas | 368566-5 | 1 | 3 | Not Inspected | FY22 | Fall 2021 | October | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 2's through 5's | 10760 |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | 40
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
TBD |  | 1 | 3 | Not Inspected | FY22 | Fall 2021 |  | 1634 BEECH ST | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | bring shovel
Joash Construction | 368745-10 | 1 | 3 | Not Inspected | FY22 | Fall 2021 |  | 2616 ALLSTON AVE | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.56
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-01-31 | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19 |  | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | 4 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works |  | By others |  | 2022-01-31 | 6'X2' OF OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5 |  | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 829 W. Main St. | 5 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | RR track in front of Frasier Museum. Investigate moving trash can to this location.
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2022-01-31 | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | 4 | Complete | FY20 | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 5 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works |  | By others |  | 2022-01-31 | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 1076 E WASHINGTON ST | 4 | 9449.1667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 5.28 |  | 2022-01-31
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 1910-1912 MAGAZINE ST | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 15 |  | 2021-01-31 | 15'X9' OF SW
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 237 E Breckinridge St | 4 | 27864 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 6'X2' of dw
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 514 BARRET AVE | 5 | 10925 | 14104.1 |  | 14104.1 | 8146 410 8211 148487 822705 | Public Works | 2 | 101.91 |  | 2021-01-31 | R5 63'X6' and 6'x4' of sw, 3 utility adjustments, 22" tree and 12" tree
TBD | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 550 S 3RD ST (possibility Utilities' fault) | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0 | 0.44 |  | 2021-01-31 | No issue observed during the 1/31/22 sw inspection
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 741 FRANKLIN ST | 5 | 4861.9444 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 63.2 |  |  | complete
| 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 747 E JEFFERSON ST | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 23'X14' OF DW
|  | 2 | 4 | Complete | FY22 | Winter 2022 | March | 833 W MAIN ST | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0 |  | 2021-01-31 | Pw operations is placing trash can on top of displaced rr track to mitigate
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | N SHELBY ST & FRANKLIN ST | 4,5 | 11553.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | S HANCOCK ST & E BRECKINRIDGE ST | 5 | 4069.7222 |  |  | 0 |  | Public Works |  | see 514 BARRET AVE |  | 2022-01-31 | 30'x11' of sw and 30' of curb and 1 utility adjustment.
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 40 |  | 2021-12-21 | REPAIRED BY OTHERS
| 368745-24 |  | 4 | Sent to Contractor |  | Winter 2022 |  | W. Jefferson St & S. 4th St | 5 | 4669.4444
| 368745-24 |  | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 1115 E Oak St | 5 | 14455.5556 | [6 empty] | 55.56
| 368745-24 |  | 4 |  |  |  |  | 1120 E. Breckinridge St | 4 | 3455.5556
|  | 2 | 4 | Not Inspected | FY22 | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  | 2021-01-31 | Snow and ice on the sw prohibited the site inspection. The sidewalk is within the floodwall right of way and is R1-R5. Set up meeting with MSD to confirm the permitting requirement or closing the gates to block off access since a new sidewalk was constructed in 2021 across from 1224 Franklin St as an altermate ADA comatible sw.
| 368745-24 |  | 4 |  |  |  |  | 130 S 3rd St | 4 | 7945
| 368745-24 |  | 4 | Sent to Contractor |  | Winter 2022 |  | 217 S 5th St | 5 | 2256.6667
| 368745-24 |  | 4 | Sent to Contractor |  | Winter 2022 |  | 315 E Main St | 5 | 9191.6667
| 368745-24 |  | 4 |  |  |  |  | 4TH ST and LIBERTY ST | 5 | 4000
| 368745-24 |  | 4 |  |  |  |  | 512 Barret Ave | 5 | 15540
| 368745-24 |  | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 530 Barret Ave/Lexington Rd | 4 | 4628.8889 | [6 empty] | 36.67
| 368745-24 |  | 4 |  |  |  |  | 721 4th St | 4 | 4000
| 368745-24 |  | 4 | Sent to Contractor |  | Winter 2022 |  | 721 S. 4th St | 4 | 5478.8889
| 368745-24 |  | 4 | Sent to Contractor |  | Winter 2022 |  | 725 ROSELANE ST | 5 | 18277.7778 | [6 empty] | 92.22
|  | 2 | 4 | Not Inspected |  |  |  | 731 FRANKLIN ST
| 368745-24 |  | 4 | Sent to Contractor | FY 22 | Winter 2022 |  | Barret Ave & Baxter Ave | 5 | 27608.8889 | [6 empty] | 55.56
Precision Concrete Cutting |  | 1 | 5 | Complete | FY21 | Winter 2021 | April | 200 Block of Southwestern Pky | 4 | 15242 | See 464 N 25TH ST |  | #VALUE! | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 201 -205 SW Parkway, 56’x6’ and 10’x6’ and 16’x6’ of sw, 227 SW Parkway 37’x6’ of sw, and 1 tree, 231 SW Parkway23’x6’ of sw and 1 tree, 235 - 237 SW Parkway 10’x6’ of sw and 14’x6’ of sw and 1 tree, 239 SW Parkway 29’x6’ of sw , 245 SW Parkway 5’x6’ of sw , 249-251 SW Parkway 45’x6’ and 4’x5’ and 3’x5’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 464 N 25TH ST | 4 | 64238 | 60103.7 |  | 60103.7 | 8146 410 8211 148487 822705 | Public Works |  | 497.31 | 120015M-92 | 2022-02-22 | 25' of curb and 12x7 of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 472 TO 468 N 29TH ST | 4 | 6500 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 67x6 of sw and 3 utility adjustments
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 474 N 29TH ST | 4 | 4490 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 20x6 of sw and 1 tree
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 804 S 39TH ST | 5 | 7750 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6'x6' of dw and 7'x6' of dw and 9'x6' of dw and 7'x3' of dw and 1 utility adjustment
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 805 S 39TH ST | 4 | 3250 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6’x10’ of sw and 6’x22’ of sw, and 4’x4’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | N 29TH ST & BANK ST | 4 | 12000 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 10’x5’ of sw and 15’ of curb, 100’x5’ of sw and 5’x25’ of dw and 91’x5’ of sw and 2 trees
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | S 28TH ST & W JEFFERSON ST | 5 | 2210 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 43’x8’ of sw at 2732 W. Jeffreson St, 8’x6’ of sw at 2729 W. Jefferson St, 86’x6’of sw at 234 S 28th St.
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2814 ROWAN ST | 4 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 7.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 38.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? |  | 60
Joash Construction | 368745-10 | 1 | 5 | Complete | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 1 | 40.69
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 4 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 18.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 4 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 40.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 4 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.77
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 1 | 46.55
Joash Construction |  | 1 | 5 | Complete | FY21 | Fall 2021 | December | 501 Northwesern Pkwy |  |  |  |  | See 3511 Northwestern Pkwy |  |  |  | 157
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 35.61
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 4 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 17.81
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 4 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 42.33
Joash Construction | 368745-10 | 1 | 5 | Complete | FY 22 | Fall 2021 | December | Vermont and Southwestern |  |  | 5289.2 |  | 5289.2 |  |  |  | 75.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1114 PLATO TER | 4 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1501 LYTLE ST | 4 | 4252.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Seven Seas | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 4501 GREENWOOD AVE #1 | 5 | 6250 |  |  | Completed by others | 8146 410 8211 148487 822705 | Public Works |  | Completed by others |  | 2022-02-22 | No R4 or R5 observed
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Winter 2022 | March | 109 N 40TH ST | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6 |  |  | repaird by LWC, a new water meter was installed in the verge next to the new 9'x6' sw,
Seven Seas |  | 1 | 5 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 80.34
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 4 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works |  | 4.44
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | 1 | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 311 N 30TH ST | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley- future paving project
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 312 N 30TH ST | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley - future paving project
Seven Seas | 368745-10 | 1 | 5 | Sent to Contractor | FY21 | Fall 2021 |  | 501 N 21st St | 4's and 5's | 22525.8 |  |  |  | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
TBD | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81 |  | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1261 S BROOK ST | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1265 S BROOK ST | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1317 S 6TH ST | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5 |  | 2021-12-21 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42 |  | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
|  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 1703 S BROOK ST | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67 |  |  | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22 |  | DECEMBER
|  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-28 | 5'X5' OF SW OR RAMP
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 635 PARK AVE | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5 |  |  | 6'X5' OF SW BY OTHERS
|  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 821 HUMLER ST | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | R3 4'X23' of dw
|  | 2 | 6 | Complete | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 5 |  | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  |  | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
|  | 2 | 6 | Complete | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 5 | 4933.5 | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
|  | 2 | 6 | Complete | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | February | 1423 ARCADE AVE | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | No R4 or R5 present
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | February | 1330 W BRECKINRIDGE ST | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67 |  |  | 60'x6' of sw
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 1434 THORNBERRY AVE | 4 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 15.5 |  |  | 35'x4' of historic sw and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 509 W ORMSBY AVE | 5 | 15200 | 52211.13 |  | 52211.13 | 8148 410 8211 148560 822705 | Public Works | 10 | 89.58 |  |  | 10'X18' and 17'x10' and 9'x10' of historic sw and 6'x10' of historic dw and 1 utility gas meter. (remove 1-22", 1-25" and 1-27" tree as marked) seed and protection. Straight cut bricks to tie into sw.
|  | 2 | 6 | Complete | FY21 | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 5 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | 8.67 |  |  | 7'x6'of sw at 2100 Grand Ave and 6'x6' of sw at 2103 Grand Ave.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY20 | Winter 2022 | March | 1336 S 6TH ST | 4 | 14200 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x7.5' of historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 15.5' x7.5' of historic sw and 15' of historic curb historic (remove 1-31" and 2-17" trees)
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1408-1410 HOMEVIEW DR | 5 | 15726.25 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1410 ARCADE AVE | 4 | 2657.7778 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x4' of historic sw and curb, 39'x4' of historic sw, and 5'x4' of historic sw, seed and protection
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | W ORMSBY AVE & S 6TH ST (1338 s 6 th St.) | 5 | 8200 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | R4 19'X8' OF SW AND 47'X8' OF historic sw and saw cut along the retaining wall as marked, remove two 18" and one 23" tree as marked, seed and protection
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31 |  |  | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67 |  |  |  | (Jason Tipton w LGE 3/18/22)
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1152 Garvin Pl | 5 | 20946.6667 | [6 empty] | 98.66
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1157 LINCOLN AVE | 5 | 4675 | [6 empty] | 11
| 368745-24 |  | 6 | Sent to Contractor |  | Winter 2022 |  | 121 W Oak St |  | See 123 W Oak St
| 368745-24 |  | 6 | Sent to Contractor |  | Winter 2022 |  | 1217 S 26th St | 5 | 4433.3333
| 368745-24 |  | 6 | Sent to Contractor |  | Winter 2022 |  | 123 W Oak St | 4 | 11433.3333
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1364 Lillian Ave | 5 | 5977.7778 | [6 empty] | 9.78
| 368745-24 |  | 6 | Sent to Contractor |  | Winter 2022 |  | 1400 S. Floyd St | 5 | 9291.6667
| 368745-24 |  | 6 |  |  |  |  | 1429 Homevied Dr | 5 | 3694.4444
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1605 DUMESNIL ST | 5 | 2966.6667 | [6 empty] | 10
| 368745-24 |  | 6 |  |  |  |  | 1635 Wilsion Ave | 5 | 5166.6667
| 368745-24 |  | 6 |  |  |  |  | 1701 Gallagher St | 5 | 9726.6667
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1775 Wilson Ave | 4 | 7028.8889 | [6 empty] | 18.44
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 2214 Hale Ave | 4 | 3553.3333 | [6 empty] | 12
| 368745-24 |  | 6 | Sent to Contractor |  | Winter 2022 |  | 2309 Date St | 4 | 3626.6667
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 907 Burton Ave | 5 | 3700 | [6 empty] | 17.33
| 368745-24 |  | 6 |  |  |  |  | Intersection of 8th & Cawthon | 5 | 11277.7778
|  | 2 | 6 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | WINKLER AVE & S 5TH ST | 5 | 5533.3333 | [6 empty] | 30
TBD |  | 3 | 7 | Inspected | FY22 | Winter 2022 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 7310 Wesboro Rd 16x4 of dw, 7314 Wesboro Rd 16x4 of sw and 1 lge mh adj, 7316 Wesboro Rd 10x4 of sw and 1 lge mh adj, 7322 Wesboro Rd 11x4 and 5x4 and 6x4 of sw and 1 lge mh adj, 7324 10x4 of sw and 1 lge mh adj, 7326 Wesboro Rd 6x4 of sw and one tree inspection. Contacted James Tipton at LGE regarding the 3 transfomers in sidewalk.
| 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 1418 MORTON AVE | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 1902 Deerwood Ave | 4 | 5556.6 | 32964.32 |  | 32964.32 | 8146 410 8211 148487 822705 | Public Works |  | 228.66
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2023 Woodbourne Ave | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2082 Douglass Blvd | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
TBD | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2105 DOUGLASS BLVD | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2115 Woodbourne Ave | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
TBD | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2208 LAUDERDALE RD | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2224 Dundee Rd | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
| 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 2246 BOULEVARD NAPOLEON | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
TBD | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2300 MEADOW RD | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2809 Montrose Ave | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | November | 1522 Rosewood Ave | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-3 | 3 | 8 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1819 Harvard Dr | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5 |  |  | 5'x9' of sw & 5’x5’ of dw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1840 SHADY LN | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 15 |  |  | 4.5'x30' of sw; 1 utility adj., seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1875 RUTHERFORD AVE | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 4'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1895 RUTHERFORD AVE | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.44 |  |  | 4'x37' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist. Upon receiving these recommendations could one of you please reach out the Larry and inform him.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1900 ROANOKE AVE | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.56 |  |  | 5'x10' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HAMPDEN CT | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.67 |  |  | 5'x25' of sw & 5’x5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HARVARD DR | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.94 |  |  | 5’x12.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1920 BONNYCASTLE AVE | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6 |  |  | 6'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2018 BOULEVARD NAPOLEON | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 74.17 |  |  | 5'x15' of sw & 5'x55' of sw & 5'x10' of sw & 5'x36.5' of sw & 5'x17' of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2137 ALTA AVE | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.78 |  |  | 5’x14’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2139 WOODBOURNE AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.33 |  |  | 5’x43’ of sw & 4’x5.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2218 WOODBOURNE AVE | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 4'x25' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-5 |  | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2219-2221 TALBOTT AVE |  | 18149 |  |  |  | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council District 8 |  | 30.42 |  |  | 5’x50’ of sw; 10’x11’ of dw; 3.5'x4.5' of courtesy pad & 3.5'x4.5' of courtesy pad, seed and protection. 2 large trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2310 BOULEVARD NAPOLEON | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 5'x13.5' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2420 LONGEST AVE | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 35.33 |  |  | Historic conc. 6'x54' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2541 Cherokee Pkwy | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 11.36 |  |  | Historic conc. 6’x15’ of sw; 3.5'x3.5' of courtesy pad, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 701 BAXTER AVE | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 105.11 |  |  | 8'x10.5' of sw & 8'x5' of sw & 8'x25' of sw & 8'x15' of sw & 8'x20' of sw & 8'x16.5' of sw & 10'x21' of sw; 1 manhole adj., seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 122 N BAYLY AVE | 5 | 2555.5556 | 29946 |  | 29946 | 8148 410 8211 148560 822705 | Public Works |  | 100.35 | 121061M-12 |  | 4'x8' of sw & 5'x26’ of sw, seed and protection, Mr. Ed Bowling His number is (502) 494-9569.once arborist reports back. He wants to save the tree
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 148 VERNON AVE | 4 | 398.6667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 3'x8' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 201 S PETERSON AVE | 5 | 9370.9667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 6'x13.5' of sw; and 1 utility adj, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 2035 EMERALD AVE | 4 | 2392 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 4.5'x36' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2022 | April | 217 MCCREADY AVE | 4 | 5000 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE |  | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 3.5'x4' of sw & 5’x30’ of sw & 4’x14’ of sw & 4’x5’ of sw; 2’x5’ of ADA pad; 26’ of curb, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3410 INGLE AVE | 4 | 1162.7778 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 5'x14' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3547 NANZ AVE | 5 | 2788.1111 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 4'x28' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1821 Frankfort Ave | 4 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1 Eastover Ct | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1801 Frankfort Ave | 4 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 5 | 213
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1805 Frankfort Ave | 4 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1807 Frankfort Ave | 4 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1809-1811 Frankfort Ave | 4 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1817 Frankfort Ave | 5 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1823 Frankfort Ave | 3 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1825 Frankfort Ave | 4 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1832-1830 Frankfort Ave | 4 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 |  | 9 | Complete |  | Fall 2021 | January | 1846 Frankfort Ave |  |  |  |  | See 1860 Frankfort Ave |  |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1860 Frankfort Ave | 4 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2039 Frankfort Ave | 3, damaged detectable warnings | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2101 Frankfort Ave | ramp is out of compliance | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | Ramps at Pope and State St |  | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-9 | 3 | 9 | Complete | FY22 | Winter 2021 | March | 118 N EWING AVE | 4 | 3588 | 13919 |  | 13919 | 8148 410 8211 148560 822705 | Public Works |  | 45.6
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1808-1800 Frankfort Ave | 4 | 15975.52 |  |  | 75718 | 8138 410 8107 148227 822705 | Council District 9 | 2 | 321.65
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1813-1815 Frankfort Ave | 3, crumbling | 7731.9 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1838 Frankfort Ave | 5 | 6019.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1870-1874 Frankfort Ave | 3, sidewalk is breaking up | 3468.23 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1880 Frankfort Ave | 3, badly spalling | 792 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1882 Frankfort Ave | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1900 MELLWOOD AVE | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1910 Frankfort Ave | holding water | 699.87 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1928 Frankfort Ave | drainage issues with ramp | 3400.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2 Eastover Ct | 4 | 1182.6 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2040 Frankfort Ave | 4 | 4884 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2138 New Main St | damaged detectable warnings | 3480 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2140 SYCAMORE AVE | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2144 Frankfort Ave | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2334-2336 Frankfort Ave | 4 | 113.4 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2368 Frankfort Ave | 4 | 2376 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2400 Frankfort Ave | 4 | 2059.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2608 Frankfort Ave | 4 | 1428.24 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3210 Frankfort Ave | 4 | 5467.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3220 MARION CT | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3230 Frankfort Ave | 4 | 275.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 405 UNIVERSITY AVE | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | Frankfort & Haldeman | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas | 368567-5 | 3 | 9 | Sent to Contractor | FY21 | Fall 2021 |  | 102 Crescent Ct | 4 | 8360.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 49.28
Seven Seas | 368567-5 | 3 | 9 | Sent to Contractor | FY21 | Fall 2021 |  | 1854 Frankfort Ave | 3, spalling | 264 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 3.33 |  |  | Historic Conc. 3'x10' of curtesy pad, seed and protection
Seven Seas | 368567-3 | 3 | 10 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 5 |  | 2107.9 |  | 2107.9 |  |  |  | 5.73
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1014 WAGNER ST | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.33 |  |  | 5’x35’ of sw; 1 utility adj., seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1031 WETTERAU AVE | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12 |  |  | 6’x16’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1107 E BURNETT AVE | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 17.33 |  |  | 6’x31’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1131 MULBERRY ST | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 11.11 |  |  | 6’x9’ of sw & 3’x10.5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 2029 ALEXANDER AVE | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 28.67 |  |  | 5.5’x9’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 220 DERBY AVE | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.67 |  |  | 4’x14’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 3 | 10 | Not Inspected | FY22 | Winter 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | Full depth repairs to be done by Seven Seas and charged to 368569-7
TBD |  | 5 | 11 | Inspected | FY22 | Winter 2021 | April | Lacevine Rd from Trumpetvine Rd to Dead End | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11 |  |  | R4 8300 Lacevine 9x4 of sw, R4 8309 Lavevine 4x4 of sw,
TBD |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | 5'X5' OF SW
TBD |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 4011 RIVULET LN | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | GRINDING BY OTHERS
TBD |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others
TBD |  | 5 | 11 | Not Inspected | FY22 | Winter 2021 | November | Lacevine Ct from Lacevine Rd to Lacevine Pl | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
Riverside Paving | 368756-4 | 4 | 12 | Complete | FY21 | Fall 2021 | January | 7002 URANAS DR | 4 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | 4'x8' of sw and 4'x12' of dw (by others)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 | October | Deady Dr from Dead End to Dead End | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln | 2021-01-3 | 2022-01-01 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 | October | Rebecca Ln from Deady Dr to Dead End | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67 |  | 2022-01-01 | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 5032 Hunters Point Cir | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 |  | 10.66 |  | 2022-01-01 | 8'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 6208 MOUNT EVEREST DR | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11 |  | 2022-01-01 | 16'x4' and 12'x4' and 12'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 7015 BIRNAMWOOD DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 |  | 2022-01-01 | 8'x4' of sw plus fill in void adjacent to sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 9612 BROOKS BEND RD | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-01-01 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.89 |  | 2022-01-01 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
TBD | PO applied for | 4 | 13 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 2's through 4's | 10138.5 |  | 5778 |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD | PO applied for | 4 | 13 | Not Inspected | FY22 | Spring 2022 | November | Auburn Oaks from New Cut Rd to Dead End | 2's through 5's | 32000 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD | PO applied for | 4 | 13 | Not Inspected | FY22 | Spring 2022 | October | Glengarry Dr from National Turnpike to Gary Way | 2's through 5's | 19500 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 200 ELK RIVER DR | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x15’ of sw & 4’x17’ of sw, seed and protection
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 211 APPOMATTOX RD | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x26’ of sw, seed and protection.
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 6013 LARKGROVE DR | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78 |  |  | 4'x9’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct |  | 2022-01-01 | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 8405 Devonshire Dr | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11500 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11702 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11703 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11707 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11708 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11711 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11712 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11714 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11717 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11719 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11721 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11800 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11802 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11803 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11805 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11810 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11810-11812 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11814-11812 Pierce Way | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12 |  | 2022-02-25 | 27'x4' of sw and 2 utility adj, s/p
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11817-11819 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11904 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 13413 HINCHBROOK BLVD | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.78 |  | 2022-02-25 | 13'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 13417 Kinross Blvd | 5 | 3327.92 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 20.44 |  | 2022-02-25 | 46'x4' of sw, 1 utility adjustment, trim tree roots if needed, s/p
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 5711 Chestnutwood Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | Applied for | 4 | 14 | Inspected | FY22 | Spring 2022 |  | 6007 Alanadale Dr | Curb Repair | 4585.07 |  |  | 0 | 8142 410 8107 148279 821344 | Council District 14 |  | 12.42 |  | 2022-02-25 | 33' of curb replacement, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 6010 Alanadale Dr | 4, curb repair | 4776 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 6012 Alanadale Dr | 4, curb repair | 2808 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  | 2022-02-25 | 12'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 7002 Nathan Hale Way | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 23.11 |  | 2022-02-25 | 52'x4' of sw, raise the sw to eliminate 2" ponding water at the low spot
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 7014 Ethan Allen Way | 4 | 550.08 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 20.89 |  | 2022-02-25 | 5'x4' and 42x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 7902 NANCY LN | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.9 |  | 2022-02-25 | 6'X4' and 6'x4' and 8'x4' of sw and and 9'x5' of dw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Inspected | FY22 | Spring 2022 |  | 9805 Sun Way Dr | 5 | 366.98 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.67 |  | 2022-02-25 | Project on hold until MSD reserved the issue - 15'x4' of sw, call msd to investigate drainage issues (2 holes in the yard next to the catch basin) msd sr# 5415608 (MSD is placing a camera throuth lateral )
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 9900 SUNKIST WAY | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 27.11 |  | 2022-02-25 | 27'x4' and 25'x4' and 9'x4' of sw, s/p
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Cedarwood Dr from Mondamon Dr to Pond Creek Dr | 2's through 5's | 17440 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Fir Ct from Leemont Dr to Dead End | 2's through 5's | 2880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Fruitwood Dr from Leemont Dr to Pond Creek Dr | 2's through 5's | 20480 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Leemont Ct from Leemont Dr to Dead End | 2's through 5's | 3680 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Leemont Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Leemont Dr from Deering Rd to Alicante Ln | 2's through 5's | 37032 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Logwood Ave from Leemont Dr to Pond Creek Dr | 2's through 5's | 20800 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | North side of Alicante Ln from Andalee Dr to Leemont Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Pond Creek Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | 10880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | South side of Cedarwood Dr from Leemont Dr to Mondamon Dr | 2's through 5's | See Cedarwood Dr from Mondamon Dr to Pond Creek Dr |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
TBD |  | 4 | 14 | Not Inspected | FY22 | Spring 2022 |  | TBD | 4's or 5's | 8266.73 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
TBD |  | 4 | 14 | Not Inspected | FY22 | Spring 2022 |  | TBD | 2's through 5's | 39789.02 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | Vevia Pl from Leemont Dr to Pond Creek Dr | 2's through 5's | See Pond Creek Dr from Cedarwood Dr to Vevia Pl |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Not Inspected | FY 22 | Spring 2022 |  | West side of Leemont Dr from Alicante Ln to Cedarwood Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell | 2021-01-3
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
TBD | 368756-20 | 4 | 15 | Complete | FY22 | Fall 2021 | March | 1031 NAVAHO PL | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 | September | 2431 EMIL AVE | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1020 Berry Blvd | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  | 2021-12-21 | 5’x16’ of sw; 8’x8’ of dw & 14’ of curb, seed and protection
Riverside Paving | 368756-18 |  | 15 | Sent to Contractor |  | Winter 2022 |  | 1421 Anna Lane |  | 981.79 |  |  |  | See 3418 Powell | Council District 15 |  | 6.22 |  |  | 4'x14' of sw & 4'x10' of dw
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1496 CLARA AVE | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78 |  |  | 5’x15’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1500 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’ of dw, seed and protection.
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1503-1505 Paula Ct | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’of sw & 16’x5’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1506 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 25’x5’of sw & 10’x5’ of dw, seed and protection
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 221 W ADAIR ST (Next to I-264) | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8 |  |  | 5’x6’ of sw & 5’x6’ of sw & 2’x6’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3418 POWELL AVE | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22 |  |  | 16’x5’of sw & 15’x5’ of sw, seed and protection ( 3'x'4 courtesy pad at 3416 Powell Ave added to NTP D-15)
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3515 HENRY AVE | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33 |  |  | 5’x15’ of sw; 5’x45’ of sw; 5’x10’ of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3705 W WHEATMORE DR | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33 |  |  | 5'x6' of sw; 5'x6' of sw; 5'x13’ of sw, seed and protection. 1 tree stump removal & 1 Magnolia tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 4035 WOODRUFF AVE | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 5'x6' of sw & 5'x6' of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4328 S 2nd St | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67 |  |  | 4’x20’ of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4400 S 2nd St | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33 |  |  | 10’ of paved over curb & Gutter, seed and protection
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 542-546 RAWLINGS ST | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56 |  |  | 6’x90’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 608 RAWLINGS ST | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15 |  |  | 6'x25’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 611 MERWIN AVE | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44 |  |  | 5'x15' of sw; 5'x5' of dw & 5'x10' of dw; 7'x10' of apron, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 613 DUVALL ST | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5 |  |  | 5’x40’ of sw; 5’x10’ of dw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 654 N BARBEE WAY | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88 |  |  | 4’x21’ of sw; 4’x9’ of sw; 4’x40’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 664 ATWOOD ST | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 6’x36’ of sw, seed and protection.
TBD | 368756-20 | 4 | 15 | Not Inspected | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 2's through 5's | 50000 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | MERHOFF ST & DUVALL ST | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17 |  |  | 5'x35' of sw; 5'x30' of sw (along Merhoof St side of 619 Duvall St), seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 4 | 15 | Not Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr |  | 37259 |  |  | 0 | 8138-410-8107-148233-822702 $15920.38 8133-410-8107-148233-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11202 Deham Dr | 5 | 336.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11215 Deham Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11301 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 5 | 1435.24 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11307 Deham Dr | 5 | 988.23 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 5 | 4940.17 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 5 | 1369.83 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11412 Hammond Dr | 5 | 1761.6 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 5 | 719.03 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 5 | 538.06 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 5 | 1309.75 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 5 | 1813.59 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11513 Fisherman Way | 5 | 881.38 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 5 | 403.7 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 5 | 210.88 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 5 | 1429.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Baywood Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 5 | 929.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | See |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 5 | 3393.1 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 5 | 3467.27 | 49112.92 |  | 49112.92 | 8101 410 8105 148234 822705 | Council District 16 |  | 332.23
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5304 Drifton Dr | 5 | 888.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 5 | 627.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5308 Drifton Dr | 5 | 1831.93 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5311 Drifton Dr | 5 | 2473.37 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5401 Baywood Dr | 5 |  |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 5 | 1114.94 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 5 | 1157.62 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 5 | 695.96 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 5 | 1726.32 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 5 | 973.89 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5410 Baywood Dr | 5 | 224.14 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5412 Lithia Dr | 5 | 1441.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5501 Lithia Dr | 5 | 2094.49 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 5 | 134.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 2's through 5's | 15000 |  | 10048 | 10048 | 8148 410 8211 148560 822705 | Public Works |  | 310
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 2's through 5's | 7500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 2's through 5's | 22500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 10630 Meeting St | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 6.5'x7.5' of sw, seed and protection.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4003 Deer Creek Dr | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4230 Ashleywood Ct | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw; 4'x12' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 3 | 17 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By Others
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13415 FOREST SPRINGS DR | 5 | 3718.3333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13419 FOREST SPRINGS DR | 5 | 3552.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13430 FOREST SPRINGS DR | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas |  | 3 | 17 | Complete | FY21 | Summer 2021 | March | 13508 Springs Station Rd | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17 |  |  |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13510 BROKEN BRANCH WAY | 5 | 398.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13512 BROKEN BRANCH WAY | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' AND 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13520 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13606 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13607 BROKEN BRANCH WAY | 5 | 996.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13700 BROKEN BRANCH WAY | 5 | 830.5556 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3610 ROCK BAY DR | 4 | 1245.8333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 WOODED SPRINGS CT | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3707 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3710 CYPRESS SPRINGS PL | 5 | 1528.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3724 CYPRESS SPRINGS PL | 4 | 332.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' AND 5'X4' AND 9'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3801 BUGLEWOOD PL | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 13'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3809 ROCK BAY DR | 4 | 581.3889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3814 ROCK BAY DR | 4 | 1827.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4'of SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3915 ROCK BAY DR | 5 | 1661.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW and
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4002 ROCK BAY DR | 5 | 913.6111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4010 ROCK BAY DR | 5 | 747.5 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW and straight cut roots only as necessary.
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 9603 MOORFIELD CIR | 4 | 332.2222 | 19391.51 |  | 19391.51 | 8148 410 8211 148560 822705 | Public Works |  | 105.67 |  |  | 12'X4' OF SW BY OTHERS
Seven Seas | 368567-6 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13408 FOREST SPRINGS DR | 5 | 2057.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' OF SW, Straight cut roots
TBD |  | 3 | 18 | Complete | FY22 | Winter 2021 | March | 2817 ENGLEWOOD AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Seven Seas | Applied for | 3 | 18 | Inspected | FY 22 | Winter 2022 |  | 10403 Sterling Springs Rd |  | 2283.41 |  |  |  | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 4’x8.5' of sw, seed and protection.
Seven Seas | Applied for | 3 | 18 | Inspected | FY 22 | Winter 2022 |  | 4429 Rockwood Dr | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 2.5'x4.5' of sw; 9'x9.5' of dw, seed and protection.
Seven Seas | 368567-12 | 3 | 18 | Sent to Contractor | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 2's through 5's | 30000 |  | 7375 | 7375 | 8148 410 8211 148560 822705 | Public Works |  | 227
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 12403 Hersfield Rd | 4 | 3029 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368567-7 |  | 19 | Complete | FY 22 | Spring 2022 | February | 125 Waterstone Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1335 Heafer Rd | 5 | 1083.37 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1337 Heafer Rd | 5 | 2093 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1340 Heafer Rd | 4 | 6518.89 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14008 CROSSBRANCH CT | 4 | 1702.27 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14202 LAKE FOREST DR | 4 | 764.53 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14306 LAKE FOREST DR | 4 | 1085.15 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 14313 Micawber Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr |  |  | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots tripstop
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 15109 Abington Ridge Pl | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 17106 Mallet Hill Dr | 5 | 12079.26 |  |  | 15681.79 | 8102 410 8105 148963 822702 | Council |  | 106.09
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 17204 MALLET HILL DR | 4 | 520 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
| 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 2213 ARNOLD PALMER BLVD | 4 | 4422.13 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 | February | 311 Lake Forest Pky | 4 | 1674 |  |  | See 610 Woodlake | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 504-506 EDGEFOREST PL | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works |  | 14
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 505 EDGEFOREST PL | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works |  | 6.2222
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 610 WOODLAKE DR | 5 | 10437.73 | 28176.24 |  | 28176.24 | 8146 410 8211 148487 822705 | Public Works |  | 192
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 612 WOODLAKE DR | 5 | 9381.95 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
TBD | 368569-4 | 5 | 19 | Complete | FY22 | Winter 2021 | February | STURBRIDGE PL & STURBRIDGE CIR | 5 | 747.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | 19 | Complete | FY22 | Winter 2021 | March | 15105 MEADOW FARMS CT | 4 | 730.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 17108 MALLET HILL DR | 5 | 1202.57 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 412-414 LAKE FOREST PKY | 4 | 2092.4 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 509 EDGEFOREST PL | 4 | 233.33 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
|  | 5 | 19 | Complete | FY19 | Fall 2021 | March | D19 Berrytown Rd Sidewalk Repair Project |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  |  | This was completed in 2019
Seven Seas | 368569-11 | 5 | 19 | Sent to Contractor | FY22 | Winter 2022 |  | 11007 FOX MOORE PL | 5,2 | 1262.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 4’x6’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Sent to Contractor | FY22 | Winter 2022 |  | 14611 LAKE BLUFF PL | 4 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 4’x4’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Sent to Contractor | FY22 | Winter 2022 |  | 803 FOXGATE RD | 4 | 3053.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 4’x8’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-11 | 5 | 19 | Sent to Contractor | FY22 | Winter 2022 |  | 836 LAKE FOREST PKWY | 4 | 2691 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 4’x18’ of sw, seed and protection
Seven Seas | 368569-12 | 5 | 19 | Sent to Contractor | FY22 | Winter 2021 |  | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 2's through 5's | 15840 |  | 8986 | 8986 | 8148 410 8211 148560 822705 | Public Works |  | 277 |  | 2022-03-22 | 6'x4' of sw across from 315 Evergreen Rd, replace 10'x4' ramp, and 7' of curb and replace 2-4'x4' sections of sw on Evergreen Rd. side of 12017 Shelbyville Rd.
Seven Seas | 368569-12 | 5 | 19 | Sent to Contractor | FY22 | Winter 2022 |  | S Beckley Station Rd from Shelbyville Rd to Dead End | 2's through 5's | 15000 |  | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | #VALUE! | 8148 410 8211 148560 822705 | Public Works |  | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd
TBD |  | 5 | 20 | Complete | FY22 | Winter 2021 | April | 3106 SHADY SPRINGS DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | Completed
TBD |  | 5 | 20 | Complete | FY22 | Spring 2022 | April | 6515 Calm River Way | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-22 | no issue observed
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 2.8889
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 9.3333
|  | 5 | 20 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 3.5556
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
Seven Seas | 368569-4 | 5 | 20 | Complete | FY22 | Winter 2022 | February | 14304 MICAWBER WAY | 5 | 2127.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11804 LONGVIEW FARM DR | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  |  | Completed
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11906 LONGVIEW FARM DR | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | CONCRETE SPALLING
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12000 LONGVIEW FARM DR | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 8'X4' OF SW
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12004 LONGVIEW FARM DR | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 2022-01-22 | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 11012 Perwinkle Ln | 4 | 264 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 3.78 |  |  | 4.5’x4’ of sw & 4’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 114 Wickfield Dr | 5 | 2567.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 8.89 | 2022-02-22 |  | 5’x4’ of sw & 15’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13602 Meadow Vista Ct | 5 | 1182.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 4.44 |  |  | 10’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13604 Meadow Vista Ct | 3 | 1976.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 2 |  |  | 4.5’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13608 Meadow Vista Ct | 4 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 5.33 |  |  | 12’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13610 Meadow Vista Ct | 5 | 2270 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 7.56 |  |  | 17’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13615 Meadow Vista Ct | 5 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 6.89 |  |  | 15.5’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13700-13701 Willow Reed Dr | 4 | 1920.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 6.67 |  |  | 5’x4’of sw & 10’x4’ of sw; 1 utility adj., seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13702 Willow Reed Dr | 5 | 2066.57 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 6.22 |  |  | 14’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13705 Willow Reed Dr | 5 | 2269.72 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 3.56 |  |  | 8’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13809 Round Top Pl | 4 | 293.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 4.22 |  |  | 9.5’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 13811 lakemont Ct | 4 | 473.07 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 4 |  |  | 9’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 14107 Glendower Dr | 4 | 7692.4 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 44.56 |  | 2022-02-22 | 14’x4’ of sw & 12’x4’ of sw, seed and protection. 3 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 14601 Landis Lakes Dr | 5 | 2448.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 5.78 |  |  | 4’x4’ of sw & 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 200 Wickfield DR | 5 | 1918 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 1956 |  | 2022-02-22 | 18’x4’ of sw & 21’x4’ of sw & 5’x4’ of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 303 Wickfield Dr | 4 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 8.89 |  | 2022-02-22 | 20’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 4004 Saratoga Woods Dr | 4 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 6.67 |  |  | 15’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 4026 Pleasant Glen Dr | 4 | 2622 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 4 |  |  | 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 4504 Stone Lakes Dr | 5 | 882.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 7.78 |  |  | 17.5’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 4517 Saratoga Woods Dr | 4 | 6216.8 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 7.11 |  |  | 16’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 505 Wickfield Dr | 5 | 2875.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 7.56 |  | 2022-02-22 | 4’x6’ of sw & 4’x11’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 615 Wickfield DR | 4 | 2991.33 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 9.78 |  | 2022-02-22 | 4’x4’ of sw & 4’x18’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 6530 Calm River Way | 4 | 1056 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 7.56 |  | 2022-02-22 | 6’x4’ of sw & 11’x4 of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | 6726 Calm River Way | 4 | 646.27 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  | 6.22 |  | 2022-02-22 | 14’x4’ of sw, seed and protection
Seven Seas | 381611-7 | 5 | 20 | Sent to Contractor | FY22 | Spring 2022 |  | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2's through 5's | 50000 |  | 12181.5 | 12181.5 | 8148 410 8211 148560 822705 | Public Works |  | 417 |  |  | The LWC SR # is 1786143959 at 9704 Mary Dell Lane. The MSD SR # is 5415539 at 9920 Mary Dell Lane. I contacted Jason Tipton about the LGE transformer adj. at 9814 Mary Dell Lane.
Riverside Paving | 368756-4 | 4 | 21 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works |  | 1
Riverside Paving | PO applied for | 4 | 21 | Inspected | FY22 | Spring 2022 | June | S 3rd St from Waterson Underpass to W Woodlawn Ave | 2's through 5's | 85000 |  | 20061 | 20061 | 8148 410 8211 148560 822705 | Public Works |  | 636
|  | 4 | 21 | Not Inspected | FY18 | Spring 2021 |  | TBD |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 10104 RIMFIRE RD | 5 | 797.3333 | 24425.28 |  | 24425.28 | 8148 410 8211 148560 822705 | Public Works |  | 101.7 | 121162M-05 | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11201 Meadow Breeze Ln | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11410 Wind Haven Way | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 3816 GREENWICH WAY | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of sw
|  | 5 | 22 | Complete | FY22 | Winter 2021 | April | 5807 BUCKS LN | 4 | By others |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | 4 |  | 2022-01-22 | 9'x4' of sw Addressed by lge
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6217 HINES MILL WAY | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 8'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6416 MOSSY OAKS DR | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 11'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7507 Kendrick Crossing Ln | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7600 Hornbeck Farm Rd | 5 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 17’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7802 Windgate Dr | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw & 18’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7804 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw & 6’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7812 Windgate Dr | 5 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7821 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 9'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7901 Windgate Dr | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7907 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Niemann Dr | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Windgate Dr | 4 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7912 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10x4 of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7913 Windgate Dr | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw and 5'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7916 Windgate Dr | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 6.58 |  | 2022-02-23 | No R4 or R5 issues observed during the February 2022 inspection
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7917 Windgate Dr | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7919 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 15'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7920 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of SW
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 12
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 18
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 8.22
TBD |  | 5 | 22 | Complete | FY22 | Winter 2021 | March | MAJOR LN & GLENWAY PL | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | No R4 or R5 issues observed during the March 2022 inspection
Precision Concrete Cutting | 381611-8 | 5 | 22 | Complete | FY22 | Spring 2022 |  | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 2's through 5's | 45000 |  | 4729.5 | 4729.5 | 8148 410 8211 148560 822705 | Public Works |  | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2021-01-5 and 1097 (2nd Invoice was for Triumph) | 2022-12-21
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 5 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | 38.99
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works |  | 47.55
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7208-7210 Quindero Run Rd | 5 | 733.76 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 7.56 |  |  | 4’x17’ of sw, seed and protection
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7213 Quindero Run Rd | 5 | 550.4 |  |  |  | 8137-410-8211-148560-822705 | public Works |  | 4.89 |  |  | 4’x11’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7226-7228 Quindero Run Rd | 5 | 917.33 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 3.56 |  |  | 4'x8’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor | FY22 | Winter 2022 |  | 8214 Happiness Way | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 30.22 |  | 2022-12-21 | 4'x54’ of sw & 4'x14’ of sw, seed and protection.
Precision Concrete Cutting | 381611-9 | 4 | 23 | Sent to Contractor | FY22 | Winter 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 2's through 5's | 55000 |  | 4171 | 4171 | 8148 410 8211 148560 822705 | Public Works |  | 102
TBD |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | 2022-12-21 | 21'X4' OF SW
TBD |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  |  | No R4 or R5 issues observed during the Jan 2022 inspection
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 7832 BRIDLEWOOD PL | 4 | 1328.8889 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | 37.32 |  |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY21 | Fall 2021 | February | 8603 Timber Hollow Ct | 4 | 1727.56 |  |  | See 8918 Elmcreek | 8146 410 8211 148487 822705 | Public Works |  | See 7832 Bridlewood PL |  |  | 4'x11' of sw and remove tree stump
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8708 SHEPHERDSVILLE RD | 4 | 3189.3333 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL |  | 2022-12-21 | 48'X4' OF Asphalt SW, straight cut roots as needed
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8918 ELMCREEK DR | 4 | 3053.8889 | 3824 |  | 3824 | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL
Precision Concrete Cutting | 381611-18 | 4 | 24 | Complete | FY 22 | Winter 2022 |  | WillowCreek Drive from Old South Park Rd to Maplecreek Dr | 5 | 37500 |  | 15831 | 15831 | 8148 410 8211 148560 822705 | Public Works |  | 390 |  | 2022-03-22 | 8902 Willowcreek Drive- Property owner stopped Precision Concrete from completing the beveling work along the sidewalk in front of the house.
Precision Concrete Cutting | 381611-11 | 4 | 25 | Sent to Contractor | FY 22 | Winter 2022 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 5 | 25000 |  | 6691.5 | 6691.5 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-13 | 4 | 26 | Sent to Contractor | FY22 | Spring 2022 |  | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 5 | 40000 |  | 15315 |  | 8148 410 8211 148560 822705 | Public Works |  | 472 |  | 2022-03-22 | Add 13'x5' of sw 3012 Boaires Ln to rio rita NTP
| 381611-14 | [6 empty] | CBD Beveling project |  | 250000
[9 empty] | Total | 3291476.8822 | 800149.62
vault top in sw - contact property owner
Note on I69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to bring shovel and see if there are any trip hazards under the grass.

## May 2022
| PO # | Area | District | Construciton Status | Date Appropriated | Start | Finish | Project Name | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | Invoice # | inspection month | inspection notes
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1050 S 32ND ST | 4 | 24817.6389 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 30'x5' of sw and 9' curb
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1112 S 26TH ST | 4 | 5813.8889 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 33'x5' of sw and 4 utiliy adj
Seven Seas | 368566-25 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1147-1149 S 42nd St |  | 2137.07 | 4459.34 |  | 4459.34 | 8133-410-8107-148283-822705 | Council Funds |  | 9.44 | 120015M-91 |  | 14'x6' of sw, remove stump, s/p
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1433-1451 HAZEL ST | 4 | 13953.3333 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 40'x6' and 37'x6' and 31x6 of sw and 4 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3511 W KENTUCKY ST | 4 | 12857 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 6'x12' of sw and 2 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3714 CHAUNCEY AVE | 5 | 5877.7778 | 22589 |  | 22589 | 8148 410 8211 148560 822705 | Public Works |  | 132.64 | 120015M-90 | 2022-01-01 | 5'x5' of sw (snow and ice covered -could not inspect on Feb 22 site visit)
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 1300 S 32ND ST | 4 | 1146.1667 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 1366 OLIVE ST | 5 | 16445 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 2 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3222 VIRGINA | 4 | 2541.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3516 COTTER DR | 5 | 1345.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 11'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4408 JENNYMAC DR | 4 | 1196 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-01-01 | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4807 HUNTERS POINT CIR | 4 | 1727.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 5616 CHRISTIAN RIDGE CT | 4 | 3070.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 743 S 43RD ST | 4 | 10695 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  |  | 14'x6' of sw and 33'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Winter 2022 | February | 808 & 810 S 42ND ST | 4 | 4983.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | 11.33
Joash Construction | 368745-10 | 1 | 1 | Complete | FY22 | Fall 2021 | January | 1152-1156 S 26TH ST | 5 | 12790.5556 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 83.33
Seven Seas | 368566-21 | 1 | 1 | Complete | FY21 | Winter 2022 | March | 3500 Block of Algonquin Pkwy | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1 |  |  |  | 2022-02-22 | 3519 9x4 of sw, 3513 5x5 0f sw, 3509 5x4 of sw, 3500 5x4 of sw, 3506 11x6 of dw and 4x4 of sw, 3508 10x10 of dw, 3512 6x5 of sw, 3516 11x8 of dw and 5x4 of sw, 3518 17x4 of dw, 3520 9x4 of sw and 1 utilty adj, 3528 5x4 of sw and 6x4 of sw, 3530 10x4 of dw, 3536 11x4 of sw and 1 tree, 3542 4x4 of sw, 3544 6x4 of dw, 3546 4x4 of sw, 3908 38'x4 of sw and 8' of curb and 1 big tree sent to arborist
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1 |  |  | 120521
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4 | 120015M-76
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 |  | 104.9
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Fall 2021 | October | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | 513.78
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Fall 2021 | October | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest
|  |  | 2 |  |  |  |  | Various Sidewalk Repairs |  | 6609 |  |  |  | 8133 410 8111 148221 822705 | Council funds |  |  |  |  | D2 needs to identify projects with this funding.
Joash Construction | 368746-1 | 1 | 3 | Complete | FY20 | Fall 2021 | February | 1413 OLEANDA AVE | 5 | 4651.1111 | 48026.16 |  | 48026.16 | 8143 410 8211 148472 822705 | Public Works |  | 287.74
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1472 DIXIE HWY | 4 | 830.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1505 OLEANDA AVE | 4 | 1993.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1509 OLEANDA AVE | 4 | 6043.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2116 OREGON AVE | 4 | 2242.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2313 ALLSTON AVE | 5 | 448.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3312 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3314 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3319 UTAH AVE | 4 | 1063.1111 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Seven Seas | 368566-28 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 | June | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 2's through 5's | 10760 | 26000 | 10760 | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | 200 |  |  | see NTP
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction | 368745-10 | 1 | 3 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 4 | 1328.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368567-16 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | 1634 BEECH ST | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 56'x6' of sw and 5'x3' courtesy pad
Seven Seas | 368567-16 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | 2616 ALLSTON AVE | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.56 |  |  | 4'x4' of sw
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-01-31 | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19 |  | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | 4 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works |  | By others |  | 2022-01-31 | 6'X2' OF OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5 |  | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 829 W. Main St. | 5 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | RR track in front of Frasier Museum. Investigate moving trash can to this location.
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2022-01-31 | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | 4 | Complete | FY20 | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 5 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works |  | By others |  | 2022-01-31 | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 1076 E WASHINGTON ST | 4 | 9449.1667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 5.28 |  | 2022-01-31
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 1910-1912 MAGAZINE ST | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 15 |  | 2021-01-31 | 15'X9' OF SW
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 237 E Breckinridge St | 4 | 27864 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 6'X2' of dw
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 514 BARRET AVE | 5 | 10925 | 14104.1 |  | 14104.1 | 8146 410 8211 148487 822705 | Public Works | 2 | 101.91 |  | 2021-01-31 | R5 63'X6' and 6'x4' of sw, 3 utility adjustments, 22" tree and 12" tree
TBD | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 550 S 3RD ST (possibility Utilities' fault) | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0 | 0.44 |  | 2021-01-31 | No issue observed during the 1/31/22 sw inspection
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 741 FRANKLIN ST | 5 | 4861.9444 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 63.2 |  |  | complete
| 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 747 E JEFFERSON ST | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 23'X14' OF DW
|  | 2 | 4 | Complete | FY22 | Winter 2022 | March | 833 W MAIN ST | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0 |  | 2021-01-31 | Pw operations is placing trash can on top of displaced rr track to mitigate
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | N SHELBY ST & FRANKLIN ST | 4,5 | 11553.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | S HANCOCK ST & E BRECKINRIDGE ST | 5 | 4069.7222 |  |  | 0 |  | Public Works |  | see 514 BARRET AVE |  | 2022-01-31 | 30'x11' of sw and 30' of curb and 1 utility adjustment.
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 1129.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 40 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | W. Jefferson St & S. 4th St | 5 | 4669.4444
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 1115 E Oak St | 5 | 14455.5556 | [6 empty] | 55.56
| 368745-24 | 2 | 4 | Not Inspected |  |  |  | 1120 E. Breckinridge St | 4 | 3455.5556
|  | 2 | 4 | Not Inspected | FY22 | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  | 2021-01-31 | Snow and ice on the sw prohibited the site inspection. The sidewalk is within the floodwall right of way and is R1-R5. Set up meeting with MSD to confirm the permitting requirement or closing the gates to block off access since a new sidewalk was constructed in 2021 across from 1224 Franklin St as an altermate ADA comatible sw.
| 368745-24 | 2 | 4 | Not Inspected |  |  |  | 130 S 3rd St | 4 | 7945
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 217 S 5th St | 5 | 2256.6667
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 315 E Main St | 5 | 9191.6667
| 368745-24 | 2 | 4 | Not Inspected |  |  |  | 4TH ST and LIBERTY ST | 5 | 4000
| 368745-24 | 2 | 4 | Not Inspected |  |  |  | 512 Barret Ave | 5 | 15540
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor | FY22 | Winter 2022 |  | 530 Barret Ave/Lexington Rd | 4 | 4628.8889 | [6 empty] | 36.67
| 368745-24 | 2 | 4 | Not Inspected |  |  |  | 721 4th St | 4 | 4000
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 721 S. 4th St | 4 | 5478.8889
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 725 ROSELANE ST | 5 | 18277.7778 | [6 empty] | 92.22
|  | 2 | 4 | Not Inspected |  |  |  | 731 FRANKLIN ST
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor | FY 22 | Winter 2022 |  | Barret Ave & Baxter Ave | 5 | 27608.8889 | [6 empty] | 55.56
Seven Seas | 368566-24 | 1 | 5 | Complete | FY21 | Winter 2021 | April | 200 Block of Southwestern Pky | 4 | 15242 | See 464 N 25TH ST |  | #VALUE! | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 201 -205 SW Parkway, 56’x6’ and 10’x6’ and 16’x6’ of sw, 227 SW Parkway 37’x6’ of sw, and 1 tree, 231 SW Parkway23’x6’ of sw and 1 tree, 235 - 237 SW Parkway 10’x6’ of sw and 14’x6’ of sw and 1 tree, 239 SW Parkway 29’x6’ of sw , 245 SW Parkway 5’x6’ of sw , 249-251 SW Parkway 45’x6’ and 4’x5’ and 3’x5’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 464 N 25TH ST | 4 | 64238 | 60103.7 |  | 60103.7 | 8146 410 8211 148487 822705 | Public Works |  | 497.31 | 120015M-92 | 2022-02-22 | 25' of curb and 12x7 of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 472 TO 468 N 29TH ST | 4 | 6500 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 67x6 of sw and 3 utility adjustments
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 474 N 29TH ST | 4 | 4490 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 20x6 of sw and 1 tree
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 804 S 39TH ST | 5 | 7750 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6'x6' of dw and 7'x6' of dw and 9'x6' of dw and 7'x3' of dw and 1 utility adjustment
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 805 S 39TH ST | 4 | 3250 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6’x10’ of sw and 6’x22’ of sw, and 4’x4’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | N 29TH ST & BANK ST | 4 | 12000 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 10’x5’ of sw and 15’ of curb, 100’x5’ of sw and 5’x25’ of dw and 91’x5’ of sw and 2 trees
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | S 28TH ST & W JEFFERSON ST | 5 | 2210 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 43’x8’ of sw at 2732 W. Jeffreson St, 8’x6’ of sw at 2729 W. Jefferson St, 86’x6’of sw at 234 S 28th St.
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2814 ROWAN ST | 4 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 7.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 38.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? |  | 60
Joash Construction | 368745-10 | 1 | 5 | Complete | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 1 | 40.69
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 4 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 18.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 4 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 40.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 4 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.77
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 1 | 46.55
Seven Seas | 368745-10 | 1 | 5 | Complete | FY21 | Fall 2021 | December | 501 N 21st St | 4's and 5's | 22525.8 |  |  |  | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
Joash Construction |  | 1 | 5 | Complete | FY21 | Fall 2021 | December | 501 Northwesern Pkwy |  |  |  |  | See 3511 Northwestern Pkwy |  |  |  | 157
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 35.61
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 4 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 17.81
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 4 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 42.33
Joash Construction | 368745-10 | 1 | 5 | Complete | FY 22 | Fall 2021 | December | Vermont and Southwestern |  |  | 5289.2 |  | 5289.2 |  |  |  | 75.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1114 PLATO TER | 4 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1501 LYTLE ST | 4 | 4252.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Seven Seas | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 4501 GREENWOOD AVE #1 | 5 | 6250 |  |  | Completed by others | 8146 410 8211 148487 822705 | Public Works |  | Completed by others |  | 2022-02-22 | No R4 or R5 observed
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Winter 2022 | March | 109 N 40TH ST | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6 |  |  | repaird by LWC, a new water meter was installed in the verge next to the new 9'x6' sw,
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 80.34
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 4 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works |  | 4.44
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | 1 | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 235 S. 41st Street | R5 | 3744.02 |  |  | 5636 | 8146-410-8107-148280-822705 | Council District 5 |  | 200 |  |  | 17'x'4 and 6'x4' and 9'x4' of sw, 14'x4' of dw and 15'x6' of dw apron, 9' of curb and 1-13" tree($5,635.21 counicl funds were alloted for 235 and 242 S. 41st St.)
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 242 S. 41st Street | R5 | 1892 |  |  | * see notes | 8146-410-8107-148280-822705 | Council District 5 |  | 23 |  |  | 6'x4' and 31'x4' of sw and 8'x'4 of dw-(($5,635.21 counicl funds were alloted for 235 and 242 S. 41st St.)
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 311 N 30TH ST | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley- future paving project
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 312 N 30TH ST | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley - future paving project
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 3430 Rudd Ave. | R5 | 2900 |  |  | 2900 | 8146-410-8107-148280-822705 | Council District 5 |  | 19 |  |  | 8'x4' and 4'x4' and 12'x4' and 15'x5' of sw
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 3914 Bank St. | R5 | 1387 |  |  | 1387 | 8146-410-8107-148280-822705 | Council District 5 |  | 8 |  |  | 5'x7' of sw and 5'x15' of dw and 10'x3' of dw apron
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81 |  | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1261 S BROOK ST | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1265 S BROOK ST | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1317 S 6TH ST | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5 |  | 2021-12-21 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42 |  | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 1703 S BROOK ST | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67 |  |  | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22 |  | DECEMBER
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-28 | 5'X5' OF SW OR RAMP
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 635 PARK AVE | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5 |  |  | 6'X5' OF SW BY OTHERS
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 821 HUMLER ST | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | R3 4'X23' of dw
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 5 |  | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  |  | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 5 | 4933.5 | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | February | 1423 ARCADE AVE | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | No R4 or R5 present
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | February | 1330 W BRECKINRIDGE ST | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67 |  |  | 60'x6' of sw
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 1434 THORNBERRY AVE | 4 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 15.5 |  |  | 35'x4' of historic sw and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 509 W ORMSBY AVE | 5 | 15200 | 52211.13 |  | 52211.13 | 8148 410 8211 148560 822705 | Public Works | 10 | 89.58 |  |  | 10'X18' and 17'x10' and 9'x10' of historic sw and 6'x10' of historic dw and 1 utility gas meter. (remove 1-22", 1-25" and 1-27" tree as marked) seed and protection. Straight cut bricks to tie into sw.
Joash Construction |  | 2 | 6 | Complete | FY21 | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 5 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | 8.67 |  |  | 7'x6'of sw at 2100 Grand Ave and 6'x6' of sw at 2103 Grand Ave.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY20 | Winter 2022 | March | 1336 S 6TH ST | 4 | 14200 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x7.5' of historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 15.5' x7.5' of historic sw and 15' of historic curb historic (remove 1-31" and 2-17" trees)
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1408-1410 HOMEVIEW DR | 5 | 15726.25 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1410 ARCADE AVE | 4 | 2657.7778 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x4' of historic sw and curb, 39'x4' of historic sw, and 5'x4' of historic sw, seed and protection
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | W ORMSBY AVE & S 6TH ST (1338 s 6 th St.) | 5 | 8200 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | R4 19'X8' OF SW AND 47'X8' OF historic sw and saw cut along the retaining wall as marked, remove two 18" and one 23" tree as marked, seed and protection
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31 |  |  | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67 |  |  |  | (Jason Tipton w LGE 3/18/22)
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1152 Garvin Pl | 5 | 20946.6667 | [6 empty] | 98.66
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1157 LINCOLN AVE | 5 | 4675 | [6 empty] | 11
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 121 W Oak St |  | See 123 W Oak St
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 1217 S 26th St | 5 | 4433.3333
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 123 W Oak St | 4 | 11433.3333
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1364 Lillian Ave | 5 | 5977.7778 | [6 empty] | 9.78
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 1400 S. Floyd St | 5 | 9291.6667
| 368745-24 | 2 | 6 | Not Inspected |  |  |  | 1429 Homevied Dr | 5 | 3694.4444
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1605 DUMESNIL ST | 5 | 2966.6667 | [6 empty] | 10
| 368745-24 | 2 | 6 | Not Inspected |  |  |  | 1635 Wilsion Ave | 5 | 5166.6667
| 368745-24 | 2 | 6 | Not Inspected |  |  |  | 1701 Gallagher St | 5 | 9726.6667
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 1775 Wilson Ave | 4 | 7028.8889 | [6 empty] | 18.44
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 2214 Hale Ave | 4 | 3553.3333 | [6 empty] | 12
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 2309 Date St | 4 | 3626.6667
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 907 Burton Ave | 5 | 3700 | [6 empty] | 17.33
| 368745-24 | 2 | 6 | Not Inspected |  |  |  | Intersection of 8th & Cawthon | 5 | 11277.7778
|  | 2 | 6 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
| 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | WINKLER AVE & S 5TH ST | 5 | 5533.3333 | [6 empty] | 30
TBD |  | 3 | 7 | Inspected | FY22 | Winter 2022 |  | Wesboro Rd fom Herr Ln to Hayward Rd | 2's through 5's | 17500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 7310 Wesboro Rd 16x4 of dw, 7314 Wesboro Rd 16x4 of sw and 1 lge mh adj, 7316 Wesboro Rd 10x4 of sw and 1 lge mh adj, 7322 Wesboro Rd 11x4 and 5x4 and 6x4 of sw and 1 lge mh adj, 7324 10x4 of sw and 1 lge mh adj, 7326 Wesboro Rd 6x4 of sw and one tree inspection. Contacted James Tipton at LGE regarding the 3 transfomers in sidewalk.
| 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 1418 MORTON AVE | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 1902 Deerwood Ave | 4 | 5556.6 | 32964.32 |  | 32964.32 | 8146 410 8211 148487 822705 | Public Works |  | 228.66
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2023 Woodbourne Ave | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2082 Douglass Blvd | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2105 DOUGLASS BLVD | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2115 Woodbourne Ave | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2208 LAUDERDALE RD | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2224 Dundee Rd | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 2246 BOULEVARD NAPOLEON | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2300 MEADOW RD | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2809 Montrose Ave | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | November | 1522 Rosewood Ave | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-3 | 3 | 8 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1819 Harvard Dr | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5 |  |  | 5'x9' of sw & 5’x5’ of dw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1840 SHADY LN | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 15 |  |  | 4.5'x30' of sw; 1 utility adj., seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1875 RUTHERFORD AVE | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 4'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1895 RUTHERFORD AVE | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.44 |  |  | 4'x37' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist. Upon receiving these recommendations could one of you please reach out the Larry and inform him.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1900 ROANOKE AVE | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.56 |  |  | 5'x10' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HAMPDEN CT | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.67 |  |  | 5'x25' of sw & 5’x5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HARVARD DR | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.94 |  |  | 5’x12.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1920 BONNYCASTLE AVE | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6 |  |  | 6'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2018 BOULEVARD NAPOLEON | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 74.17 |  |  | 5'x15' of sw & 5'x55' of sw & 5'x10' of sw & 5'x36.5' of sw & 5'x17' of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2137 ALTA AVE | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.78 |  |  | 5’x14’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2139 WOODBOURNE AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.33 |  |  | 5’x43’ of sw & 4’x5.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2218 WOODBOURNE AVE | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 4'x25' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-5 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2219 TALBOTT AVE | 5 | see 2221 Talbott Ave |  |  | 0 | see 2221 Talbott Ave | Council District 8 |  | see 2221 Talbott Ave |  | May | 28'x5' of sw and 11'x6' of apron and 11'x5' of dw and 4'x4' of courtest pad, seed and protection
Seven Seas | 368569-5 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2221 TALBOTT AVE | 5 | 18149 |  |  | 0 | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council District 8 |  | 30.42 |  | May | 36'x5'’ of sw; and 5'x4' of courtesy pad & seed and protection. Remove 42" and 24 " maple tree, Bob Ray PO applied for $6,150
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2310 BOULEVARD NAPOLEON | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 5'x13.5' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2420 LONGEST AVE | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 35.33 |  |  | Historic conc. 6'x54' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2541 Cherokee Pkwy | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 11.36 |  |  | Historic conc. 6’x15’ of sw; 3.5'x3.5' of courtesy pad, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 701 BAXTER AVE | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 105.11 |  |  | 8'x10.5' of sw & 8'x5' of sw & 8'x25' of sw & 8'x15' of sw & 8'x20' of sw & 8'x16.5' of sw & 10'x21' of sw; 1 manhole adj., seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 122 N BAYLY AVE | 5 | 2555.5556 | 29946 |  | 29946 | 8148 410 8211 148560 822705 | Public Works |  | 100.35 | 121061M-12 |  | 4'x8' of sw & 5'x26’ of sw, seed and protection, Mr. Ed Bowling His number is (502) 494-9569.once arborist reports back. He wants to save the tree
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 148 VERNON AVE | 4 | 398.6667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 3'x8' of sw, seed and protection
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | April | 1854 Frankfort Ave | 3, spalling | 264 | 3176.8 |  | 3127.56 | 8138 410 8107 148227 822705 | Council District 9 |  | 5.12 | 121061M-13 | 2022-04-17 | Historic Conc. 3'x10' of curtesy pad, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 201 S PETERSON AVE | 5 | 9370.9667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 6'x13.5' of sw; and 1 utility adj, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 2035 EMERALD AVE | 4 | 2392 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 4.5'x36' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2022 | April | 217 MCCREADY AVE | 4 | 5000 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE |  | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 3.5'x4' of sw & 5’x30’ of sw & 4’x14’ of sw & 4’x5’ of sw; 2’x5’ of ADA pad; 26’ of curb, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3410 INGLE AVE | 4 | 1162.7778 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 5'x14' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3547 NANZ AVE | 5 | 2788.1111 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 4'x28' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1821 Frankfort Ave | 4 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1 Eastover Ct | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1801 Frankfort Ave | 4 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 5 | 213
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1805 Frankfort Ave | 4 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1807 Frankfort Ave | 4 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1809-1811 Frankfort Ave | 4 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1817 Frankfort Ave | 5 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1823 Frankfort Ave | 3 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1825 Frankfort Ave | 4 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1832-1830 Frankfort Ave | 4 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete |  | Fall 2021 | January | 1846 Frankfort Ave |  |  |  |  | See 1860 Frankfort Ave |  |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1860 Frankfort Ave | 4 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2039 Frankfort Ave | 3, damaged detectable warnings | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2101 Frankfort Ave | ramp is out of compliance | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | Ramps at Pope and State St |  | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 102 Crescent Ct | 4 | 8360.8 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave |  |  | 26’ X 6’, 15’ X 6’, 13.5’ X 5’ and 13’ X 10’ of hist SW; 32.5’ of curb; S/P (I think 32.5’ of curb is quite a bit short. In my opinion 100’ of curb is needed
Seven Seas | 368567-9 | 3 | 9 | Complete | FY22 | Winter 2021 | March | 118 N EWING AVE | 4 | 3588 | 13919 |  | 13919 | 8148 410 8211 148560 822705 | Public Works |  | 45.6
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1808-1800 Frankfort Ave | 4 | 15975.52 |  |  | 75718 | 8138 410 8107 148227 822705 | Council District 9 | 2 | 321.65
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1813-1815 Frankfort Ave | 3, crumbling | 7731.9 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1838 Frankfort Ave | 5 | 6019.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1870-1874 Frankfort Ave | 3, sidewalk is breaking up | 3468.23 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1880 Frankfort Ave | 3, badly spalling | 792 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1882 Frankfort Ave | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1900 MELLWOOD AVE | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1910 Frankfort Ave | holding water | 699.87 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1928 Frankfort Ave | drainage issues with ramp | 3400.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2 Eastover Ct | 4 | 1182.6 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2040 Frankfort Ave | 4 | 4884 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2138 New Main St | damaged detectable warnings | 3480 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2140 SYCAMORE AVE | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2144 Frankfort Ave | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2334-2336 Frankfort Ave | 4 | 113.4 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2368 Frankfort Ave | 4 | 2376 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2400 Frankfort Ave | 4 | 2059.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2608 Frankfort Ave | 4 | 1428.24 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3210 Frankfort Ave | 4 | 5467.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3220 MARION CT | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3230 Frankfort Ave | 4 | 275.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 405 UNIVERSITY AVE | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | Frankfort & Haldeman | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas | 368567-3 | 3 | 10 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 5 |  | 2107.9 |  | 2107.9 |  |  |  | 5.73
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1014 WAGNER ST | 4 | 1411.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.33 |  |  | 5’x35’ of sw; 1 utility adj., seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1031 WETTERAU AVE | 5 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12 |  |  | 6’x16’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1107 E BURNETT AVE | 5 | 3818 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 17.33 |  |  | 6’x31’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 1131 MULBERRY ST | 4 | 4133.6111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 11.11 |  |  | 6’x9’ of sw & 3’x10.5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 2029 ALEXANDER AVE | 4 | 1196 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 28.67 |  |  | 5.5’x9’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | 220 DERBY AVE | 5 | 7375.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.67 |  |  | 4’x14’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-15 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2022-05-17 | 4325 Robards Ln at Gardiner Ln/Robards Ln Intersection 8’x4’ of sw, 4325 Robards Ln on Gardiner Ln side 4’x7’ of sw, 4’x12’ of sw & 1’x12’ of sw, 1516 Gardiner Ln 4’x5’ of sw, 3’x12’ of sw, 4’x4’ of sw & 4’x16’ of sw, and 1 utility adj., 4324 Bishop Ln on Gardiner Ln side 4’x4’ of sw, 4’x12’ of sw, & 3’x12’ of sw, 3340 Newberg Rd on Gardiner Ln. 18’x4’ of sw & 50’x5’ of sw, 4322 Bishop Ln on Gardiner Ln 4’x5’ of sw, 1’x11’ of sw, 4’x5’ of sw, 5’x5’ of sw & 1’x12’ of sw, 1519 Gardiner Ln 5’x5’ of sw, 0.5’x17’ of sw & 5’x5’ of sw, 1507 Gardiner Ln 4’x4’ of sw; MSD Service request 5423082 to address cave in along Gardiner Lane/Robards Lane CB
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | 5'X5' OF SW
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 4011 RIVULET LN | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | GRINDING BY OTHERS
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others
Riverside Paving |  | 5 | 11 | Inspected | FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
Riverside Paving |  | 5 | 11 | Inspected | FY22 | Winter 2021 |  | Lacevine Rd from Trumpetvine Rd to Dead End | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11 |  |  | R4 8300 Lacevine 8x4 of sw
Riverside Paving | 368756-4 | 4 | 12 | Complete | FY21 | Fall 2021 | January | 7002 URANAS DR | 4 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | 4'x8' of sw and 4'x12' of dw (by others)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 | October | Deady Dr from Dead End to Dead End | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln | 2021-01-3 | 2022-01-01 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 | October | Rebecca Ln from Deady Dr to Dead End | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67 |  | 2022-01-01 | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 5032 Hunters Point Cir | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 |  | 10.66 |  | 2022-01-01 | 8'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 6208 MOUNT EVEREST DR | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11 |  | 2022-01-01 | 16'x4' and 12'x4' and 12'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 7015 BIRNAMWOOD DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 |  | 2022-01-01 | 8'x4' of sw plus fill in void adjacent to sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 9612 BROOKS BEND RD | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-01-01 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.89 |  | 2022-01-01 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 2's through 4's | 10138.5 |  | 5778 |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St |  |  | 1 R3 5'x8' panel across from 719 Auburn Oaks was not beveled.
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Auburn Oaks from New Cut Rd to Dead End | 2's through 5's | 32000 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Glengarry Dr from National Turnpike to Gary Way | 2's through 5's | 19500 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 200 ELK RIVER DR | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x15’ of sw & 4’x17’ of sw, seed and protection
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 211 APPOMATTOX RD | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x26’ of sw, seed and protection.
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 6013 LARKGROVE DR | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78 |  |  | 4'x9’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct |  | 2022-01-01 | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 8405 Devonshire Dr | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
|  | 4 | 14 | Complete | FY22 | Spring 2022 | May | 9805 Sun Way Dr | 5 | 366.98 |  |  | By MSD | 8148 410 8211 148560 822705 | Public Works |  | 6.67 |  | 2022-05-22 | MSD repaired the sinkhole and the sidewalk at 9807 and 9805 Sun Way Drive. sr# 5415608 (MSD is placing a camera throuth lateral )
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11500 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11702 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11703 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11707 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11708 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11711 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11712 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11714 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11717 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11719 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11721 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11800 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11802 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11803 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11805 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11810 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11810-11812 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11814-11812 Pierce Way | 5, 4 | 14879.04 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12 |  | 2022-02-25 | 27'x4' of sw and 2 utility adj, s/p
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11817-11819 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 11904 Pierce Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 13413 HINCHBROOK BLVD | 4 | 1328.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.78 |  | 2022-02-25 | 13'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 13417 Kinross Blvd | 5 | 3327.92 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 20.44 |  | 2022-02-25 | 46'x4' of sw, 1 utility adjustment, trim tree roots if needed, s/p
Riverside Paving | 368756-23 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 5711 Chestnutwood Way |  | See 11814-11812 Pierce Way |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-24 | 4 | 14 | Inspected | FY22 | Spring 2022 |  | 6007 Alanadale Dr | Curb Repair | 4585.07 |  |  | 0 | 8142 410 8107 148279 821344 | Council District 14 |  | 12.42 |  | 2022-02-25 | 33' of curb replacement, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 6010 Alanadale Dr |  | 4776 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 6012 Alanadale Dr | 4 | 2808 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  | 2022-02-25 | 12'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 7002 Nathan Hale Way | 4 | 2984.96 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 23.11 |  | 2022-02-25 | 52'x4' of sw, raise the sw to eliminate 2" ponding water at the low spot
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 7014 Ethan Allen Way | 4 | 550.08 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 20.89 |  | 2022-02-25 | 5'x4' and 42x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 7902 NANCY LN | 4 | 3588 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.9 |  | 2022-02-25 | 6'X4' and 6'x4' and 8'x4' of sw and and 9'x5' of dw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 7906 NANCY LN | 5 | 1500 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.33 |  |  | 12'x4' of sw
Riverside Paving | 368756-16 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | 9900 SUNKIST WAY | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 27.11 |  | 2022-02-25 | 27'x4' and 25'x4' and 9'x4' of sw, s/p
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Cedarwood Dr from Mondamon Dr to Pond Creek Dr | 2's through 5's | 17440 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Fir Ct from Leemont Dr to Dead End | 2's through 5's | 2880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Fruitwood Dr from Leemont Dr to Pond Creek Dr | 2's through 5's | 20480 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Ct from Leemont Dr to Dead End | 2's through 5's | 3680 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Dr from Deering Rd to Alicante Ln | 2's through 5's | 37032 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Logwood Ave from Leemont Dr to Pond Creek Dr | 2's through 5's | 20800 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | North side of Alicante Ln from Andalee Dr to Leemont Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Pond Creek Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | 10880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | South side of Cedarwood Dr from Leemont Dr to Mondamon Dr | 2's through 5's | See Cedarwood Dr from Mondamon Dr to Pond Creek Dr |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Vevia Pl from Leemont Dr to Pond Creek Dr | 2's through 5's | See Pond Creek Dr from Cedarwood Dr to Vevia Pl |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | West side of Leemont Dr from Alicante Ln to Cedarwood Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell | 2021-01-3
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
TBD | 368756-20 | 4 | 15 | Complete | FY22 | Fall 2021 | March | 1031 NAVAHO PL | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 | September | 2431 EMIL AVE | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1020 Berry Blvd | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  | 2021-12-21 | 5’x16’ of sw; 8’x8’ of dw & 14’ of curb, seed and protection
Riverside Paving | 368756-18 |  | 15 | Sent to Contractor |  | Winter 2022 |  | 1421 Anna Lane |  | 981.79 |  |  |  | See 3418 Powell | Council District 15 |  | 6.22 |  |  | 4'x14' of sw & 4'x10' of dw
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1496 CLARA AVE | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78 |  |  | 5’x15’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1500 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’ of dw, seed and protection.
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1503-1505 Paula Ct | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’of sw & 16’x5’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1506 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 25’x5’of sw & 10’x5’ of dw, seed and protection
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 221 W ADAIR ST (Next to I-264) | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8 |  |  | 5’x6’ of sw & 5’x6’ of sw & 2’x6’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3418 POWELL AVE | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22 |  |  | 16’x5’of sw & 15’x5’ of sw, seed and protection ( 3'x'4 courtesy pad at 3416 Powell Ave added to NTP D-15)
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3515 HENRY AVE | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33 |  |  | 5’x15’ of sw; 5’x45’ of sw; 5’x10’ of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3705 W WHEATMORE DR | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33 |  |  | 5'x6' of sw; 5'x6' of sw; 5'x13’ of sw, seed and protection. 1 tree stump removal & 1 Magnolia tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 4035 WOODRUFF AVE | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 5'x6' of sw & 5'x6' of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4328 S 2nd St | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67 |  |  | 4’x20’ of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4400 S 2nd St | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33 |  |  | 10’ of paved over curb & Gutter, seed and protection
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 542-546 RAWLINGS ST | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56 |  |  | 6’x90’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 608 RAWLINGS ST | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15 |  |  | 6'x25’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 611 MERWIN AVE | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44 |  |  | 5'x15' of sw; 5'x5' of dw & 5'x10' of dw; 7'x10' of apron, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 613 DUVALL ST | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5 |  |  | 5’x40’ of sw; 5’x10’ of dw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 654 N BARBEE WAY | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88 |  |  | 4’x21’ of sw; 4’x9’ of sw; 4’x40’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 664 ATWOOD ST | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 6’x36’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 2's through 5's | 50000 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | MERHOFF ST & DUVALL ST | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17 |  |  | 5'x35' of sw; 5'x30' of sw (along Merhoof St side of 619 Duvall St), seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 4 | 15 | Not Inspected | FY22 | Spring 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr |  | 37259 |  |  | 0 | 8138-410-8107-148233-822702 $15920.38 8133-410-8107-148233-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11202 Deham Dr | 5 | 336.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11215 Deham Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11301 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 5 | 1435.24 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11307 Deham Dr | 5 | 988.23 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 5 | 4940.17 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 5 | 1369.83 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11412 Hammond Dr | 5 | 1761.6 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 5 | 719.03 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 5 | 538.06 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 5 | 1309.75 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 5 | 1813.59 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11513 Fisherman Way | 5 | 881.38 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 5 | 403.7 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 5 | 210.88 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 5 | 1429.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Baywood Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 5 | 929.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | See |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 5 | 3393.1 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 5 | 3467.27 | 49112.92 |  | 49112.92 | 8101 410 8105 148234 822705 | Council District 16 |  | 332.23
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5304 Drifton Dr | 5 | 888.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 5 | 627.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5308 Drifton Dr | 5 | 1831.93 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5311 Drifton Dr | 5 | 2473.37 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5401 Baywood Dr | 5 |  |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 5 | 1114.94 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 5 | 1157.62 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 5 | 695.96 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 5 | 1726.32 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 5 | 973.89 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5410 Baywood Dr | 5 | 224.14 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5412 Lithia Dr | 5 | 1441.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5501 Lithia Dr | 5 | 2094.49 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 5 | 134.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 2's through 5's | 15000 |  | 10048 | 10048 | 8148 410 8211 148560 822705 | Public Works |  | 310
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 2's through 5's | 7500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 | January | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 2's through 5's | 22500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 10630 Meeting St | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 6.5'x7.5' of sw, seed and protection.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4003 Deer Creek Dr | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4230 Ashleywood Ct | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw; 4'x12' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD |  | 3 | 17 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By Others
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13415 FOREST SPRINGS DR | 5 | 3718.3333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13419 FOREST SPRINGS DR | 5 | 3552.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13430 FOREST SPRINGS DR | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas |  | 3 | 17 | Complete | FY21 | Summer 2021 | March | 13508 Springs Station Rd | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17 |  |  |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13510 BROKEN BRANCH WAY | 5 | 398.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13512 BROKEN BRANCH WAY | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' AND 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13520 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13606 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13607 BROKEN BRANCH WAY | 5 | 996.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13700 BROKEN BRANCH WAY | 5 | 830.5556 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3610 ROCK BAY DR | 4 | 1245.8333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 WOODED SPRINGS CT | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3707 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3710 CYPRESS SPRINGS PL | 5 | 1528.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3724 CYPRESS SPRINGS PL | 4 | 332.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' AND 5'X4' AND 9'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3801 BUGLEWOOD PL | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 13'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3809 ROCK BAY DR | 4 | 581.3889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3814 ROCK BAY DR | 4 | 1827.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4'of SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3915 ROCK BAY DR | 5 | 1661.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW and
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4002 ROCK BAY DR | 5 | 913.6111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4010 ROCK BAY DR | 5 | 747.5 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW and straight cut roots only as necessary.
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 9603 MOORFIELD CIR | 4 | 332.2222 | 19391.51 |  | 19391.51 | 8148 410 8211 148560 822705 | Public Works |  | 105.67 |  |  | 12'X4' OF SW BY OTHERS
Seven Seas | 368567-6 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13408 FOREST SPRINGS DR | 5 | 2057.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' OF SW, Straight cut roots
TBD |  | 3 | 18 | Complete | FY22 | Winter 2021 | March | 2817 ENGLEWOOD AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Seven Seas | 368567-10 | 3 | 18 | Sent to Contractor | FY 22 | Winter 2022 |  | 10403 Sterling Springs Rd |  | 2283.41 |  |  |  | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 4’x8.5' of sw, seed and protection.
Seven Seas | 368567-10 | 3 | 18 | Sent to Contractor | FY 22 | Winter 2022 |  | 4429 Rockwood Dr | 4 or 5 | 1359.6 |  |  |  | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 2.5'x4.5' of sw; 9'x9.5' of dw, seed and protection.
Seven Seas | 368567-12 | 3 | 18 | Sent to Contractor | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 2's through 5's | 30000 |  | 7375 | 7375 | 8148 410 8211 148560 822705 | Public Works |  | 227
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 12403 Hersfield Rd | 4 | 3029 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368567-7 |  | 19 | Complete | FY 22 | Spring 2022 | February | 125 Waterstone Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1335 Heafer Rd | 5 | 1083.37 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1337 Heafer Rd | 5 | 2093 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1340 Heafer Rd | 4 | 6518.89 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14008 CROSSBRANCH CT | 4 | 1702.27 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14202 LAKE FOREST DR | 4 | 764.53 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14306 LAKE FOREST DR | 4 | 1085.15 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 14313 Micawber Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr |  |  | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots tripstop
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 15109 Abington Ridge Pl | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 17106 Mallet Hill Dr | 5 | 12079.26 |  |  | 15681.79 | 8102 410 8105 148963 822702 | Council |  | 106.09
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 17204 MALLET HILL DR | 4 | 520 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
| 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 2213 ARNOLD PALMER BLVD | 4 | 4422.13 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 | February | 311 Lake Forest Pky | 4 | 1674 |  |  | See 610 Woodlake | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 504-506 EDGEFOREST PL | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works |  | 14
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 505 EDGEFOREST PL | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works |  | 6.2222
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 610 WOODLAKE DR | 5 | 10437.73 | 28176.24 |  | 28176.24 | 8146 410 8211 148487 822705 | Public Works |  | 192
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 612 WOODLAKE DR | 5 | 9381.95 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
TBD | 368569-4 | 5 | 19 | Complete | FY22 | Winter 2021 | February | STURBRIDGE PL & STURBRIDGE CIR | 5 | 747.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | 19 | Complete | FY22 | Winter 2021 | March | 15105 MEADOW FARMS CT | 4 | 730.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 17108 MALLET HILL DR | 5 | 1202.57 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 412-414 LAKE FOREST PKY | 4 | 2092.4 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 509 EDGEFOREST PL | 4 | 233.33 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
|  | 5 | 19 | Complete | FY19 | Fall 2021 | March | D19 Berrytown Rd Sidewalk Repair Project |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  |  | This was completed in 2019
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 11007 FOX MOORE PL | 5,2 | 1262.4444 | 9527.25 |  | 9527.25 | 8148 410 8211 148560 822705 | Public Works |  | 17.09 | 121162M-09 | 2022-05-01 | 4’x6’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 14611 LAKE BLUFF PL | 4 | 531.5556 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x4’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 803 FOXGATE RD | 4 | 3053.8889 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x8’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 836 LAKE FOREST PKWY | 4 | 2691 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x18’ of sw, seed and protection
Seven Seas | 368569-12 | 5 | 19 | Complete | FY22 | Winter 2021 | May | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 2's through 5's | 15840 | 4535.39 | 8986 | 19307.01 | 8148 410 8211 148560 822705 | Public Works |  | 315.14 | 121162M-07 | 2022-05-01 | 6'x4' of sw across from 315 Evergreen Rd, replace 10'x4' ramp, and 7' of curb and replace 2-4'x4' sections of sw on Evergreen Rd. side of 12017 Shelbyville Rd.
Seven Seas | 368569-12 | 5 | 19 | Complete | FY22 | Winter 2022 | May | S Beckley Station Rd from Shelbyville Rd to Dead End | 2's through 5's | 15000 | 5785.62 | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 8148 410 8211 148560 822705 | Public Works |  | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 121162M-08 | 2022-05-01
TBD |  | 5 | 20 | Complete | FY22 | Winter 2021 | April | 3106 SHADY SPRINGS DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-05-01 | Completed
TBD |  | 5 | 20 | Complete | FY22 | Spring 2022 | April | 6515 Calm River Way | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-01 | no issue observed
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 2.8889
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way | 5 | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 9.3333
|  | 5 | 20 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 3.5556
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
Seven Seas | 368569-4 | 5 | 20 | Complete | FY22 | Winter 2022 | February | 14304 MICAWBER WAY | 5 | 2127.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11804 LONGVIEW FARM DR | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  |  | Completed
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11906 LONGVIEW FARM DR | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | CONCRETE SPALLING
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12000 LONGVIEW FARM DR | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 8'X4' OF SW
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12004 LONGVIEW FARM DR | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 2022-01-22 | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 11012 Perwinkle Ln | 4 | 264 | 45054.99 |  | 45054.99 | 8102 410 8105 148837 822705 | Council District 20 |  | 169.33 | 121162M-06 | 2022-05-01 | 4.5’x4’ of sw & 4’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 114 Wickfield Dr | 5 | 2567.07 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 5’x4’ of sw & 15’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13602 Meadow Vista Ct | 5 | 1182.4 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 10’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13604 Meadow Vista Ct | 3 | 1976.57 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 4.5’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13608 Meadow Vista Ct | 4 | 2269.72 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 12’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13610 Meadow Vista Ct | 5 | 2270 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 17’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13615 Meadow Vista Ct | 5 | 2622 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 15.5’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13700-13701 Willow Reed Dr | 4 | 1920.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 5’x4’of sw & 10’x4’ of sw; 1 utility adj., seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13702 Willow Reed Dr | 5 | 2066.57 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 14’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13705 Willow Reed Dr | 5 | 2269.72 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 8’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13809 Round Top Pl | 4 | 293.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9.5’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13811 lakemont Ct | 4 | 473.07 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 14107 Glendower Dr | 4 | 7692.4 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 14’x4’ of sw & 12’x4’ of sw, seed and protection. 3 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 14601 Landis Lakes Dr | 5 | 2448.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 4’x4’ of sw & 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 200 Wickfield DR | 5 | 1918 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 18’x4’ of sw & 21’x4’ of sw & 5’x4’ of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 303 Wickfield Dr | 4 | 586.67 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 20’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4004 Saratoga Woods Dr | 4 | 882.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 15’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4026 Pleasant Glen Dr | 4 | 2622 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4504 Stone Lakes Dr | 5 | 882.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 17.5’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4517 Saratoga Woods Dr | 4 | 6216.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 16’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 505 Wickfield Dr | 5 | 2875.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 4’x6’ of sw & 4’x11’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 615 Wickfield DR | 4 | 2991.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 4’x4’ of sw & 4’x18’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 6530 Calm River Way | 4 | 1056 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 6’x4’ of sw & 11’x4 of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 6726 Calm River Way | 4 | 646.27 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 14’x4’ of sw, seed and protection
Seven Seas | 368569-13 | 5 | 20 | Complete | FY22 | Spring 2022 | May | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2's through 5's | 50000 | 41401.75 | 16911 | 63042.25 | 8148 410 8211 148560 822705 | Public Works | 3 | 622.75 | 121162M-10 | 2022-05-01 | The LWC SR # is 1786143959 at 9704 Mary Dell Lane. The MSD SR # is 5415539 at 9920 Mary Dell Lane. I contacted Jason Tipton about the LGE transformer adj. at 9814 Mary Dell Lane.
Riverside Paving | 368756-4 | 4 | 21 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works |  | 1
Riverside Paving | 368756-26 | 4 | 21 | Inspected | FY22 | Spring 2022 | June | S 3rd St from Waterson Underpass to W Woodlawn Ave | 2's through 5's | 85000 |  | 20061 | 20061 | 8148 410 8211 148560 822705 | Public Works |  | 636 |  |  | 4450 S 3rd St-"Looks like an MCI vault.. I’ll take care of it." By Andrews, Al. Hole forming under sw at 223 W. Woodlawn Ave-sent to Clyde, Barry (PW Operations Administrator) to investigate
|  | 4 | 21 | Not Inspected | FY18 | Spring 2021 |  | TBD |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 10104 RIMFIRE RD | 5 | 797.3333 | 24425.28 |  | 24425.28 | 8148 410 8211 148560 822705 | Public Works |  | 101.7 | 121162M-05 | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11201 Meadow Breeze Ln | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11410 Wind Haven Way | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 3816 GREENWICH WAY | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of sw
|  | 5 | 22 | Complete | FY22 | Winter 2021 | April | 5807 BUCKS LN | 4 | By others |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | 4 |  | 2022-01-22 | 9'x4' of sw Addressed by lge
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6217 HINES MILL WAY | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 8'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6416 MOSSY OAKS DR | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 11'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7507 Kendrick Crossing Ln | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7600 Hornbeck Farm Rd | 5 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 17’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7802 Windgate Dr | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw & 18’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7804 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw & 6’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7812 Windgate Dr | 5 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7821 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 9'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7901 Windgate Dr | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7907 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Niemann Dr | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Windgate Dr | 4 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7912 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10x4 of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7913 Windgate Dr | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw and 5'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7916 Windgate Dr | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 6.58 |  | 2022-02-23 | No R4 or R5 issues observed during the February 2022 inspection
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7917 Windgate Dr | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7919 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 15'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7920 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of SW
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 12
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 18
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 8.22
TBD |  | 5 | 22 | Complete | FY22 | Winter 2021 | March | MAJOR LN & GLENWAY PL | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | No R4 or R5 issues observed during the March 2022 inspection
Seven Seas | 368569-13 | 5 | 22 | Complete | FY22 | Spring 2022 | May | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 2's through 5's | 45000 | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 4729.5 | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 8148 410 8211 148560 822705 | Public Works | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2021-01-5 and 1097 (2nd Invoice was for Triumph) | 2022-12-21
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 5 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | 38.99
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works |  | 47.55
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7208-7210 Quindero Run Rd | 5 | 733.76 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 7.56 |  |  | 4’x17’ of sw, seed and protection
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7213 Quindero Run Rd | 5 | 550.4 |  |  |  | 8137-410-8211-148560-822705 | public Works |  | 4.89 |  |  | 4’x11’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7226-7228 Quindero Run Rd | 5 | 917.33 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 3.56 |  |  | 4'x8’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor | FY22 | Winter 2022 |  | 8214 Happiness Way | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 30.22 |  | 2022-12-21 | 4'x54’ of sw & 4'x14’ of sw, seed and protection.
Riverside Paving | 368756-27 | 4 | 23 | Inspected | FY22 | Spring 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 2's through 5's | 55000 |  | 4171 | 4171 | 8148 410 8211 148560 822705 | Public Works |  | 137 |  | 2022-05-22 | 8202 Carmel Village Pl, 9x4 and 8x4 of sw and 2 trees (private) 8200 Carmel Village Pl, 8x4 of sw and 1 tree (private), 8208 Smyrna Parkway 13x4 of sw and 5x4 of sw and 1 utility
Riverside Paving |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | 2022-12-21 | 21'X4' OF SW
Riverside Paving |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  |  | No R4 or R5 issues observed during the Jan 2022 inspection
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 7832 BRIDLEWOOD PL | 4 | 1328.8889 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | 37.32 |  |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY21 | Fall 2021 | February | 8603 Timber Hollow Ct | 4 | 1727.56 |  |  | See 8918 Elmcreek | 8146 410 8211 148487 822705 | Public Works |  | See 7832 Bridlewood PL |  |  | 4'x11' of sw and remove tree stump
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8708 SHEPHERDSVILLE RD | 4 | 3189.3333 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL |  | 2022-12-21 | 48'X4' OF Asphalt SW, straight cut roots as needed
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8918 ELMCREEK DR | 4 | 3053.8889 | 3824 |  | 3824 | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL
Riverside Paving | 368756-28 | 4 | 24 | Inspected | FY 22 | Spring 2022 |  | Maplecreek Dr. from Old S. Park Rd. to Bonaventure Blvd. | 5 | See Willowcreek Dr. |  | See Willowcreek Dr. |  | 8148 410 8211 148560 822705 | Public Works |  | See Willowcreek Dr. |  | 2022-05-22 | 8802 and 8808 Maplecreek drive does not have a sidewalk. There is not repair funds available at this time to construct new sidewalks at these addresses.
Riverside Paving | 368756-28 | 4 | 24 | Inspected | FY 22 | Spring 2022 |  | WillowCreek Drive from Old South Park Rd to Bonaventure Blvd. | 5 | 37500 |  | 15831 | 15831 | 8148 410 8211 148560 822705 | Public Works |  | 390 |  | 2022-03-22 | 8902 Willowcreek Drive- Property owner stopped Precision Concrete from completing the beveling work along the sidewalk in front of the house.
Riverside Paving | 368756-29 | 4 | 25 | Inspected | FY 22 | Winter 2022 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 5 | 25000 |  | 6691.5 | 6691.5 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-13 | 4 | 26 | Complete | FY22 | Spring 2022 | May | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 5 | 40000 | 44214.8 | 15315 | 59529.8 | 8148 410 8211 148560 822705 | Public Works |  | 472 | 121061M-14 | 2022-05-01 | Add 13'x5' of sw 3012 Boaires Ln to rio rita NTP
| 381611-14 | [6 empty] | CBD Beveling project |  | 250000
[9 empty] | Total | 3254844.1522 | 935631.42
vault top in sw - contact property owner

## June 2022
| PO # | Area | District | Construciton Status | Date Appropriated | Start | Finish | Project Name | Rating | Estimate | Replacement Cost | Grinding Cost | Total Cost | Funding Accounts | Funding Source | Trees Removed | Repair SY | Invoice # | inspection month | inspection notes
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1050 S 32ND ST | 4 | 24817.6389 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 30'x5' of sw and 9' curb
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1112 S 26TH ST | 4 | 5813.8889 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 33'x5' of sw and 4 utiliy adj
Seven Seas | 368566-25 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1147-1149 S 42nd St |  | 2137.07 | 4459.34 |  | 4459.34 | 8133-410-8107-148283-822705 | Council Funds |  | 9.44 | 120015M-91 |  | 14'x6' of sw, remove stump, s/p
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 1433-1451 HAZEL ST | 4 | 13953.3333 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 40'x6' and 37'x6' and 31x6 of sw and 4 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3511 W KENTUCKY ST | 4 | 12857 |  |  | See 3714 CHAUNCEY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 3714 CHAUNCEY AVE |  | 2022-02-22 | 6'x12' of sw and 2 utility adjustments
Seven Seas | 368566-23 | 1 | 1 | Complete | FY22 | Winter 2022 | April | 3714 CHAUNCEY AVE | 5 | 5877.7778 | 22589 |  | 22589 | 8148 410 8211 148560 822705 | Public Works |  | 132.64 | 120015M-90 | 2022-01-01 | 5'x5' of sw (snow and ice covered -could not inspect on Feb 22 site visit)
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 1300 S 32ND ST | 4 | 1146.1667 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 1366 OLIVE ST | 5 | 16445 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 2 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3222 VIRGINA | 4 | 2541.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 3516 COTTER DR | 5 | 1345.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 11'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4408 JENNYMAC DR | 4 | 1196 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-01-01 | 40'x5' and 40'x5' and 30'x5' of sw and 4 utility adjustments
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | february | 4807 HUNTERS POINT CIR | 4 | 1727.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22 | 18'x5' of sw and 10'x5' of ramp
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2021 | February | 5616 CHRISTIAN RIDGE CT | 4 | 3070.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Fall 2022 | February | 743 S 43RD ST | 4 | 10695 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  |  | 14'x6' of sw and 33'x6' of sw
Joash Construction | 368746-1 | 1 | 1 | Complete | FY22 | Winter 2022 | February | 808 & 810 S 42ND ST | 4 | 4983.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | 11.33
Joash Construction | 368745-10 | 1 | 1 | Complete | FY22 | Fall 2021 | January | 1152-1156 S 26TH ST | 5 | 12790.5556 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 83.33
Seven Seas | 368566-21 | 1 | 1 | Complete | FY21 | Winter 2022 | March | 3500 Block of Algonquin Pkwy | 5 | 18894 |  |  | 0 | 8672 410 8106 048201 822705 | District 1 |  |  |  | 2022-02-22 | 3519 9x4 of sw, 3513 5x5 0f sw, 3509 5x4 of sw, 3500 5x4 of sw, 3506 11x6 of dw and 4x4 of sw, 3508 10x10 of dw, 3512 6x5 of sw, 3516 11x8 of dw and 5x4 of sw, 3518 17x4 of dw, 3520 9x4 of sw and 1 utilty adj, 3528 5x4 of sw and 6x4 of sw, 3530 10x4 of dw, 3536 11x4 of sw and 1 tree, 3542 4x4 of sw, 3544 6x4 of dw, 3546 4x4 of sw, 3908 38'x4 of sw and 8' of curb and 1 big tree sent to arborist
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1101 S 41st St | 4 | 3885.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1159 S 41st St | 4 | 963.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1162 S 41st St | 4 | 721.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1175 S 41st St | 4 | 2011.73 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1213 S 41st St | 4 | 725.33 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 1222-1224 Cypress St | 5 | 7670.93 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Precision Concrete Cutting |  | 1 | 1 | Complete | FY21 | Fall 2021 | September | 3500 Block of Algonquin Pkwy Beveling Project | 2's through 4's | 3393 |  | 3393 | 3393 | 8672 410 8106 048201 822705 | District 1 |  |  | 120521
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4112 Winnrose Way | 5 | 3279.4 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 4302 Winnrose Way | 4 | 1501.27 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | 776.4 | 120015M-76
Seven Seas | 368566-5 | 1 | 1 | Complete | FY21 | Summer 2021 | September | 6519 Hunters Creek Blvd | 4 | 433.8 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose | See 4302 Winnrose
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Concrete Beveling Poject | 2's through 5's | 20808 | 20808 |  | 20808 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY22 | Summer 2021 | August | Sidewalk Leveling Project | 2's through 5's | 3500 | 3500 |  | 3500 | 8148 410 8211 148560 822705 | Public Works
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 1403 FOREST DR | 4 | 897 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 3613-3615 E Indian Trl | 5 | 2894.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4108 St Charles St | 5 | 1919.36 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 4109 St Charles St | 5 | 12914 | 25255.88 |  | 25255.88 | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | District 2 |  | 104.9
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4310 E Indian Trl | 4 | 229.12 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4404 E Indian Trl | 5 | 784 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 4907 Sunday Dr | 4 | 251.84 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5009 ROY WILLIAMS PL | 5 | 598 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5020 Broadmoor Blvd | 4 | 838.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5023 Broadmoor Blvd | 4 | 206.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | Proposed for FY22 | Summer 2021 | July | 5101 Mediterranean Ct | 4 | 2369.6 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5105 Broadmoor Blvd | 4 | 183.68 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY19 | Summer 2021 | July | 5107 Broadmoor Blvd | 5 | 6116.4 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works / District 2 |  | See 4109 Charles
Riverside Paving | 368756-4 | 4 | 2 | Complete | FY21 | Summer 2021 | July | 5301 GARDEN GREEN WAY | 5 | 531.56 |  |  | See 4109 Charles | 8137 410 8211 148452 822705 ($7,850.51) / 8143 410 8211 148472 822705 ($7,764.63) / 8146 410 8211 148487 822705 ($9,639.74) | Public Works |  | See 4109 Charles
TBD |  | 4 | 2 | Inspected | FY22 | Summer 2022 |  | Ridgecrest Rd from Rangeland Rd to Rockwood Ave | 2's through 5's | 55000 |  | 20808 | 20808 | 8148 410 8211 148560 822705 | Public Works |  | "513.78 (bevel)+193.2 (in place) |  |  | The beveling is complete and the NTP for this sw full depth repair work is ready to be sent to the contractor.
TBD |  | 4 | 2 | Inspected | FY22 | Summer 2022 |  | West side of Robinwood Ln from Rangeland Rd to Ridgecrest Rd | 2's through 5's | 15000 |  | See Ridgecrest | See Ridgecrest | 8148 410 8211 148560 822705 | Public Works |  | See Ridgecrest |  |  | The beveling is complete and the NTP for this sw full depth repair work is ready to be sent to the contractor.
Joash Construction | 368746-1 | 1 | 3 | Complete | FY20 | Fall 2021 | February | 1413 OLEANDA AVE | 5 | 4651.1111 | 48026.16 |  | 48026.16 | 8143 410 8211 148472 822705 | Public Works |  | 287.74
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1472 DIXIE HWY | 4 | 830.5556 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1505 OLEANDA AVE | 4 | 1993.3333 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 1509 OLEANDA AVE | 4 | 6043.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works | 1 | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2116 OREGON AVE | 4 | 2242.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 2313 ALLSTON AVE | 5 | 448.5 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3312 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3314 UTAH AVE | 5 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction | 368746-1 | 1 | 3 | Complete | FY22 | Fall 2021 | February | 3319 UTAH AVE | 4 | 1063.1111 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3301 UTAH AVE | 4 | 4651.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction |  | 1 | 3 | Complete | FY22 | Fall 2021 | November | 3303 UTAH AVE | 4 | 664.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Joash Construction | 368745-10 | 1 | 3 | Complete | FY22 | Fall 2021 | October | 1503 OLEANDA AVE | 4 | 1328.8889 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1705 VALLEY FORGE WAY | 4 | 260 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1709 VALLEY FORGE WAY | 5 | 2990 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1725 W GAULBERT AVE | 5 | 8372 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1728-1734 W HILL ST | 4 | 3737.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 1749 W HILL ST | 4 | 7325.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2314 WOODLAND AVE | 4 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2322 OREGON AVE | 5 | 1943.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 3 | Complete | FY21 | Summer 2021 | September | 2328 W LEE ST | 5 | 1569.75 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368567-16 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | 1634 BEECH ST | 5 | 6478.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 56'x6' of sw and 5'x3' courtesy pad
Seven Seas | 368567-16 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | 2616 ALLSTON AVE | 5 | 747.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 13.56 |  |  | 4'x4' of sw
Seven Seas | 368566-28 | 1 | 3 | Sent to Contractor | FY22 | Spring 2022 |  | South side of Dixdale Ave from Dixie Hwy to S 23rd St | 2's through 5's | 10760 | 26000 | 10760 | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | 200 |  |  | see NTP
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 100 E JEFFERSON ST | 4 | 33189 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2021-12-21 | NEW HANDICAP RAMPS AND SW AT CONGRESS ALLEY
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 1216 FERN ST | 5 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-01-31 | 23'X14' OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 1718 MAGAZINE ST | 5 | 4964.1667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.19 |  | 2021-12-03 | BRICK SW HAS BEEN REPAIRED
|  | 2 | 4 | Inspected | FY19 | Fall 2021 | December | 200 S 5TH ST | 4 | 6000 |  |  | By others | 8137 410 8211 148452 822705 | Public Works |  | By others |  | 2022-01-31 | 6'X2' OF OF DW
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | December | 2329 W CHESTNUT ST | 5 | 1150 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.5 |  | 2022-01-22 | 2" VERTICAL OFFSET UTILITY TOP REPAIRED BY OTHERS
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | 829 W. Main St. | 5 | 5200 |  |  | By others | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | RR track in front of Frasier Museum. Investigate moving trash can to this location.
|  | 2 | 4 | Complete | FY21 | Fall 2021 | December | S 5TH ST & W MAIN ST | 4 | 5500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  | 2022-01-31 | 5.5'x73' and 5.5'x143' of sw. The sidewalk is in the floodwall right of way. Snow and ice blocked the view of the sw during the site visit on 1/31/2022. Recheck condition during warmer weather.
|  | 2 | 4 | Complete | FY20 | Fall 2021 | December | S JACKSON ST & E MUHAMMAD ALI BLVD | 5 | 7580 |  |  | By others | 8143 410 8211 148472 822705 | Public Works |  | By others |  | 2022-01-31 | Repaired by others -No issue found on 1/31/2022
Joash Construction | 368745-24 | 2 | 4 | Complete | FY22 | Winter 2022 | June | 1115 E Oak St | 5 | 14455.5556 | 27825.23 |  | 27825.23 | 8148 410 8211 148560 822705 | Public Works |  | 284.45 | 1056
Joash Construction | 368745-24 | 2 | 4 | Complete | FY22 | Winter 2022 | June | 530 Barret Ave/Lexington Rd | 4 | 4628.8889 | See 1115 E Oak St |  | See 1115 E Oak St | 8148 410 8211 148560 822705 | Public Works |  | See 1115 E Oak St | See 1115 E Oak St
Joash Construction | 368745-24 | 2 | 4 | Complete | FY22 | Winter 2022 | June | 721 4th St | 4 | 4000 | See 1115 E Oak St |  | See 1115 E Oak St | 8148 410 8211 148560 822705 | Public Works |  | See 1115 E Oak St | See 1115 E Oak St | 2022-06-03
Joash Construction | 368745-24 | 2 | 4 | Complete | FY22 | Winter 2022 | June | 725 ROSELANE ST | 5 | 18277.7778 | See 1115 E Oak St |  | See 1115 E Oak St | 8148 410 8211 148560 822705 | Public Works |  | See 1115 E Oak St | See 1115 E Oak St
Joash Construction | 368745-24 | 2 | 4 | Complete | FY22 | Winter 2022 | June | Barret Ave & Baxter Ave | 5 | 27608.8889 | See 1115 E Oak St |  | See 1115 E Oak St | 8148 410 8211 148560 822705 | Public Works |  | See 1115 E Oak St | See 1115 E Oak St
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 1076 E WASHINGTON ST | 4 | 9449.1667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 5.28 |  | 2022-01-31
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 1910-1912 MAGAZINE ST | 4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 15 |  | 2021-01-31 | 15'X9' OF SW
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 237 E Breckinridge St | 4 | 27864 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 6'X2' of dw
Joash Construction | 368745-24 | 2 | 4 | Complete |  | Winter 2022 | March | 512 Barret Ave | 5 | 15540 | See 1115 E Oak St |  | See 1115 E Oak St | 8148 410 8211 148560 822705 | Public Works | 1 | See 1115 E Oak St | See 1115 E Oak St | 2022-06-03 | No R4 or R5 observed during the inspection
Joash Construction | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 514 BARRET AVE | 5 | 10925 | 14104.1 |  | 14104.1 | 8146 410 8211 148487 822705 | Public Works | 2 | 101.91 |  | 2021-01-31 | R5 63'X6' and 6'x4' of sw, 3 utility adjustments, 22" tree and 12" tree
TBD | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 550 S 3RD ST (possibility Utilities' fault) | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 0 | 0.44 |  | 2021-01-31 | No issue observed during the 1/31/22 sw inspection
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | 741 FRANKLIN ST | 5 | 4861.9444 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 63.2 |  |  | complete
| 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | 747 E JEFFERSON ST | 4 | 3900 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | see 514 BARRET AVE |  | 2021-01-31 | R4 23'X14' OF DW
|  | 2 | 4 | Complete | FY22 | Winter 2022 | March | 833 W MAIN ST | 4 | 3000 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 0 |  | 2021-01-31 | Pw operations is placing trash can on top of displaced rr track to mitigate
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | March | N SHELBY ST & FRANKLIN ST | 4,5 | 11553.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | 22.94
TBD | 368745-22 | 2 | 4 | Complete | FY22 | Winter 2022 | March | S HANCOCK ST & E BRECKINRIDGE ST | 5 | 4069.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | see 514 BARRET AVE |  | 2022-01-31 | 30'x11' of sw and 30' of curb and 1 utility adjustment.
Joash Construction | 368745-10 | 2 | 4 | Complete | FY22 | Fall 2021 | September | 400 S 6TH ST | 4 | 1129.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 40 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | W. Jefferson St & S. 4th St | 5 | 4669.4444
| 368745-24 | 2 | 4 | Inspected |  | Winter 2022 |  | 1120 E. Breckinridge St | 4 | 3455.5556 | [8 empty] | 2022-06-03 | No R4 or R5 observed
|  | 2 | 4 | Not Inspected | FY22 | Winter 2022 |  | 1224 FRANKLIN ST (1205 E Washington St) | 4 | 12656.25 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  | 2021-01-31 | Snow and ice on the sw prohibited the site inspection. The sidewalk is within the floodwall right of way and is R1-R5. Set up meeting with MSD to confirm the permitting requirement or closing the gates to block off access since a new sidewalk was constructed in 2021 across from 1224 Franklin St as an altermate ADA comatible sw.
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 130 S 3rd St | 4 | 7945 | [6 empty] | 16 |  | 2022-06-03 | R4 Traffic handhole 2" vertical displacement, R4 -13'x8' of dw
Joash Construction | 368745-24 | 2 | 4 | Inspected |  | Winter 2022 |  | 217 S 5th St | 5 | 2256.6667 | [9 empty] | No R4 or R5 observed during the inspection
Joash Construction | 368745-24 | 2 | 4 | Sent to Contractor |  | Winter 2022 |  | 315 E Main St | 5 | 9191.6667 | [9 empty] | Asked Shayne to bevel this location on June 23, 2022
| 368745-24 | 2 | 4 | Inspected |  | Winter 2022 |  | 4TH ST and LIBERTY ST | 5 | 4000 | [8 empty] | 2022-06-03 | R4 -4'x10' of utility cut has not been reapired by the utiility company - the issue was reported to Permits and License on 6/3/2022
|  | 2 | 4 | Inspected |  |  |  | 731 FRANKLIN ST | [10 empty] | 2022-06-03 | No R4 or R5 observed during the inspection
Seven Seas | 368566-24 | 1 | 5 | Complete | FY21 | Winter 2021 | April | 200 Block of Southwestern Pky | 4 | 15242 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 201 -205 SW Parkway, 56’x6’ and 10’x6’ and 16’x6’ of sw, 227 SW Parkway 37’x6’ of sw, and 1 tree, 231 SW Parkway23’x6’ of sw and 1 tree, 235 - 237 SW Parkway 10’x6’ of sw and 14’x6’ of sw and 1 tree, 239 SW Parkway 29’x6’ of sw , 245 SW Parkway 5’x6’ of sw , 249-251 SW Parkway 45’x6’ and 4’x5’ and 3’x5’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 464 N 25TH ST | 4 | 64238 | 60103.7 |  | 60103.7 | 8146 410 8211 148487 822705 | Public Works |  | 497.31 | 120015M-92 | 2022-02-22 | 25' of curb and 12x7 of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 472 TO 468 N 29TH ST | 4 | 6500 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 67x6 of sw and 3 utility adjustments
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 474 N 29TH ST | 4 | 4490 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 20x6 of sw and 1 tree
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 804 S 39TH ST | 5 | 7750 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6'x6' of dw and 7'x6' of dw and 9'x6' of dw and 7'x3' of dw and 1 utility adjustment
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | 805 S 39TH ST | 4 | 3250 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 6’x10’ of sw and 6’x22’ of sw, and 4’x4’ of sw
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | N 29TH ST & BANK ST | 4 | 12000 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 10’x5’ of sw and 15’ of curb, 100’x5’ of sw and 5’x25’ of dw and 91’x5’ of sw and 2 trees
Seven Seas | 368566-24 | 1 | 5 | Complete | FY22 | Winter 2022 | April | S 28TH ST & W JEFFERSON ST | 5 | 2210 | See 464 N 25TH ST |  | See 464 N 25TH ST | 8146 410 8211 148487 822705 | Public Works |  | See 464 N 25TH ST | See 464 N 25TH ST | 2022-02-22 | 43’x8’ of sw at 2732 W. Jeffreson St, 8’x6’ of sw at 2729 W. Jefferson St, 86’x6’of sw at 234 S 28th St.
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2814 ROWAN ST | 4 | 996.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 7.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2917 MONTGOMERY ST | 5 | 5980 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 38.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 2934 Portland Ave | 5 |  |  |  | See 3511 Northwestern Pkwy |  | Public Works? |  | 60
Joash Construction | 368745-10 | 1 | 5 | Complete | FY21 | Fall 2021 | December | 3511 Northwestern Pkwy | 5 | 13456 | 72946.52 |  | 72946.52 | 8138-410-8107-148280-822705 | Council | 1 | 40.69
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 355 SOUTHWESTERN PKY | 4 | 2259.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 18.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 361 SOUTHWESTERN PKY | 4 | 9966.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 40.22
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4138 LARKWOOD AVE | 4 | 5116.2222 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.77
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 4303 VERMONT AVE | 5 | 8369.4444 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works | 1 | 46.55
Seven Seas | 368745-10 | 1 | 5 | Complete | FY21 | Fall 2021 | December | 501 N 21st St | 4's and 5's | 22525.8 |  |  |  | 8138 410 8107 148280 822705 | Council District 5 |  | 140.56
Joash Construction |  | 1 | 5 | Complete | FY21 | Fall 2021 | December | 501 Northwesern Pkwy |  |  |  |  | See 3511 Northwestern Pkwy |  |  |  | 157
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 641 EASTLAWN AVE | 5 | 3986.6667 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 35.61
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 654 EASTLAWN AVE | 4 | 1661.1111 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 22.78
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 734 S 38TH ST | 5 | 6245.7778 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 30.67
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 809 S 38TH ST | 5 | 4485 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 17.81
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Fall 2021 | December | 814 DEARBORN AVE | 4 | 9401.8889 |  |  | See 3511 Northwestern Pkwy | 8148 410 8211 148560 822705 | Public Works |  | 42.33
Joash Construction | 368745-10 | 1 | 5 | Complete | FY 22 | Fall 2021 | December | Vermont and Southwestern |  |  | 5289.2 |  | 5289.2 |  |  |  | 75.56
Joash Construction | 368745-10 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1114 PLATO TER | 4 | 664.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Joash Construction | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 1501 LYTLE ST | 4 | 4252.4444 |  |  | See 1413 Oleanda Ave | 8148 410 8211 148560 822705 | Public Works |  | See 1413 Oleanda Ave |  | 2022-02-22
Seven Seas | 368746-1 | 1 | 5 | Complete | FY22 | Winter 2022 | February | 4501 GREENWOOD AVE #1 | 5 | 6250 |  |  | Completed by others | 8146 410 8211 148487 822705 | Public Works |  | Completed by others |  | 2022-02-22 | No R4 or R5 observed
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Winter 2022 | March | 109 N 40TH ST | 4 | 5200 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 6 |  |  | repaird by LWC, a new water meter was installed in the verge next to the new 9'x6' sw,
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | November | 2146 DUNCAN ST | 5 |  | 4985.34 |  | 4985.34 | 8133-410-8211-148396-822705 | Public Works |  | 80.34
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Fall 2021 | November | 743 DEARBORN AVE | 4 | 18958.9 |  |  | See 4302 Winnrose | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | October | 616 N 28TH ST | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 120 S Shawnee Ter | 4 | 2694.67 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 122 NORTHWESTERN PKY | 5 | 2093 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 123 N 42nd St | 5 | 1112.6 | 5517.31 |  | 5517.31 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 1824 BANK ST | 5 | 12774.2 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 207 S 42ND ST | 4 | 1777.6 | 5517.31 |  | 5517.31 | 8133 410 8211 148396 822705 | Public Works |  | 84.28
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2403 ROWAN ST | 4 | 29697.6 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 2711 W JEFFERSON ST | 5 | 5010 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 2714 Alford Ave | 4 | 1340.4 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 2725 NORTHWESTERN PKY | 4 | 3718.3333 | 7468.84 |  | 7468.84 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3128 W MUHAMMAD ALI BLVD | 4 | 897 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3424-3426 W JEFFERSON ST | 4 | 4634.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY22 | Summer 2021 | September | 3500 W MAIN ST | 4 | 1245.8333 | 2673.54 |  | 2673.54 | 8148 410 8211 148560 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 351 N 28th St | 5 | 555.33 |  |  | 0 | 8133 410 8211 148396 822705 | Public Works |  | 4.44
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 3640 River Park Dr | 5 | 5916 | 4508.25 |  | 4508.25 | 8138 410 8107 148280 822705 | Council District 5 |  | 29
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4102 VERMONT AVE | 4 | 299 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works | 1 | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 415-417 LOUIS COLEMAN JR DR | 4 | 7176 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4308 VERMONT AVE | 5 | 5083 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 4509-4515 W Market St | 5 | 3960.6 | 2743.77 |  | 2743.77 | 8146 410 8211 148487 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 631 S 42ND ST | 5 | 3438.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 650 S 31st St | 5 |  | 2843.77 |  | 2843.77 | 8133 410 8211 148396 822705 | Public Works |  | See 207 S 42nd St
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 662 Cecil Ave | 4 | 7570.8 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY21 | Summer 2021 | September | 667 S 39TH ST | 4 | 1345.5 | 2673.54 |  | 2673.54 | 8146 410 8211 148487 822705 | Public Works |  | See 4302 Winnrose
Seven Seas | 368566-5 | 1 | 5 | Complete | FY18 | Summer 2021 | September | 682 Madelon Ct | 5 | 248.67 | 2673.54 |  | 2673.54 | 8133 410 8211 148396 822705 | Public Works |  | See 4302 Winnrose
|  | 1 | 5 | Inspected | Summer 2022 | Summer 2022 |  | 219 Southwestern Parkway | R5 | 912 |  |  |  | 8138-410-8107-148280-822705 | Council District 5 |  | 9 |  | 2022-05-01 | 6'x9' of sw and 4'x7' of courtesy pad
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 235 S. 41st Street | R5 | 3744.02 |  |  | 5636 | 8146-410-8107-148280-822705 | Council District 5 |  | 200 |  |  | 17'x'4 and 6'x4' and 9'x4' of sw, 14'x4' of dw and 15'x6' of dw apron, 9' of curb and 1-13" tree($5,635.21 counicl funds were alloted for 235 and 242 S. 41st St.)
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 242 S. 41st Street | R5 | 1892 |  |  | * see notes | 8146-410-8107-148280-822705 | Council District 5 |  | 23 |  |  | 6'x4' and 31'x4' of sw and 8'x'4 of dw-(($5,635.21 counicl funds were alloted for 235 and 242 S. 41st St.)
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 311 N 30TH ST | 4 | 7842 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley- future paving project
Seven Seas |  | 1 | 5 | Inspected | FY22 | Winter 2021 |  | 312 N 30TH ST | 5 | 4870 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2022-02-22 | Curb ramp and alley - future paving project
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 3430 Rudd Ave. | R5 | 2900 |  |  | 2900 | 8146-410-8107-148280-822705 | Council District 5 |  | 19 |  |  | 8'x4' and 4'x4' and 12'x4' and 15'x5' of sw
|  | 1 | 5 | Inspected |  | Summer 2022 |  | 3904 W. Muhammad Ali Blvd. | R5 | 1240 |  |  |  | 8138-410-8107-148280-822705 | Council District 5 |  | 9 |  | 2022-05-01 | 6'x6' and 6'x7' of sw and 1 utility adj
Seven Seas | 368566-26 | 1 | 5 | Sent to Contractor | FY 22 | Spring 2022 |  | 3914 Bank St. | R5 | 1387 |  |  | 1387 | 8146-410-8107-148280-822705 | Council District 5 |  | 8 |  |  | 5'x7' of sw and 5'x15' of dw and 10'x3' of dw apron
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 112 E ST CATHERINE ST | 4 | 1868.75 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.81 |  | 2021-12-21 | U OF L - 3' OF CURB MISSING, AND 12' OF 1.25" VERTICAL OFFSET IN SW - PRIVATE PROPERTY
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1261 S BROOK ST | 5 | 6210 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.56 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1265 S BROOK ST | 5 | 4784 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 1.78 |  | 2021-12-21 | REPAIRED BY OTHERS
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1317 S 6TH ST | 5 | 24405.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.5 |  | 2021-12-21 | 6'X6' of sw located at 2103 Grand Ave. and 5'X6' of sw at 2100 Grand Ave.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 1638 W KENTUCKY ST | 4 | 5315.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 25.42 |  | 2021-12-21 | 10'X20' OF DW, 2- 4'X5' RAMPS AND 96'X5' OF SW (BY OTHERS )
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 1703 S BROOK ST | 5 | 6720 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 1815 Hale Ave | 4 | 822.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-21 | 9'X5' OF DW AND 31'X4' OF SW, Curve out sidewalk as much as possible. Straight cut roots only as necessary.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 2623 GREENWOOD AVE | 5 | 2522.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5.67 |  |  | 12'x7.5' historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 1.5' x7.5' of historic sw and 15' of historic curb historic (Call arborist to investigate 3 marked trees)
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 3014 MONTANA AVE | 5 | 2076.3889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 14.22 |  | DECEMBER
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2021 | December | 610 W Magnolia Ave | 4 | 5473.4 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  | 2021-12-28 | 5'X5' OF SW OR RAMP
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | December | 635 PARK AVE | 5 | 2821.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 5 |  |  | 6'X5' OF SW BY OTHERS
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | 821 HUMLER ST | 5 | 6500 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | R3 4'X23' of dw
Joash Construction |  | 2 | 6 | Complete | FY21 | Summer 2020 | December | SE Corner of University Blvd & Arthur St | 5 |  | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others |  |  | 12'x4' of sw and 12' of curb, 39'x4' of sw, and 5'x4' of sw, seed and protection
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | UNIVERSITY BLVD & ARTHUR ST | 5 | 4933.5 | By Others |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction |  | 2 | 6 | Complete | FY21 | Fall 2020 | December | WILSON AVE & S 23RD ST | 4 | 9360 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By Others
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | February | 1423 ARCADE AVE | 4 | 2325.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | No R4 or R5 present
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | February | 1330 W BRECKINRIDGE ST | 5 | 7206.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.67 |  |  | 60'x6' of sw
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 1434 THORNBERRY AVE | 4 | 3000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 1 | 15.5 |  |  | 35'x4' of historic sw and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | January | 509 W ORMSBY AVE | 5 | 15200 | 52211.13 |  | 52211.13 | 8148 410 8211 148560 822705 | Public Works | 10 | 89.58 |  |  | 10'X18' and 17'x10' and 9'x10' of historic sw and 6'x10' of historic dw and 1 utility gas meter. (remove 1-22", 1-25" and 1-27" tree as marked) seed and protection. Straight cut bricks to tie into sw.
Joash Construction |  | 2 | 6 | Complete | FY21 | Winter 2022 | January | DR W J HODGE ST & GRAND AVE | 5 | 1342 |  |  |  | 8146 410 8211 148487 822705 | Public Works |  | 8.67 |  |  | 7'x6'of sw at 2100 Grand Ave and 6'x6' of sw at 2103 Grand Ave.
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1152 Garvin Pl | 5 | 20946.6667 | 49546.5 |  | 49546.5 | 8148 410 8211 148560 822705 | Public Works | 1 | 437.25 | 1057
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1157 LINCOLN AVE | 5 | 4675 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1217 S 26th St | 5 | 4433.3333 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1364 Lillian Ave | 5 | 5977.7778 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1605 DUMESNIL ST | 5 | 2966.6667 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1635 Wilson Ave | 5 | 5166.6667 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl | 2022-06-03 | no R4 or R5 obs duing the inspection
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1701 Gallagher St | 5 | 9726.6667 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl | 2022-06-03 | complete
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 1775 Wilson Ave | 4 | 7028.8889 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 2309 Date St | 4 | 3626.6667 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | 907 Burton Ave | 5 | 3700 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
| 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | Intersection of 8th & Cawthon | 5 | 11277.7778 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl | 2022-06-03 | no R4 or R5 obs duing the inspection
| 368745-24 | 2 | 6 | Complete | FY22 | Winter 2022 | June | WINKLER AVE & S 5TH ST | 5 | 5533.3333 | See 1152 Garvin Pl |  | See 1152 Garvin Pl | 8148 410 8211 148560 822705 | Public Works |  | See 1152 Garvin Pl | See 1152 Garvin Pl
Joash Construction | 368745-21 | 2 | 6 | Complete | FY20 | Winter 2022 | March | 1336 S 6TH ST | 4 | 14200 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x7.5' of historic sw and 1 utility meter adj. and 10' of historic curb, and 9.5'x7.5' of historic sw and 21'x7.5' of historic sw and 21' of historic curb, and 15.5' x7.5' of historic sw and 15' of historic curb historic (remove 1-31" and 2-17" trees)
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1408-1410 HOMEVIEW DR | 5 | 15726.25 |  |  | See 509 W Ormsby | 8143 410 8211 148472 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 10'X18' and 17'x10' and 9'x10' of sw and 6'x10' of dw and 1 utility gas meter. (remove and replace 3 public trees) seed and protection. Straight cut bricks to tie into sw.
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | 1410 ARCADE AVE | 4 | 2657.7778 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | 12'x4' of historic sw and curb, 39'x4' of historic sw, and 5'x4' of historic sw, seed and protection
Joash Construction | 368745-21 | 2 | 6 | Complete | FY22 | Winter 2022 | March | W ORMSBY AVE & S 6TH ST (1338 s 6 th St.) | 5 | 8200 |  |  | See 509 W Ormsby | 8148 410 8211 148560 822705 | Public Works |  | see 509 W ORMSBY AVE |  |  | R4 19'X8' OF SW AND 47'X8' OF historic sw and saw cut along the retaining wall as marked, remove two 18" and one 23" tree as marked, seed and protection | (Jason Tipton w LGE 3/18/22)
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 1503 EARL AVE | 5 | 3917.6667 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 3.31 |  |  | 35'x4' of SW and 35' of curb, Curve out sidewalk as much as possible or raise sw to bridge roots. Straight cut roots only as necessary. Preserve tree.
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | November | 3221 UTAH AVE | 5 | 4050.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 9.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1424 EARL AVE | 4 | 7040.5556 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works | 1 | 13.5
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1501 EARL AVE | 4 | 2389.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.92
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 1502 PHYLLIS AVE | 5 | 4382.7778 | 23535.09 |  | 23535.09 | 8148 410 8211 148560 822705 | Public Works | 1 | 6.03
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3210 UTAH AVE | 5 | 2990 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.7
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3212 UTAH AVE | 5 | 664.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 8.05
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3223 UTAH AVE | 5 | 2657.7778 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.47
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3234 UTAH AVE | 4 | 4983.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 29.27
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3238 UTAH AVE | 5 | 1661.1111 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 2.72
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3240 UTAH AVE | 5 | 3718.3333 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 10.11
Joash Construction | 368745-10 | 2 | 6 | Complete | FY22 | Summer 2021 | October | 3249 UTAH AVE | 4 | 6644.4444 |  |  | See Phylis Ave | 8148 410 8211 148560 822705 | Public Works |  | 4.67
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 121 W Oak St |  | See 123 W Oak St |  |  | 0
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 123 W Oak St | 4 | 11433.3333 |  |  | 0
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 1400 S. Floyd St | 5 | 9291.6667 |  |  | 0
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor |  | Winter 2022 |  | 1429 Homeview Dr | 5 | 3694.4444 |  |  | 0 |  |  |  | 8 |  | 2022-06-03 | 5'x14' of sw
Joash Construction | 368745-24 | 2 | 6 | Sent to Contractor | FY22 | Winter 2022 |  | 2214 Hale Ave | 4 | 3553.3333 |  |  | 0 |  |  |  | 12
|  | 2 | 6 | Not Inspected | FY21 | TBD |  | Sidewalk Reparis TBD |  | 20000 |  |  | 0 | 8146 410 8107 148225 899998 | District 6
TBD |  | 3 | 7 | Complete | FY22 | Winter 2022 | June | Wesboro Rd from Herr Ln to Hayward Rd | 2's through 5's | 17500 | By Others |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | 2022-06-07 | 7314 Wesboro Rd 16x4 of sw and 1 lge mh adj (repaired by lge), 7316 Wesboro Rd 10x4 of sw and 1 lge mh adj (repaired by lge), 7322 Wesboro Rd 11x4 and 5x4 and 6x4 of sw and 1 lge mh adj (repaired by lge), 7324 10x4 of sw and 1 lge mh adj (repaired by lge). Contacted James Tipton at LGE regarding the 3 transfomers in sidewalk.
TBD |  | 3 | 7 | Inspected |  | Winter 2022 |  | 7326 Wesboro Rd | 4 | see Wesboro Rd from Herr Ln to Hayward Rd |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-06-07 | 6x4 of sw and one tree - inspected by Cindi
| 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 1418 MORTON AVE | 5 | 1690 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 1902 Deerwood Ave | 4 | 5556.6 | 32964.32 |  | 32964.32 | 8146 410 8211 148487 822705 | Public Works |  | 228.66
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2023 Woodbourne Ave | 4 | 368.53 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2082 Douglass Blvd | 5 | 6323.47 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2105 DOUGLASS BLVD | 4 | 7973.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2115 Woodbourne Ave | 4 | 2172 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2208 LAUDERDALE RD | 5 | 498.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2224 Dundee Rd | 5 | 5667.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Winter 2021 | March | 2246 BOULEVARD NAPOLEON | 5 | 2280 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY22 | Winter 2021 | March | 2300 MEADOW RD | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | March | 2809 Montrose Ave | 5 | 1316 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368569-6 | 3 | 8 | Complete | FY21 | Fall 2021 | November | 1522 Rosewood Ave | 4 | 4071.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-3 | 3 | 8 | Complete | FY22 | Fall 2021 | November | 2303 Meadow Rd | 5 | 1913.85 | 2934.77 |  | 2934.77 |  | Council District 8 |  | 27.63
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1819 Harvard Dr | 5 | 7398.4 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 5 |  |  | 5'x9' of sw & 5’x5’ of dw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 1840 SHADY LN | 5 | 3380 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 15 |  |  | 4.5'x30' of sw; 1 utility adj., seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1875 RUTHERFORD AVE | 5 | 1727.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 4'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1895 RUTHERFORD AVE | 5 | 5842 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.44 |  |  | 4'x37' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist. Upon receiving these recommendations could one of you please reach out the Larry and inform him.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1900 ROANOKE AVE | 4 | 3145.25 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 5.56 |  |  | 5'x10' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HAMPDEN CT | 5 | 830.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 16.67 |  |  | 5'x25' of sw & 5’x5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1912 HARVARD DR | 5 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6.94 |  |  | 5’x12.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 1920 BONNYCASTLE AVE | 5 | 2622 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 6 |  |  | 6'x9' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2018 BOULEVARD NAPOLEON | 5 | 4170 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 74.17 |  |  | 5'x15' of sw & 5'x55' of sw & 5'x10' of sw & 5'x36.5' of sw & 5'x17' of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2137 ALTA AVE | 4 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.78 |  |  | 5’x14’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2139 WOODBOURNE AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 26.33 |  |  | 5’x43’ of sw & 4’x5.5’ of sw, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2218 WOODBOURNE AVE | 5 | 897 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 4'x25' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-5 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2219 TALBOTT AVE | 5 | see 2221 Talbott Ave |  |  | 0 | see 2221 Talbott Ave | Council District 8 |  | see 2221 Talbott Ave |  | May | 28'x5' of sw and 11'x6' of apron and 11'x5' of dw and 4'x4' of courtest pad, seed and protection
Seven Seas | 368569-5 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2221 TALBOTT AVE | 5 | 18149 |  |  | 0 | 8102 410 8105 148903 822705 $621.73 8138 410 8107 148903 822705 $2,281.27 8146 410 8107 148903 822705 $15,246 | Council District 8 |  | 30.42 |  | May | 36'x5'’ of sw; and 5'x4' of courtesy pad & seed and protection. Remove 42" and 24 " maple tree, Bob Ray PO# 381536-73 for $6,150
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2310 BOULEVARD NAPOLEON | 5 | 5896.9444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 7.5 |  |  | 5'x13.5' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY22 | Winter 2022 |  | 2420 LONGEST AVE | 5 | 3120.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 35.33 |  |  | Historic conc. 6'x54' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 2541 Cherokee Pkwy | 4 | 5240 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 11.36 |  |  | Historic conc. 6’x15’ of sw; 3.5'x3.5' of courtesy pad, seed and protection.
Seven Seas | 368569-6 | 3 | 8 | Sent to Contractor | FY21 | Winter 2022 |  | 701 BAXTER AVE | 5 | 8004 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 105.11 |  |  | 8'x10.5' of sw & 8'x5' of sw & 8'x25' of sw & 8'x15' of sw & 8'x20' of sw & 8'x16.5' of sw & 10'x21' of sw; 1 manhole adj., seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 122 N BAYLY AVE | 5 | 2555.5556 | 29946 |  | 29946 | 8148 410 8211 148560 822705 | Public Works |  | 100.35 | 121061M-12 |  | 4'x8' of sw & 5'x26’ of sw, seed and protection, Mr. Ed Bowling His number is (502) 494-9569.once arborist reports back. He wants to save the tree
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 148 VERNON AVE | 4 | 398.6667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 3'x8' of sw, seed and protection
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | April | 1854 Frankfort Ave | 3, spalling | 264 | 3176.8 |  | 3127.56 | 8138 410 8107 148227 822705 | Council District 9 |  | 5.12 | 121061M-13 | 2022-04-17 | Historic Conc. 3'x10' of curtesy pad, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 201 S PETERSON AVE | 5 | 9370.9667 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 6'x13.5' of sw; and 1 utility adj, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 2035 EMERALD AVE | 4 | 2392 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | Historic Conc. 4.5'x36' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2022 | April | 217 MCCREADY AVE | 4 | 5000 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE |  | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 3.5'x4' of sw & 5’x30’ of sw & 4’x14’ of sw & 4’x5’ of sw; 2’x5’ of ADA pad; 26’ of curb, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3410 INGLE AVE | 4 | 1162.7778 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 5'x14' of sw, seed and protection
Seven Seas | 368569-8 | 3 | 9 | Complete | FY22 | Winter 2021 | April | 3547 NANZ AVE | 5 | 2788.1111 | See 122 N BAYLY AVE |  | See 122 N BAYLY AVE | 8148 410 8211 148560 822705 | Public Works |  | See 122 N BAYLY AVE | See 122 N BAYLY AVE |  | 4'x28' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1821 Frankfort Ave | 4 | 265.07 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1 Eastover Ct | 5 | 876.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1801 Frankfort Ave | 4 | 5642.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | 5 | 213
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1805 Frankfort Ave | 4 | 2925.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1807 Frankfort Ave | 4 | 7220.4 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1809-1811 Frankfort Ave | 4 | 7878 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1817 Frankfort Ave | 5 | 7959.6 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1823 Frankfort Ave | 3 | 712.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1825 Frankfort Ave | 4 | 6660 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1832-1830 Frankfort Ave | 4 | 7137.8 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete |  | Fall 2021 | January | 1846 Frankfort Ave |  |  |  |  | See 1860 Frankfort Ave |  |  |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 1860 Frankfort Ave | 4 | 3484.8 | 62216.2 |  | 62216.2 | 8138 410 8107 148227 822705 | Council District 9 |  | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2039 Frankfort Ave | 3, damaged detectable warnings | 6114.36 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | 2101 Frankfort Ave | ramp is out of compliance | 6514.44 |  |  | See 1860 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | January | Ramps at Pope and State St |  | 1644.5 |  |  | See 1860 Frankfort Ave | 8148 410 8211 148560 822705 | Public Works | See 1801 Frankfort Ave | See 1801 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 102 Crescent Ct | 4 | 8360.8 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave |  |  | 26’ X 6’, 15’ X 6’, 13.5’ X 5’ and 13’ X 10’ of hist SW; 32.5’ of curb; S/P (I think 32.5’ of curb is quite a bit short. In my opinion 100’ of curb is needed
Seven Seas | 368567-9 | 3 | 9 | Complete | FY22 | Winter 2021 | March | 118 N EWING AVE | 4 | 3588 | 13919 |  | 13919 | 8148 410 8211 148560 822705 | Public Works |  | 45.6
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1808-1800 Frankfort Ave | 4 | 15975.52 |  |  | 75718 | 8138 410 8107 148227 822705 | Council District 9 | 2 | 321.65
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1813-1815 Frankfort Ave | 3, crumbling | 7731.9 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1838 Frankfort Ave | 5 | 6019.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1870-1874 Frankfort Ave | 3, sidewalk is breaking up | 3468.23 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1880 Frankfort Ave | 3, badly spalling | 792 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1882 Frankfort Ave | 3, pieces of the sidewalk are ready to pop up | 1900.8 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1900 MELLWOOD AVE | 4 | 5531.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1910 Frankfort Ave | holding water | 699.87 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 1928 Frankfort Ave | drainage issues with ramp | 3400.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2 Eastover Ct | 4 | 1182.6 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2040 Frankfort Ave | 4 | 4884 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2138 New Main St | damaged detectable warnings | 3480 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2140 SYCAMORE AVE | 4 | 448.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2144 Frankfort Ave | 4 | 6240 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2334-2336 Frankfort Ave | 4 | 113.4 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2368 Frankfort Ave | 4 | 2376 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2400 Frankfort Ave | 4 | 2059.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 2608 Frankfort Ave | 4 | 1428.24 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3210 Frankfort Ave | 4 | 5467.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3220 MARION CT | 4 | 1345.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 3230 Frankfort Ave | 4 | 275.2 |  |  | See 1808--1800 Frankfort Ave | 8138 410 8107 148227 822705 | Council District 9 |  | See 1808--1800 Frankfort Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | 405 UNIVERSITY AVE | 5 | 897 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | See 1902 Deerwood Ave
Seven Seas | 368567-5 | 3 | 9 | Complete | FY21 | Fall 2021 | March | Frankfort & Haldeman | damaged detectable warnings | 9110.4 |  |  | 0 | 8138 410 8107 148227 822705 | Council District 9 |  | 62
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 1014 WAGNER ST | 4 | 1411.9444 | 11855.74 |  | 11855.74 | 8148 410 8211 148560 822705 | Public Works |  | 106.09 | 121061M-15 |  | 5’x35’ of sw; 1 utility adj., seed and protection
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 1031 WETTERAU AVE | 5 | 1993.3333 | See 1014 WAGNER ST |  | See 1014 WAGNER ST | 8148 410 8211 148560 822705 | Public Works |  | See 1014 WAGNER ST | See 1014 WAGNER ST |  | 6’x16’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 1107 E BURNETT AVE | 5 | 3818 | See 1014 WAGNER ST |  | See 1014 WAGNER ST | 8148 410 8211 148560 822705 | Public Works | 1 | See 1014 WAGNER ST | See 1014 WAGNER ST |  | 6’x31’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 1131 MULBERRY ST | 4 | 4133.6111 | See 1014 WAGNER ST |  | See 1014 WAGNER ST | 8148 410 8211 148560 822705 | Public Works |  | See 1014 WAGNER ST | See 1014 WAGNER ST |  | 6’x9’ of sw & 3’x10.5’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 2029 ALEXANDER AVE | 4 | 1196 | See 1014 WAGNER ST |  | See 1014 WAGNER ST | 8148 410 8211 148560 822705 | Public Works |  | See 1014 WAGNER ST | See 1014 WAGNER ST |  | 5.5’x9’ of sw, seed and protection
Seven Seas | 368569-7 | 3 | 10 | Complete | FY22 | Winter 2022 | June | 220 DERBY AVE | 5 | 7375.3333 | See 1014 WAGNER ST |  | See 1014 WAGNER ST | 8148 410 8211 148560 822705 | Public Works |  | See 1014 WAGNER ST | See 1014 WAGNER ST |  | 4’x14’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-3 | 3 | 10 | Unsure | FY22 | Fall 2021 | November | 1137 Reutlinger Ave | 5 |  | 2107.9 |  | 2107.9 |  |  |  | 5.73
Seven Seas | 368567-15 | 3 | 10 | Sent to Contractor | FY22 | Winter 2022 |  | Gardiner Ln from Robards Ln to Newburg Rd | 2's through 5's | 40000 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2022-05-17 | 4325 Robards Ln at Gardiner Ln/Robards Ln Intersection 8’x4’ of sw, 4325 Robards Ln on Gardiner Ln side 4’x7’ of sw, 4’x12’ of sw & 1’x12’ of sw, 1516 Gardiner Ln 4’x5’ of sw, 3’x12’ of sw, 4’x4’ of sw & 4’x16’ of sw, and 1 utility adj., 4324 Bishop Ln on Gardiner Ln side 4’x4’ of sw, 4’x12’ of sw, & 3’x12’ of sw, 3340 Newberg Rd on Gardiner Ln. 18’x4’ of sw & 50’x5’ of sw, 4322 Bishop Ln on Gardiner Ln 4’x5’ of sw, 1’x11’ of sw, 4’x5’ of sw, 5’x5’ of sw & 1’x12’ of sw, 1519 Gardiner Ln 5’x5’ of sw, 0.5’x17’ of sw & 5’x5’ of sw, 1507 Gardiner Ln 4’x4’ of sw; MSD Service request 5423082 to address cave in along Gardiner Lane/Robards Lane CB
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 2824 SIX MILE LN | 5 | 1196 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | 5'X5' OF SW
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 4011 RIVULET LN | 4 | 664.4444 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others |  |  | GRINDING BY OTHERS
Riverside Paving |  | 5 | 11 | Complete | FY22 | Winter 2021 | December | 7800 HUNSINGER GARDENS LN | 5 | 2691 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By others
Precision Concrete Cutting |  | 5 | 11 | Complete | FY22 | Winter 2021 |  | Lacevine Ct from Lacevine Rd to Lacevine Pl | 2's through 5's |  |  | See Lacevine Rd | See Lacevine Rd | 8148 410 8211 148560 822705 | Public Works |  | See Lacevine Rd
Riverside Paving |  | 5 | 11 | Inspected | FY22 | Winter 2021 |  | Lacevine Rd from Trumpetvine Rd to Dead End | 2's through 5's | 20000 |  | 9360 | 9360 | 8148 410 8211 148560 822705 | Public Works |  | 191.11 |  |  | R4 8300 Lacevine 8x4 of sw- To be added to future NTP for grinding or replacement.
Riverside Paving | 368756-4 | 4 | 12 | Complete | FY21 | Fall 2021 | January | 7002 URANAS DR | 4 | 1196 |  |  | By Others | 8146 410 8211 148487 822705 | Public Works |  | By others |  |  | 4'x8' of sw and 4'x12' of dw (by others)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 5032 Hunters Point Cir | 4 and 5 | 962.88 |  |  | 0 | 8138 410 8107 148412 822705 | Council District 12 |  | 10.66 |  | 2022-01-01 | 8'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 6208 MOUNT EVEREST DR | 4 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11 |  | 2022-01-01 | 16'x4' and 12'x4' and 12'x4' of sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 7015 BIRNAMWOOD DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.56 |  | 2022-01-01 | 8'x4' of sw plus fill in void adjacent to sw
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | 9612 BROOKS BEND RD | 5 | 996.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  | 2022-01-01 | 6609 Rebecca Lane 4'x52' of sw plus 1 utility, 6608 Rebecca Lane 4'x16' of sw, 6616 Rebecca Lane 4'x28' of sw, 6616 Rebecca Lane 4'x36' of sw,
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | Deady Dr from Dead End to Dead End | 2's through 5's | 20000 |  | See Rebecca Ln | See Rebecca Ln | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln | 2021-01-3 | 2022-01-01 | R4 4'x4' of sw (at 6700 Miller Park Drive)
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | MILLER PARK DR & KENHURST DR | 4 | 14501.5 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 1.89 |  | 2022-01-01 | 6105 Deady Dr. 4'x16' of sw, 6103 Deady Dr. 4'x25' of sw, 6100 Deady Dr. 4'x22' of sw, 6102 Deady Dr. Adj wm, 6104 Deady Dr. 4'x31' of sw, 6202 Deady Dr. 4'x14' of sw,
Riverside Paving | 387121-3 | 4 | 12 | Sent to Contractor | FY22 | Winter 2022 |  | Rebecca Ln from Deady Dr to Dead End | 2's through 5's | 28500 |  | 5778 | 5778 | 8148 410 8211 148560 822705 | Public Works |  | 142.67 |  | 2022-01-01 | 16'x4' and 4'x4' and 4'x4' of sw and 3 trees
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 128 ELK RIVER DR | 5 | 2239.73 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18/21 | Spring 2021 | July | 804 FLICKER RD | 4 | 1324.72 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 ($461) / 8146 410 8211 148487 822705 ($864) | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 8114 ATLANTA PKY | 5 | 140 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY18 | Spring 2021 | July | 9303 Minute Men Ct | 5 | 1283.84 | 1846.55 |  | 1846.55 | 8133 410 8211 148396 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 13 | Complete | FY21 | Spring 2021 | July | 9402 Balance Ln | 5 | 7456.8 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Public Works |  | See 9303 Minute Men Ct
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Auburn Oaks Beveling Project (from New Cut Rd to Dead) | 2's through 4's | 10138.5 |  | 5778 |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St |  |  | 1 R3 5'x8' panel across from 719 Auburn Oaks was not beveled.
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Auburn Oaks from New Cut Rd to Dead End | 2's through 5's | 32000 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Beecher St
TBD | PO applied for | 4 | 13 | Complete | FY22 | Spring 2022 | May | Glengarry Dr from National Turnpike to Gary Way | 2's through 5's | 19500 |  | See Auburn Oaks |  | 8148 410 8211 148560 822705 | Public Works |  | See Rebecca Ln
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 200 ELK RIVER DR | 4,3 | 5049.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x15’ of sw & 4’x17’ of sw, seed and protection
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 211 APPOMATTOX RD | 4 | 5647.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 11.56 |  |  | 4’x26’ of sw, seed and protection.
Riverside Paving | 368756-17 | 4 | 13 | Sent to Contractor | FY22 | Winter 2022 |  | 6013 LARKGROVE DR | 5 | 863.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.78 |  |  | 4'x9’ of sw, seed and protection.
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 5708 Fruitwood Dr | 5 | 458.24 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct |  | 2022-01-01 | R5 4'x46' of sw, 1 utility cover and 1 tree
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6222-6224 Bethany Ln | 5 | 853.84 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6223 Bethany Ln | 4 | 1217.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6300 W Pages Ln | 5 | 1328.27 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 6911 Ethan Allen Way | 4 | 2201.6 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7301-7303 Ethan Allen Way | 4 | 9147.52 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 7513 Wimstock Ave | 5 | 3269.6 | 1846.55 |  | 1846.55 | 8146 410 8211 148487 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 14 | Complete | FY21 | Spring 2021 | July | 8405 Devonshire Dr | 5 | 2344 | 1846.55 |  | 1846.55 | 8146 410 8107 148279 822705 | Council District 14 |  | See 9303 Minute Men Ct
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11500 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11702 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works | 1 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11703 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11707 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11708 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11711 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11712 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11714 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11717 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11719 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11721 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | Address no found
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11800 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11802 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11803 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11805 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11810 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11810-11812 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11814-11812 Pierce Way | 5, 4 | 14879.04 | 22649.39 |  | 22649.39 | 8148 410 8211 148560 822705 | Public Works |  | 104.43 | 2022-01-10 | 2022-02-25 | 27'x4' of sw and 2 utility adj, s/p
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11817-11819 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 11904 Pierce Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 13413 HINCHBROOK BLVD | 4 | 1328.8889 | 24559.45 |  | 24559.45 | 8148 410 8211 148560 822705 | Public Works |  | 158.53 | 2022-01-2 | 2022-02-25 | 13'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 13417 Kinross Blvd | 5 | 3327.92 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 46'x4' of sw, 1 utility adjustment, trim tree roots if needed, s/p
Riverside Paving | 368756-23 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 5711 Chestnutwood Way | 5, 4 | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way |  | See 11814-11812 Pierce Way | 8148 410 8211 148560 822705 | Public Works |  | See 11814-11812 Pierce Way | See 11814-11812 Pierce Way
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 6010 Alanadale Dr |  | 4776 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd.
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 6012 Alanadale Dr | 4 | 2808 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 12'x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY22 | Spring 2022 | June | 7002 Nathan Hale Way | 4 | 2984.96 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 52'x4' of sw, raise the sw to eliminate 2" ponding water at the low spot
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY 22 | Spring 2022 | June | 7014 Ethan Allen Way | 4 | 550.08 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 5'x4' and 42x4' of sw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY 22 | Spring 2022 | June | 7902 NANCY LN | 4 | 3588 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 6'X4' and 6'x4' and 8'x4' of sw and and 9'x5' of dw, s/p
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY 22 | Spring 2022 | June | 7906 NANCY LN | 5 | 1500 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 12'x4' of sw
Riverside Paving | 368756-16 | 4 | 14 | Complete | FY 22 | Spring 2022 | June | 9900 SUNKIST WAY | 4 | 2325.5556 | See 1314 Hinchbrook blvd. |  | See 1314 Hinchbrook blvd. | 8148 410 8211 148560 822705 | Public Works |  | See 1314 Hinchbrook blvd. | See 1314 Hinchbrook blvd. | 2022-02-25 | 27'x4' and 25'x4' and 9'x4' of sw, s/p
|  | 4 | 14 | Complete | FY22 | Spring 2022 | May | 9805 Sun Way Dr | 5 | 366.98 |  |  | By MSD | 8148 410 8211 148560 822705 | Public Works |  | 6.67 |  | 2022-05-22 | MSD repaired the sinkhole and the sidewalk at 9807 and 9805 Sun Way Drive. sr# 5415608 (MSD is placing a camera throuth lateral )
Riverside Paving | 368756-24 | 4 | 14 | Sent to Contractor | FY22 | Spring 2022 |  | 6007 Alanadale Dr | Curb Repair | 4585.07 |  |  | 0 | 8142 410 8107 148279 821344 | Council District 14 |  | 12.42 |  | 2022-02-25 | 33' of curb replacement, s/p
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Cedarwood Dr from Mondamon Dr to Pond Creek Dr | 2's through 5's | 17440 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Fir Ct from Leemont Dr to Dead End | 2's through 5's | 2880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Fruitwood Dr from Leemont Dr to Pond Creek Dr | 2's through 5's | 20480 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Ct from Leemont Dr to Dead End | 2's through 5's | 3680 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Leemont Dr from Deering Rd to Alicante Ln | 2's through 5's | 37032 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Logwood Ave from Leemont Dr to Pond Creek Dr | 2's through 5's | 20800 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | North side of Alicante Ln from Andalee Dr to Leemont Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Pond Creek Dr from Cedarwood Dr to Vevia Pl | 2's through 5's | 10880 |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | South side of Cedarwood Dr from Leemont Dr to Mondamon Dr | 2's through 5's | See Cedarwood Dr from Mondamon Dr to Pond Creek Dr |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | Vevia Pl from Leemont Dr to Pond Creek Dr | 2's through 5's | See Pond Creek Dr from Cedarwood Dr to Vevia Pl |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Precision Concrete Cutting | 381611-15 | 4 | 14 | Sent to Contractor | FY 22 | Spring 2022 |  | West side of Leemont Dr from Alicante Ln to Cedarwood Dr | 2's through 5's | See Leemont Dr from Deering Rd to Alicante Ln |  |  |  | 8148 410 8211 148560 822705 ($48,056) / 8138 410 8107 148279 822705($53,574.14) / 8146 410 8107 148279 822705 ($11,561.86) | Public Works/Council District 14
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1409 Southgate Ave | 4 | 422.4 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell | 2021-01-3
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 1410 Weyler Ave | 5 | 676.8 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | Fy21 | Spring 2021 | July | 1609 Cherry Way | 4 | 412.8 | 1846.55 | 0 | 1846.55 | 8143 410 8211 148472 822705 | Public Works |  | See 9303 Minute Men Ct
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3605 POWELL AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3606 WHEELER AVE | 5 | 4216.6667 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3612 WHEELER AVE | 5 | 2906.9444 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3671 POWELL AVE | 4 | 1661.1111 | 27370.8 | 0 | 27370.8 | 8143 410 8211 148472 822705 | Public Works |  | 162.85
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3703 KAHLERT AVE | 5 | 3053.8889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3710-3712 WHEELER AVE | 5 | 4152.7778 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 3724 WHEELER AVE | 5 | 3801.3889 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY21 | Winter 2021 | July | 530 DRESDEN AVE | 4 | 5111.1111 |  |  | See 3671 Powell | 8143 410 8211 148472 822705 | Public Works |  | See 3671 Powell
TBD | 368756-20 | 4 | 15 | Complete | FY22 | Fall 2021 | March | 1031 NAVAHO PL | 5 | 2206.7222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  | 2021-12-21 | 15'X4' OF SW (REMOVE ROOTS FROM DEAD TREE STUMP ON PRIVATE PROPERTY )
Riverside Paving | 368756-4 | 4 | 15 | Complete | FY22 | Fall 2021 | November | Beecher St Beveling Project (from Warren Ave to Taylor Blvd) | 2's through 4's | 3379.5 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333.78
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1020 Berry Blvd | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  | 2021-12-21 | 5’x16’ of sw; 8’x8’ of dw & 14’ of curb, seed and protection
Riverside Paving | 368756-18 |  | 15 | Sent to Contractor |  | Winter 2022 |  | 1421 Anna Lane |  | 981.79 |  |  |  | See 3418 Powell | Council District 15 |  | 6.22 |  |  | 4'x14' of sw & 4'x10' of dw
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1496 CLARA AVE | 4 | 2491.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.78 |  |  | 5’x15’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1500 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’ of dw, seed and protection.
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1503-1505 Paula Ct | 4 | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 21’x5’of sw & 16’x5’ of sw, seed and protection
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 1506 Hobart Ct | TBD | See 3418 Powell | See 3418 Powell |  | See 3418 Powell | See 3418 Powell | Council District 15 |  |  |  |  | 25’x5’of sw & 10’x5’ of dw, seed and protection
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 221 W ADAIR ST (Next to I-264) | holding water and mud | 4912 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 8 |  |  | 5’x6’ of sw & 5’x6’ of sw & 2’x6’ of sw, seed and protection
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 2431 EMIL AVE | 5 | 5526.3889 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  |  |  | 2021-12-21 | 5'X6' AND 5'X6' OF SW AND 2'X6' OF SW
Riverside Paving | 368756-18 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3418 POWELL AVE | 5 | 4790.49 |  |  | 0 | 8138-410-8107-148233-831532 | Council District 15 |  | 7.22 |  |  | 16’x5’of sw & 15’x5’ of sw, seed and protection ( 3'x'4 courtesy pad at 3416 Powell Ave added to NTP D-15)
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3515 HENRY AVE | 5,2 | 3405.2778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works | 2 | 8.33 |  |  | 5’x15’ of sw; 5’x45’ of sw; 5’x10’ of sw, seed and protection. 4 trees need to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 3705 W WHEATMORE DR | 5 | 2410 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 3.33 |  |  | 5'x6' of sw; 5'x6' of sw; 5'x13’ of sw, seed and protection. 1 tree stump removal & 1 Magnolia tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 4035 WOODRUFF AVE | 4 | 332.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 5'x6' of sw & 5'x6' of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4328 S 2nd St | 5 | 993.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 6.67 |  |  | 4’x20’ of sw, seed and protection.
Riverside Paving | 368756-19 | 4 | 15 | Sent to Contractor | FY21 | Winter 2022 |  | 4400 S 2nd St | Curb Repair | 649.33 |  |  | 0 | 8101 410 8105 148233 822705 / 8101 410 8199 148233 822702 / 8138 410 8205 148915 822705 | Council District 15 |  | 5.33 |  |  | 10’ of paved over curb & Gutter, seed and protection
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 542-546 RAWLINGS ST | 3,4 | 8970 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 19.56 |  |  | 6’x90’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 608 RAWLINGS ST | 3,4 | 8172.6667 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 15 |  |  | 6'x25’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 611 MERWIN AVE | 5 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 0.44 |  |  | 5'x15' of sw; 5'x5' of dw & 5'x10' of dw; 7'x10' of apron, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 613 DUVALL ST | 4 | 1528.2222 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 8.5 |  |  | 5’x40’ of sw; 5’x10’ of dw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 654 N BARBEE WAY | 5 | 1495 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 12.88 |  |  | 4’x21’ of sw; 4’x9’ of sw; 4’x40’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | 664 ATWOOD ST | 4 | 1993.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4 |  |  | 6’x36’ of sw, seed and protection.
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Spring 2022 |  | Beecher St from Warren Ave to Taylor Blvd (Grinding Only is Complete) | 2's through 5's | 50000 |  | 13518 | 13518 | 8148 410 8211 148560 822705 | Public Works |  | 333
Riverside Paving | 368756-20 | 4 | 15 | Sent to Contractor | FY22 | Winter 2022 |  | MERHOFF ST & DUVALL ST | 5 | 7104.4444 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 32.17 |  |  | 5'x35' of sw; 5'x30' of sw (along Merhoof St side of 619 Duvall St), seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
TBD | PO applied for | 4 | 15 | Inspected | FY22 | Summer 2022 |  | West side of Preston Hwy between Locust Ln and Parkway Dr |  | 37259 |  |  | 0 | 8138-410-8107-148233-822702 $15920.38 8133-410-8107-148233-822705 $2,709.12 8148 410 8211 148560 822705 $18,629.50 | Public Works / Council District 15 |  |  |  | 2022-06-01 | The NTP for this sw repair work is ready to be sent to the contractor.
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11202 Deham Dr | 5 | 336.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11215 Deham Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11301 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11303-11305 Deham Dr | 5 | 584.53 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11304-11306 Deham Dr | 5 | 1435.24 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11307 Deham Dr | 5 | 988.23 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11406 Kendrick Dr | 5 | 4940.17 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11408 Kendrick Dr | 5 | 1369.83 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11412 Hammond Dr | 5 | 1761.6 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11414 Kendrick Dr | 5 | 719.03 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11415 Kendrick Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11500 Kendrick Dr | 5 | 538.06 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11504 Kendrick Dr | 5 | 1309.75 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11505-11509 Fisherman Way | 5 | 1813.59 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11506 Kendrick Dr | 5 | 448.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11513 Fisherman Way | 5 | 881.38 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11514 Kendrick Dr | 5 | 403.7 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 11516 Kendrick Dr | 5 | 210.88 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5110 Windy Willow Dr | 5 | 1429.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Baywood Dr | 5 | 201.85 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5204 Windy Willow Dr | 5 | 929.29 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5207 Windy Willow Dr | 5 | 3393.1 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5211 Windy Willow Dr | 5 | 3467.27 | 49112.92 |  | 49112.92 | 8101 410 8105 148234 822705 | Council District 16 |  | 332.23
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5304 Drifton Dr | 5 | 888.27 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5305-5307 Baywood Dr | 5 | 627.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5308 Drifton Dr | 5 | 1831.93 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5311 Drifton Dr | 5 | 2473.37 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5401 Baywood Dr | 5 |  |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5403 Windy Willow Dr | 5 | 1114.94 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5404-5406 Baywood Dr | 5 | 1157.62 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5405 Windy Willow Dr | 5 | 695.96 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5407 Windy Willow Dr | 5 | 1726.32 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5408-5410 Windy Willow Dr | 5 | 973.89 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5410 Baywood Dr | 5 | 224.14 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5412 Lithia Dr | 5 | 1441.84 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5501 Lithia Dr | 5 | 2094.49 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Complete | FY21 | Fall 2021 | December | 5505 Windy Willow Dr | 5 | 134.36 |  |  | See 5211 Windy Willow Dr | 8101 410 8105 148234 822705 | Council District 16 |  | See 5211 Windy Willow Dr
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 10630 Meeting St | 4 | 610.13 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 6.5'x7.5' of sw, seed and protection.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4003 Deer Creek Dr | 4 | 969.33 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-8 | 3 | 16 | Sent to Contractor | FY21 | Winter 2022 |  | 4230 Ashleywood Ct | 5 | 2748.23 |  |  | 0 | 8101 410 8105 148234 822705 | Council District 16 |  |  |  |  | 4'x12' of sw; 4'x12' of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 |  | Chamberlain Lane from Brownsboro Rd to Glasgow blvd | 2's through 5's | 15000 |  | 10048 | 10048 | 8148 410 8211 148560 822705 | Public Works |  | 310
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 |  | North side of Angies Way from Chamberlain ln to Norton Health Care Blvd | 2's through 5's | 7500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
Seven Seas | 368567-11 | 3 | 16 | Sent to Contractor | FY22 | Winter 2022 |  | Norton Health Care Blvd from Brownsboro Rd to Angies Way | 2's through 5's | 22500 |  | See Chamberlain Lane from Brownsboro Rd to Glasgow blvd |  | 8148 410 8211 148560 822705 | Public Works |  | See Chamberlan Way
TBD |  | 3 | 17 | Complete | FY22 | Winter 2021 | December | 3219 WYNBROOKE CIR | 5 | 2472.5 |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | By Others
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13415 FOREST SPRINGS DR | 5 | 3718.3333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | R4 5'X4' and Water valve (R3 5'X4' OF SW block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13419 FOREST SPRINGS DR | 5 | 3552.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13430 FOREST SPRINGS DR | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas |  | 3 | 17 | Complete | FY21 | Summer 2021 | March | 13508 Springs Station Rd | 4 | 900 |  |  | 0 | 8146 410 8211 148317 899998 / 8146 410 8107 148317 899998 | Council District 17 |  |  |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13510 BROKEN BRANCH WAY | 5 | 398.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 12'X4' OF ADA RAMP AND 4'X4' OF SW, and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13512 BROKEN BRANCH WAY | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' AND 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13520 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13606 BROKEN BRANCH WAY | 5 | 2524.8889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 14'X4' OF SW 1-ADA Ramp and Asphalt to repair pavement
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13607 BROKEN BRANCH WAY | 5 | 996.6667 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 13700 BROKEN BRANCH WAY | 5 | 830.5556 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 6'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3610 ROCK BAY DR | 4 | 1245.8333 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 4'X4' OF SW (1-R3 5'x4' of sw block repair)
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 9'X4' AND 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3700 WOODED SPRINGS CT | 5 | 930.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3707 ROCK BAY DR | 4 | 3386.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3710 CYPRESS SPRINGS PL | 5 | 1528.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 4'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3724 CYPRESS SPRINGS PL | 4 | 332.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' AND 5'X4' AND 9'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3801 BUGLEWOOD PL | 5 | 3136.9444 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 13'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3809 ROCK BAY DR | 4 | 581.3889 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3814 ROCK BAY DR | 4 | 1827.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4'of SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 3915 ROCK BAY DR | 5 | 1661.1111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW and
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4002 ROCK BAY DR | 5 | 913.6111 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 10'X4' OF SW
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 4010 ROCK BAY DR | 5 | 747.5 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 5'X4' OF SW and straight cut roots only as necessary.
Seven Seas | 368567-4 | 3 | 17 | Complete | FY22 | Winter 2022 | March | 9603 MOORFIELD CIR | 4 | 332.2222 | 19391.51 |  | 19391.51 | 8148 410 8211 148560 822705 | Public Works |  | 105.67 |  |  | 12'X4' OF SW BY OTHERS
Seven Seas | 368567-6 | 3 | 17 | Complete | FY22 | Winter 2021 | March | 13408 FOREST SPRINGS DR | 5 | 2057.2222 |  |  | See 9603 MOORFIELD CIR | 8148 410 8211 148560 822705 | Public Works |  | See 9603 MOORFIELD CIR |  | 2022-12-21 | 7'X4' OF SW, Straight cut roots
TBD |  | 3 | 18 | Complete | FY22 | Winter 2021 | March | 2817 ENGLEWOOD AVE | 5 | 2242.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44
Seven Seas | 368567-10 | 3 | 18 | Sent to Contractor | FY 22 | Winter 2022 |  | 10403 Sterling Springs Rd |  | 2283.41 |  |  | 0 | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 4’x8.5' of sw, seed and protection.
Seven Seas | 368567-17 | 3 | 18 | Inspected | FY 22 | Spring 2022 |  | 1917 Arboro Place | 4 | 4000 |  |  | 0 | 8148-410-8211-148560-822705($2900)/8102-410-8105-148267-822705($1250) | Public Works/Council District 18 |  |  |  |  | 10'x4' of dw; 4'x4' of sw; 1 tree(private), seed and protection
Seven Seas | 368567-10 | 3 | 18 | Sent to Contractor | FY 22 | Winter 2022 |  | 4429 Rockwood Dr | 4 or 5 | 1359.6 |  |  | 0 | 8102-410-8105-148267-822705 | Council District 18 |  |  |  |  | 2.5'x4.5' of sw; 9'x9.5' of dw, seed and protection.
Seven Seas | 368567-12 | 3 | 18 | Sent to Contractor | FY22 | Spring 2022 |  | Browns Ln from Lowe Rd to Greathouse/Shyrock Trad Elementery | 2's through 5's | 30000 |  | 7375 | 7375 | 8148 410 8211 148560 822705 | Public Works |  | 227
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 12403 Hersfield Rd | 4 | 3029 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368567-7 |  | 19 | Complete | FY 22 | Spring 2022 | February | 125 Waterstone Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1335 Heafer Rd | 5 | 1083.37 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1337 Heafer Rd | 5 | 2093 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 1340 Heafer Rd | 4 | 6518.89 |  |  | See 610 Woodlake | 8138 410 8107 148963 822705 ($10,860.75) / 8102 410 8105 148963 822705 ($1,420.25) | Council District 19 |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14008 CROSSBRANCH CT | 4 | 1702.27 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14202 LAKE FOREST DR | 4 | 764.53 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 10'x4 of sw, seed and protection
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 14306 LAKE FOREST DR | 4 | 1085.15 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake |  |  | 10'x4' and 25'x4 of sw, seed and protection
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 14313 Micawber Way | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr |  |  | 36'x4', 10'x4' and 25'x4 of sw, seed and protection, retain tree, bridge roots tripstop
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 15109 Abington Ridge Pl | 5 | See 17106 Mallet Hill |  |  | See 17106 Mallet Hill Dr | 8102 410 8105 148963 822702 | Council |  | See 17106 Mallet Hill Dr
Seven Seas | 368567-7 | 5 | 19 | Complete | FY 22 | Spring 2022 | February | 17106 Mallet Hill Dr | 5 | 12079.26 |  |  | 15681.79 | 8102 410 8105 148963 822702 | Council |  | 106.09
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 17204 MALLET HILL DR | 4 | 520 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
| 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 2213 ARNOLD PALMER BLVD | 4 | 4422.13 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY17 ($3,347) / FY18 ($11,202) / FY19 ($22,252) | Fall 2021 | February | 311 Lake Forest Pky | 4 | 1674 |  |  | See 610 Woodlake | 8101 410 8211 148933 822705 / 8133 410 8211 148396 822705 / 8137 410 8211 148452 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 504-506 EDGEFOREST PL | 4 | 6016.8 | 4177.68 |  | 4177.68 | 8146 410 8211 148487 822705 | Public Works |  | 14
Seven Seas |  | 5 | 19 | Complete | FY21 | Fall 2021 | February | 505 EDGEFOREST PL | 4 | 3159 |  |  | See 504 Edgeforest | 8146 410 8211 148487 822705 | Public Works |  | 6.2222
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 610 WOODLAKE DR | 5 | 10437.73 | 28176.24 |  | 28176.24 | 8146 410 8211 148487 822705 | Public Works |  | 192
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | February | 612 WOODLAKE DR | 5 | 9381.95 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
TBD | 368569-4 | 5 | 19 | Complete | FY22 | Winter 2021 | February | STURBRIDGE PL & STURBRIDGE CIR | 5 | 747.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
TBD |  | 5 | 19 | Complete | FY22 | Winter 2021 | March | 15105 MEADOW FARMS CT | 4 | 730.8889 |  |  |  | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 17108 MALLET HILL DR | 5 | 1202.57 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 412-414 LAKE FOREST PKY | 4 | 2092.4 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
Seven Seas | 368569-4 | 5 | 19 | Complete | FY21 | Fall 2021 | March | 509 EDGEFOREST PL | 4 | 233.33 |  |  | See 610 Woodlake | 8146 410 8211 148487 822705 | Public Works |  | See 610 Woodlake
|  | 5 | 19 | Complete | FY19 | Fall 2021 | March | D19 Berrytown Rd Sidewalk Repair Project |  | 4638 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  |  |  |  | This was completed in 2019
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 11007 FOX MOORE PL | 5,2 | 1262.4444 | 9527.25 |  | 9527.25 | 8148 410 8211 148560 822705 | Public Works |  | 17.09 | 121162M-09 | 2022-05-01 | 4’x6’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 14611 LAKE BLUFF PL | 4 | 531.5556 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x4’ of sw, seed and protection
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 803 FOXGATE RD | 4 | 3053.8889 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x8’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-11 | 5 | 19 | Complete | FY22 | Winter 2022 | May | 836 LAKE FOREST PKWY | 4 | 2691 | See 11007 FOX MOORE PL |  | See 11007 FOX MOORE PL | 8148 410 8211 148560 822705 | Public Works |  | See 11007 FOX MOORE PL | See 11007 FOX MOORE PL | 2022-05-01 | 4’x18’ of sw, seed and protection
Seven Seas | 368569-12 | 5 | 19 | Complete | FY22 | Winter 2021 | May | Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 2's through 5's | 15840 | 4535.39 | 8986 | 19307.01 | 8148 410 8211 148560 822705 | Public Works |  | 315.14 | 121162M-07 | 2022-05-01 | 6'x4' of sw across from 315 Evergreen Rd, replace 10'x4' ramp, and 7' of curb and replace 2-4'x4' sections of sw on Evergreen Rd. side of 12017 Shelbyville Rd.
Seven Seas | 368569-12 | 5 | 19 | Complete | FY22 | Winter 2022 | May | S Beckley Station Rd from Shelbyville Rd to Dead End | 2's through 5's | 15000 | 5785.62 | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 8148 410 8211 148560 822705 | Public Works |  | See Evergreen Rd from Weatherby Ave to Old Shelbyville Rd | 121162M-08 | 2022-05-01
TBD |  | 5 | 20 | Complete | FY22 | Winter 2021 | April | 3106 SHADY SPRINGS DR | 5 | 598 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  | 2022-05-01 | Completed
TBD |  | 5 | 20 | Complete | FY22 | Spring 2022 | April | 6515 Calm River Way | 5 | 586.67 |  |  | 0 | 8102 410 8105 148837 822705 | Council District 20 |  |  |  | 2022-02-01 | no issue observed
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 10417-10419 Pinoak View Dr | 5 | 4024.32 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 11109-11111 Little Spring Blvd | 4 | 3815.69 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 2.8889
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 13909-13911 Laclara Way |  | 2552.3 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 9.3333
|  | 5 | 20 | Complete | FY21 | Spring 2021 | August | 4010 Stone Lakes Dr | 4 | 2323 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 3.5556
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 4015 Stone Lakes Dr | 4 | 1506.97 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 8800 Sanctuary Ln | out of compliance sidewalk ramp |  |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5
|  | 5 | 20 | Complete | FY19 | Spring 2021 | August | 9818 Stanalouise Dr | 5 | 1032.08 |  |  | 0 | 8137 410 8211 148452 822705 | Public Works |  | 5.3333
Seven Seas | 368569-4 | 5 | 20 | Complete | FY22 | Winter 2022 | February | 14304 MICAWBER WAY | 5 | 2127.5 |  |  | See 610 Woodlake | 8148 410 8211 148560 822705 | Public Works |  | See 610 Woodlake
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11804 LONGVIEW FARM DR | 4 | 797.3333 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 4.44 |  |  | Completed
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 11906 LONGVIEW FARM DR | 4 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | CONCRETE SPALLING
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12000 LONGVIEW FARM DR | 5 | 531.5556 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  |  |  |  | 8'X4' OF SW
Seven Seas |  | 5 | 20 | Complete | FY22 | Winter 2021 | March | 12004 LONGVIEW FARM DR | 5 | 531.5556 |  |  |  | 8148 410 8211 148560 822705 | Public Works |  | 3.11 |  | 2022-01-22 | R5 36'X4' , 10'x4' and 10'X4' OF SW hinged joints for 1 tree, seed and protection. Curve out sidewalk as much as possible. Straight cut roots as needed. Use TripStop.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 11012 Perwinkle Ln | 4 | 264 | 45054.99 |  | 45054.99 | 8102 410 8105 148837 822705 | Council District 20 |  | 169.33 | 121162M-06 | 2022-05-01 | 4.5’x4’ of sw & 4’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 114 Wickfield Dr | 5 | 2567.07 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 5’x4’ of sw & 15’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13602 Meadow Vista Ct | 5 | 1182.4 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 10’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13604 Meadow Vista Ct | 3 | 1976.57 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 4.5’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13608 Meadow Vista Ct | 4 | 2269.72 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 12’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13610 Meadow Vista Ct | 5 | 2270 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 17’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13615 Meadow Vista Ct | 5 | 2622 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 15.5’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13700-13701 Willow Reed Dr | 4 | 1920.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 5’x4’of sw & 10’x4’ of sw; 1 utility adj., seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13702 Willow Reed Dr | 5 | 2066.57 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 14’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13705 Willow Reed Dr | 5 | 2269.72 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 8’x4’of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13809 Round Top Pl | 4 | 293.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9.5’x4’of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 13811 lakemont Ct | 4 | 473.07 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 14107 Glendower Dr | 4 | 7692.4 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 14’x4’ of sw & 12’x4’ of sw, seed and protection. 3 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 14601 Landis Lakes Dr | 5 | 2448.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 4’x4’ of sw & 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 200 Wickfield DR | 5 | 1918 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 18’x4’ of sw & 21’x4’ of sw & 5’x4’ of sw, seed and protection. 2 trees need to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 303 Wickfield Dr | 4 | 586.67 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 20’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4004 Saratoga Woods Dr | 4 | 882.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 15’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4026 Pleasant Glen Dr | 4 | 2622 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 9’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4504 Stone Lakes Dr | 5 | 882.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 17.5’x4’ of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 4517 Saratoga Woods Dr | 4 | 6216.8 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln |  | 16’x4’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 505 Wickfield Dr | 5 | 2875.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 4’x6’ of sw & 4’x11’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 615 Wickfield DR | 4 | 2991.33 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 4’x4’ of sw & 4’x18’ of sw, seed and protection. 1 tree needs to be inspected; we are awaiting recommendations from the arborist.
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 6530 Calm River Way | 4 | 1056 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 6’x4’ of sw & 11’x4 of sw, seed and protection
Seven Seas | 368569-10 | 5 | 20 | Complete | FY22 | Spring 2022 | May | 6726 Calm River Way | 4 | 646.27 | See 11012 Perwinkle Ln |  | See 11012 Perwinkle Ln | 8102 410 8105 148837 822705 | Council District 20 |  | See 11012 Perwinkle Ln | See 11012 Perwinkle Ln | 2022-02-22 | 14’x4’ of sw, seed and protection
Seven Seas | 368569-13 | 5 | 20 | Complete | FY22 | Spring 2022 | May | Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2's through 5's | 50000 | 41401.75 | 16911 | 63042.25 | 8148 410 8211 148560 822705 | Public Works | 3 | 622.75 | 121162M-10 | 2022-05-01 | The LWC SR # is 1786143959 at 9704 Mary Dell Lane. The MSD SR # is 5415539 at 9920 Mary Dell Lane. I contacted Jason Tipton about the LGE transformer adj. at 9814 Mary Dell Lane.
Riverside Paving | 368756-4 | 4 | 21 | Complete | FY21 | Summer 2021 | July | 223 Iroquios Ave | 4 | 2323 | 72 |  | 72 | 8146 410 8211 148487 822705 | Public Works |  | 1
Riverside Paving | 368756-26 | 4 | 21 | Sent to Contractor | FY22 | Spring 2022 |  | S 3rd St from Waterson Underpass to W Woodlawn Ave | 2's through 5's | 85000 |  | 20061 | 20061 | 8148 410 8211 148560 822705 | Public Works |  | 636 |  |  | 4450 S 3rd St-"Looks like an MCI vault.. I’ll take care of it." By Andrews, Al. Hole forming under sw at 223 W. Woodlawn Ave-sent to Clyde, Barry (PW Operations Administrator) to investigate
|  | 4 | 21 | Not Inspected | FY18 | Spring 2021 |  | TBD |  | 6561.32 |  |  | 0 | 8133 410 8111 148322 822705 ($4669.78) / 8133 410 8107 148322 822705 ($1,891.54) | Council District 21
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 10104 RIMFIRE RD | 5 | 797.3333 | 24425.28 |  | 24425.28 | 8148 410 8211 148560 822705 | Public Works |  | 101.7 | 121162M-05 | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11201 Meadow Breeze Ln | 4 | 489.18 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 11410 Wind Haven Way | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 3816 GREENWICH WAY | 4 | 1063.1111 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of sw
|  | 5 | 22 | Complete | FY22 | Winter 2021 | April | 5807 BUCKS LN | 4 | By others |  |  | By others | 8148 410 8211 148560 822705 | Public Works |  | 4 |  | 2022-01-22 | 9'x4' of sw Addressed by lge
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6217 HINES MILL WAY | 5 | 265.7778 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 8'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY22 | Winter 2022 | April | 6416 MOSSY OAKS DR | 4 | 730.8889 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 11'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7507 Kendrick Crossing Ln | 4 | 910.4 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7600 Hornbeck Farm Rd | 5 | 782.86 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 17’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7802 Windgate Dr | 5 | 268.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 4’x4’ of sw & 18’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7804 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw & 6’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7812 Windgate Dr | 5 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 5’x4’ of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7821 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 9'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7901 Windgate Dr | 5 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7907 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Niemann Dr | 4 | 195.89 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7909 Windgate Dr | 4 | 586.97 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7912 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 10x4 of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7913 Windgate Dr | 4 | 832.17 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw and 5'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7916 Windgate Dr | 3 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 6.58 |  | 2022-02-23 | No R4 or R5 issues observed during the February 2022 inspection
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7917 Windgate Dr | 4 | 293.83 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 12'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7919 Windgate Dr | 4 | 489.03 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 15'x4' of sw
Seven Seas | 368569-9 | 5 | 22 | Complete | FY21 | Fall 2021 | April | 7920 Windgate Dr | 4 | 244.51 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | See 10104 RIMFIRE RD | See 10104 RIMFIRE RD | 2022-02-23 | 6'x4' of SW
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3806 GREENWICH RD | 4 | 1794 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 12
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3811 GREENWICH RD | 4 | 2401.57 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 3812 GREENWICH RD | 5 | 2392 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 4
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 5803 BUCKS LN | 4 | 6141 |  |  | 0 | 8146 410 8211 148487 822705 | Public Works |  | 18
|  | 5 | 22 | Complete | FY21 | Spring 2021 | August | 6016 Mercury Dr | 5 | 1223.33 |  |  | 0 | 8102 410 8105 148838 822705 | Council District 22 |  | 8.22
TBD |  | 5 | 22 | Complete | FY22 | Winter 2021 | March | MAJOR LN & GLENWAY PL | 5 | 448.5 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 2.67 |  |  | No R4 or R5 issues observed during the March 2022 inspection
Seven Seas | 368569-13 | 5 | 22 | Complete | FY22 | Spring 2022 | May | East side of Fairground Rd from Plumwood Rd to Hudson Ln | 2's through 5's | 45000 | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 4729.5 | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 8148 410 8211 148560 822705 | Public Works | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | See Mary Dell Ln from Billtown Rd to Sprigwood Ln | 2021-01-5 and 1097 (2nd Invoice was for Triumph) | 2022-12-21
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6707 VANDRE AVE | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 6711 VANDRE AVE | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7802 APPLEVIEW LN | 5 | 8000 |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | 38.99
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7818 APPLEVIEW LN | 3,4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 7820 APPLEVIEW LN | 4 |  |  |  | See 8218 Vaughn Mill Rd | 8146 410 8211 143058 899998 | Council District 23 |  | See 7802 Appleview
Riverside Paving | 368756-4 | 4 | 23 | Complete | FY21 | Summer 2021 | August | 8218 VAUGHN MILL RD | 4 | 7109.56 | 7885.46 |  | 7885.46 | 8146 410 8211 148487 822705 | Public Works |  | 47.55
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7208-7210 Quindero Run Rd | 5 | 733.76 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 7.56 |  |  | 4’x17’ of sw, seed and protection
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7213 Quindero Run Rd | 5 | 550.4 |  |  |  | 8137-410-8211-148560-822705 | public Works |  | 4.89 |  |  | 4’x11’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor |  | Winter 2022 |  | 7226-7228 Quindero Run Rd | 5 | 917.33 |  |  |  | 8137-410-8211-148560-822705 | Public Works |  | 3.56 |  |  | 4'x8’ of sw, seed and protection.
Riverside Paving | 368756-21 | 4 | 23 | Sent to Contractor | FY22 | Winter 2022 |  | 8214 Happiness Way | 5 | 5112.44 |  |  | 0 | 8148 410 8211 148560 822705 | Public Works |  | 30.22 |  | 2022-12-21 | 4'x54’ of sw & 4'x14’ of sw, seed and protection.
Riverside Paving | 368756-27 | 4 | 23 | Sent to Contractor | FY22 | Spring 2022 |  | West side of Smyrna Pkwy from E Manslick Rd to Applegate ln | 2's through 5's | 55000 |  | 4171 | 4171 | 8148 410 8211 148560 822705 | Public Works |  | 137 |  | 2022-05-22 | 8202 Carmel Village Pl, 9x4 and 8x4 of sw and 2 trees (private) 8200 Carmel Village Pl, 8x4 of sw and 1 tree (private), 8208 Smyrna Parkway 13x4 of sw and 5x4 of sw and 1 utility
Riverside Paving |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | 5204 MONACO DR | 5 | 996.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  | 2022-12-21 | 21'X4' OF SW
Riverside Paving |  | 4 | 24 | Complete | FY22 | Winter 2021 | December | SHEPHERDSVILLE RD & CLEARWATER FARM BLVD | 5 | 697.6667 |  |  | By Others | 8148 410 8211 148560 822705 | Public Works |  | By Others |  |  | No R4 or R5 issues observed during the Jan 2022 inspection
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 7832 BRIDLEWOOD PL | 4 | 1328.8889 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | 37.32 |  |  | 4'x12' and 4'x7' and 4'x3' and 4'x4' of sw and 25" tree
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY21 | Fall 2021 | February | 8603 Timber Hollow Ct | 4 | 1727.56 |  |  | See 8918 Elmcreek | 8146 410 8211 148487 822705 | Public Works |  | See 7832 Bridlewood PL |  |  | 4'x11' of sw and remove tree stump
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8708 SHEPHERDSVILLE RD | 4 | 3189.3333 |  |  | See 8918 Elmcreek | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL |  | 2022-12-21 | 48'X4' OF Asphalt SW, straight cut roots as needed
Riverside Paving | 368758-1 | 4 | 24 | Complete | FY22 | Winter 2022 | February | 8918 ELMCREEK DR | 4 | 3053.8889 | 3824 |  | 3824 | 8148 410 8211 148560 822705 | Public Works |  | See 7832 Bridlewood PL
Riverside Paving | 368756-28 | 4 | 24 | Sent to Contractor | FY 22 | Spring 2022 |  | Maplecreek Dr. from Old S. Park Rd. to Bonaventure Blvd. | 5 | See Willowcreek Dr. |  | See Willowcreek Dr. |  | 8148 410 8211 148560 822705 | Public Works |  | See Willowcreek Dr. |  | 2022-05-22 | 8802 and 8808 Maplecreek drive does not have a sidewalk. There is not repair funds available at this time to construct new sidewalks at these addresses.
Riverside Paving | 368756-28 | 4 | 24 | Sent to Contractor | FY 22 | Spring 2022 |  | WillowCreek Drive from Old South Park Rd to Bonaventure Blvd. | 5 | 37500 |  | 15831 | 15831 | 8148 410 8211 148560 822705 | Public Works |  | 390 |  | 2022-03-22 | 8902 Willowcreek Drive- Property owner stopped Precision Concrete from completing the beveling work along the sidewalk in front of the house.
Riverside Paving | 368756-29 | 4 | 25 | Sent to Contractor | FY 22 | Winter 2022 |  | Stone Wynde Dr from Valley College Dr to E Pages Ln | 5 | 25000 |  | 6691.5 | 6691.5 | 8148 410 8211 148560 822705 | Public Works
Seven Seas | 368567-13 | 4 | 26 | Complete | FY22 | Spring 2022 | May | Rio Rita Ave from Goldsmith Ln to Comander Dr. | 5 | 40000 | 44214.8 | 15315 | 59529.8 | 8148 410 8211 148560 822705 | Public Works |  | 472 | 121061M-14 | 2022-05-01 | Add 13'x5' of sw 3012 Boaires Ln to rio rita NTP
vault top in sw - contact property owner
Note on E45: Muhanuka, Thierry P.: NTP is ready to be sent out to contractor. We just waiting for them to catchup with the work they got now. Or will be sent to Joash during FY23. Still need to apply for PO
Note on E46: Muhanuka, Thierry P.: NTP is ready to be sent out to contractor. We just waiting for them to catchup with the work they got now. Or will be sent to Joash during FY23. Still need to apply for PO
Note on E419: Muhanuka, Thierry P.: NTP is ready to be sent out to contractor. We just waiting for them to catchup with the work they got now. Or will be sent to Joash during FY23. Still need to apply for PO

## Key
Color Key
Complete
Pending Issue (funding or utility conflict)
Beveling complete, need to complete full depth replacement where necessary