## July 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  | FY 23 |  |  |  | Bridwell Dr | Kaufman Ln | Dead End | 30.6881 | 1 | Local | [13 empty] | 1 |  |  |  | 100503 |  |  | Public Works | [16 empty] | 2965.84 | 19 | 55835.26 | 0.90616
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Virginia Ave | Wilson Ave | 30.1848 | 1 | Local | [13 empty] | 14 |  |  |  | 155020 |  |  | Public Works | [15 empty] | Speed Humps and rail crossing | 2421.8757 | 35.25 | 86122.4396 | 1.3977
|  |  |  | FY 23 |  |  |  | D1 Paving |  |  |  | 1 | [18 empty] | 40000 |  |  | Council | [19 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | Dead End (east) | 22.533 | 1 | Local | [13 empty] | 6 |  |  |  | 23711 |  |  | Public Works | [15 empty] | Looks like an alley. Base Failures likely | 1061.01 | 12.6667 | 13172.86 | 0.21378
| Hall |  |  | FY 23 |  |  |  | Farnsley Rd (west) | Cane Run Rd | Dead End | 37.2527 | 1 | Local | [13 empty] | 2 |  |  |  | 41202 |  |  | Public Works | [15 empty] | Narrows at dead end. Look to possibly add Zoeller and Van Winkle to Paving | 1321.12 | 17 | 22889.77 | 0.37148
| Hall |  |  | FY 23 |  |  |  | Greenwood Ave | S 26th St | S 29th St | 29.2162 | 1 | Local | [13 empty] | 8 |  |  |  | 100582 |  |  | Public Works | [15 empty] | alley just west of S 28th | 1582.87 | 35.5 | 55879.08 | 0.90687
| Hall |  |  | FY 23 |  |  |  | Mary Rose Dr | Bridwell Dr | Lencott Dr | 51.4364 | 1 | Local | [13 empty] | 0 |  |  |  | 27007 |  |  | Public Works | [15 empty] | Likely illegal driveway at Wilkie, but leave it alone | 759.69 | 20 | 15003.7 | 0.2435
| Hall |  |  | FY 23 |  |  |  | Ronald Ct | Cane Run Rd | Dead End | 37 | 1 | Local | [13 empty] | 2 |  |  |  | 12907 |  |  | Public Works | [15 empty] | Possible base failure | 358.54 | 20 | 7170.8 | 0.11638
| Hall |  |  | FY 23 |  |  |  | S 31st St | Southern Ave | Dr William G Weathers Dr | 30.9738 | 1 | Local | [13 empty] | 12 |  |  |  | 62558 |  |  | Public Works | [15 empty] | do not repalce east sidewalk median on weathers where bump out is | 1579.74 | 22 | 34754.28 | 0.56403
| Hall |  |  | FY 22 |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  | FY 22 |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  | FY 22 |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  | FY 23 |  |  |  | Van Winkle Dr | Cane Run Rd | Dead End | 90 | 1 | Local | [13 empty] | 0 |  |  |  | 48286 |  |  | Public Works | [15 empty] | Check to see if this needs to be paved |  |  | 26825 | 0.43535
| Hall |  |  | FY 23 |  |  |  | Woodland Ave | Olive St | S 32nd St | 19.9396 | 1 | Local | [13 empty] | 21 |  |  |  | 144319 |  |  | Public Works | [16 empty] | 2380.0935 | 33.4286 | 80177.1976 | 1.3012
| Hall |  |  | FY 23 |  |  |  | Zoeller Ave | Farnsley Rd | Van Winkle Dr | 48 | 1 | Local | [13 empty] | 0 |  |  |  | 11885 |  |  | Public Works | [18 empty] | 6603 | 0.10716
| Hall |  | 350002-536 | FY 22 |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 88144.05 | [17 empty] | LWC main replacement, LPA project | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  | FY 23 |  |  |  | Ayars Ct | Lambert Ave | Dead End | 11 | 2 | Local | [13 empty] | 0 |  |  |  | 12440.52 |  |  | Public Works | [16 empty] | 345.57 | 20 | 6911.4 | 0.11217
| Hall |  |  | FY 23 |  |  |  | Bartholomew Dr | Lambert Ave | Dead End | 62 | 2 | Local | [13 empty] | 0 |  |  |  | 16778.949 |  |  | Public Works | [15 empty] | Don’t update ramps at end of roaday | 462.23 | 22 | 10169.06 | 0.16503
| Hall |  |  | FY 23 |  |  |  | Beechbrook Rd | Kranet Way | Norfolk Dr | 38.6177 | 2 | Local | [13 empty] | 0 |  |  |  | 26909.712 |  |  | Public Works | [16 empty] | 622.91 | 24 | 14949.84 | 0.24262
| Hall |  | 350002-536 | FY 22 |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [17 empty] | LWC main replacement, LPA project | 674 | 24 | 14370 | 0.23321
| Hall |  |  | FY 23 |  |  |  | Bunche Ct | Ellington Ave | Dead End | 64 | 2 | Local | [13 empty] | 0 |  |  |  | 7492.176 |  |  | Public Works | [16 empty] | 173.43 | 24 | 4162.32 | 0.067551
| Hall |  |  | FY 23 |  |  |  | Ellington Ave | Stokes Ct | Petersburg Rd | 46.0801 | 2 | Local | [13 empty] | 8 |  |  |  | 93178.512 |  |  | Public Works | [16 empty] | 1437.94 | 36 | 51765.84 | 0.84011
| Hall |  |  | FY 23 |  |  |  | Exeter Ave | E Indian Trl | Stokes Ct | 19.8519 | 2 | Local | [13 empty] | 12 |  |  |  | 92320.56 |  |  | Public Works | [15 empty] | 2 bar walks at school which should go back. Do not add ramp at shared use path | 1424.7 | 36 | 51289.2 | 0.83238
| LP |  |  | FY 23 |  |  |  | Fegenbush Ln | Bardstown Rd | Fern Valley Rd | 55.6081 | 2 | Min Art | [13 empty] | 16 |  |  |  | 938271.8611 |  |  | Public Works | [16 empty] | 9572.4106 | 47.8182 | 481165.057 | 7.8089
| Hall |  |  | FY 23 |  |  |  | Heller St | Buechel Bank Rd | Dead End | 20 | 2 | Local | [13 empty] | 0 |  |  |  | 94402.764 |  |  | Public Works | [16 empty] | 2280.26 | 23 | 52445.98 | 0.85115
| Hall |  |  | FY 23 |  |  |  | Kilgore Ct | Exeter Ave | Dead End | 39 | 2 | Local | [13 empty] | 0 |  |  |  | 15129.504 |  |  | Public Works | [16 empty] | 350.22 | 24 | 8405.28 | 0.13641
| Hall |  |  | FY 23 |  |  |  | Lambert Ave | Buechel Bank Rd | Beechbrook Rd | 25.1893 | 2 | Local | [13 empty] | 9 |  |  |  | 79433 |  |  | Public Works | [15 empty] | Speed Humps | 1922.24 | 23 | 44129.26 | 0.71618
| Hall |  |  | FY 23 |  |  |  | Lambert Ct | Lambert Ave | Dead End | 54 | 2 | Local | [13 empty] | 0 |  |  |  | 14204 |  |  | Public Works | [16 empty] | 438.4 | 18 | 7891.2 | 0.12807
| Hall |  |  | FY 23 |  |  |  | Landing Dr | Lambert Ave | Norfolk Dr | 55 | 2 | Local | [13 empty] | 0 |  |  |  | 20582.208 |  |  | Public Works | [15 empty] | Include little dead end seciton just northof norfolk | 476.44 | 24 | 11434.56 | 0.18557
| Hall |  |  | FY 23 |  |  |  | Norbrook Dr | Fegenbush Ln | Dead End | 54.7966 | 2 | Local | [13 empty] | 2 |  |  |  | 56620.872 |  |  | Public Works | [16 empty] | 1123.43 | 28 | 31456.04 | 0.5105
| Hall |  |  | FY 23 |  |  |  | Norfolk Dr | Fegenbush Ln | Landing Dr | 18.9326 | 2 | Local | [13 empty] | 1 |  |  |  | 67012.92 |  |  | Public Works | [15 empty] | Believe this section of roadway includes base failures | 1431.9 | 26 | 37229.4 | 0.6042
| Hall |  |  | FY 23 |  |  |  | Sanford Ave | Buechel Bank Rd | Lambert Ave | 53 | 2 | Local | [13 empty] | 4 |  |  |  | 59871.798 |  |  | Public Works | [16 empty] | 1583.91 | 21 | 33262.11 | 0.53982
| Hall |  |  | FY 23 |  |  |  | Stokes Ct | Ellington Ave | Dead End | 46 | 2 | Local | [13 empty] | 0 |  |  |  | 15148.08 |  |  | Public Works | [16 empty] | 350.65 | 24 | 8415.6 | 0.13658
| Hall |  |  | FY 23 |  |  |  | Tubman Ct | Ellington Ave | Dead End | 25 | 2 | Local | [13 empty] | 0 |  |  |  | 7706.88 |  |  | Public Works | [16 empty] | 178.4 | 24 | 4281.6 | 0.069487
| Hall |  |  | FY 23 |  |  |  | Wheatley Ct | Exeter Ave | Dead End | 66 | 2 | Local | [13 empty] | 0 |  |  |  | 19063.2829 |  |  | Public Works | [16 empty] | 441.2797 | 24 | 10590.7127 | 0.17188
| Hall |  |  | FY 23 |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [13 empty] | Done |  |  |  | 67784.6 | Cost in FY 22 | June | Public Works | [16 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  |  | FY 23 |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [13 empty] | Done |  |  |  | 31238.7 | Cost in FY 22 | june | Public Works | [16 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [13 empty] | Done |  |  |  | 28873.4 | Cost in FY 22 | June | Public Works | [16 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall |  |  | FY 23 |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [13 empty] | Done |  |  |  | 50573.4 | Cost in FY 22 | June | Public Works | [16 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Wilson Ave | Dead End (south) | 29.2907 | 3 | Local | [13 empty] | 6 |  |  |  | 54951.192 |  |  | Public Works | [16 empty] | 984.82 | 30.6667 | 30528.44 | 0.49545
| Hall |  |  | FY 23 |  |  |  | Hardesty Ave | Dixie Hwy | S 23rd St | 23 | 3 | Local | [13 empty] | 0 |  |  |  | 42265.4 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1514.8574 | 18.0004 | 27268 | 0.44254
| Hall |  |  | FY 23 |  |  |  | Hemlock Ct | W Gaulbert Ave | Dead End | 56 | 3 | Local | [13 empty] | 0 |  |  |  | 9432 |  |  | Public Works | [16 empty] | 187 | 28 | 5240 | 0.085041
| Hall |  |  | FY 23 |  |  |  | Olive St | W Gaulbert Ave | Dead End | 55 | 3 | Local | [13 empty] | 0 |  |  |  | 16247.52 |  |  | Public Works | [16 empty] | 300.88 | 30 | 9026.4 | 0.14649
| Hall |  |  | FY 23 |  |  |  | Plantation Dr | Wingfield Ln | Millers Ln | 42.7091 | 3 | Local | [13 empty] | 0 |  |  |  | 42614.15 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1527.3899 | 18 | 27493 | 0.44619
| Hall |  |  | FY 22 |  |  |  | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [18 empty] | On Hold |  |  |  | 0
| Hall |  |  | FY 22 |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [18 empty] | On Hold | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  |  | FY 23 |  |  |  | S 28th ST | W Gaulbert Ave | Dead End | 51 | 3 | Local | [13 empty] | 0 |  |  |  | 10071.828 |  |  | Public Works | [16 empty] | 215.21 | 26 | 5595.46 | 0.090809
| Hall |  |  | FY 23 |  |  |  | W Gaulbert Ave | Cypress St | Wilson Ave | 35.2883 | 3 | Local | [13 empty] | 9 |  |  |  | 79050.6 |  |  | Public Works | [16 empty] | 1631.47 | 26.8 | 43917 | 0.71273
| Hall |  | 350002-571 | FY 22 |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 141383.01 | July | [17 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-571 | FY 22 |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | July | [17 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  |  | FY 23 |  |  |  | Guthrie St | S 2nd St | S 3rd St | 17 | 4 | Local | [13 empty] | Done |  |  |  | 31156.488 | Cost in FY 22 | June | Public Works | [16 empty] | 480.81 | 36 | 17309.16 | 0.28091
| Hall |  |  | FY 23 |  |  |  | Benton Ave | St Anthony Pl | Rubel Ave | 23 | 4 | Local | [13 empty] | 4 |  |  |  | 15710.688 |  |  | Public Works | [16 empty] | 311.72 | 28 | 8728.16 | 0.14165
| Hall |  |  | FY23 |  |  |  | Bus Pad at 6th & Jefferson |  |  |  | 4 | [18 empty] | 50000 |  |  | Public Works
| Hall |  |  | FY 23 |  |  |  | Cedar St | S 19th St | S 15th St | 38.9167 | 4 | Local | [13 empty] | 15 |  |  |  | 128110.8343 |  |  | Public Works | [16 empty] | 1923.464 | 37 | 71172.6857 | 1.1551
| Hall |  |  | FY 23 |  |  |  | Debarr St | Rubel Ave | Barret Ave | 32.4769 | 4 | Local | [13 empty] | 11 |  |  |  | 60853.68 |  |  | Public Works | [16 empty] | 1126.92 | 30 | 33807.6 | 0.54867
| Hall |  |  | FY 23 |  |  |  | Duncan St | N 22nd St | N 24th St | 14.0205 | 4 | Local | [13 empty] | 12 |  |  |  | 62193.096 |  |  | Public Works | [16 empty] | 959.77 | 36 | 34551.72 | 0.56074
| Hall |  | 350002-472 | FY 22 |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 | FY 22 |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 | FY 22 |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 | FY 22 |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 | FY 22 |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  | FY 23 |  |  |  | E Washington St | N 1st St | N Preston St | 54.508 | 4 | Pri Coll | [13 empty] | 11 |  |  |  | 95355 |  |  | Public Works | [16 empty] | 1654.55 | 29.3333 | 48899.86 | 0.7936
| Hall |  |  | FY 23 |  |  |  | Edward St | St Anthony Pl | Morton Ave | 24.8631 | 4 | Local | [13 empty] | 34 |  |  |  | 80043.228 |  |  | Public Works | [16 empty] | 1234.23 | 36 | 44468.46 | 0.72168
| Hall |  |  | FY 23 |  |  |  | Magazine St | S 10th St | S 11th St | 34 | 4 | Local | [13 empty] | 1? |  |  |  | 35643.132 |  |  | Public Works | [15 empty] | Maybe make a new ramp where Magazine hits 10th st | 471.47 | 42 | 19801.74 | 0.32136
| Hall |  |  | FY 23 |  |  |  | N 2nd St | River Rd | W Main St | 55.2249 | 4 | Pri Coll | [13 empty] | 6 |  |  |  | 35953 |  |  | Public Works | [16 empty] | 904.75 | 20 | 18437.4 | 0.29922
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 | FY 22 |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  | FY 23 |  |  |  | Rowan St | N 22nd St | N 24th St | 15.9641 | 4 | Local | [13 empty] | 8 |  |  |  | 62099.136 |  |  | Public Works | [16 empty] | 958.32 | 36 | 34499.52 | 0.5599
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  | FY 23 |  |  |  | Rubel Ave | E Broadway | Morton Ave | 30.1586 | 4 | Local | [13 empty] | 33 |  |  |  | 84858.9042 |  |  | Public Works | [16 empty] | 1341.3399 | 35.2 | 47143.8357 | 0.7651
| Hall |  |  | FY 23 |  |  |  | S 10th St | Magazine St | Read Alley | 34 | 4 | Local | [13 empty] | 2 |  |  |  | 16551.5921 |  |  | Public Works | [16 empty] | 218.9364 | 42 | 9195.3289 | 0.14923
| Hall |  |  | FY 23 |  |  |  | S 11th St | W Chestnut St | W Broadway | 33.1751 | 4 | Local | [13 empty] | 11 |  |  |  | 79179.012 |  |  | Public Works | [16 empty] | 1063.09 | 41.3333 | 43988.34 | 0.71389
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Broadway | Cedar St | 17.6734 | 4 | Local | [13 empty] | 33 |  |  |  | 145131.84 |  |  | Public Works | [18 empty] | 142801 | 2.3175
| Hall |  |  | FY 23 |  |  |  | S 18th St | Green Alley | Eddy St | 47.405 | 4 | Local | [13 empty] | 2 |  |  |  | 30136.104 |  |  | Public Works | [16 empty] | 492.42 | 34 | 16742.28 | 0.27171
| Hall |  | 350002-472 | FY 22 |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 | FY 22 |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 | FY 22 |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  | FY 23 |  |  |  | S Preston St | E Hill St | I 65 Ramp | 52.6318 | 4 | Min Art | [13 empty] | 9 |  |  |  | 66983 |  |  | Public Works | [16 empty] | 911.2283 | 34.6667 | 31896.4441 | 0.51765
| Hall |  |  | FY 23 |  |  |  | St Anthony Pl | E Broadway | Barret Ave | 33.4304 | 4 | Local | [13 empty] | 5 |  |  |  | 63780.804 |  |  | Public Works | [16 empty] | 1161.78 | 31.3333 | 35433.78 | 0.57506
| Hall |  |  | FY 23 |  |  |  | W Main St | N 22nd St | N 25th St | 39.6711 | 4 | Local | [13 empty] | 17 |  |  |  | 155392.56 |  |  | Public Works | [16 empty] | 1438.82 | 60 | 86329.2 | 1.401
| Hall |  | 350002-590 | FY 22 |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  |  | FY 23 |  |  |  | W Washington St | N 1st St | N 2nd St | 29 | 4 | Pri Coll | [13 empty] | 4 |  |  |  | 21168 |  |  | Public Works | [16 empty] | 493.42 | 22 | 10855.24 | 0.17617
| Hall |  |  | FY 23 |  |  |  | Walter Barnes Way | W Chestnut St | Read Alley | 37 | 4 | Local | [13 empty] | 0 |  |  |  | 18051.3374 |  |  | Public Works | [16 empty] | 250.713 | 40 | 10028.5208 | 0.16275
| Hall |  | 350002-583 | FY 22 |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | See S 32nd St | July | [17 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | See S 32nd St | July | [17 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  | 350002-583 | FY 22 |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | See S 32nd St | July | [17 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  | 350002-583 | FY 22 |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | See S 32nd St | July | [17 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  | 350002-583 | FY 22 |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | 589179.69 | July | [17 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall |  | 350002-582 | FY 22 |  |  |  | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | 183786.63 | July | [17 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall |  | 350002-583 | FY 22 |  |  |  | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | 68387.89 | July | [16 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  | 350002-583 | FY 22 |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | See S 32nd St | July | [17 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall |  | 350002-583 | FY 22 |  |  |  | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | See S 32nd St | July | [17 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | See S 32nd St | July | [17 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  | 350002-583 | FY 22 |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | See S 32nd St | July | [17 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  | FY 23 |  |  |  | Carter St | Portland Ave | Northwestern Pkwy | 25 | 5 | Local | [13 empty] | 3 |  |  |  | 38924.712 |  |  | Public Works | [15 empty] | Concrete Roadway, look to Overlay if possible. Otehrwise select panel replacement | 600.69 | 36 | 21624.84 | 0.35095
| Hall |  | 388368-9 | FY 22 |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  | FY 23 |  |  |  | Cedar Grove Ter | Northwestern Pkwy | Dead End | 20.0333 | 5 | Local | [13 empty] | 6 |  |  |  | 75938.472 |  |  | Public Works | [16 empty] | 781.26 | 54 | 42188.04 | 0.68468
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | S 45th St | 25.4062 | 5 | Local | [13 empty] | 6 |  |  |  | 16091.928 |  |  | Public Works | [16 empty] | 599.49 | 15 | 8939.96 | 0.14509
| Hall |  |  | FY 23 |  |  |  | Griffiths Ave | N 22nd St | Bank St | 18.0951 | 5 | Local | [13 empty] | 25 |  |  |  | 107352.144 |  |  | Public Works | [16 empty] | 1754.12 | 34 | 59640.08 | 0.96791
| Hall |  |  | FY 23 |  |  |  | Lytle St | N 20th St | N 22nd St | 23 | 5 | Local | [13 empty] | 0 |  |  |  | 46251 |  |  | Public Works | [16 empty] | 713.75 | 36 | 25695 | 0.41701
| Hall |  |  | FY 23 |  |  |  | N 20th St | Rowan St | Bank St | 15.4973 | 5 | Local | [13 empty] | 28 |  |  |  | 98944.488 |  |  | Public Works | [16 empty] | 1616.74 | 34 | 54969.16 | 0.8921
| Hall |  |  | FY 23 |  |  |  | N 20th St | Bank St | Portland Ave | 14.9549 | 5 | Local | [13 empty] | See N 20th |  |  |  | 43443.432 |  |  | Public Works | [16 empty] | 709.86 | 34 | 24135.24 | 0.39169
| Hall |  |  | FY 23 |  |  |  | N 21st St | Bank St | Rowan St | 18.5511 | 5 | Local | [13 empty] | 30 |  |  |  | 80968.464 |  |  | Public Works | [16 empty] | 1874.27 | 24 | 44982.48 | 0.73003
| Hall |  |  | FY 23 |  |  |  | N 23rd St | Portland Ave | Northwestern Pkwy | 20.4356 | 5 | Local | [13 empty] | 10 |  |  |  | 56586.996 |  |  | Public Works | [16 empty] | 911.12 | 34.5 | 31437.22 | 0.5102
| Hall |  |  | FY 23 |  |  |  | N 25th St | Portland Ave | Northwestern Pkwy | 27.0214 | 5 | Local | [13 empty] | 15 |  |  |  | 64663.6283 |  |  | Public Works | [15 empty] | Brick paver ramp to replace with concrete. Need to check if histroic preservation dist. | 1025.8987 | 35 | 35924.2379 | 0.58302
| Hall |  |  | FY 23 |  |  |  | N 27th St | Portland Ave | Northwestern Pkwy | 17.9248 | 5 | Local | [13 empty] | 11 |  |  |  | 64603.008 |  |  | Public Works | [16 empty] | 996.96 | 36 | 35890.56 | 0.58247
| Hall |  |  | FY 23 |  |  |  | N 33rd St | Northwestern Pkwy | Pflanz St | 20 | 5 | Local | [13 empty] | 8 |  |  |  | 89696.592 |  |  | Public Works | [18 empty] | 49831 | 0.80871
| Hall |  |  | FY 23 |  |  |  | N 34th St | Northwestern Pkwy | Pflanz Ave | 35 | 5 | Local | [13 empty] | 5 |  |  |  | 17153.856 |  |  | Public Works | [16 empty] | 264.72 | 36 | 9529.92 | 0.15466
| Hall |  |  | FY 23 |  |  |  | N 35th St | Northwestern Pkwy | Parker Ave | 17.674 | 5 | Local | [13 empty] | 10 |  |  |  | 159050.88 |  |  | Public Works | [16 empty] | 2209.04 | 40 | 88361.6 | 1.434
| Hall |  |  | FY 23 |  |  |  | N 36th St | Northwestern Pkwy | Pflanz Ave | 38 | 5 | Local | [13 empty] | 4 |  |  |  | 11527.488 |  |  | Public Works | [16 empty] | 266.84 | 24 | 6404.16 | 0.10393
| Hall |  |  | FY 23 |  |  |  | S 45th St | W Broadway | Garland Ave | 32.9625 | 5 | Local | [13 empty] | 7 |  |  |  | 58936.86 |  |  | Public Works | [16 empty] | 1117.9 | 29.3333 | 32742.7 | 0.53139
| Hall |  |  | FY 23 |  |  |  | Short St | Griffiths Ave | Owen St | 16 | 5 | Local | [13 empty] | 5 |  |  |  | 16947.684 |  |  | Public Works | [16 empty] | 362.13 | 26 | 9415.38 | 0.1528
| Hall |  | 350002-588 | FY 22 |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | see S Floyd | July | [17 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  | 350002-588 | FY 22 |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | 222661.02 | July | [17 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  | 350002-579 | FY 22 |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | 94995.62 | July | [17 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  | 350002-587 | FY 22 |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | 186252.09 | July | [17 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  |  | FY 23 |  |  |  | Colorado Ave | Central Ave | Algonquin Pkwy | 20.2796 | 6 | Local | [13 empty] | 14 |  |  |  | 105470.388 |  |  | Public Works | [16 empty] | 2259.89 | 27.2 | 58594.66 | 0.95094
| Hall |  |  | FY 23 |  |  |  | Dixie Hwy | Hale Ave | W Burnett Ave | 55.4031 | 6 | Min Art | [13 empty] | 29 |  |  |  | 236607 |  |  | Public Works | [16 empty] | 3120.29 | 35.5455 | 112669.83 | 1.8285
| Hall |  |  | FY 23 |  |  |  | Lillian Ave | 7th Street Rd | Colorado Ave | 31.3741 | 6 | Local | [13 empty] | 11 |  |  |  | 92745.72 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 2015.69 | 25.3333 | 51525.4 | 0.83621
| Hall |  |  | FY 23 |  |  |  | Lincoln Ave | 7th Street Rd | Taylor Blvd | 24.899 | 6 | Local | [13 empty] | 18 |  |  |  | 183027.456 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 3815.61 | 26.7143 | 101681.92 | 1.6502
| Hall |  |  | FY 23 |  |  |  | Lindbergh Dr | Algonquin Pkwy | Dead End (Homeview) | 45.5354 | 6 | Local | [13 empty] | 35 |  |  |  | 166826.304 |  |  | Public Works | [15 empty] | Some ramps may be technically infeasible. Dead end at homeview is strange | 3138.68 | 29 | 94313.98 | 1.5306
| Hall |  |  | FY 23 |  |  |  | S 16th St | W Breckinridge St | W Oak St | 29.2853 | 6 | Local | [13 empty] | 47 |  |  |  | 150568.704 |  |  | Public Works | [16 empty] | 2614.04 | 32 | 83649.28 | 1.3576
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Kentucky St | W Oak St | 28.3593 | 6 | Local | [13 empty] | 37 |  |  |  | 104515.344 |  |  | Public Works | [16 empty] | 1746.26 | 33.2 | 58064.08 | 0.94233
| Hall |  |  | FY 23 |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  | FY 22 |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  | FY 23 |  |  |  | Tennessee Ave | 7th Street Rd | Lindbergh Dr | 33 | 6 | Local | [13 empty] | 4 |  |  |  | 62034.264 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1380.5 | 25 | 34463.48 | 0.55931
| Hall |  |  | FY 23 |  |  |  | W Oak St | Dixie Hwy | S 26th St | 20.437 | 6 | Min Art | [13 empty] | 22 |  |  |  | 224089 |  |  | Public Works | [16 empty] | 2754.22 | 38.8 | 106709.2 | 1.7318
| Hall |  |  | FY 23 |  |  |  | W St Catherine St | S 15th St | S 16th St | 21 | 6 | Local | [13 empty] | 4 |  |  |  | 40212.18 |  |  | Public Works | [16 empty] | 744.67 | 30 | 22340.1 | 0.36256
| Hall |  |  | FY 23 |  |  |  | Weller Ave | 7th Street Rd | Dead End | 28.6273 | 6 | Local | [13 empty] | 4 |  |  |  | 64972.44 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1388.3 | 26 | 36095.8 | 0.5858
| Hall |  |  | FY 23 |  |  |  | Wurtele Ave | 7th Street Rd | Colorado Ave | 32.2659 | 6 | Local | [13 empty] | 3 |  |  |  | 109582.272 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1902.47 | 32 | 60879.04 | 0.98801
| Hall |  |  | FY 23 |  |  |  | Chippewa Rd | Elfin Ave | Napanee Rd | 42 | 7 | Local | [13 empty] | 0 |  |  |  | 12590.424 |  |  | Public Works | [15 empty] | Big base failure north of Elfin need to complete with this work. | 317.94 | 22 | 6994.68 | 0.11352
| Hall |  |  | FY 23 |  |  |  | Napanee Rd | Chippewa Rd | St Matthews Ave | 19 | 7 | Local | [13 empty] | 0 |  |  |  | 25394.256 |  |  | Public Works | [16 empty] | 587.83 | 24 | 14107.92 | 0.22896
| Hall |  |  | FY 23 |  |  |  | Alta Ave | Bardstown Rd | Cherokee Rd | 25.0798 | 8 | Local | [13 empty] | 29 |  |  |  | 169299.18 |  |  | Public Works | [16 empty] | 3135.17 | 30 | 94055.1 | 1.5264
| Hall |  | 350002-584 | FY 22 |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  | 350002-584 | FY 22 |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  |  | FY 23 |  |  |  | Bonnycastle Ave | Bardstown Rd | Cherokee Rd | 37.5047 | 8 | Local | [13 empty] | 29 |  |  |  | 149154.516 |  |  | Public Works | [16 empty] | 2858.8 | 29 | 82863.62 | 1.3448
| Hall |  |  | FY 23 |  |  |  | Edward St | Morton Ave | Rufer Ave | 18.7033 | 8 | Local | [13 empty] | 39 |  |  |  | 116619.264 |  |  | Public Works | [16 empty] | 1799.68 | 36 | 64788.48 | 1.0515
| Hall |  |  | FY 23 |  |  |  | Grasmere Ter | Grasmere Dr | Dead End | 10.6363 | 8 | Local | [13 empty] | 0 |  |  |  | 6760.584 |  |  | Public Works | [15 empty] | Small alley, could be a nightmare | 312.99 | 12 | 3755.88 | 0.060955
| Louisville Paving |  | 388368-7 | FY 22 |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  |  | FY 23 |  |  |  | Parsons Pl | Alta Ave | Bonnycastle Ave | 30 | 8 | Local | [13 empty] | 0 |  |  |  | 14329.548 |  |  | Public Works | [16 empty] | 442.27 | 18 | 7960.86 | 0.1292
| Hall |  |  | FY 23 |  |  |  | Ray Ave | Grinstead Dr | Longest Ave | 22.8729 | 8 | Local | [13 empty] | 7 |  |  |  | 71597.52 |  |  | Public Works | [16 empty] | 1325.88 | 30 | 39776.4 | 0.64554
| Hall |  |  | FY 23 |  |  |  | Ridgeway Ave | Willow Ave | Dead End | 10 | 8 | Local | [13 empty] | 2 |  |  |  | 44804.52 |  |  | Public Works | [15 empty] | Looks like an alley | 1244.57 | 20 | 24891.4 | 0.40397
| Hall |  |  | FY 23 |  |  |  | Spring Dr | Speed Ave | Woodford Pl | 18.0204 | 8 | Local | [13 empty] | 2 |  |  |  | 111570.696 |  |  | Public Works | [16 empty] | 1721.77 | 36 | 61983.72 | 1.0059
| LP |  | 366368-17 | FY 23 |  |  |  | Trevilian Way | Newburg Rd | Dundee Rd | 68.6911 | 8 | Min Art | [13 empty] | 0 |  |  |  | 192812 |  |  | Google Funds | [16 empty] | 3604.72 | 26 | 91815.32 | 1.4901
| Hall |  |  | FY 23 |  |  |  | Avon Ct | Kennedy Ave | Kennedy Ct | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 6826.644 |  |  | Public Works | [16 empty] | 172.39 | 22 | 3792.58 | 0.06155
| Hall |  |  | FY 23 |  |  |  | Bauer Ave | Lexington Rd | Wilmington Ave | 21 | 9 | Local | [13 empty] | 0 |  |  |  | 20857.32 |  |  | Public Works | [16 empty] | 526.7 | 22 | 11587.4 | 0.18805
| Hall |  |  | FY 23 |  |  |  | Chamberry Cir (All) | Old Cannons Ln | Old Cannons Ln | 28.3517 | 9 | Local | [13 empty] | 0 |  |  |  | 86199.228 |  |  | Public Works | [16 empty] | 1958.4 | 25 | 47888.46 | 0.77719
| Hall |  |  | FY 23 |  |  |  | Circle Hill Rd | Rock Creek Dr | Old Cannons Ln | 28.8803 | 9 | Local | [13 empty] | 0 |  |  |  | 120190.7284 |  |  | Public Works | [16 empty] | 2587.9703 | 23 | 60702.3881 | 0.98515
| Hall |  |  | FY 23 |  |  |  | Crescent Ct | Frankfort Ave | Grinstead Dr | 27.5652 | 9 | Local | [13 empty] | 2 |  |  |  | 49072.7871 |  |  | Public Works | [15 empty] | Base failures? | 1239.2118 | 22 | 27262.6595 | 0.44245
| Hall |  |  | FY 22 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  |  | FY 23 |  |  |  | Homestead Blvd | Rock Creek Dr | Circle Hill Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 48453.688 |  |  | Public Works | [16 empty] | 1121.6131 | 24 | 26918.7155 | 0.43687
| Hall |  |  | FY 23 |  |  |  | Huntington Rd | Rock Creek Dr | Old Cannons Ln | 18.7864 | 9 | Local | [13 empty] | 0 |  |  |  | 67794.408 |  |  | Public Works | [16 empty] | 1711.98 | 22 | 37663.56 | 0.61125
| Hall |  |  | FY 23 |  |  |  | Kennedy Ave | Frankfort Ave | Grinstead Dr | 31.0011 | 9 | Local | [13 empty] | 2 |  |  |  | 45585.036 |  |  | Public Works | [16 empty] | 1384.26 | 18 | 25325.02 | 0.411
| Hall |  |  | FY 23 |  |  |  | Kennedy Ct | Kennedy Ave | Dead End | 41.1453 | 9 | Local | [13 empty] | 2 |  |  |  | 20407.788 |  |  | Public Works | [16 empty] | 586.15 | 20 | 11337.66 | 0.184
| Hall |  |  | FY 23 |  |  |  | Lake Ave | Mellwood Ave | Dead End | 19 | 9 | Local | [13 empty] | 1 |  |  |  | 82170.72 |  |  | Public Works | [16 empty] | 1984.8 | 23 | 45650.4 | 0.74087
| Hall |  |  | FY 23 |  |  |  | Macon Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 20824.128 |  |  | Public Works | [16 empty] | 482.04 | 24 | 11568.96 | 0.18775
| Hall |  |  | FY 23 |  |  |  | Meadowlark Ave | Seminary Rd | Stilz Ave | 15.5126 | 9 | Local | [13 empty] | 11 |  |  |  | 24502.176 |  |  | Public Works | [16 empty] | 850.77 | 16 | 13612.32 | 0.22092
| Hall |  |  | FY 23 |  |  |  | Mount Holly Ave | Brownsboro Rd | Lindsay Ave | 19.4575 | 9 | Local | [13 empty] | 2 |  |  |  | 49280.832 |  |  | Public Works | [15 empty] | Base fialure by Lindsay | 1215.32 | 24 | 27378.24 | 0.44432
| Hall |  |  | FY 23 |  |  |  | Pleasantview Ave | Grinstead Dr | Lexington Rd | 18.075 | 9 | Local | [13 empty] | 10 |  |  |  | 98573.688 |  |  | Public Works | [16 empty] | 1878.18 | 29 | 54763.16 | 0.88876
| Hall |  |  | FY 23 |  |  |  | Rock Creek Dr | Cannons Ln | Pee Wee Reese Rd | 32.2104 | 9 | Local | [13 empty] | 0 |  |  |  | 114983.244 |  |  | Public Works | [15 empty] | Base failures | 3260.83 | 19.6 | 63879.58 | 1.0367
| Hall |  | 350002-604 | FY 23 |  |  |  | S Hubbards Ln | Bowling Blvd | Shelbyville Rd | 27 | 9 | Min Art | [17 empty] | 253130 |  |  | Public Works | [18 empty] | 120538 | 1.9562
| Hall |  |  | FY 23 |  |  |  | Springdale Rd | Grinstead Dr | Pleasantview Ave | 20 | 9 | Local | [13 empty] | 3 |  |  |  | 29623.104 |  |  | Public Works | [16 empty] | 685.72 | 24 | 16457.28 | 0.26709
| Hall |  |  | FY 23 |  |  |  | St Matthews Ave | Napanee Rd | Ormond Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 14326.884 |  |  | Public Works | [16 empty] | 361.79 | 22 | 7959.38 | 0.12917
| Hall |  |  | FY 23 |  |  |  | Stilz Ave | Lexington Rd | Frankfort Ave | 53.6459 | 9 | Pri Coll | [13 empty] | 13 |  |  |  | 114290 |  |  | Public Works | [16 empty] | 2574.69 | 34.3333 | 87915.6 | 1.4268
| Hall |  |  | FY 23 |  |  |  | Wallace Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 18104.112 |  |  | Public Works | [16 empty] | 386.84 | 26 | 10057.84 | 0.16323
| Hall |  |  | FY 23 |  |  |  | Wendover Ave | Lexington Rd | Wilmington Ave | 26 | 9 | Local | [13 empty] | 0 |  |  |  | 17264.808 |  |  | Public Works | [16 empty] | 435.98 | 22 | 9591.56 | 0.15566
| Hall |  |  | FY 23 |  |  |  | Willis Ave | Wiltshire Ave | Breckenridge Ln | 76 | 9 | Collector | [17 empty] | 14626.8 | [21 empty] | 8126 | 0.13188
| Hall |  |  | FY 23 |  |  |  | Wilmington Ave | Wallace Ave | Frankfort Ave | 28.1016 | 9 | Local | [13 empty] | 3 |  |  |  | 24518.88 |  |  | Public Works | [16 empty] | 536.86 | 25 | 13621.6 | 0.22107
| Hall |  |  | FY 23 |  |  |  | Wiltshire Ave | Wilmington Ave | Willis Ave | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 22864.644 |  |  | Public Works | [16 empty] | 577.39 | 22 | 12702.58 | 0.20615
| Hall |  |  | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Dead End |  | 9 | Local | [17 empty] | 23706.8246 | [21 empty] | 13170 | 0.21374
| Hall |  |  | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Thompson Ave | 44.4846 | 9 | Pri Coll | [13 empty] | 6 |  |  |  | 118575 |  |  | Public Works | [16 empty] | 2147.8793 | 29.3333 | 60807.4923 | 0.98685
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Ct | Audubon Ridge Dr | Dead End | 19.8104 | 10 | Local | [13 empty] | 0 |  |  |  | 33929.676 |  |  | Public Works | [16 empty] | 856.81 | 22 | 18849.82 | 0.30592
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Dr | Illinois Ave | Dead End | 48.9775 | 10 | Local | [13 empty] | 5 |  |  |  | 44784.36 |  |  | Public Works | [16 empty] | 1027.09 | 31 | 24880.2 | 0.40378
| Hall |  |  | FY 23 |  |  |  | Ellison Ave | Barret Ave | Spratt Ave | 35.6822 | 10 | Local | [13 empty] | 15 |  |  |  | 166187.376 |  |  | Public Works | [16 empty] | 2429.64 | 38 | 92326.32 | 1.4984
| Hall |  |  | FY 23 |  |  |  | Grantswood Ct | Audubon Ridge Ct | Dead End |  | 10 | Local | [13 empty] | 2 |  |  |  | 16264.8 |  |  | Public Works | [16 empty] | 502 | 18 | 9036 | 0.14665
| Hall |  |  | FY 23 |  |  |  | Reutlinger Ave | E Oak St | Ellison Ave | 23.3308 | 10 | Local | [13 empty] | 6 |  |  |  | 67047.624 |  |  | Public Works | [16 empty] | 1330.31 | 28 | 37248.68 | 0.60451
| LP |  | 366368-16 | FY 23 |  |  |  | Robards Ln | Gardiner Ln | Bishop Ln | 42.3597 | 10 | Pri Coll | [13 empty] | 2 |  |  |  | 147273 |  |  | Public Works | [16 empty] | 3717.62 | 20 | 75524.68 | 1.2257
| Hall |  |  | FY 23 |  |  |  | Spratt St | Goss Ave | St Michael St | 35.9444 | 10 | Local | [13 empty] | 16 |  |  |  | 74506.176 |  |  | Public Works | [16 empty] | 1171.43 | 35.3333 | 41392.32 | 0.67176
| Hall |  |  | FY 23 |  |  |  | St Michael St | Ellison Ave | Dead End | 41 | 10 | Local | [13 empty] | 0 |  |  |  | 35897.4 |  |  | Public Works | [16 empty] | 712.25 | 28 | 19943 | 0.32366
| Hall |  |  | FY 23 |  |  |  | Bircham Rd | Shelbyville Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 110000 |  |  | Council | [18 empty] | 66212 | 1.0746
| Hall |  |  | FY 23 |  |  |  | Burleigh Ct | Burcham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 31000 |  |  | Council | [18 empty] | 17407 | 0.2825
| Hall |  |  | FY 23 |  |  |  | Burleigh Pl | Burleigh Ct | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 8500 |  |  | Council | [18 empty] | 4726 | 0.076699
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Rd | Blankenbaker Pkwy | Taylorsville Rd | 36.517 | 11 | Pri Coll | [13 empty] | 0 |  |  |  | 196876 |  |  | Public Works | [16 empty] | 4135.4154 | 24 | 100961.8158 | 1.6385
| Hall |  |  | FY 23 |  |  |  | Constant Comment Pl | From J-Town R/W north of Electron | Dead End (south) | 22.3743 | 11 | Local | [13 empty] | 1 |  |  |  | 76709.25 |  |  | Public Works | [16 empty] | 987 | 35 | 42616.25 | 0.69162
| Hall |  |  | FY 23 |  |  |  | Dorshire Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 20000 |  |  | Council | [18 empty] | 11350 | 0.1842
| LP |  |  | FY 23 |  |  |  | E Rehl Ct | Rehl Rd | Dead End |  | 11 | Local | [17 empty] | 60541 |  |  | Public Works | [18 empty] | 33634 | 0.54585
| Hall |  |  | FY 23 |  |  |  | Electron Dr | Blankenbaker Pkwy | Constant Comment Pl | 19 | 11 | Local | [13 empty] | 1 |  |  |  | 51249.132 |  |  | Public Works | [16 empty] | 862.78 | 33 | 28471.74 | 0.46207
| Hall |  |  | FY 23 |  |  |  | Hurstbourne Park Blvd | Hurstbourne Pkwy | Dead End |  | 11 | Local | [17 empty] | 48685 |  |  | Public Works | [18 empty] | 27047 | 0.43895
| Hall |  |  | FY 23 |  |  |  | Landis Lakes Dr | S English Station Rd | Landis Lakes Ct | 32.9592 | 11 | Local | [13 empty] | 10 |  |  |  | 66457.368 |  |  | Public Works | [16 empty] | 1682.32 | 25.3333 | 41128.06 | 0.66747
| Hall |  |  | FY 23 |  |  |  | Summerfield Dr | Six Mile Ln | Weather Way |  | 11 | Local | [13 empty] | 17 |  |  |  | 75000 |  |  | Council | [18 empty] | 112833 | 1.8312
| Hall |  |  | FY 23 |  |  |  | Willoughby Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 26000 |  |  | Council | [18 empty] | 14983 | 0.24316
| LP |  |  | FY 23 |  |  |  | Blanton Ln | St Andrews Church Rd | Dixie Hwy | 35.5419 | 12 | Pri Coll | [13 empty] | 0 |  |  |  | 226546 |  |  | Public Works | [16 empty] | 5256.12 | 22.5714 | 116177.36 | 1.8855
| Hall |  |  | FY 23 |  |  |  | De Mel Ave | Manslick Rd | Dead End | 23.8808 | 12 | Local | [13 empty] | 0 |  |  |  | 73224.6988 |  |  | Public Works | [16 empty] | 1904.3118 | 21.6667 | 40680.3882 | 0.66021
| Hall |  |  | FY 23 |  |  |  | Frank Lee Ave | Terry Rd | Dead End | 41.2207 | 12 | Local | [13 empty] | 5 |  |  |  | 29502 |  |  | Public Works | [16 empty] | 819.5 | 20 | 16390 | 0.266
| Hall |  | 350002-470 | FY 22 |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-601 | FY 23 |  |  |  | Lynn Myra Ct | Vista John Dr | Dead End | 40 | 12 | Local | [13 empty] | 0 |  |  |  | 9422.424 |  |  | Public Works | [16 empty] | 237.94 | 22 | 5234.68 | 0.084954
| Hall |  | 350002-600 | FY 23 |  |  |  | Maryview Dr | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 79947 | [21 empty] | 45684
| Hall |  | 350002-518 | FY 22 |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [18 empty] | LWC Project | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  |  | FY 23 |  |  |  | Mount Marcy Rd | Mount Holyoke Dr | Alps Rd | 25 | 12 | Local | [13 empty] | 6 |  |  |  | 57474.144 |  |  | Public Works | [16 empty] | 1330.42 | 24 | 31930.08 | 0.5182
| Hall |  | 350002-600 | FY 23 |  |  |  | Nancy Ave | Dawn Dr | Dead End | 22 | 12 | Local | [13 empty] | 0 |  |  |  | 34899.984 |  |  | Public Works | [16 empty] | 807.87 | 24 | 19388.88 | 0.31466
| Hall |  | 350002-600 | FY 23 |  |  |  | Princewood Pl | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 18314 | [21 empty] | 10465 | 0.16984
| Hall |  | 350002-601 | FY 23 |  |  |  | Stephan Rd | Vista John Dr | Oswego Cir | 25.3696 | 12 | Local | [13 empty] | 0 |  |  |  | 37562.1531 |  |  | Public Works | [16 empty] | 1043.3931 | 20 | 20867.8628 | 0.33867
| Hall |  | 350002-601 | FY 23 |  |  |  | Terudon Dr | Manslick Rd | Vista John Dr | 28 | 12 | Local | [13 empty] | 0 |  |  |  | 31798.656 |  |  | Public Works | [16 empty] | 736.08 | 24 | 17665.92 | 0.2867
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 9956.96 | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-601 | FY 23 |  |  |  | Vista John Dr | Manslick Rd | Stephan Dr | 36.6481 | 12 | Local | [13 empty] | 0 |  |  |  | 59112.684 |  |  | Public Works | [16 empty] | 1411.04 | 23.3333 | 32840.38 | 0.53297
| Hall |  |  | FY 23 |  |  |  | Wade Lee Ct | Wilke Farm Ave | Dead End | 37 | 12 | Local | [13 empty] | 0 |  |  |  | 7507.08 |  |  | Public Works | [16 empty] | 208.53 | 20 | 4170.6 | 0.067685
| Hall |  |  | FY 23 |  |  |  | Wilke Farm Ave | Frank Lee Ave | Ree Dr | 48.9395 | 12 | Local | [13 empty] | 5 |  |  |  | 50846.004 |  |  | Public Works | [16 empty] | 1283.99 | 22 | 28247.78 | 0.45844
| Hall |  | 350002-592 | FY 23 |  |  |  | Clay Ave | Minor Ln | Preston Hwy | 25.2005 | 13 | Local | [13 empty] | 0 |  |  |  | 102532.608 |  |  | Public Works | [16 empty] | 3415.39 | 16.8 | 56962.56 | 0.92445
|  |  |  | FY 22 |  |  |  | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
| Hall |  | 350002-560 | FY 22 |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| LP |  |  | FY 23 |  |  |  | Jefferson Hill Rd | Keys Ferry Rd | Snawder Ln | 37.0674 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 444131 |  |  | Public Works | [16 empty] | 12300.93 | 18.6667 | 227759.57 | 3.6963
| LP |  |  | FY 23 |  |  |  | Joyner Hill Rd | Lonesome Hollow Rd | Dead End | 33 | 13 | Local | [13 empty] | 0 |  |  |  | 22761.882 |  |  | Public Works | [16 empty] | 1149.59 | 11 | 12645.49 | 0.20523
| LP |  |  | FY 23 |  |  |  | Lonesome Hollow Rd | Bleevins Gap Rd | Dead End | 23.6259 | 13 | Local | [13 empty] | 0 |  |  |  | 93498.0588 |  |  | Public Works | [16 empty] | 2990.1966 | 18 | 51943.366 | 0.843
| LP |  |  | FY 23 |  |  |  | Lonesome Hollow Rd | Jefferson Hill Rd | Dead End | 37 | 13 | Local | [13 empty] | 0 |  |  |  | 16334.784 |  |  | Public Works | [16 empty] | 756.24 | 12 | 9074.88 | 0.14728
| Hall |  | 350002-592 | FY 23 |  |  |  | Meadow Hill Rd | Minyard Dr | Dead End | 9 | 13 | Local | [13 empty] | 2 |  |  |  | 8903.2847 |  |  | Public Works | [15 empty] | Metro ROW is small, only 4 houses, rest private | 206.0946 | 24 | 4946.2693 | 0.080274
| Hall |  | 350002-592 | FY 23 |  |  |  | Minyard Dr | Clay Ave | Minor Ln | 28.853 | 13 | Local | [13 empty] | 0 |  |  |  | 91895.328 |  |  | Public Works | [16 empty] | 1930.73 | 26.25 | 51052.96 | 0.82855
| LP |  |  | FY 23 |  |  |  | Snawder Ln | Jefferson Hill Rd | Dead End | 21 | 13 | Local | [13 empty] | 0 |  |  |  | 22803.48 |  |  | Public Works | [16 empty] | 1266.86 | 10 | 12668.6 | 0.2056
| Hall |  | 350002-592 | FY 23 |  |  |  | Sunset Dr | Minor Ln | Clay Ave | 39 | 13 | Local | [13 empty] | 0 |  |  |  | 36200.52 |  |  | Public Works | [16 empty] | 1117.3 | 18 | 20111.4 | 0.32639
| LP |  |  | FY 23 |  |  |  | Tidwell Rd | Lonesome Hollow Rd | Dead End | 35 | 13 | Local | [13 empty] | 0 |  |  |  | 16525.8 |  |  | Public Works | [16 empty] | 765 | 12 | 9181 | 0.149
| LP |  |  | FY 23 |  |  |  | Top Hill Rd | Snawder Ln | Mitchell Hill Rd | 45.371 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 377132 |  |  | Public Works | [16 empty] | 9913.74 | 19 | 193400.8 | 3.1387
| Hall |  | 350002-552 | FY 22 |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| Hall |  | 350002-599 | FY 23 |  |  |  | Chase Rd | W Pages Ln | Stephan Dr | 43 | 14 | Local | [13 empty] | 2 |  |  |  | 41561.28 |  |  | Public Works | [16 empty] | 1154.48 | 20 | 23089.6 | 0.37472
| Hall |  | 350002-594 | FY 23 |  |  |  | Dixie Garden Dr | Dixie Hwy | Blaze Way | 51.9782 | 14 | Local | [13 empty] | 4 |  |  |  | 123696.396 |  |  | Public Works | [16 empty] | 2734.59 | 27.3333 | 68720.22 | 1.1153
| Hall |  | 350002-594 | FY 23 |  |  |  | Fashion Way | Bethany Ln | Nocturne Dr | 17.6755 | 14 | Local | [13 empty] | 11 |  |  |  | 68407.524 |  |  | Public Works | [16 empty] | 1659.78 | 22.8 | 38004.18 | 0.61677
| Hall |  | 350002-598 | FY 23 |  |  |  | Johnsontown Rd | Dixie Hwy | Trade Port Dr | 47.0122 | 14 | Min Art | [13 empty] | 22 |  |  |  | 568391 |  |  | Public Works | [15 empty] | Applied for rubber aspahlt grant on this roadway | 7412.9412 | 36.1429 | 270662.5039 | 4.3926
| Hall |  | 350002-599 | FY 23 |  |  |  | Mark Dr | Vicki Ln | Robbins Rd | 21 | 14 | Local | [13 empty] | 0 |  |  |  | 17582.832 |  |  | Public Works | [16 empty] | 407.01 | 24 | 9768.24 | 0.15853
| LP |  |  | FY 23 |  |  |  | Medora Rd | Blevins Gap Rd | Pendleton Rd | 30 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 201498 |  |  | Public Works | [16 empty] | 5166.62 | 20 | 103332.4 | 1.677
| Hall |  | 350002-599 | FY 23 |  |  |  | Minette Ct | Stephan Dr | public dead end | 13 | 14 | Local | [13 empty] | 0 |  |  |  | 12123.108 |  |  | Public Works | [15 empty] | Likely has base failures, ROW ends half way and turns private | 374.17 | 18 | 6735.06 | 0.1093
| Hall |  | 350002-594 | FY 23 |  |  |  | Nocturne Dr | Fashion Way | Blaze Way | 59 | 14 | Local | [13 empty] | 4 |  |  |  | 50247.216 |  |  | Public Works | [16 empty] | 1163.13 | 24 | 27915.12 | 0.45304
| LP |  |  | FY 23 |  |  |  | Pendleton Rd | Deixie Hwy | County Line |  | 14 | Collector | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works
| Hall |  | 350002-599 | FY 23 |  |  |  | Sally Dr | W Pages Ln | Stephan Dr | 36 | 14 | Local | [13 empty] | 2 |  |  |  | 46032.84 |  |  | Public Works | [16 empty] | 1217.8 | 21 | 25573.8 | 0.41504
| LP |  |  | FY 23 |  |  |  | Schooler Ln | Stonestreet Rd | Dead End | 17 | 14 | Local | [13 empty] | 0 |  |  |  | 25697 |  |  | Public Works | [16 empty] | 1190 | 12 | 14276 | 0.23169
| Hall |  | 350002-599 | FY 23 |  |  |  | Stephan Dr | Dixie Hwy | Vicki Ln | 29.4396 | 14 | Local | [13 empty] | 0 |  |  |  | 100447.704 |  |  | Public Works | [16 empty] | 2218.41 | 24.8 | 55804.28 | 0.90565
| Hall |  | 350002-599 | FY 23 |  |  |  | Vicki Ln | W Pages Ln | Stephan Dr | 30.6944 | 14 | Local | [13 empty] | 2 |  |  |  | 50143.5 |  |  | Public Works | [16 empty] | 1266.25 | 22 | 27857.5 | 0.4521
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Locust Ave | 35 | 15 | Local | [13 empty] | 0 |  |  |  | 6959.304 |  |  | Public Works | [16 empty] | 322.19 | 12 | 3866.28 | 0.062746
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Hazelwood Ave | 35.5932 | 15 | Local | [13 empty] | 15 |  |  |  | 49112.784 |  |  | Public Works | [16 empty] | 1269.19 | 21.5 | 27284.88 | 0.44281
| Hall |  |  | FY 23 |  |  |  | Bicknell Ave | Taylor Blvd | Parthenia Ave | 25.5625 | 15 | Local | [13 empty] | 30 |  |  |  | 146000.0686 |  |  | Public Works | [16 empty] | 2752.4779 | 28.2857 | 81111.1492 | 1.3164
| Hall |  |  | FY 23 |  |  |  | Churchman Ave | Cayuga St | Bluegrass Ave | 22.1273 | 15 | Local | [13 empty] | 6 |  |  |  | 111811.392 |  |  | Public Works | [16 empty] | 2384.91 | 26.4 | 62117.44 | 1.0081
| Hall |  |  | FY 23 |  |  |  | Delmar Ct | Sadie Ln | Dead End | 27 | 15 | Local | [13 empty] | 0 |  |  |  | 22756.536 |  |  | Public Works | [16 empty] | 574.66 | 22 | 12642.52 | 0.20518
| Hall |  |  | FY 23 |  |  |  | Delmar Ln | Naneen Dr | Sadie Ln | 32.8435 | 15 | Local | [13 empty] | 5 |  |  |  | 56828.736 |  |  | Public Works | [16 empty] | 1315.48 | 24 | 31571.52 | 0.51238
| Hall |  |  | FY 23 |  |  |  | Estate Dr | Delmar Ln | Dead End | 19.2977 | 15 | Local | [13 empty] | 11 |  |  |  | 37388.052 |  |  | Public Works | [16 empty] | 907.18 | 22.6667 | 20771.14 | 0.3371
| Hall |  |  | FY 23 |  |  |  | Friden Way | Manslick Rd | Tracy Way | 35.1576 | 15 | Local | [13 empty] | 0 |  |  |  | 41825.052 |  |  | Public Works | [16 empty] | 1010.87 | 23 | 23236.14 | 0.3771
| Hall |  |  | FY 23 |  |  |  | Garvey Ct | Garvey Dr | Dead End | 50 | 15 | Local | [13 empty] | 0 |  |  |  | 9785.664 |  |  | Public Works | [16 empty] | 226.52 | 24 | 5436.48 | 0.088229
| Hall |  |  | FY 23 |  |  |  | Garvey Dr | Estate Dr | Dead End | 19.068 | 15 | Local | [13 empty] | 3 |  |  |  | 48994.416 |  |  | Public Works | [16 empty] | 1223.68 | 22.6667 | 27219.12 | 0.44174
| Hall |  |  | FY 23 |  |  |  | Hazelwood Ave | Bicknell Ave | Bluegrass Ave | 23.8773 | 15 | Local | [13 empty] | 10 |  |  |  | 65304.3784 |  |  | Public Works | [16 empty] | 1511.6754 | 24 | 36280.2102 | 0.5888
| Hall |  |  | FY 23 |  |  |  | Joetta Ct | Rhonda Way | Dead End | 37 | 15 | Local | [13 empty] | 0 |  |  |  | 7142.256 |  |  | Public Works | [16 empty] | 165.33 | 24 | 3967.92 | 0.064396
| Hall |  |  | FY 23 |  |  |  | Knight Rd | Tracy Way | Manslick Rd | 21 | 15 | Local | [13 empty] | 1 |  |  |  | 21031.2 |  |  | Public Works | [16 empty] | 531 | 22 | 11684 | 0.18962
| Hall |  |  | FY 23 |  |  |  | La Salle Ave | Cayuga St | Bluegrass Ave | 34.3206 | 15 | Local | [13 empty] | 10 |  |  |  | 98051.346 |  |  | Public Works | [16 empty] | 2151.96 | 25 | 54472.97 | 0.88405
| Hall |  |  | FY 23 |  |  |  | Locust Ave | Alma Ave | Old Bluegrass Ave | 43 | 15 | Local | [13 empty] | 0 |  |  |  | 9529.56 |  |  | Public Works | [16 empty] | 529.42 | 10 | 5294.2 | 0.08592
| LP |  | 388368-14 | FY 22 |  |  |  | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  | FY 23 |  |  |  | Old Bluegrass Ave | Churchman Ave | Dead end near Locust Ave | 63.3936 | 15 | Local | [13 empty] | 0 |  |  |  | 17200.0653 |  |  | Public Works | [15 empty] | ROW ends just past Locust | 434.3451 | 22 | 9555.5918 | 0.15508
| Hall |  |  | FY 23 |  |  |  | Rhonda Way | Naneen Dr | Garvey Dr | 45.2191 | 15 | Local | [13 empty] | 4 |  |  |  | 57205.44 |  |  | Public Works | [16 empty] | 1324.2 | 24 | 31780.8 | 0.51577
| Hall |  |  | FY 23 |  |  |  | Rolling Ridge Rd | Friden Way | Dead End | 39 | 15 | Local | [13 empty] | 0 |  |  |  | 20820.6 |  |  | Public Works | [16 empty] | 482 | 24 | 11567 | 0.18772
| Hall |  |  | FY 23 |  |  |  | Sadie Ln | Bryce Dr | Dead End (north) | 54.408 | 15 | Local | [13 empty] | 1 |  |  |  | 24534.756 |  |  | Public Works | [16 empty] | 878.21 | 14.6667 | 13630.42 | 0.22121
| Hall |  |  | FY 23 |  |  |  | Tracy Way | Knight Rd | Hazelwood Ave | 62.5221 | 15 | Local | [13 empty] | 1 |  |  |  | 38359.008 |  |  | Public Works | [16 empty] | 887.94 | 24 | 21310.56 | 0.34585
| Hall |  |  | FY 23 |  |  |  | Barbour Manor Ct | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7000 |  |  | Council | [18 empty] | 4681 | 0.075969
| Hall |  |  | FY 23 |  |  |  | Barbour Manor Dr | Barbour Ln | Dead End |  | 16 | Local | [13 empty] | 6 |  |  |  | 200000 |  |  | Council | [18 empty] | 117151 | 1.9013
| Hall |  |  | FY 23 |  |  |  | Branning Rd | Brownsboro Rd | end of Metro R/W | 15 | 16 | Local | [13 empty] | 0 |  |  |  | 27000 |  |  | Public Works | [16 empty] | 596.7397 | 18 | 15000 | 0.24344
| Hall |  |  | FY 23 |  |  |  | Brentler Rd | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 9000 |  |  | Council | [18 empty] | 7123 | 0.1156
| Hall |  |  | FY 23 |  |  |  | Cronin Dr | Halifax Dr | Halifax Dr | 47.1575 | 16 | Local | [13 empty] | 8 |  |  |  | 84968.496 |  |  | Public Works | [16 empty] | 1988.68 | 23.5 | 47204.72 | 0.76609
| Hall |  |  | FY 23 |  |  |  | Debsom Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7500 |  |  | Council | [18 empty] | 6759 | 0.10969
| LP |  | 388368-20 | FY 23 |  |  |  | Hitt Rd | Ballardsville Rd | County Line | 46 | 16 | Sec Coll | [13 empty] | 5 |  |  |  | 18747 |  |  | Public Works | [16 empty] | 4369.7222 | 21.9936 | 96106 | 1.5597
| Hall |  |  | FY 23 |  |  |  | Jenica Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 25000 |  |  | Council | [18 empty] | 16165 | 0.26234
| Hall |  |  | FY 23 |  |  |  | Machupe Ct | Machupe Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | [18 empty] | 4920 | 0.079847
| Hall |  |  | FY 23 |  |  |  | Machupe Dr | Barbour Manor Dr | Machupe Ct |  | 16 | Local | [13 empty] | 3 |  |  |  | 6000 |  |  | Council | [18 empty] | 5388 | 0.087443
| Hall |  |  | FY 23 |  |  |  | Oak Pointe Dr (south) | Halifax Dr | Halifax Dr | 27 | 16 | Local | [13 empty] | 2 |  |  |  | 60335.712 |  |  | Public Works | [16 empty] | 1396.66 | 24 | 33519.84 | 0.544
| Hall |  |  | FY 23 |  |  |  | Spring Farm Rd | Wolf Pen Branch Rd | 4945 Spring Farm Rd | 33.8399 | 16 | Local | [13 empty] | 0 |  |  |  | 140331.8097 |  |  | Public Works | [16 empty] | 3543.7326 | 22 | 77962.1165 | 1.2653
| Hall |  |  | FY 23 |  |  |  | Tamerlane Ct | Tamerlane Rd | Dead End | 27 | 16 | Local | [13 empty] | 0 |  |  |  | 9991.8 |  |  | Public Works | [16 empty] | 278 | 20 | 5551 | 0.090088
| Hall |  |  | FY 23 |  |  |  | Tamerlane Rd | Woodside Rd | Tuckaho Rd | 32.5001 | 16 | Local | [13 empty] | 0 |  |  |  | 41516.496 |  |  | Public Works | [16 empty] | 961.03 | 24 | 23064.72 | 0.37432
| Hall |  |  | FY 23 |  |  |  | Therina Ct | Therina Way | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | [18 empty] | 3399 | 0.055163
| Hall |  |  | FY 23 |  |  |  | Therina Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 3 |  |  |  | 20000 |  |  | Council | [18 empty] | 14191 | 0.23031
| Hall |  |  | FY 23 |  |  |  | Tuckaho Rd | Tamerlane Rd | 2510 Tuckaho Rd | 38 | 16 | Local | [13 empty] | 0 |  |  |  | 15400.8644 |  |  | Public Works | [16 empty] | 388.9107 | 22 | 8556.0358 | 0.13886
| Hall |  | 350002-392 | FY 22 |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 | FY 22 |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-392 | FY 22 |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  | FY 23 |  |  |  | Glen Meadow Rd | Brownsboro Glen Rd | Spring Gate Dr | 16 | 17 | Local | [13 empty] | 4 |  |  |  | 10759.716 |  |  | Public Works | [16 empty] | 271.71 | 22 | 5977.62 | 0.097012
| Hall |  |  | FY 23 |  |  |  | Murphy Ln | Halifax Dr | Ballardsville Rd | 37 | 17 | Pri Coll | [13 empty] | 0 |  |  |  | 115825 |  |  | Public Works | [16 empty] | 2969.88 | 20 | 59397.6 | 0.96397
| LP |  | 388368-19 | FY 23 |  |  |  | N English Station Rd | Aiken Rd | Old Henry Rd | 31 | 17 | Min Art | [13 empty] | 0 |  |  |  | 122122 |  |  | Public Works | [16 empty] | 2423.0596 | 24 | 58153.4298 | 0.94378
| Hall |  |  | FY 23 |  |  |  | Oakland Forest Ct | Spring Mill Rd | Dead End | 47 | 17 | Local | [13 empty] | 0 |  |  |  | 11897.28 |  |  | Public Works | [16 empty] | 275.4 | 24 | 6609.6 | 0.10727
| LP |  | 388368-23 | FY 23 |  |  |  | Old Harrods Creek Rd | LaGrange Rd | End of Metro R/W | 32.4157 | 17 | Sec Coll | [13 empty] | 0 |  |  |  | 38914 |  |  | Public Works | [16 empty] | 1085.356 | 19 | 19956.0265 | 0.32387
| Hall |  | 350002-392 | FY 22 |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Ct | Rock Bay Dr | Dead End | 27.7903 | 17 | Local | [13 empty] | 3 |  |  |  | 28799.712 |  |  | Public Works | [16 empty] | 666.66 | 24 | 15999.84 | 0.25966
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Pl | Rolling Springs Ct | Dead End | 53 | 17 | Local | [13 empty] | 0 |  |  |  | 12216.528 |  |  | Public Works | [16 empty] | 282.79 | 24 | 6786.96 | 0.11015
| Hall |  |  | FY 23 |  |  |  | Spring Forest Ct | Spring Forest Dr | Dead End | 36 | 17 | Local | [13 empty] | 0 |  |  |  | 8882.352 |  |  | Public Works | [16 empty] | 205.61 | 24 | 4934.64 | 0.080085
| Hall |  |  | FY 23 |  |  |  | Spring Forest Dr | Spring Mill Rd | Dead End | 31.2435 | 17 | Local | [13 empty] | 2 |  |  |  | 20158.848 |  |  | Public Works | [16 empty] | 466.64 | 24 | 11199.36 | 0.18176
| Hall |  |  | FY 23 |  |  |  | Spring Gate Dr | Chamberlain Ln | Stone Glen Rd | 20.3691 | 17 | Local | [13 empty] | 8 |  |  |  | 35943.264 |  |  | Public Works | [16 empty] | 832.02 | 24 | 19968.48 | 0.32407
| Hall |  |  | FY 23 |  |  |  | Spring Mill Pl | Spring Mill Rd | Dead End | 25 | 17 | Local | [13 empty] | 0 |  |  |  | 22846.32 |  |  | Public Works | [16 empty] | 528.85 | 24 | 12692.4 | 0.20599
| Hall |  |  | FY 23 |  |  |  | Spring Mill Rd | Rock Bay Dr | Rock Bay Dr | 33.8903 | 17 | Local | [13 empty] | 14 |  |  |  | 140905.008 |  |  | Public Works | [16 empty] | 3261.69 | 24 | 78280.56 | 1.2704
| Hall |  |  | FY 23 |  |  |  | Woods View Pl | Spring Mill Rd | Dead End | 21 | 17 | Local | [13 empty] | 0 |  |  |  | 31692.384 |  |  | Public Works | [16 empty] | 733.62 | 24 | 17606.88 | 0.28574
| Hall |  | 350002-559 | FY 22 |  |  |  | Dorsey Ln | N Hurstbourne | Nearest Joint |  | 18 | Pri Coll | [17 empty] | 41000
| Hall |  |  | FY 23 |  |  |  | Dorsey Ln | Hurstbourne Rd | Mayhurst |  | 18 | Collector | [13 empty] | 0 |  |  |  | 41000 |  |  | Council | [18 empty] | 20000 | 0.32458
| Hall |  |  | FY 23 |  |  |  | Dorsey Way | Elsmete Cir | Dead End |  | 18 | Local | [13 empty] | 0 |  |  |  | 126000 |  |  | Council | Republican Pool | 90k |  | CIF? | 36k | [13 empty] | 67992 | 1.1035
| Hall |  |  | FY 23 |  |  |  | Hobbs Station Rd | Lodge Hill Rd (south) | Sable Wing Cir (south) | 34.5421 | 18 | Local | [13 empty] | 14 |  |  |  | 343037 |  |  | Public Works | [16 empty] | 4051.56 | 51.2857 | 190575.9 | 3.0929
| Hall |  |  | FY 23 |  |  |  | Talon Way | Dead End | Dead End | 30.4359 | 18 | Local | [13 empty] | 0 |  |  |  | 39874 |  |  | Public Works | [16 empty] | 1006.93 | 22 | 22152.46 | 0.35952
| Hall |  |  | FY 23 |  |  |  | UPS Dr | Whipps Mill Rd | Ormsby Station Rd | 34 | 18 | Pri Coll | [13 empty] | 2 |  |  |  | 86968 |  |  | Public Works | [16 empty] | 1238.86 | 36 | 44598.96 | 0.7238
| LP |  |  | FY 23 |  |  |  | Aiken Rd | Bush Farm Rd | N Beckley Station Rd | 22.1639 | 19 | Sec Coll | [13 empty] | 0 |  |  |  | 102472 |  |  | Public Works | [16 empty] | 2201.95 | 23.5 | 52549.75 | 0.85284
| Hall |  | 350002-559 | FY 22 |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  |  | FY 23 |  |  |  | Forest Oaks Dr | Arnold Palmer Blvd | N Beckley Station Rd | 32.0199 | 19 | Local | [13 empty] | 2 |  |  |  | 133678.548 |  |  | Public Works | [16 empty] | 3064.06 | 24 | 74265.86 | 1.2053
| Hall |  |  | FY 23 |  |  |  | Forest Trace Ct | Spring Mill Rd | Dead End | 79 | 19 | Local | [17 empty] | 7902 |  |  | Public Works | [18 empty] | 4390 | 0.071246
| Hall |  |  | FY 23 |  |  |  | Garden Hill Pl | N Beckley Station Rd | Dead End | 67 | 19 | Local | [13 empty] | 0 |  |  |  | 38556.54 |  |  | Public Works | [16 empty] | 973.65 | 22 | 21420.3 | 0.34763
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Pl | Golden Leaf Way | Dead End | 24.4599 | 19 | Local | [13 empty] | 4 |  |  |  | 37940.652 |  |  | Public Works | [16 empty] | 921.38 | 23 | 21078.14 | 0.34208
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Way (all) | Forest Oaks Dr | Golden Leaf Way | 24.4823 | 19 | Local | [13 empty] | 6 |  |  |  | 80431.938 |  |  | Public Works | [16 empty] | 1933.05 | 23 | 44684.41 | 0.72519
| Hall |  |  | FY 23 |  |  |  | Greensbrook Pl | Forest Oaks Dr | Dead End | 40 | 19 | Local | [13 empty] | 2 |  |  |  | 24575.184 |  |  | Public Works | [16 empty] | 568.87 | 24 | 13652.88 | 0.22157
| Hall |  |  | FY 23 |  |  |  | Hiawatha Ave | Heafer Rd | N English Station Rd | 26.069 | 19 | Local | [13 empty] | 5 |  |  |  | 53858.2262 |  |  | Public Works | [16 empty] | 1789.2936 | 22.25 | 29921.2368 | 0.4856
| Hall |  |  | FY 23 |  |  |  | Hines Ct | Heafer Rd | Dead End | 34 | 19 | Local | [13 empty] | 2 |  |  |  | 14106.816 |  |  | Public Works | [16 empty] | 489.82 | 16 | 7837.12 | 0.12719
| Hall |  |  | FY 23 |  |  |  | Hines Rd | Berrytown Rd | Dead End | 36.953 | 19 | Local | [13 empty] | 0 |  |  |  | 24453.3305 |  |  | Public Works | [16 empty] | 930.572 | 14 | 13585.1836 | 0.22048
| Hall |  |  | FY 23 |  |  |  | Lilly Ln | LaGrange Rd | Dead End | 40 | 19 | Local | [13 empty] | 0 |  |  |  | 48427.92 |  |  | Public Works | [16 empty] | 672.61 | 20 | 13452.2 | 0.21832
| Hall |  |  | FY 23 |  |  |  | Majestic Woods Pl | Forest Oaks Dr | Dead End | 68 | 19 | Local | [13 empty] | 2 |  |  |  | 15169.572 |  |  | Public Works | [16 empty] | 383.07 | 22 | 8427.54 | 0.13677
| Hall |  |  | FY 23 |  |  |  | Treeline Ct | Winding Creek Pl | Dead End | 23 | 19 | Local | [13 empty] | 0 |  |  |  | 11213.856 |  |  | Public Works | [16 empty] | 129.79 | 48 | 6229.92 | 0.10111
| LP |  |  | FY 23 |  |  |  | Urton Ln | N English Station Rd | Rockbridge Rd | 51.4001 | 19 | Pri Coll | [13 empty] | 0 |  |  |  | 389882 |  |  | Public Works | [16 empty] | 9449.3838 | 24.7143 | 199939.2989 | 3.2448
| Hall |  |  | FY 23 |  |  |  | Whisperwood Trace | Forest Oaks Dr | Dead End | 54 | 19 | Local | [13 empty] | 2 |  |  |  | 13030.38 |  |  | Public Works | [16 empty] | 329.05 | 22 | 7239.1 | 0.11748
| Hall |  |  | FY 23 |  |  |  | Winding Creek Ct | Winding Creek Pl | Dead End | 24 | 19 | Local | [13 empty] | 0 |  |  |  | 8396.784 |  |  | Public Works | [16 empty] | 194.37 | 24 | 4664.88 | 0.075707
| Hall |  |  | FY 23 |  |  |  | Winding Creek Pl | Oakhurst Rd | Dead End | 32.4998 | 19 | Local | [13 empty] | 4 |  |  |  | 47345.904 |  |  | Public Works | [16 empty] | 1095.97 | 24 | 26303.28 | 0.42688
| Hall |  |  | FY 23 |  |  |  | Winterbranch Way | Forest Oaks Dr | Dead End | 72 | 19 | Local | [13 empty] | 2 |  |  |  | 33957 |  |  | Public Works | [16 empty] | 857.5 | 22 | 18865 | 0.30616
| Hall |  |  | FY 23 |  |  |  | Wood Thrush Trace | Golden Leaf Pl | Dead End | 18 | 19 | Local | [13 empty] | 0 |  |  |  | 10616.4 |  |  | Public Works | [16 empty] | 245.75 | 24 | 5898 | 0.095719
| Hall |  |  | FY 23 |  |  |  | Burkett Ct | Mary Dell Ln | Dead End | 52 | 20 | Local | [13 empty] | 0 |  |  |  | 24655.752 |  |  | Public Works | [16 empty] | 257.85 | 18 | 4641.3 | 0.075324
| LP |  |  | FY 23 |  |  |  | Cenoweth Run Service Rd | Off Chenoweth Run Rd |  |  | 20 | Local | [13 empty] | 0 |  |  |  | 35000 |  |  | Council/PW | See Chenoweth Run
| Hall |  |  | FY 23 |  |  |  | Chenoweth Park Ln | Mary Dell Ln | Dead End (south) | 22.4943 | 20 | Local | [13 empty] | 0 |  |  |  | 55485.936 |  |  | Public Works | [16 empty] | 622.62 | 22 | 13697.64 | 0.2223
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Rd | Taylorsville Rd | Old Heady Rd |  | 20 | Collector | [13 empty] | 0 |  |  |  | 600000 |  |  | Council/PW | Council | 252493.22 | [16 empty] | 321828 | 5.223
| LP |  |  | FY 23 |  |  |  | Dawson Hill Rd | Brush Run Rd | End of Metro R/W | 42.6283 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 568462 |  |  | Public Works | [16 empty] | 16893.8891 | 18.1111 | 291518.9848 | 4.7311
| Hall |  |  | FY 23 |  |  |  | Dry Ridge Ln | Dry Ridge Rd | Dead End | 18 | 20 | Local | [13 empty] | 0 |  |  |  | 7328.232 |  |  | Public Works | [16 empty] | 3076.73 | 12 | 36920.76 | 0.59919
| Hall |  |  | FY 23 |  |  |  | Hopewell Rd | Taylorsville Rd | Dead End | 23.2664 | 20 | Local | [13 empty] | 0 |  |  |  | 94449.744 |  |  | Public Works | [16 empty] | 2707.72 | 20.5 | 52472.08 | 0.85158
| Hall |  |  | FY 23 |  |  |  | Mary Dell Ln | Billtown Rd | Cynthia Dr | 26.1581 | 20 | Local | [13 empty] | 7 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 1401.16 | 22 | 30825.52 | 0.50027
| LP |  |  | FY 22 |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  |  | FY 23 |  |  |  | Old Heady Rd | Dead End | Dead End | 18.0252 | 20 | Local | [13 empty] | 0 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 669.4406 | 20 | 13388.8119 | 0.21729
| LP |  |  | FY 23 |  |  |  | Old Heady Rd | Taylorsville Rd | Hopewell Rd | 42.6384 | 20 | Sec Coll | [13 empty] | 10 |  |  |  | 50671 |  |  | Public Works | [16 empty] | 12887.1089 | 19.7273 | 256754.4486 | 4.1669
| LP |  |  | FY 23 |  |  |  | Rehl Rd | S Pope Lick Rd | S English Station Rd | 41 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 76297 |  |  | Public Works | [16 empty] | 1956.3229 | 20 | 39126.4576 | 0.63499
| Hall |  |  | FY 23 |  |  |  | Sloane Ct | Mary Dell Ln | Dead End | 61 | 20 | Local | [13 empty] | 0 |  |  |  | 8354.34 |  |  | Public Works | [16 empty] | 226.18 | 18 | 4071.24 | 0.066073
| Hall |  | 350002-505 | FY 22 |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | 208260.52 | July | [16 empty] | Asphalt done on forum/school Need to make concrete repairs | 1121 | 24 | 26906 | 0.43666
| Hall |  |  | FY 23 |  |  |  | Campobello St | Howard St | Zeta Ct | 79 | 21 | Local | [17 empty] | 30106.944 |  |  | Public Works | [18 empty] | 16726 | 0.27145
| Hall |  |  | FY 23 |  |  |  | Carroll Ave | Durrett Ln | Scholar St | 27.7446 | 21 | Local | [13 empty] | 0 |  |  |  | 63563.112 |  |  | Public Works | [16 empty] | 1773.87 | 20 | 35312.84 | 0.5731
| Hall |  |  | FY 23 |  |  |  | Cavelle Ave | Durrett Ln | Dead End | 26.7981 | 21 | Local | [13 empty] | 0 |  |  |  | 58023.216 |  |  | Public Works | [16 empty] | 1790.84 | 18 | 32235.12 | 0.52315
| Hall |  |  | FY23 |  |  |  | Crittenden Dr | Grade Lane | Dead End |  | 21 | Local | [17 empty] | 790710 |  |  | Public Works | [18 empty] | 395355 | 6.4163
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [13 empty] | LWC Project in area | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-603 | FY 23 |  |  |  | E Kenwood Dr | Southside Dr | Tecumseh Ave | 22.2323 | 21 | Pri Coll | [13 empty] | 6 |  |  |  | 90116 |  |  | Public Works | [16 empty] | 1992.2543 | 23.2 | 46213.3095 | 0.75
| Hall |  |  | FY 23 |  |  |  | Greenleaf Rd | Rosemary Dr | Fern Dr | 25.4686 | 21 | Local | [13 empty] | 6 |  |  |  | 51594.948 |  |  | Public Works | [16 empty] | 1691.27 | 17 | 28663.86 | 0.46519
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  |  | FY 23 |  |  |  | Howard St | Carroll Ave | Dead End | 35.3777 | 21 | Local | [13 empty] | 0 |  |  |  | 47118.96 |  |  | Public Works | [16 empty] | 1583.17 | 16.25 | 26177.2 | 0.42483
| Hall |  |  | FY 23 |  |  |  | Lacona Ln | Carroll Ave | Campobello St | 20 | 21 | Local | [13 empty] | 0 |  |  |  | 43749.504 |  |  | Public Works | [16 empty] | 1012.72 | 24 | 24305.28 | 0.39445
| Hall |  |  | FY 23 |  |  |  | Meridale Ave | W Southern Heights Ave | S 2nd St | 59 | 21 | Local | [13 empty] | 2 |  |  |  | 47460.15 |  |  | Public Works | [16 empty] | 1054.67 | 25 | 26366.75 | 0.42791
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [13 empty] | LWC Project in area | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [13 empty] | LWC Project in area | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  | FY 23 |  |  |  | S 2nd St | W Southern Heights Ave | W Wellington Ave | 30.9927 | 21 | Local | [13 empty] | 10 |  |  |  | 107083.08 |  |  | Public Works | [16 empty] | 2074.1 | 29.75 | 59490.6 | 0.96548
| Hall |  |  | FY 23 |  |  |  | Scholar St | Carroll Ave | Campobello St | 14 | 21 | Local | [13 empty] | 0 |  |  |  | 43307.298 |  |  | Public Works | [16 empty] | 1046.07 | 23 | 24059.61 | 0.39047
| Hall |  | 350002-603 | FY 23 |  |  |  | W Kenwood Dr | Tecumseh Ave | New Cut Rd | 45.879 | 21 | Pri Coll | [13 empty] | 7 |  |  |  | 130320 |  |  | Public Works | [16 empty] | 2906.21 | 22.8 | 66830.86 | 1.0846
| Hall |  |  | FY 23 |  |  |  | W Wampum Ave | S 3rd St | S 1st St | 27.4999 | 21 | Local | [13 empty] | 2 |  |  |  | 45249.516 |  |  | Public Works | [16 empty] | 966.87 | 26 | 25138.62 | 0.40798
| Hall |  |  | FY 23 |  |  |  | W Wellington Ave | Southern Pkwy | S 1st St | 31.391 | 21 | Local | [13 empty] | 4 |  |  |  | 80171.1 |  |  | Public Works | [16 empty] | 1484.65 | 30 | 44539.5 | 0.72284
| Hall |  | 350002-596 | FY 23 |  |  |  | Woodmore Ave | New Cut Rd | Southside Dr | 45.5274 | 21 | Local | [13 empty] | 0 |  |  |  | 116415.36 |  |  | Public Works | [16 empty] | 2694.8 | 24 | 64675.2 | 1.0496
| Hall |  |  | FY 23 |  |  |  | Zeta Ct | Campobello St | Dead End | 52 | 21 | Local | [13 empty] | 0 |  |  |  | 3236.76 |  |  | Public Works | [16 empty] | 89.91 | 20 | 1798.2 | 0.029183
| Hall |  |  | FY 23 |  |  |  | Artis Pl | Artis Way | Dead End | 39 | 22 | Local | [13 empty] | 2 |  |  |  | 7681.212 |  |  | Public Works | [16 empty] | 193.97 | 22 | 4267.34 | 0.069255
| Hall |  |  | FY 23 |  |  |  | Artis Way | Beulah Church Rd | Dead End | 39.0264 | 22 | Local | [13 empty] | 10 |  |  |  | 133542.432 |  |  | Public Works | [16 empty] | 3091.26 | 24 | 74190.24 | 1.204
| LP |  |  | FY 23 |  |  |  | Brentlinger Ln (Old Alignment) | Dobson Ln | Dead End | 30 | 22 | Local | [13 empty] | 0 |  |  |  | 8915 |  |  | Public Works | [18 empty] | 4953 | 0.080383
| LP |  |  | FY 23 |  |  |  | Dobson Ln | Brentlinger Ln | Dead End | 17.6261 | 22 | Local | [13 empty] | 0 |  |  |  | 49091 |  |  | Public Works | [16 empty] | 2400.0313 | 10.6667 | 27272.787 | 0.44261
| Hall |  |  | FY 23 |  |  |  | Fox Ledge Ct | Artis Way | Dead End | 50 | 22 | Local | [13 empty] | 0 |  |  |  | 12031.56 |  |  | Public Works | [16 empty] | 334.21 | 20 | 6684.2 | 0.10848
| Hall |  |  | FY 23 |  |  |  | Gainsborough Dr | Johnson School Rd | Annalisa Dr | 32.3999 | 22 | Local | [13 empty] | 6 |  |  |  | 87744.284 |  |  | Public Works | [16 empty] | 2076.5444 | 23.4286 | 48746.8245 | 0.79112
| LP |  |  | FY 23 |  |  |  | Johnson School Rd | Beulah Church Rd | Cedar Creek Rd | 50.9745 | 22 | Sec Coll | [13 empty] | 0 |  |  |  | 291737 |  |  | Public Works | [16 empty] | 7438.24 | 20 | 149608.76 | 2.428
| Hall |  |  | FY 23 |  |  |  | Ledge Pointe Ct | Artis Way | Dead End | 63 | 22 | Local | [13 empty] | 0 |  |  |  | 11113.56 |  |  | Public Works | [16 empty] | 308.71 | 20 | 6174.2 | 0.1002
| LP |  | 366368-18 | FY 23 |  |  |  | S Watterson Trl | Bardstown Rd | S Hurstbourne Pkwy | 53.8655 | 22 | Pri Coll | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works | [16 empty] | 7830.1598 | 21.3333 | 177103.3586 | 2.8742
| Hall |  |  | FY 23 |  |  |  | Stone Ledge Ct | Stone Ledge Rd | Dead End | 71 | 22 | Local | [13 empty] | 0 |  |  |  | 11923.848 |  |  | Public Works | [16 empty] | 368.02 | 18 | 6624.36 | 0.10751
| Hall |  |  | FY 23 |  |  |  | Stone Ledge Rd | Artis Way | Dead End | 54.5897 | 22 | Local | [13 empty] | 2 |  |  |  | 46839.96 |  |  | Public Works | [16 empty] | 1301.11 | 20 | 26022.2 | 0.42232
| Hall |  |  | FY 23 |  |  |  | Warrenton Hill Ct | Artis Way | Dead End | 38.1799 | 22 | Local | [13 empty] | 0 |  |  |  | 35755.2 |  |  | Public Works | [16 empty] | 993.2 | 20 | 19864 | 0.32238
| Hall |  |  | FY 23 |  |  |  | Wellington Hill Ct | Warrenton Hill Ct | Dead End | 31 | 22 | Local | [13 empty] | 0 |  |  |  | 29155.32 |  |  | Public Works | [16 empty] | 809.87 | 20 | 16197.4 | 0.26287
| Hall |  | 350002-597 | FY 23 |  |  |  | Adkins Rd | Honor Ave | Dead End | 44.5373 | 23 | Local | [13 empty] | 0 |  |  |  | 43504.956 |  |  | Public Works | [16 empty] | 1098.61 | 22 | 24169.42 | 0.39225
| Hall |  | 350002-597 | FY 23 |  |  |  | Amalfi Ave | Dead End | Honor Ave | 58.5583 | 23 | Local | [13 empty] | 0 |  |  |  | 38727.108 |  |  | Public Works | [16 empty] | 940.89 | 22.6667 | 21515.06 | 0.34917
| Hall |  | 350002-597 | FY 23 |  |  |  | Beth Rd | Denise Dr | Dead End | 45.0781 | 23 | Local | [13 empty] | 0 |  |  |  | 80040.96 |  |  | Public Works | [16 empty] | 1927.18 | 23.3333 | 44467.2 | 0.72166
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherita Rd | Denise Dr | Dead End | 52.2629 | 23 | Local | [13 empty] | 0 |  |  |  | 41878.98 |  |  | Public Works | [16 empty] | 1057.55 | 22 | 23266.1 | 0.37759
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherriville Rd | Manslick Rd | Amalfi Ave | 67 | 23 | Local | [13 empty] | 0 |  |  |  | 26279.856 |  |  | Public Works | [16 empty] | 608.33 | 24 | 14599.92 | 0.23694
| Hall |  | 350002-555 | FY 22 |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  | 350002-597 | FY 23 |  |  |  | Denise Dr | Lois Ave | Dead End | 33.26 | 23 | Local | [13 empty] | 0 |  |  |  | 189163.728 |  |  | Public Works | [16 empty] | 4378.79 | 24 | 105090.96 | 1.7055
| Hall |  | 350002-597 | FY23 |  |  |  | Elise Way | Shepherdsville Rd | Dead End |  | 23 | Local | [13 empty] | 0 |  |  |  | 5000
| Hall |  | 350002-597 | FY 23 |  |  |  | Honor Ave | Adkins Rd | Dead End | 50.0632 | 23 | Local | [13 empty] | 0 |  |  |  | 68010.732 |  |  | Public Works | [16 empty] | 1652.42 | 22.8 | 37783.74 | 0.6132
| Hall |  | 350002-597 | FY 23 |  |  |  | Lois Ave | Beth Rd | Dead End | 58.3886 | 23 | Local | [13 empty] | 0 |  |  |  | 87275.016 |  |  | Public Works | [16 empty] | 2033.95 | 23.3333 | 48486.12 | 0.78689
| Hall |  | 350002-597 | FY 23 |  |  |  | Senator Ln | Denise Dr | Honor Ave | 19 | 23 | Local | [13 empty] | 0 |  |  |  | 38432.016 |  |  | Public Works | [16 empty] | 889.63 | 24 | 21351.12 | 0.34651
| Hall |  | 350002-593 | FY 23 |  |  |  | Abbydale Ct | Wood Hollow Rd | Dead End | 36 | 24 | Local | [13 empty] | 0 |  |  |  | 19077.12 |  |  | Public Works | [16 empty] | 588.8 | 18 | 10598.4 | 0.172
| Hall |  | 350002-591 | FY 23 |  |  |  | Bellflower Dr | Blue Lick Rd | Dead End | 36.645 | 24 | Local | [13 empty] | 0 |  |  |  | 24800.76 |  |  | Public Works | [16 empty] | 607.95 | 23 | 13778.2 | 0.22361
| Hall |  | 350002-591 | FY 23 |  |  |  | Bluebell Dr | Blue Lick Rd | Narcissus Dr | 48.3834 | 24 | Local | [13 empty] | 2 |  |  |  | 113040.576 |  |  | Public Works | [16 empty] | 2616.68 | 24 | 62800.32 | 1.0192
| Hall |  |  | FY 23 |  |  |  | Burnt Cedar Ct | Burnt Cedar Ln | Dead End | 36 | 24 | Local | [13 empty] | 0 |  |  |  | 11867 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  | 7192 | 0.11672
| Hall |  |  | FY 23 |  |  |  | Burnt Cedar Ln | Dead End | Dead End | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 39631 |  |  | Council | See Burnt cedar | [17 empty] | 24019 | 0.38981
| Hall |  |  | FY 23 |  |  |  | Cameo Ct | Pebblebrook Ln | Dead End | 33 | 24 | Local | [13 empty] | 0 |  |  |  | 7625 |  |  | Council | See Burnt cedar | [17 empty] | 4621 | 0.074995
| Hall |  |  | FY 23 |  |  |  | Cathay Ct | Linda Rd | Dead End | 35 | 24 | Local | [13 empty] | 0 |  |  |  | 17416 |  |  | Council | See Burnt cedar | [17 empty] | 10555 | 0.1713
| Hall |  |  | FY 23 |  |  |  | Delee Way | Narcissus Dr | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 15685.056 |  |  | Public Works | [16 empty] | 363.08 | 24 | 8713.92 | 0.14142
| Hall |  |  | FY 22 |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  | 350002-591 | FY 23 |  |  |  | Narcissus Dr | Bluebell Dr | Dead End | 19.0231 | 24 | Local | [13 empty] | 2 |  |  |  | 51919.488 |  |  | Public Works | [16 empty] | 1201.84 | 24 | 28844.16 | 0.46812
| Hall |  |  | FY 23 |  |  |  | Pebblebrook Ln | Burnt Cedar Ln | Santa Paula Ln |  | 24 | Local | [17 empty] | 5000 |  |  | Council Funded | See Burnt cedar
| LP |  |  | FY 23 |  |  |  | Smyrna Rd | Briscoe Ln | Outer Loop | 26 | 24 | Sec Coll | [13 empty] | 0 |  |  |  | 97192 |  |  | Public Works | [16 empty] | 2265.55 | 22 | 49842.1 | 0.80889
| Hall |  | 350002-593 | FY 23 |  |  |  | Tolkien Ct | Wood Hollow Rd | Dead End | 16 | 24 | Local | [13 empty] | 0 |  |  |  | 19069.02 |  |  | Public Works | [16 empty] | 588.55 | 18 | 10593.9 | 0.17193
| Hall |  | 350002-591 | FY 23 |  |  |  | Tulip Cir | Bluebell Dr | Dead End | 56 | 24 | Local | [13 empty] | 0 |  |  |  | 8485.488 |  |  | Public Works | [16 empty] | 214.28 | 22 | 4714.16 | 0.076507
| Hall |  | 350002-591 | FY 23 |  |  |  | Weigela Dr | Blue Lick Rd | Bluebell Dr | 45 | 24 | Local | [13 empty] | 0 |  |  |  | 23762.592 |  |  | Public Works | [16 empty] | 550.06 | 24 | 13201.44 | 0.21425
| Hall |  | 350002-593 | FY 23 |  |  |  | Wood Hollow Rd | Oldshire Rd | Woodsend Rd | 37.445 | 24 | Local | [13 empty] | 6 |  |  |  | 34705.152 |  |  | Public Works | [16 empty] | 803.36 | 24 | 19280.64 | 0.31291
| Hall |  | 350002-593 | FY 23 |  |  |  | Woodsend Rd | Dead End | Dead End | 26.2616 | 24 | Local | [13 empty] | 2 |  |  |  | 34921.368 |  |  | Public Works | [16 empty] | 1077.82 | 18 | 19400.76 | 0.31486
| Hall |  | 350002-602 | FY 23 |  |  |  | Bamberrie Cross Rd | Chet Ln | 3rd Street Rd | 46.757 | 25 | Local | [13 empty] | 0 |  |  |  | 41704 |  |  | Public Works | [16 empty] | 1053.13 | 22 | 23168.86 | 0.37601
| LP |  | 388368-4 | FY 22 |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded
| Hall |  | 350002-602 | FY 23 |  |  |  | Burr Ln | Carol Way | Dead End | 28 | 25 | Local | [13 empty] | 0 |  |  |  | 35239 |  |  | Public Works | [16 empty] | 815.71 | 24 | 19577.04 | 0.31772
| Hall |  | 350002-602 | FY 23 |  |  |  | Carol Way | Manslick Rd | Chet Ln | 20.8911 | 25 | Local | [13 empty] | 0 |  |  |  | 56753 |  |  | Public Works | [16 empty] | 1433.15 | 22 | 31529.3 | 0.51169
| Hall |  | 350002-602 | FY 23 |  |  |  | Cartledge Ct | Chet Ln | 3rd Street Rd | 45 | 25 | Local | [13 empty] | 0 |  |  |  | 33549 |  |  | Public Works | [16 empty] | 1164.91 | 16 | 18638.56 | 0.30249
| Hall |  | 350002-602 | FY 23 |  |  |  | Chet Ln | Carol Way | Cartledge Ct | 26.9408 | 25 | Local | [13 empty] | 0 |  |  |  | 32341 |  |  | Public Works | [16 empty] | 816.69 | 22 | 17967.18 | 0.29159
| Hall |  | 350002-595 | FY 23 |  |  |  | Constitution Dr | Manslick Rd | Dead End | 45.4192 | 25 | Local | [13 empty] | 0 |  |  |  | 49339 |  |  | Public Works | [16 empty] | 1105.27 | 25 | 27410.36 | 0.44485
| LP |  | 388368-1 | FY 23 |  |  |  | Fordhaven Rd | St Anthony Church Rd | public road end | 37 | 25 | Local | [13 empty] | 0 |  |  |  | 70953 |  |  | Public Works | [16 empty] | 1359.2584 | 29 | 39418.4924 | 0.63973
| Hall |  | 350002-595 | FY 23 |  |  |  | Heritage Pl | Manslick Rd | Dead End | 26 | 25 | Local | [13 empty] | 0 |  |  |  | 32230 |  |  | Public Works | [16 empty] | 596.85 | 30 | 17905.5 | 0.29059
| LP |  | 388368-1 | FY 23 |  |  |  | Manslick Rd | St Anthony Church Rd | Palatka Rd | 41.9559 | 25 | Pri Coll | [13 empty] | 0 |  |  |  | 357026 |  |  | Public Works | [16 empty] | 8143.41 | 22.6 | 183090.48 | 2.9714
| Hall |  | 350002-595 | FY 23 |  |  |  | Potomac Pl | Manslick Rd | Dead End | 30 | 25 | Local | [13 empty] | 0 |  |  |  | 28850 |  |  | Public Works | [16 empty] | 616.45 | 26 | 16027.7 | 0.26012
| Hall |  | 350002-595 | FY 23 |  |  |  | Quaker Ct | Constitution Dr | Dead End | 17 | 25 | Local | [13 empty] | 0 |  |  |  | 14012 |  |  | Public Works | [16 empty] | 389.22 | 20 | 7784.4 | 0.12633
| Hall |  | 350002-544 | FY 22 |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| LP |  | 388368-1 | FY 23 |  |  |  | Springfield Dr | St Anthony Church Rd | public road end | 14 | 25 | Local | [13 empty] | 0 |  |  |  | 38326 |  |  | Public Works | [16 empty] | 887.1779 | 24 | 21292.2706 | 0.34556
| LP |  | 388368-1 | FY 22 |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  |  | FY 23 |  |  |  | Brockton Ln | Hendon Rd | Commander Dr | 41.8604 | 26 | Local | [13 empty] | 0 |  |  |  | 92931.3659 |  |  | Public Works | [16 empty] | 2239.9299 | 23 | 51628.5366 | 0.83789
| Hall |  |  | FY 23 |  |  |  | Bryan Way | Dogwood Dr | Deibel Way | 37 | 26 | Local | [13 empty] | 6 |  |  |  | 47250 |  |  | Council | [18 empty] | 27008 | 0.43832
| Hall |  |  | FY 23 |  |  |  | Commander Dr | Brockton Ln | Herb Ln | 35 | 26 | Local | [13 empty] | 1 |  |  |  | 39974.22 |  |  | Public Works | [16 empty] | 854.15 | 26 | 22207.9 | 0.36041
|  |  |  | FY 23 |  |  |  | D26 Paving |  |  |  | 26 | [18 empty] | 122844 |  |  | Council | [19 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doreen Way | Brockton Ln | Dead End | 32 | 26 | Local | [13 empty] | 4 |  |  |  | 69295.464 |  |  | Public Works | [18 empty] | 38497 | 0.62477
| Hall |  |  | FY 23 |  |  |  | Eastside Ct | Eastside Dr | Dead End | 69 | 26 | Local | [13 empty] | 0 |  |  |  | 3877.2 |  |  | Public Works | [16 empty] | 89.75 | 24 | 2154 | 0.034958
| Hall |  |  | FY 23 |  |  |  | Eastside Dr | Manner Gate Dr | Hunsinger Ln | 18.5457 | 26 | Local | [13 empty] | 24 |  |  |  | 38431.584 |  |  | Public Works | [16 empty] | 889.62 | 24 | 21350.88 | 0.34651
| Hall |  |  | FY 23 |  |  |  | Enridge Dr | Manner Dale Dr | Landside Dr | 42 | 26 | Local | [13 empty] | 5 |  |  |  | 38500 |  |  | Council | [18 empty] | 21891 | 0.35527
| Hall |  |  | FY 23 |  |  |  | Garden View Ct | Westwood Farms Dr | Dead End | 58 | 26 | Local | [13 empty] | 0 |  |  |  | 17266.788 |  |  | Public Works | [16 empty] | 436.03 | 22 | 9592.66 | 0.15568
| Hall |  |  | FY 23 |  |  |  | Kings Hwy | Rosedale Blvd | Talisman Rd | 34.4907 | 26 | Local | [13 empty] | 0 |  |  |  | 31081.536 |  |  | Public Works | [16 empty] | 719.48 | 24 | 17267.52 | 0.28024
| Hall |  |  | FY 23 |  |  |  | Nadina Dr | Wedgewood Way | Herb Ln | 39 | 26 | Local | [13 empty] | 6 |  |  |  | 36193.95 |  |  | Public Works | [16 empty] | 874.25 | 23 | 20107.75 | 0.32633
| Hall |  |  | FY 23 |  |  |  | Plain Field Ct | Shaker Mill Rd | Dead End | 33 | 26 | Local | [13 empty] | 0 |  |  |  | 12043.548 |  |  | Public Works | [16 empty] | 304.13 | 22 | 6690.86 | 0.10859
| Hall |  |  | FY 23 |  |  |  | Rosedale Blvd | Brockton Ln | Radiance Rd | 41 | 26 | Local | [13 empty] | 6 |  |  |  | 10746.432 |  |  | Public Works | [16 empty] | 248.76 | 24 | 5970.24 | 0.096892
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Ct | Shaker Mill Rd | Dead End | 28 | 26 | Local | [13 empty] | 0 |  |  |  | 10504.692 |  |  | Public Works | [16 empty] | 265.27 | 22 | 5835.94 | 0.094712
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Rd | Westwood Farms Dr | Plain Field Ct | 50.7877 | 26 | Local | [13 empty] | 8 |  |  |  | 85603.392 |  |  | Public Works | [16 empty] | 1981.56 | 24 | 47557.44 | 0.77182
| Hall |  |  | FY 23 |  |  |  | Taylorsville Rd | Brockton Ln | Dead End | 64 | 26 | Local | [13 empty] | 1 |  |  |  | 21875.328 |  |  | Public Works | [16 empty] | 759.56 | 16 | 12152.96 | 0.19723
| Hall |  |  | FY 23 |  |  |  | Wedgewood Way (north) | Brockton Ln | Herb Ln | 26.4861 | 26 | Local | [13 empty] | 4 |  |  |  | 38181.924 |  |  | Public Works | [16 empty] | 936.5 | 23 | 21212.18 | 0.34426
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Ct | Westwood Farms Dr | Dead End | 80 | 26 | Local | [13 empty] | 0 |  |  |  | 12974.94 |  |  | Public Works | [16 empty] | 327.65 | 22 | 7208.3 | 0.11698
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Dr | Six Mile Ln | Plain Field Ct | 50.7893 | 26 | Local | [13 empty] | 13 |  |  |  | 117732.096 |  |  | Public Works | [16 empty] | 2395.29 | 30 | 65406.72 | 1.0615
| Michael Baker |  | 387658-1 | FY 22 |  |  |  | Supplemental Inspections | [22 empty] | 71609 | 46994.22

## August 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  |  | FY 23 |  |  |  | Bridwell Dr | Kaufman Ln | Dead End | 30.6881 | 1 | Local | [13 empty] | 1 |  |  |  | 100503 |  |  | Public Works | [16 empty] | 2965.84 | 19 | 55835.26 | 0.90616
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Virginia Ave | Wilson Ave | 30.1848 | 1 | Local | [13 empty] | 14 |  |  |  | 155020 |  |  | Public Works | [15 empty] | Speed Humps and rail crossing | 2421.8757 | 35.25 | 86122.4396 | 1.3977
|  |  |  | FY 23 |  |  |  | D1 Paving |  |  |  | 1 | [18 empty] | 40000 |  |  | Council | 8102-410-8210-148991-899998 | 40000 | [17 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | Dead End (east) | 22.533 | 1 | Local | [13 empty] | 6 |  |  |  | 23711 |  |  | Public Works | [15 empty] | Looks like an alley. Base Failures likely | 1061.01 | 12.6667 | 13172.86 | 0.21378
| Hall |  |  | FY 23 |  |  |  | Farnsley Rd (west) | Cane Run Rd | Dead End | 37.2527 | 1 | Local | [13 empty] | 2 |  |  |  | 41202 |  |  | Public Works | [15 empty] | Narrows at dead end. Look to possibly add Zoeller and Van Winkle to Paving | 1321.12 | 17 | 22889.77 | 0.37148
| Hall |  |  | FY 23 |  |  |  | Greenwood Ave | S 26th St | S 29th St | 29.2162 | 1 | Local | [13 empty] | 8 |  |  |  | 100582 |  |  | Public Works | [15 empty] | alley just west of S 28th | 1582.87 | 35.5 | 55879.08 | 0.90687
| Hall |  |  | FY 23 |  |  |  | Mary Rose Dr | Bridwell Dr | Lencott Dr | 51.4364 | 1 | Local | [13 empty] | 0 |  |  |  | 27007 |  |  | Public Works | [15 empty] | Likely illegal driveway at Wilkie, but leave it alone | 759.69 | 20 | 15003.7 | 0.2435
| Hall |  |  | FY 23 |  |  |  | Ronald Ct | Cane Run Rd | Dead End | 37 | 1 | Local | [13 empty] | 2 |  |  |  | 12907 |  |  | Public Works | [15 empty] | Possible base failure | 358.54 | 20 | 7170.8 | 0.11638
| Hall |  |  | FY 23 |  |  |  | S 31st St | Southern Ave | Dr William G Weathers Dr | 30.9738 | 1 | Local | [13 empty] | 12 |  |  |  | 62558 |  |  | Public Works | [15 empty] | do not repalce east sidewalk median on weathers where bump out is | 1579.74 | 22 | 34754.28 | 0.56403
| Hall |  |  | FY 22 |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  | FY 22 |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  | FY 22 |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  |  | FY 23 |  |  |  | Van Winkle Dr | Cane Run Rd | Dead End | 90 | 1 | Local | [13 empty] | 0 |  |  |  | 48286 |  |  | Public Works | [15 empty] | Check to see if this needs to be paved |  |  | 26825 | 0.43535
| Hall |  |  | FY 23 |  |  |  | Woodland Ave | Olive St | S 32nd St | 19.9396 | 1 | Local | [13 empty] | 21 |  |  |  | 144319 |  |  | Public Works | [16 empty] | 2380.0935 | 33.4286 | 80177.1976 | 1.3012
| Hall |  |  | FY 23 |  |  |  | Zoeller Ave | Farnsley Rd | Van Winkle Dr | 48 | 1 | Local | [13 empty] | 0 |  |  |  | 11885 |  |  | Public Works | [18 empty] | 6603 | 0.10716
| Hall |  | 350002-536 | FY 22 |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 88144.05 | [17 empty] | LWC main replacement, LPA project | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  | FY 23 |  |  |  | Ayars Ct | Lambert Ave | Dead End | 11 | 2 | Local | [13 empty] | 0 |  |  |  | 12440.52 |  |  | Public Works | [16 empty] | 345.57 | 20 | 6911.4 | 0.11217
| Hall |  |  | FY 23 |  |  |  | Bartholomew Dr | Lambert Ave | Dead End | 62 | 2 | Local | [13 empty] | 0 |  |  |  | 16778.949 |  |  | Public Works | [15 empty] | Don’t update ramps at end of roaday | 462.23 | 22 | 10169.06 | 0.16503
| Hall |  |  | FY 23 |  |  |  | Beechbrook Rd | Kranet Way | Norfolk Dr | 38.6177 | 2 | Local | [13 empty] | 0 |  |  |  | 26909.712 |  |  | Public Works | [16 empty] | 622.91 | 24 | 14949.84 | 0.24262
| Hall |  | 350002-536 | FY 22 |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [17 empty] | LWC main replacement, LPA project | 674 | 24 | 14370 | 0.23321
| Hall |  |  | FY 23 |  |  |  | Bunche Ct | Ellington Ave | Dead End | 64 | 2 | Local | [13 empty] | 0 |  |  |  | 7492.176 |  |  | Public Works | [16 empty] | 173.43 | 24 | 4162.32 | 0.067551
| Hall |  |  | FY 23 |  |  |  | Ellington Ave | Stokes Ct | Petersburg Rd | 46.0801 | 2 | Local | [13 empty] | 8 |  |  |  | 93178.512 |  |  | Public Works | [16 empty] | 1437.94 | 36 | 51765.84 | 0.84011
| Hall |  |  | FY 23 |  |  |  | Exeter Ave | E Indian Trl | Stokes Ct | 19.8519 | 2 | Local | [13 empty] | 12 |  |  |  | 92320.56 |  |  | Public Works | [15 empty] | 2 bar walks at school which should go back. Do not add ramp at shared use path | 1424.7 | 36 | 51289.2 | 0.83238
| LP |  |  | FY 23 |  |  |  | Fegenbush Ln | Bardstown Rd | Fern Valley Rd | 55.6081 | 2 | Min Art | [13 empty] | 16 |  |  |  | 938271.8611 |  |  | Public Works | [16 empty] | 9572.4106 | 47.8182 | 481165.057 | 7.8089
| Hall |  |  | FY 23 |  |  |  | Heller St | Buechel Bank Rd | Dead End | 20 | 2 | Local | [13 empty] | 0 |  |  |  | 94402.764 |  |  | Public Works | [16 empty] | 2280.26 | 23 | 52445.98 | 0.85115
| Hall |  |  | FY 23 |  |  |  | Kilgore Ct | Exeter Ave | Dead End | 39 | 2 | Local | [13 empty] | 0 |  |  |  | 15129.504 |  |  | Public Works | [16 empty] | 350.22 | 24 | 8405.28 | 0.13641
| Hall |  |  | FY 23 |  |  |  | Lambert Ave | Buechel Bank Rd | Beechbrook Rd | 25.1893 | 2 | Local | [13 empty] | 9 |  |  |  | 79433 |  |  | Public Works | [15 empty] | Speed Humps | 1922.24 | 23 | 44129.26 | 0.71618
| Hall |  |  | FY 23 |  |  |  | Lambert Ct | Lambert Ave | Dead End | 54 | 2 | Local | [13 empty] | 0 |  |  |  | 14204 |  |  | Public Works | [16 empty] | 438.4 | 18 | 7891.2 | 0.12807
| Hall |  |  | FY 23 |  |  |  | Landing Dr | Lambert Ave | Norfolk Dr | 55 | 2 | Local | [13 empty] | 0 |  |  |  | 20582.208 |  |  | Public Works | [15 empty] | Include little dead end seciton just northof norfolk | 476.44 | 24 | 11434.56 | 0.18557
| Hall |  |  | FY 23 |  |  |  | Norbrook Dr | Fegenbush Ln | Dead End | 54.7966 | 2 | Local | [13 empty] | 2 |  |  |  | 56620.872 |  |  | Public Works | [16 empty] | 1123.43 | 28 | 31456.04 | 0.5105
| Hall |  |  | FY 23 |  |  |  | Norfolk Dr | Fegenbush Ln | Landing Dr | 18.9326 | 2 | Local | [13 empty] | 1 |  |  |  | 67012.92 |  |  | Public Works | [15 empty] | Believe this section of roadway includes base failures | 1431.9 | 26 | 37229.4 | 0.6042
| Hall |  |  | FY 23 |  |  |  | Sanford Ave | Buechel Bank Rd | Lambert Ave | 53 | 2 | Local | [13 empty] | 4 |  |  |  | 59871.798 |  |  | Public Works | [16 empty] | 1583.91 | 21 | 33262.11 | 0.53982
| Hall |  |  | FY 23 |  |  |  | Stokes Ct | Ellington Ave | Dead End | 46 | 2 | Local | [13 empty] | 0 |  |  |  | 15148.08 |  |  | Public Works | [16 empty] | 350.65 | 24 | 8415.6 | 0.13658
| Hall |  |  | FY 23 |  |  |  | Tubman Ct | Ellington Ave | Dead End | 25 | 2 | Local | [13 empty] | 0 |  |  |  | 7706.88 |  |  | Public Works | [16 empty] | 178.4 | 24 | 4281.6 | 0.069487
| Hall |  |  | FY 23 |  |  |  | Wheatley Ct | Exeter Ave | Dead End | 66 | 2 | Local | [13 empty] | 0 |  |  |  | 19063.2829 |  |  | Public Works | [16 empty] | 441.2797 | 24 | 10590.7127 | 0.17188
| Hall |  |  | FY 23 |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [13 empty] | Done |  |  |  | 67784.6 | Cost in FY 22 | June | Public Works | [16 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  |  | FY 23 |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [13 empty] | Done |  |  |  | 31238.7 | Cost in FY 22 | june | Public Works | [16 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [13 empty] | Done |  |  |  | 28873.4 | Cost in FY 22 | June | Public Works | [16 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall |  |  | FY 23 |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [13 empty] | Done |  |  |  | 50573.4 | Cost in FY 22 | June | Public Works | [16 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Wilson Ave | Dead End (south) | 29.2907 | 3 | Local | [13 empty] | 6 |  |  |  | 54951.192 |  |  | Public Works | [16 empty] | 984.82 | 30.6667 | 30528.44 | 0.49545
| Hall |  |  | FY 23 |  |  |  | Hardesty Ave | Dixie Hwy | S 23rd St | 23 | 3 | Local | [13 empty] | 0 |  |  |  | 42265.4 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1514.8574 | 18.0004 | 27268 | 0.44254
| Hall |  |  | FY 23 |  |  |  | Hemlock Ct | W Gaulbert Ave | Dead End | 56 | 3 | Local | [13 empty] | 0 |  |  |  | 9432 |  |  | Public Works | [16 empty] | 187 | 28 | 5240 | 0.085041
| Hall |  |  | FY 23 |  |  |  | Olive St | W Gaulbert Ave | Dead End | 55 | 3 | Local | [13 empty] | 0 |  |  |  | 16247.52 |  |  | Public Works | [16 empty] | 300.88 | 30 | 9026.4 | 0.14649
| Hall |  |  | FY 23 |  |  |  | Plantation Dr | Wingfield Ln | Millers Ln | 42.7091 | 3 | Local | [13 empty] | 0 |  |  |  | 42614.15 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1527.3899 | 18 | 27493 | 0.44619
| Hall |  |  | FY 22 |  |  |  | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [18 empty] | On Hold |  |  |  | 0
| Hall |  |  | FY 22 |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [18 empty] | On Hold | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  |  | FY 23 |  |  |  | S 28th ST | W Gaulbert Ave | Dead End | 51 | 3 | Local | [13 empty] | 0 |  |  |  | 10071.828 |  |  | Public Works | [16 empty] | 215.21 | 26 | 5595.46 | 0.090809
| Hall |  |  | FY 23 |  |  |  | W Gaulbert Ave | Cypress St | Wilson Ave | 35.2883 | 3 | Local | [13 empty] | 9 |  |  |  | 79050.6 |  |  | Public Works | [16 empty] | 1631.47 | 26.8 | 43917 | 0.71273
| Hall |  | 350002-571 | FY 22 |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 141383.01 | July | [17 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-571 | FY 22 |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | July | [17 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  |  | FY 23 |  |  |  | Guthrie St | S 2nd St | S 3rd St | 17 | 4 | Local | [13 empty] | Done |  |  |  | 31156.488 | Cost in FY 22 | June | Public Works | [16 empty] | 480.81 | 36 | 17309.16 | 0.28091
| Hall |  |  | FY 23 |  |  |  | Benton Ave | St Anthony Pl | Rubel Ave | 23 | 4 | Local | [13 empty] | 4 |  |  |  | 15710.688 |  |  | Public Works | [16 empty] | 311.72 | 28 | 8728.16 | 0.14165
| Hall |  |  | FY23 |  |  |  | Bus Pad at 6th & Jefferson |  |  |  | 4 | [18 empty] | 50000 |  |  | Public Works
| Hall |  |  | FY 23 |  |  |  | Cedar St | S 19th St | S 15th St | 38.9167 | 4 | Local | [13 empty] | 15 |  |  |  | 128110.8343 |  |  | Public Works | [16 empty] | 1923.464 | 37 | 71172.6857 | 1.1551
| Hall |  |  | FY 23 |  |  |  | Debarr St | Rubel Ave | Barret Ave | 32.4769 | 4 | Local | [13 empty] | 11 |  |  |  | 60853.68 |  |  | Public Works | [16 empty] | 1126.92 | 30 | 33807.6 | 0.54867
| Hall |  |  | FY 23 |  |  |  | Duncan St | N 22nd St | N 24th St | 14.0205 | 4 | Local | [13 empty] | 12 |  |  |  | 62193.096 |  |  | Public Works | [16 empty] | 959.77 | 36 | 34551.72 | 0.56074
| Hall |  | 350002-472 | FY 22 |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 | FY 22 |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 | FY 22 |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 | FY 22 |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 | FY 22 |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  |  | FY 23 |  |  |  | E Washington St | N 1st St | N Preston St | 54.508 | 4 | Pri Coll | [13 empty] | 11 |  |  |  | 95355 |  |  | Public Works | [16 empty] | 1654.55 | 29.3333 | 48899.86 | 0.7936
| Hall |  |  | FY 23 |  |  |  | Edward St | St Anthony Pl | Morton Ave | 24.8631 | 4 | Local | [13 empty] | 34 |  |  |  | 80043.228 |  |  | Public Works | [16 empty] | 1234.23 | 36 | 44468.46 | 0.72168
| Hall |  |  | FY 23 |  |  |  | Magazine St | S 10th St | S 11th St | 34 | 4 | Local | [13 empty] | 1? |  |  |  | 35643.132 |  |  | Public Works | [15 empty] | Maybe make a new ramp where Magazine hits 10th st | 471.47 | 42 | 19801.74 | 0.32136
| Hall |  |  | FY 23 |  |  |  | N 2nd St | River Rd | W Main St | 55.2249 | 4 | Pri Coll | [13 empty] | 6 |  |  |  | 35953 |  |  | Public Works | [16 empty] | 904.75 | 20 | 18437.4 | 0.29922
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 | FY 22 |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  | FY 23 |  |  |  | Rowan St | N 22nd St | N 24th St | 15.9641 | 4 | Local | [13 empty] | 8 |  |  |  | 62099.136 |  |  | Public Works | [16 empty] | 958.32 | 36 | 34499.52 | 0.5599
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  | FY 23 |  |  |  | Rubel Ave | E Broadway | Morton Ave | 30.1586 | 4 | Local | [13 empty] | 33 |  |  |  | 84858.9042 |  |  | Public Works | [16 empty] | 1341.3399 | 35.2 | 47143.8357 | 0.7651
| Hall |  |  | FY 23 |  |  |  | S 10th St | Magazine St | Read Alley | 34 | 4 | Local | [13 empty] | 2 |  |  |  | 16551.5921 |  |  | Public Works | [16 empty] | 218.9364 | 42 | 9195.3289 | 0.14923
| Hall |  |  | FY 23 |  |  |  | S 11th St | W Chestnut St | W Broadway | 33.1751 | 4 | Local | [13 empty] | 11 |  |  |  | 79179.012 |  |  | Public Works | [16 empty] | 1063.09 | 41.3333 | 43988.34 | 0.71389
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Broadway | Cedar St | 17.6734 | 4 | Local | [13 empty] | 33 |  |  |  | 145131.84 |  |  | Public Works | [18 empty] | 142801 | 2.3175
| Hall |  |  | FY 23 |  |  |  | S 18th St | Green Alley | Eddy St | 47.405 | 4 | Local | [13 empty] | 2 |  |  |  | 30136.104 |  |  | Public Works | [16 empty] | 492.42 | 34 | 16742.28 | 0.27171
| Hall |  | 350002-472 | FY 22 |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 | FY 22 |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 | FY 22 |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  | FY 23 |  |  |  | S Preston St | E Hill St | I 65 Ramp | 52.6318 | 4 | Min Art | [13 empty] | 9 |  |  |  | 66983 |  |  | Public Works | [16 empty] | 911.2283 | 34.6667 | 31896.4441 | 0.51765
| Hall |  |  | FY 23 |  |  |  | St Anthony Pl | E Broadway | Barret Ave | 33.4304 | 4 | Local | [13 empty] | 5 |  |  |  | 63780.804 |  |  | Public Works | [16 empty] | 1161.78 | 31.3333 | 35433.78 | 0.57506
| Hall |  |  | FY 23 |  |  |  | W Main St | N 22nd St | N 25th St | 39.6711 | 4 | Local | [13 empty] | 17 |  |  |  | 155392.56 |  |  | Public Works | [16 empty] | 1438.82 | 60 | 86329.2 | 1.401
| Hall |  | 350002-590 | FY 22 |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  |  | FY 23 |  |  |  | W Washington St | N 1st St | N 2nd St | 29 | 4 | Pri Coll | [13 empty] | 4 |  |  |  | 21168 |  |  | Public Works | [16 empty] | 493.42 | 22 | 10855.24 | 0.17617
| Hall |  |  | FY 23 |  |  |  | Walter Barnes Way | W Chestnut St | Read Alley | 37 | 4 | Local | [13 empty] | 0 |  |  |  | 18051.3374 |  |  | Public Works | [16 empty] | 250.713 | 40 | 10028.5208 | 0.16275
| Hall |  | 350002-608 | FY 23 |  |  |  | S 32nd St | Grand Ave | Greenwood Ave | 50 | 5 | Local | [17 empty] | 13598.63 | 13598.63 | August | Public Works | [18 empty] | 14567 | 0.23641
| Hall |  | 350002-583 | FY 22 |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | See S 32nd St | July | [17 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | See S 32nd St | July | [17 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  | 350002-583 | FY 22 |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | See S 32nd St | July | [17 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  | 350002-583 | FY 22 |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | See S 32nd St | July | [17 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  | 350002-583 | FY 22 |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | 589179.69 | July | [17 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall |  | 350002-582 | FY 22 |  |  |  | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | 183786.63 | July | [17 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall |  | 350002-583 | FY 22 |  |  |  | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | 68387.89 | July | [16 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  | 350002-583 | FY 22 |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | See S 32nd St | July | [17 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall |  | 350002-583 | FY 22 |  |  |  | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | See S 32nd St | July | [17 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | See S 32nd St | July | [17 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  | 350002-583 | FY 22 |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | See S 32nd St | July | [17 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  | FY 23 |  |  |  | Carter St | Portland Ave | Northwestern Pkwy | 25 | 5 | Local | [13 empty] | 3 |  |  |  | 38924.712 |  |  | Public Works | [15 empty] | Concrete Roadway, look to Overlay if possible. Otehrwise select panel replacement | 600.69 | 36 | 21624.84 | 0.35095
| Hall |  | 388368-9 | FY 22 |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  | FY 23 |  |  |  | Cedar Grove Ter | Northwestern Pkwy | Dead End | 20.0333 | 5 | Local | [13 empty] | 6 |  |  |  | 75938.472 |  |  | Public Works | [16 empty] | 781.26 | 54 | 42188.04 | 0.68468
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | S 45th St | 25.4062 | 5 | Local | [13 empty] | 6 |  |  |  | 16091.928 |  |  | Public Works | [16 empty] | 599.49 | 15 | 8939.96 | 0.14509
| Hall |  |  | FY 23 |  |  |  | Griffiths Ave | N 22nd St | Bank St | 18.0951 | 5 | Local | [13 empty] | 25 |  |  |  | 107352.144 |  |  | Public Works | [16 empty] | 1754.12 | 34 | 59640.08 | 0.96791
| Hall |  |  | FY 23 |  |  |  | Lytle St | N 20th St | N 22nd St | 23 | 5 | Local | [13 empty] | 0 |  |  |  | 46251 |  |  | Public Works | [16 empty] | 713.75 | 36 | 25695 | 0.41701
| Hall |  |  | FY 23 |  |  |  | N 20th St | Rowan St | Bank St | 15.4973 | 5 | Local | [13 empty] | 28 |  |  |  | 98944.488 |  |  | Public Works | [16 empty] | 1616.74 | 34 | 54969.16 | 0.8921
| Hall |  |  | FY 23 |  |  |  | N 20th St | Bank St | Portland Ave | 14.9549 | 5 | Local | [13 empty] | See N 20th |  |  |  | 43443.432 |  |  | Public Works | [16 empty] | 709.86 | 34 | 24135.24 | 0.39169
| Hall |  |  | FY 23 |  |  |  | N 21st St | Bank St | Rowan St | 18.5511 | 5 | Local | [13 empty] | 30 |  |  |  | 80968.464 |  |  | Public Works | [16 empty] | 1874.27 | 24 | 44982.48 | 0.73003
| Hall |  |  | FY 23 |  |  |  | N 23rd St | Portland Ave | Northwestern Pkwy | 20.4356 | 5 | Local | [13 empty] | 10 |  |  |  | 56586.996 |  |  | Public Works | [16 empty] | 911.12 | 34.5 | 31437.22 | 0.5102
| Hall |  |  | FY 23 |  |  |  | N 25th St | Portland Ave | Northwestern Pkwy | 27.0214 | 5 | Local | [13 empty] | 15 |  |  |  | 64663.6283 |  |  | Public Works | [15 empty] | Brick paver ramp to replace with concrete. Need to check if histroic preservation dist. | 1025.8987 | 35 | 35924.2379 | 0.58302
| Hall |  |  | FY 23 |  |  |  | N 27th St | Portland Ave | Northwestern Pkwy | 17.9248 | 5 | Local | [13 empty] | 11 |  |  |  | 64603.008 |  |  | Public Works | [16 empty] | 996.96 | 36 | 35890.56 | 0.58247
| Hall |  |  | FY 23 |  |  |  | N 33rd St | Northwestern Pkwy | Pflanz St | 20 | 5 | Local | [13 empty] | 8 |  |  |  | 89696.592 |  |  | Public Works | [18 empty] | 49831 | 0.80871
| Hall |  |  | FY 23 |  |  |  | N 34th St | Northwestern Pkwy | Pflanz Ave | 35 | 5 | Local | [13 empty] | 5 |  |  |  | 17153.856 |  |  | Public Works | [16 empty] | 264.72 | 36 | 9529.92 | 0.15466
| Hall |  |  | FY 23 |  |  |  | N 35th St | Northwestern Pkwy | Parker Ave | 17.674 | 5 | Local | [13 empty] | 10 |  |  |  | 159050.88 |  |  | Public Works | [16 empty] | 2209.04 | 40 | 88361.6 | 1.434
| Hall |  |  | FY 23 |  |  |  | N 36th St | Northwestern Pkwy | Pflanz Ave | 38 | 5 | Local | [13 empty] | 4 |  |  |  | 11527.488 |  |  | Public Works | [16 empty] | 266.84 | 24 | 6404.16 | 0.10393
| Hall |  |  | FY 23 |  |  |  | S 45th St | W Broadway | Garland Ave | 32.9625 | 5 | Local | [13 empty] | 7 |  |  |  | 58936.86 |  |  | Public Works | [16 empty] | 1117.9 | 29.3333 | 32742.7 | 0.53139
| Hall |  |  | FY 23 |  |  |  | Short St | Griffiths Ave | Owen St | 16 | 5 | Local | [13 empty] | 5 |  |  |  | 16947.684 |  |  | Public Works | [16 empty] | 362.13 | 26 | 9415.38 | 0.1528
| Hall |  | 350002-588 | FY 22 |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | see S Floyd | July | [17 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  | 350002-588 | FY 22 |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | 222661.02 | July | [17 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  | 350002-579 | FY 22 |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | 94995.62 | July | [17 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  | 350002-587 | FY 22 |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | 186252.09 | July | [17 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  |  | FY 23 |  |  |  | Colorado Ave | Central Ave | Algonquin Pkwy | 20.2796 | 6 | Local | [13 empty] | 14 |  |  |  | 105470.388 |  |  | Public Works | [16 empty] | 2259.89 | 27.2 | 58594.66 | 0.95094
| Hall |  | 350002-606 | FY 23 |  |  |  | Dixie Hwy | Hale Ave | W Burnett Ave | 55.4031 | 6 | Min Art | [13 empty] | 29 |  |  |  | 236607 | 72451.89 |  | Public Works | [16 empty] | 3120.29 | 35.5455 | 112669.83 | 1.8285
| Hall |  |  | FY 23 |  |  |  | Lillian Ave | 7th Street Rd | Colorado Ave | 31.3741 | 6 | Local | [13 empty] | 11 |  |  |  | 92745.72 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 2015.69 | 25.3333 | 51525.4 | 0.83621
| Hall |  |  | FY 23 |  |  |  | Lincoln Ave | 7th Street Rd | Taylor Blvd | 24.899 | 6 | Local | [13 empty] | 18 |  |  |  | 183027.456 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 3815.61 | 26.7143 | 101681.92 | 1.6502
| Hall |  |  | FY 23 |  |  |  | Lindbergh Dr | Algonquin Pkwy | Dead End (Homeview) | 45.5354 | 6 | Local | [13 empty] | 35 |  |  |  | 166826.304 |  |  | Public Works | [15 empty] | Some ramps may be technically infeasible. Dead end at homeview is strange | 3138.68 | 29 | 94313.98 | 1.5306
| Hall |  |  | FY 23 |  |  |  | S 16th St | W Breckinridge St | W Oak St | 29.2853 | 6 | Local | [13 empty] | 47 |  |  |  | 150568.704 |  |  | Public Works | [16 empty] | 2614.04 | 32 | 83649.28 | 1.3576
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Kentucky St | W Oak St | 28.3593 | 6 | Local | [13 empty] | 37 |  |  |  | 104515.344 |  |  | Public Works | [16 empty] | 1746.26 | 33.2 | 58064.08 | 0.94233
| Hall |  |  | FY 23 |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  | FY 22 |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  | FY 23 |  |  |  | Tennessee Ave | 7th Street Rd | Lindbergh Dr | 33 | 6 | Local | [13 empty] | 4 |  |  |  | 62034.264 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1380.5 | 25 | 34463.48 | 0.55931
| Hall |  |  | FY 23 |  |  |  | W Oak St | Dixie Hwy | S 26th St | 20.437 | 6 | Min Art | [13 empty] | 22 |  |  |  | 224089 |  |  | Public Works | [16 empty] | 2754.22 | 38.8 | 106709.2 | 1.7318
| Hall |  |  | FY 23 |  |  |  | W St Catherine St | S 15th St | S 16th St | 21 | 6 | Local | [13 empty] | 4 |  |  |  | 40212.18 |  |  | Public Works | [16 empty] | 744.67 | 30 | 22340.1 | 0.36256
| Hall |  |  | FY 23 |  |  |  | Weller Ave | 7th Street Rd | Dead End | 28.6273 | 6 | Local | [13 empty] | 4 |  |  |  | 64972.44 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1388.3 | 26 | 36095.8 | 0.5858
| Hall |  |  | FY 23 |  |  |  | Wurtele Ave | 7th Street Rd | Colorado Ave | 32.2659 | 6 | Local | [13 empty] | 3 |  |  |  | 109582.272 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1902.47 | 32 | 60879.04 | 0.98801
| Hall |  |  | FY 23 |  |  |  | Chippewa Rd | Elfin Ave | Napanee Rd | 42 | 7 | Local | [13 empty] | 0 |  |  |  | 12590.424 |  |  | Public Works | [15 empty] | Big base failure north of Elfin need to complete with this work. | 317.94 | 22 | 6994.68 | 0.11352
| Hall |  |  | FY 23 |  |  |  | Napanee Rd | Chippewa Rd | St Matthews Ave | 19 | 7 | Local | [13 empty] | 0 |  |  |  | 25394.256 |  |  | Public Works | [16 empty] | 587.83 | 24 | 14107.92 | 0.22896
| Hall |  | 350002-584 | FY 22 |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 |  | August | [16 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  | 350002-584 | FY 22 |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 |  | August | [17 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Louisville Paving |  | 388368-7 | FY 22 |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [13 empty] | 0 |  |  | 0 | 44635.35 | 31523.81 | August | [17 empty] | 800 | 36 | 28797 | 0.46735
| LP |  | 366368-17 | FY 23 |  |  |  | Trevilian Way | Newburg Rd | Dundee Rd | 68.6911 | 8 | Min Art | [13 empty] | 0 |  |  | 0 | 192812 | 136694.4 | August | Google Funds | [16 empty] | 3604.72 | 26 | 91815.32 | 1.4901
| Hall |  |  | FY 23 |  |  |  | Alta Ave | Bardstown Rd | Cherokee Rd | 25.0798 | 8 | Local | [13 empty] | 29 |  |  |  | 169299.18 |  |  | Public Works | [16 empty] | 3135.17 | 30 | 94055.1 | 1.5264
| Hall |  |  | FY 23 |  |  |  | Bonnycastle Ave | Bardstown Rd | Cherokee Rd | 37.5047 | 8 | Local | [13 empty] | 29 |  |  |  | 149154.516 |  |  | Public Works | [16 empty] | 2858.8 | 29 | 82863.62 | 1.3448
| Hall |  |  | FY 23 |  |  |  | Edward St | Morton Ave | Rufer Ave | 18.7033 | 8 | Local | [13 empty] | 39 |  |  |  | 116619.264 |  |  | Public Works | [16 empty] | 1799.68 | 36 | 64788.48 | 1.0515
| Hall |  |  | FY 23 |  |  |  | Grasmere Ter | Grasmere Dr | Dead End | 10.6363 | 8 | Local | [13 empty] | 0 |  |  |  | 6760.584 |  |  | Public Works | [15 empty] | Small alley, could be a nightmare | 312.99 | 12 | 3755.88 | 0.060955
| Hall |  |  | FY 23 |  |  |  | Parsons Pl | Alta Ave | Bonnycastle Ave | 30 | 8 | Local | [13 empty] | 0 |  |  |  | 14329.548 |  |  | Public Works | [16 empty] | 442.27 | 18 | 7960.86 | 0.1292
| Hall |  |  | FY 23 |  |  |  | Ray Ave | Grinstead Dr | Longest Ave | 22.8729 | 8 | Local | [13 empty] | 7 |  |  |  | 71597.52 |  |  | Public Works | [16 empty] | 1325.88 | 30 | 39776.4 | 0.64554
| Hall |  |  | FY 23 |  |  |  | Ridgeway Ave | Willow Ave | Dead End | 10 | 8 | Local | [13 empty] | 2 |  |  |  | 44804.52 |  |  | Public Works | [15 empty] | Looks like an alley | 1244.57 | 20 | 24891.4 | 0.40397
| Hall |  |  | FY 23 |  |  |  | Spring Dr | Speed Ave | Woodford Pl | 18.0204 | 8 | Local | [13 empty] | 2 |  |  |  | 111570.696 |  |  | Public Works | [16 empty] | 1721.77 | 36 | 61983.72 | 1.0059
| Hall |  |  | FY 23 |  |  |  | Avon Ct | Kennedy Ave | Kennedy Ct | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 6826.644 |  |  | Public Works | [16 empty] | 172.39 | 22 | 3792.58 | 0.06155
| Hall |  |  | FY 23 |  |  |  | Bauer Ave | Lexington Rd | Wilmington Ave | 21 | 9 | Local | [13 empty] | 0 |  |  |  | 20857.32 |  |  | Public Works | [16 empty] | 526.7 | 22 | 11587.4 | 0.18805
| Hall |  |  | FY 23 |  |  |  | Chamberry Cir (All) | Old Cannons Ln | Old Cannons Ln | 28.3517 | 9 | Local | [13 empty] | 0 |  |  |  | 86199.228 |  |  | Public Works | [16 empty] | 1958.4 | 25 | 47888.46 | 0.77719
| Hall |  |  | FY 23 |  |  |  | Circle Hill Rd | Rock Creek Dr | Old Cannons Ln | 28.8803 | 9 | Local | [13 empty] | 0 |  |  |  | 120190.7284 |  |  | Public Works | [16 empty] | 2587.9703 | 23 | 60702.3881 | 0.98515
| Hall |  |  | FY 23 |  |  |  | Crescent Ct | Frankfort Ave | Grinstead Dr | 27.5652 | 9 | Local | [13 empty] | 2 |  |  |  | 49072.7871 |  |  | Public Works | [15 empty] | Base failures? | 1239.2118 | 22 | 27262.6595 | 0.44245
| Hall |  |  | FY 22 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  |  | FY 23 |  |  |  | Homestead Blvd | Rock Creek Dr | Circle Hill Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 48453.688 |  |  | Public Works | [16 empty] | 1121.6131 | 24 | 26918.7155 | 0.43687
| Hall |  |  | FY 23 |  |  |  | Huntington Rd | Rock Creek Dr | Old Cannons Ln | 18.7864 | 9 | Local | [13 empty] | 0 |  |  |  | 67794.408 |  |  | Public Works | [16 empty] | 1711.98 | 22 | 37663.56 | 0.61125
| Hall |  |  | FY 23 |  |  |  | Kennedy Ave | Frankfort Ave | Grinstead Dr | 31.0011 | 9 | Local | [13 empty] | 2 |  |  |  | 45585.036 |  |  | Public Works | [16 empty] | 1384.26 | 18 | 25325.02 | 0.411
| Hall |  |  | FY 23 |  |  |  | Kennedy Ct | Kennedy Ave | Dead End | 41.1453 | 9 | Local | [13 empty] | 2 |  |  |  | 20407.788 |  |  | Public Works | [16 empty] | 586.15 | 20 | 11337.66 | 0.184
| Hall |  |  | FY 23 |  |  |  | Lake Ave | Mellwood Ave | Dead End | 19 | 9 | Local | [13 empty] | 1 |  |  |  | 82170.72 |  |  | Public Works | [16 empty] | 1984.8 | 23 | 45650.4 | 0.74087
| Hall |  |  | FY 23 |  |  |  | Macon Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 20824.128 |  |  | Public Works | [16 empty] | 482.04 | 24 | 11568.96 | 0.18775
| Hall |  |  | FY 23 |  |  |  | Meadowlark Ave | Seminary Rd | Stilz Ave | 15.5126 | 9 | Local | [13 empty] | 11 |  |  |  | 24502.176 |  |  | Public Works | [16 empty] | 850.77 | 16 | 13612.32 | 0.22092
| Hall |  |  | FY 23 |  |  |  | Mount Holly Ave | Brownsboro Rd | Lindsay Ave | 19.4575 | 9 | Local | [13 empty] | 2 |  |  |  | 49280.832 |  |  | Public Works | [15 empty] | Base fialure by Lindsay | 1215.32 | 24 | 27378.24 | 0.44432
| Hall |  |  | FY 23 |  |  |  | Pleasantview Ave | Grinstead Dr | Lexington Rd | 18.075 | 9 | Local | [13 empty] | 10 |  |  |  | 98573.688 |  |  | Public Works | [16 empty] | 1878.18 | 29 | 54763.16 | 0.88876
| Hall |  |  | FY 23 |  |  |  | Rock Creek Dr | Cannons Ln | Pee Wee Reese Rd | 32.2104 | 9 | Local | [13 empty] | 0 |  |  |  | 114983.244 |  |  | Public Works | [15 empty] | Base failures | 3260.83 | 19.6 | 63879.58 | 1.0367
| Hall |  | 350002-604 | FY 23 |  |  |  | S Hubbards Ln | Bowling Blvd | Shelbyville Rd | 27 | 9 | Min Art | [17 empty] | 253130 |  |  | Public Works | [18 empty] | 120538 | 1.9562
| Hall |  |  | FY 23 |  |  |  | Springdale Rd | Grinstead Dr | Pleasantview Ave | 20 | 9 | Local | [13 empty] | 3 |  |  |  | 29623.104 |  |  | Public Works | [16 empty] | 685.72 | 24 | 16457.28 | 0.26709
| Hall |  |  | FY 23 |  |  |  | St Matthews Ave | Napanee Rd | Ormond Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 14326.884 |  |  | Public Works | [16 empty] | 361.79 | 22 | 7959.38 | 0.12917
| Hall |  |  | FY 23 |  |  |  | Stilz Ave | Lexington Rd | Frankfort Ave | 53.6459 | 9 | Pri Coll | [13 empty] | 13 |  |  |  | 114290 |  |  | Public Works | [16 empty] | 2574.69 | 34.3333 | 87915.6 | 1.4268
| Hall |  |  | FY 23 |  |  |  | Wallace Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 18104.112 |  |  | Public Works | [16 empty] | 386.84 | 26 | 10057.84 | 0.16323
| Hall |  |  | FY 23 |  |  |  | Wendover Ave | Lexington Rd | Wilmington Ave | 26 | 9 | Local | [13 empty] | 0 |  |  |  | 17264.808 |  |  | Public Works | [16 empty] | 435.98 | 22 | 9591.56 | 0.15566
| Hall |  |  | FY 23 |  |  |  | Willis Ave | Wiltshire Ave | Breckenridge Ln | 76 | 9 | Collector | [17 empty] | 14626.8 | [21 empty] | 8126 | 0.13188
| Hall |  |  | FY 23 |  |  |  | Wilmington Ave | Wallace Ave | Frankfort Ave | 28.1016 | 9 | Local | [13 empty] | 3 |  |  |  | 24518.88 |  |  | Public Works | [16 empty] | 536.86 | 25 | 13621.6 | 0.22107
| Hall |  |  | FY 23 |  |  |  | Wiltshire Ave | Wilmington Ave | Willis Ave | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 22864.644 |  |  | Public Works | [16 empty] | 577.39 | 22 | 12702.58 | 0.20615
| Hall |  |  | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Dead End |  | 9 | Local | [17 empty] | 23706.8246 | [21 empty] | 13170 | 0.21374
| Hall |  |  | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Thompson Ave | 44.4846 | 9 | Pri Coll | [13 empty] | 6 |  |  |  | 118575 |  |  | Public Works | [16 empty] | 2147.8793 | 29.3333 | 60807.4923 | 0.98685
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Ct | Audubon Ridge Dr | Dead End | 19.8104 | 10 | Local | [13 empty] | 0 |  |  |  | 33929.676 |  |  | Public Works | [16 empty] | 856.81 | 22 | 18849.82 | 0.30592
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Dr | Illinois Ave | Dead End | 48.9775 | 10 | Local | [13 empty] | 5 |  |  |  | 44784.36 |  |  | Public Works | [16 empty] | 1027.09 | 31 | 24880.2 | 0.40378
| Hall |  |  | FY 23 |  |  |  | Ellison Ave | Barret Ave | Spratt Ave | 35.6822 | 10 | Local | [13 empty] | 15 |  |  |  | 166187.376 |  |  | Public Works | [16 empty] | 2429.64 | 38 | 92326.32 | 1.4984
| Hall |  |  | FY 23 |  |  |  | Grantswood Ct | Audubon Ridge Ct | Dead End |  | 10 | Local | [13 empty] | 2 |  |  |  | 16264.8 |  |  | Public Works | [16 empty] | 502 | 18 | 9036 | 0.14665
| Hall |  |  | FY 23 |  |  |  | Reutlinger Ave | E Oak St | Ellison Ave | 23.3308 | 10 | Local | [13 empty] | 6 |  |  |  | 67047.624 |  |  | Public Works | [16 empty] | 1330.31 | 28 | 37248.68 | 0.60451
| LP |  | 366368-16 | FY 23 |  |  |  | Robards Ln | Gardiner Ln | Bishop Ln | 42.3597 | 10 | Pri Coll | [13 empty] | 2 |  |  |  | 147273 |  |  | Public Works | [16 empty] | 3717.62 | 20 | 75524.68 | 1.2257
| Hall |  |  | FY 23 |  |  |  | Spratt St | Goss Ave | St Michael St | 35.9444 | 10 | Local | [13 empty] | 16 |  |  |  | 74506.176 |  |  | Public Works | [16 empty] | 1171.43 | 35.3333 | 41392.32 | 0.67176
| Hall |  |  | FY 23 |  |  |  | St Michael St | Ellison Ave | Dead End | 41 | 10 | Local | [13 empty] | 0 |  |  |  | 35897.4 |  |  | Public Works | [16 empty] | 712.25 | 28 | 19943 | 0.32366
| LP |  | 388368-27 | FY 23 |  |  |  | E Rehl Ct | Rehl Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | 0 | 60541 | See Rehl Rd | August | Public Works | [18 empty] | 33634 | 0.54585
| Hall |  |  | FY 23 |  |  |  | Bircham Rd | Shelbyville Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 110000 |  |  | Council | 8102-410-8210-148628-899998 | 110000 | [16 empty] | 66212 | 1.0746
| Hall |  |  | FY 23 |  |  |  | Burleigh Ct | Burcham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 31000 |  |  | Council | 8102-410-8210-148628-899998 | 31000 | [16 empty] | 17407 | 0.2825
| Hall |  |  | FY 23 |  |  |  | Burleigh Pl | Burleigh Ct | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 8500 |  |  | Council | 8102-410-8210-148628-899998 | 8500 | [16 empty] | 4726 | 0.076699
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Rd | Blankenbaker Pkwy | Taylorsville Rd | 36.517 | 11 | Pri Coll | [13 empty] | 0 |  |  |  | 196876 |  |  | Public Works | [16 empty] | 4135.4154 | 24 | 100961.8158 | 1.6385
| Hall |  |  | FY 23 |  |  |  | Constant Comment Pl | From J-Town R/W north of Electron | Dead End (south) | 22.3743 | 11 | Local | [13 empty] | 1 |  |  |  | 76709.25 |  |  | Public Works | [16 empty] | 987 | 35 | 42616.25 | 0.69162
| Hall |  |  | FY 23 |  |  |  | Dorshire Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 20000 |  |  | Council | 8102-410-8210-148628-899998 | 20000 | [16 empty] | 11350 | 0.1842
| Hall |  |  | FY 23 |  |  |  | Electron Dr | Blankenbaker Pkwy | Constant Comment Pl | 19 | 11 | Local | [13 empty] | 1 |  |  |  | 51249.132 |  |  | Public Works | [16 empty] | 862.78 | 33 | 28471.74 | 0.46207
| Hall |  |  | FY 23 |  |  |  | Hurstbourne Park Blvd | Hurstbourne Pkwy | Dead End |  | 11 | Local | [17 empty] | 48685 |  |  | Public Works | [18 empty] | 27047 | 0.43895
| Hall |  |  | FY 23 |  |  |  | Landis Lakes Dr | S English Station Rd | Landis Lakes Ct | 32.9592 | 11 | Local | [13 empty] | 10 |  |  |  | 66457.368 |  |  | Public Works | [16 empty] | 1682.32 | 25.3333 | 41128.06 | 0.66747
| Hall |  |  | FY 23 |  |  |  | Summerfield Dr | Six Mile Ln | Weather Way |  | 11 | Local | [13 empty] | 17 |  |  |  | 75000 |  |  | Council | 8102-410-8210-148628-899998 | 28500 |  | 8150-410-8210-148628-899998 | 44500 |  | 8133-410-8210-148628-899998 | 2000 | [10 empty] | 112833 | 1.8312
| Hall |  |  | FY 23 |  |  |  | Willoughby Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 26000 |  |  | Council | 8102-410-8210-148628-899998 | 26000 | [16 empty] | 14983 | 0.24316
| LP |  |  | FY 23 |  |  |  | Blanton Ln | St Andrews Church Rd | Dixie Hwy | 35.5419 | 12 | Pri Coll | [13 empty] | 0 |  |  |  | 226546 |  |  | Public Works | [16 empty] | 5256.12 | 22.5714 | 116177.36 | 1.8855
| Hall |  |  | FY 23 |  |  |  | De Mel Ave | Manslick Rd | Dead End | 23.8808 | 12 | Local | [13 empty] | 0 |  |  |  | 73224.6988 |  |  | Public Works | [16 empty] | 1904.3118 | 21.6667 | 40680.3882 | 0.66021
| Hall |  |  | FY 23 |  |  |  | Frank Lee Ave | Terry Rd | Dead End | 41.2207 | 12 | Local | [13 empty] | 5 |  |  |  | 29502 |  |  | Public Works | [16 empty] | 819.5 | 20 | 16390 | 0.266
| Hall |  | 350002-470 | FY 22 |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-601 | FY 23 |  |  |  | Lynn Myra Ct | Vista John Dr | Dead End | 40 | 12 | Local | [13 empty] | 0 |  |  |  | 9422.424 | See Vista John Dr |  | Public Works | [16 empty] | 237.94 | 22 | 5234.68 | 0.084954
| Hall |  | 350002-600 | FY 23 |  |  |  | Maryview Dr | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 79947 | [21 empty] | 45684
| Hall |  | 350002-518 | FY 22 |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [18 empty] | LWC Project | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  |  | FY 23 |  |  |  | Mount Marcy Rd | Mount Holyoke Dr | Alps Rd | 25 | 12 | Local | [13 empty] | 6 |  |  |  | 57474.144 |  |  | Public Works | [16 empty] | 1330.42 | 24 | 31930.08 | 0.5182
| Hall |  | 350002-600 | FY 23 |  |  |  | Nancy Ave | Dawn Dr | Dead End | 22 | 12 | Local | [13 empty] | 0 |  |  |  | 34899.984 |  |  | Public Works | [16 empty] | 807.87 | 24 | 19388.88 | 0.31466
| Hall |  | 350002-600 | FY 23 |  |  |  | Princewood Pl | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 18314 | [21 empty] | 10465 | 0.16984
| Hall |  | 350002-601 | FY 23 |  |  |  | Stephan Rd | Vista John Dr | Oswego Cir | 25.3696 | 12 | Local | [13 empty] | 0 |  |  |  | 37562.1531 | See Vista John Dr |  | Public Works | [16 empty] | 1043.3931 | 20 | 20867.8628 | 0.33867
| Hall |  | 350002-601 | FY 23 |  |  |  | Terudon Dr | Manslick Rd | Vista John Dr | 28 | 12 | Local | [13 empty] | 0 |  |  |  | 31798.656 | See Vista John Dr |  | Public Works | [16 empty] | 736.08 | 24 | 17665.92 | 0.2867
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 9956.96 | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-601 | FY 23 |  |  |  | Vista John Dr | Manslick Rd | Stephan Dr | 36.6481 | 12 | Local | [13 empty] | 0 |  |  |  | 59112.684 | 2151.17 |  | Public Works | [16 empty] | 1411.04 | 23.3333 | 32840.38 | 0.53297
| Hall |  |  | FY 23 |  |  |  | Wade Lee Ct | Wilke Farm Ave | Dead End | 37 | 12 | Local | [13 empty] | 0 |  |  |  | 7507.08 |  |  | Public Works | [16 empty] | 208.53 | 20 | 4170.6 | 0.067685
| Hall |  |  | FY 23 |  |  |  | Wilke Farm Ave | Frank Lee Ave | Ree Dr | 48.9395 | 12 | Local | [13 empty] | 5 |  |  |  | 50846.004 |  |  | Public Works | [16 empty] | 1283.99 | 22 | 28247.78 | 0.45844
| Hall |  | 350002-592 | FY 23 |  |  |  | Clay Ave | Minor Ln | Preston Hwy | 25.2005 | 13 | Local | [13 empty] | 0 |  |  |  | 102532.608 |  |  | Public Works | [16 empty] | 3415.39 | 16.8 | 56962.56 | 0.92445
|  |  |  | FY 22 |  |  |  | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
| Hall |  | 350002-560 | FY 22 |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| LP |  |  | FY 23 |  |  |  | Jefferson Hill Rd | Keys Ferry Rd | Snawder Ln | 37.0674 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 444131 |  |  | Public Works | [16 empty] | 12300.93 | 18.6667 | 227759.57 | 3.6963
| LP |  |  | FY 23 |  |  |  | Joyner Hill Rd | Lonesome Hollow Rd | Dead End | 33 | 13 | Local | [13 empty] | 0 |  |  |  | 22761.882 |  |  | Public Works | [16 empty] | 1149.59 | 11 | 12645.49 | 0.20523
| LP |  |  | FY 23 |  |  |  | Lonesome Hollow Rd | Blevins Gap Rd | Dead End | 23.6259 | 13 | Local | [13 empty] | 0 |  |  |  | 93498.0588 |  |  | Public Works | [16 empty] | 2990.1966 | 18 | 51943.366 | 0.843
| LP |  |  | FY 23 |  |  |  | Lonesome Hollow Rd | Jefferson Hill Rd | Dead End | 37 | 13 | Local | [13 empty] | 0 |  |  |  | 16334.784 |  |  | Public Works | [16 empty] | 756.24 | 12 | 9074.88 | 0.14728
| Hall |  | 350002-592 | FY 23 |  |  |  | Meadow Hill Rd | Minyard Dr | Dead End | 9 | 13 | Local | [13 empty] | 2 |  |  |  | 8903.2847 |  |  | Public Works | [15 empty] | Metro ROW is small, only 4 houses, rest private | 206.0946 | 24 | 4946.2693 | 0.080274
| Hall |  | 350002-592 | FY 23 |  |  |  | Minyard Dr | Clay Ave | Minor Ln | 28.853 | 13 | Local | [13 empty] | 0 |  |  |  | 91895.328 |  |  | Public Works | [16 empty] | 1930.73 | 26.25 | 51052.96 | 0.82855
| LP |  |  | FY 23 |  |  |  | Snawder Ln | Jefferson Hill Rd | Dead End | 21 | 13 | Local | [13 empty] | 0 |  |  |  | 22803.48 |  |  | Public Works | [16 empty] | 1266.86 | 10 | 12668.6 | 0.2056
| Hall |  | 350002-592 | FY 23 |  |  |  | Sunset Dr | Minor Ln | Clay Ave | 39 | 13 | Local | [13 empty] | 0 |  |  |  | 36200.52 |  |  | Public Works | [16 empty] | 1117.3 | 18 | 20111.4 | 0.32639
| LP |  |  | FY 23 |  |  |  | Tidwell Rd | Lonesome Hollow Rd | Dead End | 35 | 13 | Local | [13 empty] | 0 |  |  |  | 16525.8 |  |  | Public Works | [16 empty] | 765 | 12 | 9181 | 0.149
| LP |  |  | FY 23 |  |  |  | Top Hill Rd | Snawder Ln | Mitchell Hill Rd | 45.371 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 377132 |  |  | Public Works | [16 empty] | 9913.74 | 19 | 193400.8 | 3.1387
| Hall |  | 350002-552 | FY 22 |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| Hall |  | 350002-599 | FY 23 |  |  |  | Chase Rd | W Pages Ln | Stephan Dr | 43 | 14 | Local | [13 empty] | 2 |  |  |  | 41561.28 | See Stephan Dr |  | Public Works | [16 empty] | 1154.48 | 20 | 23089.6 | 0.37472
| Hall |  | 350002-594 | FY 23 |  |  |  | Dixie Garden Dr | Dixie Hwy | Blaze Way | 51.9782 | 14 | Local | [13 empty] | 4 |  |  |  | 123696.396 | 32366.42 |  | Public Works | [16 empty] | 2734.59 | 27.3333 | 68720.22 | 1.1153
| Hall |  | 350002-594 | FY 23 |  |  |  | Fashion Way | Bethany Ln | Nocturne Dr | 17.6755 | 14 | Local | [13 empty] | 11 |  |  |  | 68407.524 | See dixie Garden Dr |  | Public Works | [16 empty] | 1659.78 | 22.8 | 38004.18 | 0.61677
| Hall |  | 350002-598 | FY 23 |  |  |  | Johnsontown Rd | Dixie Hwy | Trade Port Dr | 47.0122 | 14 | Min Art | [13 empty] | 22 |  |  |  | 568391 |  |  | Public Works | [15 empty] | Applied for rubber aspahlt grant on this roadway | 7412.9412 | 36.1429 | 270662.5039 | 4.3926
| Hall |  | 350002-599 | FY 23 |  |  |  | Mark Dr | Vicki Ln | Robbins Rd | 21 | 14 | Local | [13 empty] | 0 |  |  |  | 17582.832 | See Stephan Dr |  | Public Works | [16 empty] | 407.01 | 24 | 9768.24 | 0.15853
| LP |  |  | FY 23 |  |  |  | Medora Rd | Blevins Gap Rd | Pendleton Rd | 30 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 201498 |  |  | Public Works | [16 empty] | 5166.62 | 20 | 103332.4 | 1.677
| Hall |  | 350002-599 | FY 23 |  |  |  | Minette Ct | Stephan Dr | public dead end | 13 | 14 | Local | [13 empty] | 0 |  |  |  | 12123.108 | See Stephan Dr |  | Public Works | [15 empty] | Likely has base failures, ROW ends half way and turns private | 374.17 | 18 | 6735.06 | 0.1093
| Hall |  | 350002-594 | FY 23 |  |  |  | Nocturne Dr | Fashion Way | Blaze Way | 59 | 14 | Local | [13 empty] | 4 |  |  |  | 50247.216 | See dixie Garden Dr |  | Public Works | [16 empty] | 1163.13 | 24 | 27915.12 | 0.45304
| LP |  |  | FY 23 |  |  |  | Pendleton Rd | Deixie Hwy | County Line |  | 14 | Collector | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works
| Hall |  | 350002-599 | FY 23 |  |  |  | Sally Dr | W Pages Ln | Stephan Dr | 36 | 14 | Local | [13 empty] | 2 |  |  |  | 46032.84 | See Stephan Dr |  | Public Works | [16 empty] | 1217.8 | 21 | 25573.8 | 0.41504
| LP |  |  | FY 23 |  |  |  | Schooler Ln | Stonestreet Rd | Dead End | 17 | 14 | Local | [13 empty] | 0 |  |  |  | 25697 |  |  | Public Works | [16 empty] | 1190 | 12 | 14276 | 0.23169
| Hall |  | 350002-599 | FY 23 |  |  |  | Stephan Dr | Dixie Hwy | Vicki Ln | 29.4396 | 14 | Local | [13 empty] | 0 |  |  |  | 100447.704 | 6375.48 |  | Public Works | [16 empty] | 2218.41 | 24.8 | 55804.28 | 0.90565
| Hall |  | 350002-599 | FY 23 |  |  |  | Vicki Ln | W Pages Ln | Stephan Dr | 30.6944 | 14 | Local | [13 empty] | 2 |  |  |  | 50143.5 | See Stephan Dr |  | Public Works | [16 empty] | 1266.25 | 22 | 27857.5 | 0.4521
| LP |  | 388368-14 | FY 22 |  |  |  | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [14 empty] | 0 |  |  | 0 | 40000 | 33834.75 | August | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Locust Ave | 35 | 15 | Local | [13 empty] | 0 |  |  |  | 6959.304 |  |  | Public Works | [16 empty] | 322.19 | 12 | 3866.28 | 0.062746
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Hazelwood Ave | 35.5932 | 15 | Local | [13 empty] | 15 |  |  |  | 49112.784 |  |  | Public Works | [16 empty] | 1269.19 | 21.5 | 27284.88 | 0.44281
| Hall |  |  | FY 23 |  |  |  | Bicknell Ave | Taylor Blvd | Parthenia Ave | 25.5625 | 15 | Local | [13 empty] | 30 |  |  |  | 146000.0686 |  |  | Public Works | [16 empty] | 2752.4779 | 28.2857 | 81111.1492 | 1.3164
| Hall |  |  | FY 23 |  |  |  | Churchman Ave | Cayuga St | Bluegrass Ave | 22.1273 | 15 | Local | [13 empty] | 6 |  |  |  | 111811.392 |  |  | Public Works | [16 empty] | 2384.91 | 26.4 | 62117.44 | 1.0081
| Hall |  |  | FY 23 |  |  |  | Delmar Ct | Sadie Ln | Dead End | 27 | 15 | Local | [13 empty] | 0 |  |  |  | 22756.536 |  |  | Public Works | [16 empty] | 574.66 | 22 | 12642.52 | 0.20518
| Hall |  |  | FY 23 |  |  |  | Delmar Ln | Naneen Dr | Sadie Ln | 32.8435 | 15 | Local | [13 empty] | 5 |  |  |  | 56828.736 |  |  | Public Works | [16 empty] | 1315.48 | 24 | 31571.52 | 0.51238
| Hall |  |  | FY 23 |  |  |  | Estate Dr | Delmar Ln | Dead End | 19.2977 | 15 | Local | [13 empty] | 11 |  |  |  | 37388.052 |  |  | Public Works | [16 empty] | 907.18 | 22.6667 | 20771.14 | 0.3371
| Hall |  |  | FY 23 |  |  |  | Friden Way | Manslick Rd | Tracy Way | 35.1576 | 15 | Local | [13 empty] | 0 |  |  |  | 41825.052 |  |  | Public Works | [16 empty] | 1010.87 | 23 | 23236.14 | 0.3771
| Hall |  |  | FY 23 |  |  |  | Garvey Ct | Garvey Dr | Dead End | 50 | 15 | Local | [13 empty] | 0 |  |  |  | 9785.664 |  |  | Public Works | [16 empty] | 226.52 | 24 | 5436.48 | 0.088229
| Hall |  |  | FY 23 |  |  |  | Garvey Dr | Estate Dr | Dead End | 19.068 | 15 | Local | [13 empty] | 3 |  |  |  | 48994.416 |  |  | Public Works | [16 empty] | 1223.68 | 22.6667 | 27219.12 | 0.44174
| Hall |  |  | FY 23 |  |  |  | Hazelwood Ave | Bicknell Ave | Bluegrass Ave | 23.8773 | 15 | Local | [13 empty] | 10 |  |  |  | 65304.3784 |  |  | Public Works | [16 empty] | 1511.6754 | 24 | 36280.2102 | 0.5888
| Hall |  |  | FY 23 |  |  |  | Joetta Ct | Rhonda Way | Dead End | 37 | 15 | Local | [13 empty] | 0 |  |  |  | 7142.256 |  |  | Public Works | [16 empty] | 165.33 | 24 | 3967.92 | 0.064396
| Hall |  |  | FY 23 |  |  |  | Knight Rd | Tracy Way | Manslick Rd | 21 | 15 | Local | [13 empty] | 1 |  |  |  | 21031.2 |  |  | Public Works | [16 empty] | 531 | 22 | 11684 | 0.18962
| Hall |  |  | FY 23 |  |  |  | La Salle Ave | Cayuga St | Bluegrass Ave | 34.3206 | 15 | Local | [13 empty] | 10 |  |  |  | 98051.346 |  |  | Public Works | [16 empty] | 2151.96 | 25 | 54472.97 | 0.88405
| Hall |  |  | FY 23 |  |  |  | Locust Ave | Alma Ave | Old Bluegrass Ave | 43 | 15 | Local | [13 empty] | 0 |  |  |  | 9529.56 |  |  | Public Works | [16 empty] | 529.42 | 10 | 5294.2 | 0.08592
| Hall |  |  | FY 23 |  |  |  | Old Bluegrass Ave | Churchman Ave | Dead end near Locust Ave | 63.3936 | 15 | Local | [13 empty] | 0 |  |  |  | 17200.0653 |  |  | Public Works | [15 empty] | ROW ends just past Locust | 434.3451 | 22 | 9555.5918 | 0.15508
| Hall |  |  | FY 23 |  |  |  | Rhonda Way | Naneen Dr | Garvey Dr | 45.2191 | 15 | Local | [13 empty] | 4 |  |  |  | 57205.44 |  |  | Public Works | [16 empty] | 1324.2 | 24 | 31780.8 | 0.51577
| Hall |  |  | FY 23 |  |  |  | Rolling Ridge Rd | Friden Way | Dead End | 39 | 15 | Local | [13 empty] | 0 |  |  |  | 20820.6 |  |  | Public Works | [16 empty] | 482 | 24 | 11567 | 0.18772
| Hall |  |  | FY 23 |  |  |  | Sadie Ln | Bryce Dr | Dead End (north) | 54.408 | 15 | Local | [13 empty] | 1 |  |  |  | 24534.756 |  |  | Public Works | [16 empty] | 878.21 | 14.6667 | 13630.42 | 0.22121
| Hall |  |  | FY 23 |  |  |  | Tracy Way | Knight Rd | Hazelwood Ave | 62.5221 | 15 | Local | [13 empty] | 1 |  |  |  | 38359.008 |  |  | Public Works | [16 empty] | 887.94 | 24 | 21310.56 | 0.34585
| LP |  | 388368-20 | FY 23 |  |  |  | Hitt Rd | Ballardsville Rd | County Line | 46 | 16 | Sec Coll | [13 empty] | 5 |  |  | 0 | 18747 | 92359.62 | August | Public Works | [14 empty] | 92359.62 |  | 4369.7222 | 21.9936 | 96106 | 1.5597
| Hall |  |  | FY 23 |  |  |  | Barbour Manor Ct | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7000 |  |  | Council | 8150-410-8210-148628-899998 | 7000 | [16 empty] | 4681 | 0.075969
| Hall |  |  | FY 23 |  |  |  | Barbour Manor Dr | Barbour Ln | Dead End |  | 16 | Local | [13 empty] | 6 |  |  |  | 200000 |  |  | Council | 8150-410-8210-148628-899998 | 200000 | [16 empty] | 117151 | 1.9013
| Hall |  |  | FY 23 |  |  |  | Branning Rd | Brownsboro Rd | end of Metro R/W | 15 | 16 | Local | [13 empty] | 0 |  |  |  | 27000 |  |  | Public Works | [16 empty] | 596.7397 | 18 | 15000 | 0.24344
| Hall |  |  | FY 23 |  |  |  | Brentler Rd | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 9000 |  |  | Council | 8150-410-8210-148628-899998 | 9000 | [16 empty] | 7123 | 0.1156
| Hall |  |  | FY 23 |  |  |  | Cronin Dr | Halifax Dr | Halifax Dr | 47.1575 | 16 | Local | [13 empty] | 8 |  |  |  | 84968.496 |  |  | Public Works | [16 empty] | 1988.68 | 23.5 | 47204.72 | 0.76609
| Hall |  |  | FY 23 |  |  |  | Debsom Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7500 |  |  | Council | 8150-410-8210-148628-899998 | 7500 | [16 empty] | 6759 | 0.10969
| Hall |  |  | FY 23 |  |  |  | Jenica Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 25000 |  |  | Council | 8150-410-8210-148628-899998 | 25000 | [16 empty] | 16165 | 0.26234
| Hall |  |  | FY 23 |  |  |  | Machupe Ct | Machupe Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 4920 | 0.079847
| Hall |  |  | FY 23 |  |  |  | Machupe Dr | Barbour Manor Dr | Machupe Ct |  | 16 | Local | [13 empty] | 3 |  |  |  | 6000 |  |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 5388 | 0.087443
| Hall |  |  | FY 23 |  |  |  | Oak Pointe Dr (south) | Halifax Dr | Halifax Dr | 27 | 16 | Local | [13 empty] | 2 |  |  |  | 60335.712 |  |  | Public Works | [16 empty] | 1396.66 | 24 | 33519.84 | 0.544
| Hall |  |  | FY 23 |  |  |  | Spring Farm Rd | Wolf Pen Branch Rd | 4945 Spring Farm Rd | 33.8399 | 16 | Local | [13 empty] | 0 |  |  |  | 140331.8097 |  |  | Public Works | [16 empty] | 3543.7326 | 22 | 77962.1165 | 1.2653
| Hall |  |  | FY 23 |  |  |  | Tamerlane Ct | Tamerlane Rd | Dead End | 27 | 16 | Local | [13 empty] | 0 |  |  |  | 9991.8 |  |  | Public Works | [16 empty] | 278 | 20 | 5551 | 0.090088
| Hall |  |  | FY 23 |  |  |  | Tamerlane Rd | Woodside Rd | Tuckaho Rd | 32.5001 | 16 | Local | [13 empty] | 0 |  |  |  | 41516.496 |  |  | Public Works | [16 empty] | 961.03 | 24 | 23064.72 | 0.37432
| Hall |  |  | FY 23 |  |  |  | Therina Ct | Therina Way | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | 8133-410-8210-148628-899998 | 6000 | [16 empty] | 3399 | 0.055163
| Hall |  |  | FY 23 |  |  |  | Therina Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 3 |  |  |  | 20000 |  |  | Council | 8133-410-8210-148628-899998 | 20000 | [16 empty] | 14191 | 0.23031
| Hall |  |  | FY 23 |  |  |  | Tuckaho Rd | Tamerlane Rd | 2510 Tuckaho Rd | 38 | 16 | Local | [13 empty] | 0 |  |  |  | 15400.8644 |  |  | Public Works | [16 empty] | 388.9107 | 22 | 8556.0358 | 0.13886
| Hall |  | 350002-392 | FY 22 |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 | FY 22 |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-392 | FY 22 |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  |  | FY 23 |  |  |  | Glen Meadow Rd | Brownsboro Glen Rd | Spring Gate Dr | 16 | 17 | Local | [13 empty] | 4 |  |  |  | 10759.716 |  |  | Public Works | [16 empty] | 271.71 | 22 | 5977.62 | 0.097012
| Hall |  |  | FY 23 |  |  |  | Murphy Ln | Halifax Dr | Ballardsville Rd | 37 | 17 | Pri Coll | [13 empty] | 0 |  |  |  | 115825 |  |  | Public Works | [16 empty] | 2969.88 | 20 | 59397.6 | 0.96397
| LP |  | 388368-19 | FY 23 |  |  |  | N English Station Rd | Aiken Rd | Old Henry Rd | 31 | 17 | Min Art | [13 empty] | 0 |  |  |  | 122122 |  |  | Public Works | [16 empty] | 2423.0596 | 24 | 58153.4298 | 0.94378
| Hall |  |  | FY 23 |  |  |  | Oakland Forest Ct | Spring Mill Rd | Dead End | 47 | 17 | Local | [13 empty] | 0 |  |  |  | 11897.28 |  |  | Public Works | [16 empty] | 275.4 | 24 | 6609.6 | 0.10727
| LP |  | 388368-23 | FY 23 |  |  |  | Old Harrods Creek Rd | LaGrange Rd | End of Metro R/W | 32.4157 | 17 | Sec Coll | [13 empty] | 0 |  |  |  | 38914 |  |  | Public Works | [16 empty] | 1085.356 | 19 | 19956.0265 | 0.32387
| Hall |  | 350002-392 | FY 22 |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Ct | Rock Bay Dr | Dead End | 27.7903 | 17 | Local | [13 empty] | 3 |  |  |  | 28799.712 |  |  | Public Works | [16 empty] | 666.66 | 24 | 15999.84 | 0.25966
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Pl | Rolling Springs Ct | Dead End | 53 | 17 | Local | [13 empty] | 0 |  |  |  | 12216.528 |  |  | Public Works | [16 empty] | 282.79 | 24 | 6786.96 | 0.11015
| Hall |  |  | FY 23 |  |  |  | Spring Forest Ct | Spring Forest Dr | Dead End | 36 | 17 | Local | [13 empty] | 0 |  |  |  | 8882.352 |  |  | Public Works | [16 empty] | 205.61 | 24 | 4934.64 | 0.080085
| Hall |  |  | FY 23 |  |  |  | Spring Forest Dr | Spring Mill Rd | Dead End | 31.2435 | 17 | Local | [13 empty] | 2 |  |  |  | 20158.848 |  |  | Public Works | [16 empty] | 466.64 | 24 | 11199.36 | 0.18176
| Hall |  |  | FY 23 |  |  |  | Spring Gate Dr | Chamberlain Ln | Stone Glen Rd | 20.3691 | 17 | Local | [13 empty] | 8 |  |  |  | 35943.264 |  |  | Public Works | [16 empty] | 832.02 | 24 | 19968.48 | 0.32407
| Hall |  |  | FY 23 |  |  |  | Spring Mill Pl | Spring Mill Rd | Dead End | 25 | 17 | Local | [13 empty] | 0 |  |  |  | 22846.32 |  |  | Public Works | [16 empty] | 528.85 | 24 | 12692.4 | 0.20599
| Hall |  |  | FY 23 |  |  |  | Spring Mill Rd | Rock Bay Dr | Rock Bay Dr | 33.8903 | 17 | Local | [13 empty] | 14 |  |  |  | 140905.008 |  |  | Public Works | [16 empty] | 3261.69 | 24 | 78280.56 | 1.2704
| Hall |  |  | FY 23 |  |  |  | Woods View Pl | Spring Mill Rd | Dead End | 21 | 17 | Local | [13 empty] | 0 |  |  |  | 31692.384 |  |  | Public Works | [16 empty] | 733.62 | 24 | 17606.88 | 0.28574
| Hall |  | 350002-559 | FY 22 |  |  |  | Dorsey Ln | N Hurstbourne | Nearest Joint |  | 18 | Pri Coll | [17 empty] | 41000 |  |  | Council | 8133-410-8210-148628-899998 | 41000
| Hall |  |  | FY 23 |  |  |  | Dorsey Way | Elsmete Cir | Dead End |  | 18 | Local | [13 empty] | 0 |  |  |  | 126000 |  |  | Council | 8133-410-8210-148628-899998 | 90000 |  | 8102-410-8210-148922-899998 | 36000 | [13 empty] | 67992 | 1.1035
| Hall |  |  | FY 23 |  |  |  | Hobbs Station Rd | Lodge Hill Rd (south) | Sable Wing Cir (south) | 34.5421 | 18 | Local | [13 empty] | 14 |  |  |  | 343037 |  |  | Public Works | [16 empty] | 4051.56 | 51.2857 | 190575.9 | 3.0929
| Hall |  |  | FY 23 |  |  |  | Talon Way | Dead End | Dead End | 30.4359 | 18 | Local | [13 empty] | 0 |  |  |  | 39874 |  |  | Public Works | [16 empty] | 1006.93 | 22 | 22152.46 | 0.35952
| Hall |  |  | FY 23 |  |  |  | UPS Dr | Whipps Mill Rd | Ormsby Station Rd | 34 | 18 | Pri Coll | [13 empty] | 2 |  |  |  | 86968 |  |  | Public Works | [16 empty] | 1238.86 | 36 | 44598.96 | 0.7238
| LP |  | 388368-26 | FY 23 |  |  |  | Aiken Rd | Bush Farm Rd | N Beckley Station Rd | 22.1639 | 19 | Sec Coll | [13 empty] | 0 |  |  | 0 | 102472 | 62992.17 | August | Public Works | [16 empty] | 2201.95 | 23.5 | 52549.75 | 0.85284
| Hall |  | 350002-559 | FY 22 |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  |  | FY 23 |  |  |  | Forest Oaks Dr | Arnold Palmer Blvd | N Beckley Station Rd | 32.0199 | 19 | Local | [13 empty] | 2 |  |  |  | 133678.548 |  |  | Public Works | [16 empty] | 3064.06 | 24 | 74265.86 | 1.2053
| Hall |  |  | FY 23 |  |  |  | Forest Trace Ct | Spring Mill Rd | Dead End | 79 | 19 | Local | [17 empty] | 7902 |  |  | Public Works | [18 empty] | 4390 | 0.071246
| Hall |  |  | FY 23 |  |  |  | Garden Hill Pl | N Beckley Station Rd | Dead End | 67 | 19 | Local | [13 empty] | 0 |  |  |  | 38556.54 |  |  | Public Works | [16 empty] | 973.65 | 22 | 21420.3 | 0.34763
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Pl | Golden Leaf Way | Dead End | 24.4599 | 19 | Local | [13 empty] | 4 |  |  |  | 37940.652 |  |  | Public Works | [16 empty] | 921.38 | 23 | 21078.14 | 0.34208
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Way (all) | Forest Oaks Dr | Golden Leaf Way | 24.4823 | 19 | Local | [13 empty] | 6 |  |  |  | 80431.938 |  |  | Public Works | [16 empty] | 1933.05 | 23 | 44684.41 | 0.72519
| Hall |  |  | FY 23 |  |  |  | Greensbrook Pl | Forest Oaks Dr | Dead End | 40 | 19 | Local | [13 empty] | 2 |  |  |  | 24575.184 |  |  | Public Works | [16 empty] | 568.87 | 24 | 13652.88 | 0.22157
| Hall |  |  | FY 23 |  |  |  | Hiawatha Ave | Heafer Rd | N English Station Rd | 26.069 | 19 | Local | [13 empty] | 5 |  |  |  | 53858.2262 |  |  | Public Works | [16 empty] | 1789.2936 | 22.25 | 29921.2368 | 0.4856
| Hall |  |  | FY 23 |  |  |  | Hines Ct | Heafer Rd | Dead End | 34 | 19 | Local | [13 empty] | 2 |  |  |  | 14106.816 |  |  | Public Works | [16 empty] | 489.82 | 16 | 7837.12 | 0.12719
| Hall |  |  | FY 23 |  |  |  | Hines Rd | Berrytown Rd | Dead End | 36.953 | 19 | Local | [13 empty] | 0 |  |  |  | 24453.3305 |  |  | Public Works | [16 empty] | 930.572 | 14 | 13585.1836 | 0.22048
| Hall |  |  | FY 23 |  |  |  | Lilly Ln | LaGrange Rd | Dead End | 40 | 19 | Local | [13 empty] | 0 |  |  |  | 48427.92 |  |  | Public Works | [16 empty] | 672.61 | 20 | 13452.2 | 0.21832
| Hall |  |  | FY 23 |  |  |  | Majestic Woods Pl | Forest Oaks Dr | Dead End | 68 | 19 | Local | [13 empty] | 2 |  |  |  | 15169.572 |  |  | Public Works | [16 empty] | 383.07 | 22 | 8427.54 | 0.13677
| Hall |  |  | FY 23 |  |  |  | Treeline Ct | Winding Creek Pl | Dead End | 23 | 19 | Local | [13 empty] | 0 |  |  |  | 11213.856 |  |  | Public Works | [16 empty] | 129.79 | 48 | 6229.92 | 0.10111
| LP |  |  | FY 23 |  |  |  | Urton Ln | N English Station Rd | Rockbridge Rd | 51.4001 | 19 | Pri Coll | [13 empty] | 0 |  |  |  | 389882 |  |  | Public Works | [16 empty] | 9449.3838 | 24.7143 | 199939.2989 | 3.2448
| Hall |  |  | FY 23 |  |  |  | Whisperwood Trace | Forest Oaks Dr | Dead End | 54 | 19 | Local | [13 empty] | 2 |  |  |  | 13030.38 |  |  | Public Works | [16 empty] | 329.05 | 22 | 7239.1 | 0.11748
| Hall |  |  | FY 23 |  |  |  | Winding Creek Ct | Winding Creek Pl | Dead End | 24 | 19 | Local | [13 empty] | 0 |  |  |  | 8396.784 |  |  | Public Works | [16 empty] | 194.37 | 24 | 4664.88 | 0.075707
| Hall |  |  | FY 23 |  |  |  | Winding Creek Pl | Oakhurst Rd | Dead End | 32.4998 | 19 | Local | [13 empty] | 4 |  |  |  | 47345.904 |  |  | Public Works | [16 empty] | 1095.97 | 24 | 26303.28 | 0.42688
| Hall |  |  | FY 23 |  |  |  | Winterbranch Way | Forest Oaks Dr | Dead End | 72 | 19 | Local | [13 empty] | 2 |  |  |  | 33957 |  |  | Public Works | [16 empty] | 857.5 | 22 | 18865 | 0.30616
| Hall |  |  | FY 23 |  |  |  | Wood Thrush Trace | Golden Leaf Pl | Dead End | 18 | 19 | Local | [13 empty] | 0 |  |  |  | 10616.4 |  |  | Public Works | [16 empty] | 245.75 | 24 | 5898 | 0.095719
| LP |  | 388368-27 | FY 23 |  |  |  | Rehl Rd | S Pope Lick Rd | S English Station Rd | 41 | 20 | Sec Coll | [13 empty] | 0 |  |  | 0 | 76297 | 79319.14 | August | Public Works | [16 empty] | 1956.3229 | 20 | 39126.4576 | 0.63499
| Hall |  |  | FY 23 |  |  |  | Burkett Ct | Mary Dell Ln | Dead End | 52 | 20 | Local | [13 empty] | 0 |  |  |  | 24655.752 |  |  | Public Works | [16 empty] | 257.85 | 18 | 4641.3 | 0.075324
| Hall |  |  | FY 23 |  |  |  | Chenoweth Park Ln | Mary Dell Ln | Dead End (south) | 22.4943 | 20 | Local | [13 empty] | 0 |  |  |  | 55485.936 |  |  | Public Works | [16 empty] | 622.62 | 22 | 13697.64 | 0.2223
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Rd | Taylorsville Rd | Old Heady Rd |  | 20 | Collector | [13 empty] | 0 |  |  |  | 600000 |  |  | Council/PW | 8133-410-8210-148628-899998 | 20171.81 |  | 8131-410-8210-148628-899998 | 111849.75 |  | 8125-410-8210-148628-899998 | 30910.5 |  | 8108-410-8210-148628-899998 | 55476.24 |  | 8115-410-8210-148628-899998 | 34084.92 |  |  |  |  | 321828 | 5.223
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Service Rd | Off Chenoweth Run Rd |  |  | 20 | Local | [13 empty] | 0 |  |  |  | 35000 |  |  | Council/PW | 8133-410-8210-148619-899998 | 12572.06 |  | 8123-410-8210-148619-899998 | 5273.67 |  | 8102-410-8210-148619-899998 | 17154.27
| LP |  |  | FY 23 |  |  |  | Dawson Hill Rd | Brush Run Rd | End of Metro R/W | 42.6283 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 568462 |  |  | Public Works | [16 empty] | 16893.8891 | 18.1111 | 291518.9848 | 4.7311
| Hall |  |  | FY 23 |  |  |  | Dry Ridge Ln | Dry Ridge Rd | Dead End | 18 | 20 | Local | [13 empty] | 0 |  |  |  | 7328.232 |  |  | Public Works | [16 empty] | 3076.73 | 12 | 36920.76 | 0.59919
| Hall |  |  | FY 23 |  |  |  | Hopewell Rd | Taylorsville Rd | Dead End | 23.2664 | 20 | Local | [13 empty] | 0 |  |  |  | 94449.744 |  |  | Public Works | [16 empty] | 2707.72 | 20.5 | 52472.08 | 0.85158
| Hall |  |  | FY 23 |  |  |  | Mary Dell Ln | Billtown Rd | Cynthia Dr | 26.1581 | 20 | Local | [13 empty] | 7 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 1401.16 | 22 | 30825.52 | 0.50027
| LP |  |  | FY 22 |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  |  | FY 23 |  |  |  | Old Heady Rd | Dead End | Dead End | 18.0252 | 20 | Local | [13 empty] | 0 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 669.4406 | 20 | 13388.8119 | 0.21729
| LP |  |  | FY 23 |  |  |  | Old Heady Rd | Taylorsville Rd | Hopewell Rd | 42.6384 | 20 | Sec Coll | [13 empty] | 10 |  |  |  | 50671 |  |  | Public Works | [16 empty] | 12887.1089 | 19.7273 | 256754.4486 | 4.1669
| Hall |  |  | FY 23 |  |  |  | Sloane Ct | Mary Dell Ln | Dead End | 61 | 20 | Local | [13 empty] | 0 |  |  |  | 8354.34 |  |  | Public Works | [16 empty] | 226.18 | 18 | 4071.24 | 0.066073
| Hall |  | 350002-505 | FY 22 |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | 208260.52 | July | [16 empty] | Asphalt done on forum/school Need to make concrete repairs | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-609 | FY 23 |  |  |  | Campobello St | Howard St | Zeta Ct | 79 | 21 | Local | [17 empty] | 30106.944 | See Howard St |  | Public Works | [18 empty] | 16726 | 0.27145
| Hall |  | 350002-609 | FY 23 |  |  |  | Carroll Ave | Durrett Ln | Scholar St | 27.7446 | 21 | Local | [13 empty] | 0 |  |  |  | 63563.112 | See Howard St |  | Public Works | [16 empty] | 1773.87 | 20 | 35312.84 | 0.5731
| Hall |  | 350002-609 | FY 23 |  |  |  | Cavelle Ave | Durrett Ln | Dead End | 26.7981 | 21 | Local | [13 empty] | 0 |  |  |  | 58023.216 | See Howard St |  | Public Works | [16 empty] | 1790.84 | 18 | 32235.12 | 0.52315
| Hall |  |  | FY23 |  |  |  | Crittenden Dr | Grade Lane | Dead End |  | 21 | Local | [17 empty] | 790710 |  |  | Public Works | [18 empty] | 395355 | 6.4163
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [13 empty] | LWC Project in area | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-603 | FY 23 |  |  |  | E Kenwood Dr | Southside Dr | Tecumseh Ave | 22.2323 | 21 | Pri Coll | [13 empty] | 6 |  |  |  | 90116 |  |  | Public Works | [16 empty] | 1992.2543 | 23.2 | 46213.3095 | 0.75
| Hall |  | 350002-610 | FY 23 |  |  |  | Greenleaf Rd | Rosemary Dr | Fern Dr | 25.4686 | 21 | Local | [13 empty] | 6 |  |  |  | 51594.948 | 21680.6 |  | Public Works | [16 empty] | 1691.27 | 17 | 28663.86 | 0.46519
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-609 | FY 23 |  |  |  | Howard St | Carroll Ave | Dead End | 35.3777 | 21 | Local | [13 empty] | 0 |  |  |  | 47118.96 | 5437 |  | Public Works | [16 empty] | 1583.17 | 16.25 | 26177.2 | 0.42483
| Hall |  | 350002-609 | FY 23 |  |  |  | Lacona Ln | Carroll Ave | Campobello St | 20 | 21 | Local | [13 empty] | 0 |  |  |  | 43749.504 | See Howard St |  | Public Works | [16 empty] | 1012.72 | 24 | 24305.28 | 0.39445
| Hall |  |  | FY 23 |  |  |  | Meridale Ave | W Southern Heights Ave | S 2nd St | 59 | 21 | Local | [13 empty] | 2 |  |  |  | 47460.15 |  |  | Public Works | [16 empty] | 1054.67 | 25 | 26366.75 | 0.42791
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [13 empty] | LWC Project in area | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [13 empty] | LWC Project in area | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  |  | FY 23 |  |  |  | S 2nd St | W Southern Heights Ave | W Wellington Ave | 30.9927 | 21 | Local | [13 empty] | 10 |  |  |  | 107083.08 |  |  | Public Works | [16 empty] | 2074.1 | 29.75 | 59490.6 | 0.96548
| Hall |  | 350002-609 | FY 23 |  |  |  | Scholar St | Carroll Ave | Campobello St | 14 | 21 | Local | [13 empty] | 0 |  |  |  | 43307.298 | See Howard St |  | Public Works | [16 empty] | 1046.07 | 23 | 24059.61 | 0.39047
| Hall |  | 350002-603 | FY 23 |  |  |  | W Kenwood Dr | Tecumseh Ave | New Cut Rd | 45.879 | 21 | Pri Coll | [13 empty] | 7 |  |  |  | 130320 |  |  | Public Works | [16 empty] | 2906.21 | 22.8 | 66830.86 | 1.0846
| Hall |  |  | FY 23 |  |  |  | W Wampum Ave | S 3rd St | S 1st St | 27.4999 | 21 | Local | [13 empty] | 2 |  |  |  | 45249.516 |  |  | Public Works | [16 empty] | 966.87 | 26 | 25138.62 | 0.40798
| Hall |  |  | FY 23 |  |  |  | W Wellington Ave | Southern Pkwy | S 1st St | 31.391 | 21 | Local | [13 empty] | 4 |  |  |  | 80171.1 |  |  | Public Works | [16 empty] | 1484.65 | 30 | 44539.5 | 0.72284
| Hall |  | 350002-596 | FY 23 |  |  |  | Woodmore Ave | New Cut Rd | Southside Dr | 45.5274 | 21 | Local | [13 empty] | 0 |  |  |  | 116415.36 | 1711.66 |  | Public Works | [16 empty] | 2694.8 | 24 | 64675.2 | 1.0496
| Hall |  |  | FY 23 |  |  |  | Zeta Ct | Campobello St | Dead End | 52 | 21 | Local | [13 empty] | 0 |  |  |  | 3236.76 |  |  | Public Works | [16 empty] | 89.91 | 20 | 1798.2 | 0.029183
| Hall |  |  | FY 23 |  |  |  | Artis Pl | Artis Way | Dead End | 39 | 22 | Local | [13 empty] | 2 |  |  |  | 7681.212 |  |  | Public Works | [16 empty] | 193.97 | 22 | 4267.34 | 0.069255
| Hall |  |  | FY 23 |  |  |  | Artis Way | Beulah Church Rd | Dead End | 39.0264 | 22 | Local | [13 empty] | 10 |  |  |  | 133542.432 |  |  | Public Works | [16 empty] | 3091.26 | 24 | 74190.24 | 1.204
| LP |  |  | FY 23 |  |  |  | Brentlinger Ln (Old Alignment) | Dobson Ln | Dead End | 30 | 22 | Local | [13 empty] | 0 |  |  |  | 8915 |  |  | Public Works | [18 empty] | 4953 | 0.080383
| LP |  |  | FY 23 |  |  |  | Dobson Ln | Brentlinger Ln | Dead End | 17.6261 | 22 | Local | [13 empty] | 0 |  |  |  | 49091 |  |  | Public Works | [16 empty] | 2400.0313 | 10.6667 | 27272.787 | 0.44261
| Hall |  |  | FY 23 |  |  |  | Fox Ledge Ct | Artis Way | Dead End | 50 | 22 | Local | [13 empty] | 0 |  |  |  | 12031.56 |  |  | Public Works | [16 empty] | 334.21 | 20 | 6684.2 | 0.10848
| Hall |  | 391627 | FY 23 |  |  |  | Gainsborough Dr | Johnson School Rd | Annalisa Dr | 32.3999 | 22 | Local | [13 empty] | 6 |  |  |  | 87744.284 | 13412.04 |  | Public Works | [16 empty] | 2076.5444 | 23.4286 | 48746.8245 | 0.79112
| LP |  |  | FY 23 |  |  |  | Johnson School Rd | Beulah Church Rd | Cedar Creek Rd | 50.9745 | 22 | Sec Coll | [13 empty] | 0 |  |  |  | 291737 |  |  | Public Works | [16 empty] | 7438.24 | 20 | 149608.76 | 2.428
| Hall |  |  | FY 23 |  |  |  | Ledge Pointe Ct | Artis Way | Dead End | 63 | 22 | Local | [13 empty] | 0 |  |  |  | 11113.56 |  |  | Public Works | [16 empty] | 308.71 | 20 | 6174.2 | 0.1002
| LP |  | 366368-18 | FY 23 |  |  |  | S Watterson Trl | Bardstown Rd | S Hurstbourne Pkwy | 53.8655 | 22 | Pri Coll | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works | [16 empty] | 7830.1598 | 21.3333 | 177103.3586 | 2.8742
| Hall |  |  | FY 23 |  |  |  | Stone Ledge Ct | Stone Ledge Rd | Dead End | 71 | 22 | Local | [13 empty] | 0 |  |  |  | 11923.848 |  |  | Public Works | [16 empty] | 368.02 | 18 | 6624.36 | 0.10751
| Hall |  |  | FY 23 |  |  |  | Stone Ledge Rd | Artis Way | Dead End | 54.5897 | 22 | Local | [13 empty] | 2 |  |  |  | 46839.96 |  |  | Public Works | [16 empty] | 1301.11 | 20 | 26022.2 | 0.42232
| Hall |  |  | FY 23 |  |  |  | Warrenton Hill Ct | Artis Way | Dead End | 38.1799 | 22 | Local | [13 empty] | 0 |  |  |  | 35755.2 |  |  | Public Works | [16 empty] | 993.2 | 20 | 19864 | 0.32238
| Hall |  |  | FY 23 |  |  |  | Wellington Hill Ct | Warrenton Hill Ct | Dead End | 31 | 22 | Local | [13 empty] | 0 |  |  |  | 29155.32 |  |  | Public Works | [16 empty] | 809.87 | 20 | 16197.4 | 0.26287
| Hall |  | 350002-555 | FY 22 |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 | 118962.35 | July | PW/CIF/Local Contribution
| Hall |  | 350002-597 | FY 23 |  |  |  | Adkins Rd | Honor Ave | Dead End | 44.5373 | 23 | Local | [13 empty] | 0 |  |  |  | 43504.956 |  |  | Public Works | [16 empty] | 1098.61 | 22 | 24169.42 | 0.39225
| Hall |  | 350002-597 | FY 23 |  |  |  | Amalfi Ave | Dead End | Honor Ave | 58.5583 | 23 | Local | [13 empty] | 0 |  |  |  | 38727.108 |  |  | Public Works | [16 empty] | 940.89 | 22.6667 | 21515.06 | 0.34917
| Hall |  | 350002-597 | FY 23 |  |  |  | Beth Rd | Denise Dr | Dead End | 45.0781 | 23 | Local | [13 empty] | 0 |  |  |  | 80040.96 |  |  | Public Works | [16 empty] | 1927.18 | 23.3333 | 44467.2 | 0.72166
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherita Rd | Denise Dr | Dead End | 52.2629 | 23 | Local | [13 empty] | 0 |  |  |  | 41878.98 |  |  | Public Works | [16 empty] | 1057.55 | 22 | 23266.1 | 0.37759
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherriville Rd | Manslick Rd | Amalfi Ave | 67 | 23 | Local | [13 empty] | 0 |  |  |  | 26279.856 |  |  | Public Works | [16 empty] | 608.33 | 24 | 14599.92 | 0.23694
| Hall |  | 350002-597 | FY 23 |  |  |  | Denise Dr | Lois Ave | Dead End | 33.26 | 23 | Local | [13 empty] | 0 |  |  |  | 189163.728 |  |  | Public Works | [16 empty] | 4378.79 | 24 | 105090.96 | 1.7055
| Hall |  | 350002-597 | FY23 |  |  |  | Elise Way | Shepherdsville Rd | Dead End |  | 23 | Local | [13 empty] | 0 |  |  |  | 5000
| Hall |  | 350002-597 | FY 23 |  |  |  | Honor Ave | Adkins Rd | Dead End | 50.0632 | 23 | Local | [13 empty] | 0 |  |  |  | 68010.732 |  |  | Public Works | [16 empty] | 1652.42 | 22.8 | 37783.74 | 0.6132
| Hall |  | 350002-597 | FY 23 |  |  |  | Lois Ave | Beth Rd | Dead End | 58.3886 | 23 | Local | [13 empty] | 0 |  |  |  | 87275.016 |  |  | Public Works | [16 empty] | 2033.95 | 23.3333 | 48486.12 | 0.78689
| Hall |  | 350002-597 | FY 23 |  |  |  | Senator Ln | Denise Dr | Honor Ave | 19 | 23 | Local | [13 empty] | 0 |  |  |  | 38432.016 |  |  | Public Works | [16 empty] | 889.63 | 24 | 21351.12 | 0.34651
| Hall |  | 350002-593 | FY 23 |  |  |  | Abbydale Ct | Wood Hollow Rd | Dead End | 36 | 24 | Local | [13 empty] | 0 |  |  |  | 19077.12 | See Woodsend Rd |  | Public Works | [16 empty] | 588.8 | 18 | 10598.4 | 0.172
| Hall |  | 350002-591 | FY 23 |  |  |  | Bellflower Dr | Blue Lick Rd | Dead End | 36.645 | 24 | Local | [13 empty] | 0 |  |  |  | 24800.76 | See Bluebell Dr |  | Public Works | [16 empty] | 607.95 | 23 | 13778.2 | 0.22361
| Hall |  | 350002-591 | FY 23 |  |  |  | Bluebell Dr | Blue Lick Rd | Narcissus Dr | 48.3834 | 24 | Local | [13 empty] | 2 |  |  |  | 113040.576 | 24274.75 |  | Public Works | [16 empty] | 2616.68 | 24 | 62800.32 | 1.0192
| Hall |  |  | FY 23 |  |  |  | Burnt Cedar Ln | Dead End | Dead End | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 39631 |  |  | Council | 8102-410-8210-148386-899998 | 3342.34 |  | 8672-410-8210-148385-899998 | 3342.34 |  | 8101-410-8210-148386-899998 | 48420.4 |  | 8137-410-8210-148385-899998 | 19301.47 |  | 8131-410-8210-148385-899998 | 1520.9 |  |  |  |  | 24019 | 0.38981
| Hall |  |  | FY 23 |  |  |  | Cameo Ct | Pebblebrook Ln | Dead End | 33 | 24 | Local | [13 empty] | 0 |  |  |  | 7625 |  |  | Council | See Burnt cedar | [17 empty] | 4621 | 0.074995
| Hall |  |  | FY 23 |  |  |  | Cathay Ct | Linda Rd | Dead End | 35 | 24 | Local | [13 empty] | 0 |  |  |  | 17416 |  |  | Council | See Burnt cedar | [17 empty] | 10555 | 0.1713
| Hall |  |  | FY 23 |  |  |  | Delee Way | Narcissus Dr | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 15685.056 |  |  | Public Works | [16 empty] | 363.08 | 24 | 8713.92 | 0.14142
| Hall |  |  | FY 22 |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  | 350002-591 | FY 23 |  |  |  | Narcissus Dr | Bluebell Dr | Dead End | 19.0231 | 24 | Local | [13 empty] | 2 |  |  |  | 51919.488 | See Bluebell Dr |  | Public Works | [16 empty] | 1201.84 | 24 | 28844.16 | 0.46812
| Hall |  |  | FY 23 |  |  |  | Pebblebrook Ln | Burnt Cedar Ln | Santa Paula Ln |  | 24 | Local | [17 empty] | 5000 |  |  | Council Funded | See Burnt cedar
| LP |  |  | FY 23 |  |  |  | Smyrna Rd | Briscoe Ln | Outer Loop | 26 | 24 | Sec Coll | [13 empty] | 0 |  |  |  | 97192 |  |  | Public Works | [16 empty] | 2265.55 | 22 | 49842.1 | 0.80889
| Hall |  | 350002-593 | FY 23 |  |  |  | Tolkien Ct | Wood Hollow Rd | Dead End | 16 | 24 | Local | [13 empty] | 0 |  |  |  | 19069.02 | See Woodsend Rd |  | Public Works | [16 empty] | 588.55 | 18 | 10593.9 | 0.17193
| Hall |  | 350002-591 | FY 23 |  |  |  | Tulip Cir | Bluebell Dr | Dead End | 56 | 24 | Local | [13 empty] | 0 |  |  |  | 8485.488 | See Bluebell Dr |  | Public Works | [16 empty] | 214.28 | 22 | 4714.16 | 0.076507
| Hall |  | 350002-591 | FY 23 |  |  |  | Weigela Dr | Blue Lick Rd | Bluebell Dr | 45 | 24 | Local | [13 empty] | 0 |  |  |  | 23762.592 | See Bluebell Dr |  | Public Works | [16 empty] | 550.06 | 24 | 13201.44 | 0.21425
| Hall |  | 350002-593 | FY 23 |  |  |  | Wood Hollow Rd | Oldshire Rd | Woodsend Rd | 37.445 | 24 | Local | [13 empty] | 6 |  |  |  | 34705.152 | See Woodsend Rd |  | Public Works | [16 empty] | 803.36 | 24 | 19280.64 | 0.31291
| Hall |  | 350002-593 | FY 23 |  |  |  | Woodsend Rd | Dead End | Dead End | 26.2616 | 24 | Local | [13 empty] | 2 |  |  |  | 34921.368 | 14281.9 |  | Public Works | [16 empty] | 1077.82 | 18 | 19400.76 | 0.31486
| LP |  | 388368-1 | FY 23 |  |  |  | Fordhaven Rd | St Anthony Church Rd | public road end | 37 | 25 | Local | [13 empty] | 0 |  |  | 0 | 70953 | See St Anthony Church Rd | August | Public Works | [16 empty] | 1359.2584 | 29 | 39418.4924 | 0.63973
| LP |  | 388368-1 | FY 23 |  |  |  | Manslick Rd | St Anthony Church Rd | Palatka Rd | 41.9559 | 25 | Pri Coll | [13 empty] | 0 |  |  | 2 | 357026 | See St Anthony Church Rd | August | Public Works | [16 empty] | 8143.41 | 22.6 | 183090.48 | 2.9714
| LP |  | 388368-1 | FY 23 |  |  |  | Springfield Dr | St Anthony Church Rd | public road end | 14 | 25 | Local | [13 empty] | 0 |  |  | 0 | 38326 | See St Anthony Church Rd | August | Public Works | [16 empty] | 887.1779 | 24 | 21292.2706 | 0.34556
| LP |  | 388368-1 | FY 22 |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [13 empty] | 0 |  |  | 0 | 390484.05 | 1025274.42 | August | [17 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-602 | FY 23 |  |  |  | Bamberrie Cross Rd | Chet Ln | 3rd Street Rd | 46.757 | 25 | Local | [13 empty] | 0 |  |  |  | 41704 |  |  | Public Works | [16 empty] | 1053.13 | 22 | 23168.86 | 0.37601
| LP |  | 388368-4 | FY 22 |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded | 8138-410-8107-148547-82134 | 83369.78 |  | 8146-410-8107-148547-822705 | 88630.22 |  | 8138-410-8210-148386-822702 | 19000
| Hall |  | 350002-602 | FY 23 |  |  |  | Burr Ln | Carol Way | Dead End | 28 | 25 | Local | [13 empty] | 0 |  |  |  | 35239 |  |  | Public Works | [16 empty] | 815.71 | 24 | 19577.04 | 0.31772
| Hall |  | 350002-602 | FY 23 |  |  |  | Carol Way | Manslick Rd | Chet Ln | 20.8911 | 25 | Local | [13 empty] | 0 |  |  |  | 56753 |  |  | Public Works | [16 empty] | 1433.15 | 22 | 31529.3 | 0.51169
| Hall |  | 350002-602 | FY 23 |  |  |  | Cartledge Ct | Chet Ln | 3rd Street Rd | 45 | 25 | Local | [13 empty] | 0 |  |  |  | 33549 |  |  | Public Works | [16 empty] | 1164.91 | 16 | 18638.56 | 0.30249
| Hall |  | 350002-602 | FY 23 |  |  |  | Chet Ln | Carol Way | Cartledge Ct | 26.9408 | 25 | Local | [13 empty] | 0 |  |  |  | 32341 |  |  | Public Works | [16 empty] | 816.69 | 22 | 17967.18 | 0.29159
| Hall |  | 350002-595 | FY 23 |  |  |  | Constitution Dr | Manslick Rd | Dead End | 45.4192 | 25 | Local | [13 empty] | 0 |  |  |  | 49339 |  |  | Public Works | [16 empty] | 1105.27 | 25 | 27410.36 | 0.44485
| Hall |  | 350002-595 | FY 23 |  |  |  | Heritage Pl | Manslick Rd | Dead End | 26 | 25 | Local | [13 empty] | 0 |  |  |  | 32230 |  |  | Public Works | [16 empty] | 596.85 | 30 | 17905.5 | 0.29059
| Hall |  | 350002-595 | FY 23 |  |  |  | Potomac Pl | Manslick Rd | Dead End | 30 | 25 | Local | [13 empty] | 0 |  |  |  | 28850 |  |  | Public Works | [16 empty] | 616.45 | 26 | 16027.7 | 0.26012
| Hall |  | 350002-595 | FY 23 |  |  |  | Quaker Ct | Constitution Dr | Dead End | 17 | 25 | Local | [13 empty] | 0 |  |  |  | 14012 |  |  | Public Works | [16 empty] | 389.22 | 20 | 7784.4 | 0.12633
| Hall |  | 350002-544 | FY 22 |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  |  | FY 23 |  |  |  | Brockton Ln | Hendon Rd | Commander Dr | 41.8604 | 26 | Local | [13 empty] | 0 |  |  |  | 92931.3659 |  |  | Public Works | [16 empty] | 2239.9299 | 23 | 51628.5366 | 0.83789
| Hall |  |  | FY 23 |  |  |  | Bryan Way | Dogwood Dr | Deibel Way | 37 | 26 | Local | [13 empty] | 6 |  |  |  | 47250 |  |  | Council | 8102-410-8210-148626-899998 | 112284.06 |  | 8672-410-8210-148626-899998 | 50492.42 |  | 8131-410-8210-148626-899998 | 17653.65 |  | 8133-410-8210-148626-899998 | 28163.58 | [7 empty] | 27008 | 0.43832
| Hall |  |  | FY 23 |  |  |  | Commander Dr | Brockton Ln | Herb Ln | 35 | 26 | Local | [13 empty] | 1 |  |  |  | 39974.22 |  |  | Public Works | [16 empty] | 854.15 | 26 | 22207.9 | 0.36041
|  |  |  | FY 23 |  |  |  | D26 Paving |  |  |  | 26 | [18 empty] | 122844 |  |  | Council | [19 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doreen Way | Brockton Ln | Dead End | 32 | 26 | Local | [13 empty] | 4 |  |  |  | 69295.464 |  |  | Public Works | [18 empty] | 38497 | 0.62477
| Hall |  |  | FY 23 |  |  |  | Eastside Ct | Eastside Dr | Dead End | 69 | 26 | Local | [13 empty] | 0 |  |  |  | 3877.2 |  |  | Public Works | [16 empty] | 89.75 | 24 | 2154 | 0.034958
| Hall |  |  | FY 23 |  |  |  | Eastside Dr | Manner Gate Dr | Hunsinger Ln | 18.5457 | 26 | Local | [13 empty] | 24 |  |  |  | 38431.584 |  |  | Public Works | [16 empty] | 889.62 | 24 | 21350.88 | 0.34651
| Hall |  |  | FY 23 |  |  |  | Enridge Dr | Manner Dale Dr | Landside Dr | 42 | 26 | Local | [13 empty] | 5 |  |  |  | 38500 |  |  | Council | See Bryan Way | [17 empty] | 21891 | 0.35527
| Hall |  |  | FY 23 |  |  |  | Garden View Ct | Westwood Farms Dr | Dead End | 58 | 26 | Local | [13 empty] | 0 |  |  |  | 17266.788 |  |  | Public Works | [16 empty] | 436.03 | 22 | 9592.66 | 0.15568
| Hall |  |  | FY 23 |  |  |  | Kings Hwy | Rosedale Blvd | Talisman Rd | 34.4907 | 26 | Local | [13 empty] | 0 |  |  |  | 31081.536 |  |  | Public Works | [16 empty] | 719.48 | 24 | 17267.52 | 0.28024
| Hall |  |  | FY 23 |  |  |  | Nadina Dr | Wedgewood Way | Herb Ln | 39 | 26 | Local | [13 empty] | 6 |  |  |  | 36193.95 |  |  | Public Works | [16 empty] | 874.25 | 23 | 20107.75 | 0.32633
| Hall |  |  | FY 23 |  |  |  | Plain Field Ct | Shaker Mill Rd | Dead End | 33 | 26 | Local | [13 empty] | 0 |  |  |  | 12043.548 |  |  | Public Works | [16 empty] | 304.13 | 22 | 6690.86 | 0.10859
| Hall |  |  | FY 23 |  |  |  | Rosedale Blvd | Brockton Ln | Radiance Rd | 41 | 26 | Local | [13 empty] | 6 |  |  |  | 10746.432 |  |  | Public Works | [16 empty] | 248.76 | 24 | 5970.24 | 0.096892
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Ct | Shaker Mill Rd | Dead End | 28 | 26 | Local | [13 empty] | 0 |  |  |  | 10504.692 |  |  | Public Works | [16 empty] | 265.27 | 22 | 5835.94 | 0.094712
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Rd | Westwood Farms Dr | Plain Field Ct | 50.7877 | 26 | Local | [13 empty] | 8 |  |  |  | 85603.392 |  |  | Public Works | [16 empty] | 1981.56 | 24 | 47557.44 | 0.77182
| Hall |  |  | FY 23 |  |  |  | Taylorsville Rd | Brockton Ln | Dead End | 64 | 26 | Local | [13 empty] | 1 |  |  |  | 21875.328 |  |  | Public Works | [16 empty] | 759.56 | 16 | 12152.96 | 0.19723
| Hall |  |  | FY 23 |  |  |  | Wedgewood Way (north) | Brockton Ln | Herb Ln | 26.4861 | 26 | Local | [13 empty] | 4 |  |  |  | 38181.924 |  |  | Public Works | [16 empty] | 936.5 | 23 | 21212.18 | 0.34426
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Ct | Westwood Farms Dr | Dead End | 80 | 26 | Local | [13 empty] | 0 |  |  |  | 12974.94 |  |  | Public Works | [16 empty] | 327.65 | 22 | 7208.3 | 0.11698
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Dr | Six Mile Ln | Plain Field Ct | 50.7893 | 26 | Local | [13 empty] | 13 |  |  |  | 117732.096 |  |  | Public Works | [16 empty] | 2395.29 | 30 | 65406.72 | 1.0615
| Strand |  | 373479-43 | FY 23 |  |  |  | Alley paving administration | [23 empty] | 2005.42
| Michael Baker |  | 387658-1 | FY 23 |  |  |  | Supplemental Inspections | [22 empty] | 71609 | 112063.14

## Sept 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-628 | FY 23 |  |  |  | Bridwell Dr | Kaufman Ln | Dead End | 30.6881 | 1 | Local | [13 empty] | 1 |  |  |  | 100503 | 5448.79 |  | Public Works | [16 empty] | 2965.84 | 19 | 55835.26 | 0.90616
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Virginia Ave | Wilson Ave | 30.1848 | 1 | Local | [13 empty] | 14 |  |  |  | 155020 |  |  | Public Works | [15 empty] | Speed Humps and rail crossing | 2421.8757 | 35.25 | 86122.4396 | 1.3977
|  |  |  | FY 23 |  |  |  | D1 Paving |  |  |  | 1 | [18 empty] | 40000 |  |  | Council | 8102-410-8210-148991-899998 | 40000 | [17 empty] | 0
|  |  |  | FY 23 |  |  |  | Gregg Ave | Vorster Ave | Dead End (Alley) |  | 1 | Local | [17 empty] | 20000 |  |  | Council | 8676-410-8106-048201-822702 | 20000
|  |  |  | FY23 |  |  |  | S 36th St | Dumesnil St | Colmar Dr |  | 1 | Local | [17 empty] | 43747 |  |  | Council | 8101-410-8105-148391-822702 | 10754.93 |  | 8102-410-8105-148371-822702 | 48791.07 |  | 8133-410-8107-148911-822702 | 9000
|  |  |  | FY 23 |  |  |  | Kirby Ave | Louis Coleman Jr Dr | Rosewell Ave |  | 1 | Local | [17 empty] | 18250 |  |  | Council | See S 36th
|  |  |  | FY 23 |  |  |  | Challis Cir | Regatta Way | Dead End |  | 1 | Local | [17 empty] | 6549 |  |  | Council | See S 36th
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | Dead End (east) | 22.533 | 1 | Local | [13 empty] | 6 |  |  |  | 23711 |  |  | Public Works | [15 empty] | Looks like an alley. Base Failures likely | 1061.01 | 12.6667 | 13172.86 | 0.21378
| Hall |  | 350002-629 | FY 23 |  |  |  | Farnsley Rd (west) | Cane Run Rd | Dead End | 37.2527 | 1 | Local | [13 empty] | 2 |  |  |  | 41202 |  |  | Public Works | [15 empty] | Narrows at dead end. Look to possibly add Zoeller and Van Winkle to Paving | 1321.12 | 17 | 22889.77 | 0.37148
| Hall |  |  | FY 23 |  |  |  | Greenwood Ave | S 26th St | S 29th St | 29.2162 | 1 | Local | [13 empty] | 8 |  |  |  | 100582 |  |  | Public Works | [15 empty] | alley just west of S 28th | 1582.87 | 35.5 | 55879.08 | 0.90687
| Hall |  | 350002-628 | FY 23 |  |  |  | Mary Rose Dr | Bridwell Dr | Lencott Dr | 51.4364 | 1 | Local | [13 empty] | 0 |  |  |  | 27007 | See Bridwell |  | Public Works | [15 empty] | Likely illegal driveway at Wilkie, but leave it alone | 759.69 | 20 | 15003.7 | 0.2435
| Hall |  | 350002-629 | FY 23 |  |  |  | Ronald Ct | Cane Run Rd | Dead End | 37 | 1 | Local | [13 empty] | 2 |  |  |  | 12907 |  |  | Public Works | [15 empty] | Possible base failure | 358.54 | 20 | 7170.8 | 0.11638
| Hall |  |  | FY 23 |  |  |  | S 31st St | Southern Ave | Dr William G Weathers Dr | 30.9738 | 1 | Local | [13 empty] | 12 |  |  |  | 62558 |  |  | Public Works | [15 empty] | do not repalce east sidewalk median on weathers where bump out is | 1579.74 | 22 | 34754.28 | 0.56403
| Hall |  |  | FY 22 |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  | FY 22 |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  | FY 22 |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-629 | FY 23 |  |  |  | Van Winkle Dr | Cane Run Rd | Dead End | 90 | 1 | Local | [13 empty] | 0 |  |  |  | 48286 |  |  | Public Works | [15 empty] | Check to see if this needs to be paved |  |  | 26825 | 0.43535
| Hall |  |  | FY 23 |  |  |  | Woodland Ave | Olive St | S 32nd St | 19.9396 | 1 | Local | [13 empty] | 21 |  |  |  | 144319 |  |  | Public Works | [16 empty] | 2380.0935 | 33.4286 | 80177.1976 | 1.3012
| Hall |  | 350002-629 | FY 23 |  |  |  | Zoeller Ave | Farnsley Rd | Van Winkle Dr | 48 | 1 | Local | [13 empty] | 0 |  |  |  | 11885 |  |  | Public Works | [18 empty] | 6603 | 0.10716
| Hall |  | 350002-536 | FY 22 |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 88144.05 | [17 empty] | LWC main replacement, LPA project | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  | FY 23 |  |  |  | Ayars Ct | Lambert Ave | Dead End | 11 | 2 | Local | [13 empty] | 0 |  |  |  | 12440.52 |  |  | Public Works | [16 empty] | 345.57 | 20 | 6911.4 | 0.11217
| Hall |  |  | FY 23 |  |  |  | Bartholomew Dr | Lambert Ave | Dead End | 62 | 2 | Local | [13 empty] | 0 |  |  |  | 16778.949 |  |  | Public Works | [15 empty] | Don’t update ramps at end of roaday | 462.23 | 22 | 10169.06 | 0.16503
| Hall |  |  | FY 23 |  |  |  | Beechbrook Rd | Kranet Way | Norfolk Dr | 38.6177 | 2 | Local | [13 empty] | 0 |  |  |  | 26909.712 |  |  | Public Works | [16 empty] | 622.91 | 24 | 14949.84 | 0.24262
| Hall |  | 350002-536 | FY 22 |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [17 empty] | LWC main replacement, LPA project | 674 | 24 | 14370 | 0.23321
| Hall |  |  | FY 23 |  |  |  | Bunche Ct | Ellington Ave | Dead End | 64 | 2 | Local | [13 empty] | 0 |  |  |  | 7492.176 |  |  | Public Works | [16 empty] | 173.43 | 24 | 4162.32 | 0.067551
| Hall |  |  | FY 23 |  |  |  | Ellington Ave | Stokes Ct | Petersburg Rd | 46.0801 | 2 | Local | [13 empty] | 8 |  |  |  | 93178.512 |  |  | Public Works | [16 empty] | 1437.94 | 36 | 51765.84 | 0.84011
| Hall |  |  | FY 23 |  |  |  | Exeter Ave | E Indian Trl | Stokes Ct | 19.8519 | 2 | Local | [13 empty] | 12 |  |  |  | 92320.56 |  |  | Public Works | [15 empty] | 2 bar walks at school which should go back. Do not add ramp at shared use path | 1424.7 | 36 | 51289.2 | 0.83238
| LP |  |  | FY 23 |  |  |  | Fegenbush Ln | Bardstown Rd | Fern Valley Rd | 55.6081 | 2 | Min Art | [13 empty] | 16 |  |  |  | 938271.8611 |  |  | Public Works | [16 empty] | 9572.4106 | 47.8182 | 481165.057 | 7.8089
| Hall |  |  | FY 23 |  |  |  | Heller St | Buechel Bank Rd | Dead End | 20 | 2 | Local | [13 empty] | 0 |  |  |  | 94402.764 |  |  | Public Works | [16 empty] | 2280.26 | 23 | 52445.98 | 0.85115
| Hall |  |  | FY 23 |  |  |  | Kilgore Ct | Exeter Ave | Dead End | 39 | 2 | Local | [13 empty] | 0 |  |  |  | 15129.504 |  |  | Public Works | [16 empty] | 350.22 | 24 | 8405.28 | 0.13641
| Hall |  |  | FY 23 |  |  |  | Lambert Ave | Buechel Bank Rd | Beechbrook Rd | 25.1893 | 2 | Local | [13 empty] | 9 |  |  |  | 79433 |  |  | Public Works | [15 empty] | Speed Humps | 1922.24 | 23 | 44129.26 | 0.71618
| Hall |  |  | FY 23 |  |  |  | Lambert Ct | Lambert Ave | Dead End | 54 | 2 | Local | [13 empty] | 0 |  |  |  | 14204 |  |  | Public Works | [16 empty] | 438.4 | 18 | 7891.2 | 0.12807
| Hall |  |  | FY 23 |  |  |  | Landing Dr | Lambert Ave | Norfolk Dr | 55 | 2 | Local | [13 empty] | 0 |  |  |  | 20582.208 |  |  | Public Works | [15 empty] | Include little dead end seciton just northof norfolk | 476.44 | 24 | 11434.56 | 0.18557
| Hall |  |  | FY 23 |  |  |  | Norbrook Dr | Fegenbush Ln | Dead End | 54.7966 | 2 | Local | [13 empty] | 2 |  |  |  | 56620.872 |  |  | Public Works | [16 empty] | 1123.43 | 28 | 31456.04 | 0.5105
| Hall |  |  | FY 23 |  |  |  | Norfolk Dr | Fegenbush Ln | Landing Dr | 18.9326 | 2 | Local | [13 empty] | 1 |  |  |  | 67012.92 |  |  | Public Works | [15 empty] | Believe this section of roadway includes base failures | 1431.9 | 26 | 37229.4 | 0.6042
| Hall |  |  | FY 23 |  |  |  | Sanford Ave | Buechel Bank Rd | Lambert Ave | 53 | 2 | Local | [13 empty] | 4 |  |  |  | 59871.798 |  |  | Public Works | [16 empty] | 1583.91 | 21 | 33262.11 | 0.53982
| Hall |  |  | FY 23 |  |  |  | Stokes Ct | Ellington Ave | Dead End | 46 | 2 | Local | [13 empty] | 0 |  |  |  | 15148.08 |  |  | Public Works | [16 empty] | 350.65 | 24 | 8415.6 | 0.13658
| Hall |  |  | FY 23 |  |  |  | Tubman Ct | Ellington Ave | Dead End | 25 | 2 | Local | [13 empty] | 0 |  |  |  | 7706.88 |  |  | Public Works | [16 empty] | 178.4 | 24 | 4281.6 | 0.069487
| Hall |  |  | FY 23 |  |  |  | Wheatley Ct | Exeter Ave | Dead End | 66 | 2 | Local | [13 empty] | 0 |  |  |  | 19063.2829 |  |  | Public Works | [16 empty] | 441.2797 | 24 | 10590.7127 | 0.17188
| Hall |  |  | FY 23 |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [13 empty] | Done |  |  |  | 67784.6 | Cost in FY 22 | June | Public Works | [16 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  |  | FY 23 |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [13 empty] | Done |  |  |  | 31238.7 | Cost in FY 22 | june | Public Works | [16 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [13 empty] | Done |  |  |  | 28873.4 | Cost in FY 22 | June | Public Works | [16 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall |  |  | FY 23 |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [13 empty] | Done |  |  |  | 50573.4 | Cost in FY 22 | June | Public Works | [16 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Wilson Ave | Dead End (south) | 29.2907 | 3 | Local | [13 empty] | 6 |  |  |  | 54951.192 |  |  | Public Works | [16 empty] | 984.82 | 30.6667 | 30528.44 | 0.49545
| Hall |  |  | FY 23 |  |  |  | Hardesty Ave | Dixie Hwy | S 23rd St | 23 | 3 | Local | [13 empty] | 0 |  |  |  | 42265.4 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1514.8574 | 18.0004 | 27268 | 0.44254
| Hall |  |  | FY 23 |  |  |  | Hemlock Ct | W Gaulbert Ave | Dead End | 56 | 3 | Local | [13 empty] | 0 |  |  |  | 9432 |  |  | Public Works | [16 empty] | 187 | 28 | 5240 | 0.085041
| Hall |  |  | FY 23 |  |  |  | Olive St | W Gaulbert Ave | Dead End | 55 | 3 | Local | [13 empty] | 0 |  |  |  | 16247.52 |  |  | Public Works | [16 empty] | 300.88 | 30 | 9026.4 | 0.14649
| Hall |  |  | FY 23 |  |  |  | Plantation Dr | Wingfield Ln | Millers Ln | 42.7091 | 3 | Local | [13 empty] | 0 |  |  |  | 42614.15 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1527.3899 | 18 | 27493 | 0.44619
| Hall |  |  | FY 22 |  |  |  | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [18 empty] | On Hold |  |  |  | 0
| Hall |  |  | FY 22 |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [18 empty] | On Hold | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  |  | FY 23 |  |  |  | S 28th ST | W Gaulbert Ave | Dead End | 51 | 3 | Local | [13 empty] | 0 |  |  |  | 10071.828 |  |  | Public Works | [16 empty] | 215.21 | 26 | 5595.46 | 0.090809
| Hall |  |  | FY 23 |  |  |  | W Gaulbert Ave | Cypress St | Wilson Ave | 35.2883 | 3 | Local | [13 empty] | 9 |  |  |  | 79050.6 |  |  | Public Works | [16 empty] | 1631.47 | 26.8 | 43917 | 0.71273
| Hall |  | 350002-571 | FY 22 |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 141383.01 | July | [17 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-571 | FY 22 |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | July | [17 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  |  | FY 23 |  |  |  | Guthrie St | S 2nd St | S 3rd St | 17 | 4 | Local | [13 empty] | Done |  |  |  | 31156.488 | Cost in FY 22 | June | Public Works | [16 empty] | 480.81 | 36 | 17309.16 | 0.28091
| Hall |  | 350002-590 | FY23 |  |  |  | Bus Pad at 6th & Jefferson |  |  |  | 4 | [18 empty] | 50000 | 29557.09 | September | Public Works
| Hall |  | 350002-472 | FY 22 |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | 116336.29 | September | [17 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-472 | FY 22 |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | 248959.71 | September | [17 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 | FY 22 |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 |  | September | [17 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  | 350002-472 | FY 22 |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | See E Madison | September | [17 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-399 | FY 22 |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | September | [17 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  | FY 23 |  |  |  | Benton Ave | St Anthony Pl | Rubel Ave | 23 | 4 | Local | [13 empty] | 4 |  |  |  | 15710.688 |  |  | Public Works | [16 empty] | 311.72 | 28 | 8728.16 | 0.14165
| Hall |  |  | FY 23 |  |  |  | Cedar St | S 19th St | S 15th St | 38.9167 | 4 | Local | [13 empty] | 15 |  |  |  | 128110.8343 |  |  | Public Works | [16 empty] | 1923.464 | 37 | 71172.6857 | 1.1551
| Hall |  |  | FY 23 |  |  |  | Debarr St | Rubel Ave | Barret Ave | 32.4769 | 4 | Local | [13 empty] | 11 |  |  |  | 60853.68 |  |  | Public Works | [16 empty] | 1126.92 | 30 | 33807.6 | 0.54867
| Hall |  | 350002-625 | FY 23 |  |  |  | Duncan St | N 22nd St | N 24th St | 14.0205 | 4 | Local | [13 empty] | 12 |  |  |  | 62193.096 | See W Main |  | Public Works | [16 empty] | 959.77 | 36 | 34551.72 | 0.56074
| Hall |  | 350002-400 | FY 22 |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 | FY 22 |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  | FY 23 |  |  |  | E Washington St | N 1st St | N Preston St | 54.508 | 4 | Pri Coll | [13 empty] | 11 |  |  |  | 95355 |  |  | Public Works | [16 empty] | 1654.55 | 29.3333 | 48899.86 | 0.7936
| Hall |  |  | FY 23 |  |  |  | Edward St | St Anthony Pl | Morton Ave | 24.8631 | 4 | Local | [13 empty] | 34 |  |  |  | 80043.228 |  |  | Public Works | [16 empty] | 1234.23 | 36 | 44468.46 | 0.72168
| Hall |  |  | FY 23 |  |  |  | Magazine St | S 10th St | S 11th St | 34 | 4 | Local | [13 empty] | 1? |  |  |  | 35643.132 |  |  | Public Works | [15 empty] | Maybe make a new ramp where Magazine hits 10th st | 471.47 | 42 | 19801.74 | 0.32136
| Hall |  |  | FY 23 |  |  |  | N 2nd St | River Rd | W Main St | 55.2249 | 4 | Pri Coll | [13 empty] | 6 |  |  |  | 35953 |  |  | Public Works | [16 empty] | 904.75 | 20 | 18437.4 | 0.29922
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 |  |  | See Roy Wilkins Ave | [16 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 | FY 22 |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  | 350002-625 | FY 23 |  |  |  | Rowan St | N 22nd St | N 24th St | 15.9641 | 4 | Local | [13 empty] | 8 |  |  |  | 62099.136 | See W Main |  | Public Works | [16 empty] | 958.32 | 36 | 34499.52 | 0.5599
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 |  |  | 7849.84 | [16 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  | FY 23 |  |  |  | Rubel Ave | E Broadway | Morton Ave | 30.1586 | 4 | Local | [13 empty] | 33 |  |  |  | 84858.9042 |  |  | Public Works | [16 empty] | 1341.3399 | 35.2 | 47143.8357 | 0.7651
| Hall |  |  | FY 23 |  |  |  | S 10th St | Magazine St | Read Alley | 34 | 4 | Local | [13 empty] | 2 |  |  |  | 16551.5921 |  |  | Public Works | [16 empty] | 218.9364 | 42 | 9195.3289 | 0.14923
| Hall |  |  | FY 23 |  |  |  | S 11th St | W Chestnut St | W Broadway | 33.1751 | 4 | Local | [13 empty] | 11 |  |  |  | 79179.012 |  |  | Public Works | [16 empty] | 1063.09 | 41.3333 | 43988.34 | 0.71389
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Broadway | Cedar St | 17.6734 | 4 | Local | [13 empty] | 33 |  |  |  | 145131.84 |  |  | Public Works | [18 empty] | 142801 | 2.3175
| Hall |  |  | FY 23 |  |  |  | S 18th St | Green Alley | Eddy St | 47.405 | 4 | Local | [13 empty] | 2 |  |  |  | 30136.104 |  |  | Public Works | [16 empty] | 492.42 | 34 | 16742.28 | 0.27171
| Hall |  | 350002-630 | FY 23 |  |  |  | S 4th St | Muhammad Ali | Chestnut St |  | 4 | Local | [13 empty] | 0 |  |  |  | 25000 |  |  | Public Works
| Hall |  | 350002-472 | FY 22 |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  |  | FY 23 |  |  |  | S Preston St | E Hill St | I 65 Ramp | 52.6318 | 4 | Min Art | [13 empty] | 9 |  |  |  | 66983 |  |  | Public Works | [16 empty] | 911.2283 | 34.6667 | 31896.4441 | 0.51765
| Hall |  |  | FY 23 |  |  |  | St Anthony Pl | E Broadway | Barret Ave | 33.4304 | 4 | Local | [13 empty] | 5 |  |  |  | 63780.804 |  |  | Public Works | [16 empty] | 1161.78 | 31.3333 | 35433.78 | 0.57506
| Hall |  | 350002-625 | FY 23 |  |  |  | W Main St | N 22nd St | N 25th St | 39.6711 | 4 | Local | [13 empty] | 17 |  |  |  | 155392.56 | 50805.43 |  | Public Works | [16 empty] | 1438.82 | 60 | 86329.2 | 1.401
| Hall |  | 350002-590 | FY 22 |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 |  |  | See Roy Wilkins Ave | [16 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  |  | FY 23 |  |  |  | W Washington St | N 1st St | N 2nd St | 29 | 4 | Pri Coll | [13 empty] | 4 |  |  |  | 21168 |  |  | Public Works | [16 empty] | 493.42 | 22 | 10855.24 | 0.17617
| Hall |  |  | FY 23 |  |  |  | Walter Barnes Way | W Chestnut St | Read Alley | 37 | 4 | Local | [13 empty] | 0 |  |  |  | 18051.3374 |  |  | Public Works | [16 empty] | 250.713 | 40 | 10028.5208 | 0.16275
| Hall |  | 350002-608 | FY 23 |  |  |  | S 32nd St | Grand Ave | Greenwood Ave | 50 | 5 | Local | [17 empty] | 13598.63 | 13598.63 | August | Public Works | [18 empty] | 14567 | 0.23641
| Hall |  | 350002-583 | FY 22 |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | See S 32nd St | July | [17 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | See S 32nd St | July | [17 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  | 350002-583 | FY 22 |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | See S 32nd St | July | [17 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  | 350002-583 | FY 22 |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | See S 32nd St | July | [17 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  | 350002-583 | FY 22 |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | 598239.34 | July | [17 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall |  | 350002-582 | FY 22 |  |  |  | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | 183786.63 | July | [17 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall |  | 350002-583 | FY 22 |  |  |  | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | 68387.89 | July | [16 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  | 350002-583 | FY 22 |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | See S 32nd St | July | [17 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall |  | 350002-583 | FY 22 |  |  |  | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | See S 32nd St | July | [17 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | See S 32nd St | July | [17 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  | 350002-583 | FY 22 |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | See S 32nd St | July | [17 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  | 350002-626 | FY 23 |  |  |  | Carter St | Portland Ave | Northwestern Pkwy | 25 | 5 | Local | [13 empty] | 3 |  |  |  | 38924.712 |  |  | Public Works | [15 empty] | Concrete Roadway, look to Overlay if possible. Otehrwise select panel replacement | 600.69 | 36 | 21624.84 | 0.35095
| Hall |  | 388368-9 | FY 22 |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  | FY 23 |  |  |  | Cedar Grove Ter | Northwestern Pkwy | Dead End | 20.0333 | 5 | Local | [13 empty] | 6 |  |  |  | 75938.472 |  |  | Public Works | [16 empty] | 781.26 | 54 | 42188.04 | 0.68468
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | S 45th St | 25.4062 | 5 | Local | [13 empty] | 6 |  |  |  | 16091.928 |  |  | Public Works | [16 empty] | 599.49 | 15 | 8939.96 | 0.14509
| Hall |  | 350002-626 | FY 23 |  |  |  | Griffiths Ave | N 22nd St | Bank St | 18.0951 | 5 | Local | [13 empty] | 25 |  |  |  | 107352.144 |  |  | Public Works | [16 empty] | 1754.12 | 34 | 59640.08 | 0.96791
| Hall |  |  | FY 23 |  |  |  | Lytle St | N 20th St | N 22nd St | 23 | 5 | Local | [13 empty] | 0 |  |  |  | 46251 |  |  | Public Works | [16 empty] | 713.75 | 36 | 25695 | 0.41701
| Hall |  | 350002-626 | FY 23 |  |  |  | N 20th St | Rowan St | Bank St | 15.4973 | 5 | Local | [13 empty] | 28 |  |  |  | 98944.488 |  |  | Public Works | [16 empty] | 1616.74 | 34 | 54969.16 | 0.8921
| Hall |  | 350002-626 | FY 23 |  |  |  | N 20th St | Bank St | Portland Ave | 14.9549 | 5 | Local | [13 empty] | See N 20th |  |  |  | 43443.432 |  |  | Public Works | [16 empty] | 709.86 | 34 | 24135.24 | 0.39169
| Hall |  | 350002-626 | FY 23 |  |  |  | N 21st St | Bank St | Rowan St | 18.5511 | 5 | Local | [13 empty] | 30 |  |  |  | 80968.464 |  |  | Public Works | [16 empty] | 1874.27 | 24 | 44982.48 | 0.73003
| Hall |  | 350002-626 | FY 23 |  |  |  | N 23rd St | Portland Ave | Northwestern Pkwy | 20.4356 | 5 | Local | [13 empty] | 10 |  |  |  | 56586.996 |  |  | Public Works | [16 empty] | 911.12 | 34.5 | 31437.22 | 0.5102
| Hall |  | 350002-626 | FY 23 |  |  |  | N 25th St | Portland Ave | Northwestern Pkwy | 27.0214 | 5 | Local | [13 empty] | 15 |  |  |  | 64663.6283 |  |  | Public Works | [15 empty] | Brick paver ramp to replace with concrete. Need to check if histroic preservation dist. | 1025.8987 | 35 | 35924.2379 | 0.58302
| Hall |  | 350002-626 | FY 23 |  |  |  | N 27th St | Portland Ave | Northwestern Pkwy | 17.9248 | 5 | Local | [13 empty] | 11 |  |  |  | 64603.008 |  |  | Public Works | [16 empty] | 996.96 | 36 | 35890.56 | 0.58247
| Hall |  |  | FY 23 |  |  |  | N 33rd St | Northwestern Pkwy | Pflanz St | 20 | 5 | Local | [13 empty] | 8 |  |  |  | 89696.592 |  |  | Public Works | [18 empty] | 49831 | 0.80871
| Hall |  |  | FY 23 |  |  |  | N 34th St | Northwestern Pkwy | Pflanz Ave | 35 | 5 | Local | [13 empty] | 5 |  |  |  | 17153.856 |  |  | Public Works | [16 empty] | 264.72 | 36 | 9529.92 | 0.15466
| Hall |  |  | FY 23 |  |  |  | N 35th St | Northwestern Pkwy | Parker Ave | 17.674 | 5 | Local | [13 empty] | 10 |  |  |  | 159050.88 |  |  | Public Works | [16 empty] | 2209.04 | 40 | 88361.6 | 1.434
| Hall |  |  | FY 23 |  |  |  | N 36th St | Northwestern Pkwy | Pflanz Ave | 38 | 5 | Local | [13 empty] | 4 |  |  |  | 11527.488 |  |  | Public Works | [16 empty] | 266.84 | 24 | 6404.16 | 0.10393
| Hall |  |  | FY 23 |  |  |  | S 45th St | W Broadway | Garland Ave | 32.9625 | 5 | Local | [13 empty] | 7 |  |  |  | 58936.86 |  |  | Public Works | [16 empty] | 1117.9 | 29.3333 | 32742.7 | 0.53139
| Hall |  |  | FY 23 |  |  |  | Short St | Griffiths Ave | Owen St | 16 | 5 | Local | [13 empty] | 5 |  |  |  | 16947.684 |  |  | Public Works | [16 empty] | 362.13 | 26 | 9415.38 | 0.1528
| Hall |  | 350002-588 | FY 22 |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | see S Floyd | July | [17 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  | 350002-588 | FY 22 |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | 222661.02 | July | [17 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  | 350002-579 | FY 22 |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | 94995.62 | July | [17 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  | 350002-587 | FY 22 |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | 186252.09 | July | [17 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-606 | FY 23 |  |  |  | Dixie Hwy | Hale Ave | W Burnett Ave | 55.4031 | 6 | Min Art | [13 empty] | 29 |  |  |  | 236607 | 72451.89 | September | Public Works | [16 empty] | 3120.29 | 35.5455 | 112669.83 | 1.8285
| Hall |  | 350002-615 | FY 22 |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 |  | September | [17 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  | FY 23 |  |  |  | Colorado Ave | Central Ave | Algonquin Pkwy | 20.2796 | 6 | Local | [13 empty] | 14 |  |  |  | 105470.388 |  |  | Public Works | [16 empty] | 2259.89 | 27.2 | 58594.66 | 0.95094
| Hall |  |  | FY 23 |  |  |  | Lillian Ave | 7th Street Rd | Colorado Ave | 31.3741 | 6 | Local | [13 empty] | 11 |  |  |  | 92745.72 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 2015.69 | 25.3333 | 51525.4 | 0.83621
| Hall |  |  | FY 23 |  |  |  | Lincoln Ave | 7th Street Rd | Taylor Blvd | 24.899 | 6 | Local | [13 empty] | 18 |  |  |  | 183027.456 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 3815.61 | 26.7143 | 101681.92 | 1.6502
| Hall |  |  | FY 23 |  |  |  | Lindbergh Dr | Algonquin Pkwy | Dead End (Homeview) | 45.5354 | 6 | Local | [13 empty] | 35 |  |  |  | 166826.304 |  |  | Public Works | [15 empty] | Some ramps may be technically infeasible. Dead end at homeview is strange | 3138.68 | 29 | 94313.98 | 1.5306
| Hall |  |  | FY 23 |  |  |  | S 16th St | W Breckinridge St | W Oak St | 29.2853 | 6 | Local | [13 empty] | 47 |  |  |  | 150568.704 |  |  | Public Works | [16 empty] | 2614.04 | 32 | 83649.28 | 1.3576
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Kentucky St | W Oak St | 28.3593 | 6 | Local | [13 empty] | 37 |  |  |  | 104515.344 |  |  | Public Works | [16 empty] | 1746.26 | 33.2 | 58064.08 | 0.94233
| Hall |  | 350002-627 | FY 23 |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | 52685.98 | [17 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  | FY 23 |  |  |  | Tennessee Ave | 7th Street Rd | Lindbergh Dr | 33 | 6 | Local | [13 empty] | 4 |  |  |  | 62034.264 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1380.5 | 25 | 34463.48 | 0.55931
| Hall |  |  | FY 23 |  |  |  | W Oak St | Dixie Hwy | S 26th St | 20.437 | 6 | Min Art | [13 empty] | 22 |  |  |  | 224089 |  |  | Public Works | [16 empty] | 2754.22 | 38.8 | 106709.2 | 1.7318
|  |  |  | FY 23 |  |  |  | W Oak St | S 13th St | S 15th St |  | 6 | Min Art | [17 empty] | 100000 | [18 empty] | Will likely need specialty equipment
| Hall |  |  | FY 23 |  |  |  | W St Catherine St | S 15th St | S 16th St | 21 | 6 | Local | [13 empty] | 4 |  |  |  | 40212.18 |  |  | Public Works | [16 empty] | 744.67 | 30 | 22340.1 | 0.36256
| Hall |  |  | FY 23 |  |  |  | Weller Ave | 7th Street Rd | Dead End | 28.6273 | 6 | Local | [13 empty] | 4 |  |  |  | 64972.44 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1388.3 | 26 | 36095.8 | 0.5858
| Hall |  |  | FY 23 |  |  |  | Wurtele Ave | 7th Street Rd | Colorado Ave | 32.2659 | 6 | Local | [13 empty] | 3 |  |  |  | 109582.272 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1902.47 | 32 | 60879.04 | 0.98801
| Hall |  |  | FY 23 |  |  |  | Chippewa Rd | Elfin Ave | Napanee Rd | 42 | 7 | Local | [13 empty] | 0 |  |  |  | 12590.424 |  |  | Public Works | [15 empty] | Big base failure north of Elfin need to complete with this work. | 317.94 | 22 | 6994.68 | 0.11352
| Hall |  |  | FY 23 |  |  |  | Napanee Rd | Chippewa Rd | St Matthews Ave | 19 | 7 | Local | [13 empty] | 0 |  |  |  | 25394.256 |  |  | Public Works | [16 empty] | 587.83 | 24 | 14107.92 | 0.22896
| Hall |  | 350002-584 | FY 22 |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | See Alta Vista Rd | August | [16 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  | 350002-584 | FY 22 |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | 121935.01 | August | [17 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Louisville Paving |  | 388368-7 | FY 22 |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [13 empty] | 0 |  |  | 0 | 44635.35 | 31523.81 | August | [17 empty] | 800 | 36 | 28797 | 0.46735
| LP |  | 366368-17 | FY 23 |  |  |  | Trevilian Way | Newburg Rd | Dundee Rd | 68.6911 | 8 | Min Art | [13 empty] | 0 |  |  | 0 | 192812 | 136694.4 | August | Google Funds | [16 empty] | 3604.72 | 26 | 91815.32 | 1.4901
| Hall |  |  | FY 23 |  |  |  | Alta Ave | Bardstown Rd | Cherokee Rd | 25.0798 | 8 | Local | [13 empty] | 29 |  |  |  | 169299.18 |  |  | Public Works | [16 empty] | 3135.17 | 30 | 94055.1 | 1.5264
| Hall |  |  | FY 23 |  |  |  | Bonnycastle Ave | Bardstown Rd | Cherokee Rd | 37.5047 | 8 | Local | [13 empty] | 29 |  |  |  | 149154.516 |  |  | Public Works | [16 empty] | 2858.8 | 29 | 82863.62 | 1.3448
| Hall |  |  | FY 23 |  |  |  | Edward St | Morton Ave | Rufer Ave | 18.7033 | 8 | Local | [13 empty] | 39 |  |  |  | 116619.264 |  |  | Public Works | [16 empty] | 1799.68 | 36 | 64788.48 | 1.0515
| Hall |  |  | FY 23 |  |  |  | Grasmere Ter | Grasmere Dr | Dead End | 10.6363 | 8 | Local | [13 empty] | 0 |  |  |  | 6760.584 |  |  | Public Works | [15 empty] | Small alley, could be a nightmare | 312.99 | 12 | 3755.88 | 0.060955
| Hall |  |  | FY 23 |  |  |  | Parsons Pl | Alta Ave | Bonnycastle Ave | 30 | 8 | Local | [13 empty] | 0 |  |  |  | 14329.548 |  |  | Public Works | [16 empty] | 442.27 | 18 | 7960.86 | 0.1292
| Hall |  |  | FY 23 |  |  |  | Ray Ave | Grinstead Dr | Longest Ave | 22.8729 | 8 | Local | [13 empty] | 7 |  |  |  | 71597.52 |  |  | Public Works | [16 empty] | 1325.88 | 30 | 39776.4 | 0.64554
| Hall |  |  | FY 23 |  |  |  | Ridgeway Ave | Willow Ave | Dead End | 10 | 8 | Local | [13 empty] | 2 |  |  |  | 44804.52 |  |  | Public Works | [15 empty] | Looks like an alley | 1244.57 | 20 | 24891.4 | 0.40397
| Hall |  |  | FY 23 |  |  |  | Spring Dr | Speed Ave | Woodford Pl | 18.0204 | 8 | Local | [13 empty] | 2 |  |  |  | 111570.696 |  |  | Public Works | [16 empty] | 1721.77 | 36 | 61983.72 | 1.0059
| Hall |  |  | FY 23 |  |  |  | Avon Ct | Kennedy Ave | Kennedy Ct | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 6826.644 |  |  | Public Works | [16 empty] | 172.39 | 22 | 3792.58 | 0.06155
| Hall |  | 350002-612 | FY 23 |  |  |  | Bauer Ave | Lexington Rd | Wilmington Ave | 21 | 9 | Local | [13 empty] | 0 |  |  |  | 20857.32 | 29889.06 |  | Public Works | [16 empty] | 526.7 | 22 | 11587.4 | 0.18805
| Hall |  |  | FY 23 |  |  |  | Chamberry Cir (All) | Old Cannons Ln | Old Cannons Ln | 28.3517 | 9 | Local | [13 empty] | 0 |  |  |  | 86199.228 |  |  | Public Works | [16 empty] | 1958.4 | 25 | 47888.46 | 0.77719
| Hall |  |  | FY 23 |  |  |  | Circle Hill Rd | Rock Creek Dr | Old Cannons Ln | 28.8803 | 9 | Local | [13 empty] | 0 |  |  |  | 120190.7284 |  |  | Public Works | [16 empty] | 2587.9703 | 23 | 60702.3881 | 0.98515
| Hall |  |  | FY 23 |  |  |  | Crescent Ct | Frankfort Ave | Grinstead Dr | 27.5652 | 9 | Local | [13 empty] | 2 |  |  |  | 49072.7871 |  |  | Public Works | [15 empty] | Base failures? | 1239.2118 | 22 | 27262.6595 | 0.44245
| Hall |  | 35002-616 | FY 22 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  |  | FY 23 |  |  |  | Homestead Blvd | Rock Creek Dr | Circle Hill Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 48453.688 |  |  | Public Works | [16 empty] | 1121.6131 | 24 | 26918.7155 | 0.43687
| Hall |  |  | FY 23 |  |  |  | Huntington Rd | Rock Creek Dr | Old Cannons Ln | 18.7864 | 9 | Local | [13 empty] | 0 |  |  |  | 67794.408 |  |  | Public Works | [16 empty] | 1711.98 | 22 | 37663.56 | 0.61125
| Hall |  |  | FY 23 |  |  |  | Kennedy Ave | Frankfort Ave | Grinstead Dr | 31.0011 | 9 | Local | [13 empty] | 2 |  |  |  | 45585.036 |  |  | Public Works | [16 empty] | 1384.26 | 18 | 25325.02 | 0.411
| Hall |  |  | FY 23 |  |  |  | Kennedy Ct | Kennedy Ave | Dead End | 41.1453 | 9 | Local | [13 empty] | 2 |  |  |  | 20407.788 |  |  | Public Works | [16 empty] | 586.15 | 20 | 11337.66 | 0.184
| Hall |  |  | FY 23 |  |  |  | Lake Ave | Mellwood Ave | Dead End | 19 | 9 | Local | [13 empty] | 1 |  |  |  | 82170.72 |  |  | Public Works | [16 empty] | 1984.8 | 23 | 45650.4 | 0.74087
| Hall |  | 350002-612 | FY 23 |  |  |  | Macon Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 20824.128 | See Bauer Ave |  | Public Works | [16 empty] | 482.04 | 24 | 11568.96 | 0.18775
| Hall |  |  | FY 23 |  |  |  | Meadowlark Ave | Seminary Rd | Stilz Ave | 15.5126 | 9 | Local | [13 empty] | 11 |  |  |  | 24502.176 |  |  | Public Works | [16 empty] | 850.77 | 16 | 13612.32 | 0.22092
| Hall |  |  | FY 23 |  |  |  | Mount Holly Ave | Brownsboro Rd | Lindsay Ave | 19.4575 | 9 | Local | [13 empty] | 2 |  |  |  | 49280.832 |  |  | Public Works | [15 empty] | Base fialure by Lindsay | 1215.32 | 24 | 27378.24 | 0.44432
| Hall |  |  | FY 23 |  |  |  | Pleasantview Ave | Grinstead Dr | Lexington Rd | 18.075 | 9 | Local | [13 empty] | 10 |  |  |  | 98573.688 |  |  | Public Works | [16 empty] | 1878.18 | 29 | 54763.16 | 0.88876
| Hall |  |  | FY 23 |  |  |  | Rock Creek Dr | Cannons Ln | Pee Wee Reese Rd | 32.2104 | 9 | Local | [13 empty] | 0 |  |  |  | 114983.244 |  |  | Public Works | [15 empty] | Base failures | 3260.83 | 19.6 | 63879.58 | 1.0367
| Hall |  | 350002-612 | FY 23 |  |  |  | S Hubbards Ln | Bowling Blvd | Shelbyville Rd | 27 | 9 | Min Art | [17 empty] | 253130 |  |  | Public Works | [18 empty] | 120538 | 1.9562
| Hall |  |  | FY 23 |  |  |  | Springdale Rd | Grinstead Dr | Pleasantview Ave | 20 | 9 | Local | [13 empty] | 3 |  |  |  | 29623.104 |  |  | Public Works | [16 empty] | 685.72 | 24 | 16457.28 | 0.26709
| Hall |  |  | FY 23 |  |  |  | St Matthews Ave | Napanee Rd | Ormond Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 14326.884 |  |  | Public Works | [16 empty] | 361.79 | 22 | 7959.38 | 0.12917
| Hall |  |  | FY 23 |  |  |  | Stilz Ave | Lexington Rd | Frankfort Ave | 53.6459 | 9 | Pri Coll | [13 empty] | 13 |  |  |  | 114290 |  |  | Public Works | [16 empty] | 2574.69 | 34.3333 | 87915.6 | 1.4268
| Hall |  | 350002-612 | FY 23 |  |  |  | Wallace Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 18104.112 | See Bauer Ave |  | Public Works | [16 empty] | 386.84 | 26 | 10057.84 | 0.16323
| Hall |  | 350002-612 | FY 23 |  |  |  | Wendover Ave | Lexington Rd | Wilmington Ave | 26 | 9 | Local | [13 empty] | 0 |  |  |  | 17264.808 | See Bauer Ave |  | Public Works | [16 empty] | 435.98 | 22 | 9591.56 | 0.15566
| Hall |  | 350002-612 | FY 23 |  |  |  | Willis Ave | Wiltshire Ave | Breckenridge Ln | 76 | 9 | Collector | [17 empty] | 14626.8 | See Bauer Ave | [20 empty] | 8126 | 0.13188
| Hall |  | 350002-612 | FY 23 |  |  |  | Wilmington Ave | Wallace Ave | Frankfort Ave | 28.1016 | 9 | Local | [13 empty] | 3 |  |  |  | 24518.88 | See Bauer Ave |  | Public Works | [16 empty] | 536.86 | 25 | 13621.6 | 0.22107
| Hall |  | 350002-612 | FY 23 |  |  |  | Wiltshire Ave | Wilmington Ave | Willis Ave | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 22864.644 | See Bauer Ave |  | Public Works | [16 empty] | 577.39 | 22 | 12702.58 | 0.20615
| Hall |  | 350002-611 | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Dead End |  | 9 | Local | [17 empty] | 23706.8246 | See Winchester Rd | [20 empty] | 13170 | 0.21374
| Hall |  | 350002-611 | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Thompson Ave | 44.4846 | 9 | Pri Coll | [13 empty] | 6 |  |  |  | 118575 | 13643.27 |  | Public Works | [16 empty] | 2147.8793 | 29.3333 | 60807.4923 | 0.98685
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Ct | Audubon Ridge Dr | Dead End | 19.8104 | 10 | Local | [13 empty] | 0 |  |  |  | 33929.676 |  |  | Public Works | [16 empty] | 856.81 | 22 | 18849.82 | 0.30592
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Dr | Illinois Ave | Dead End | 48.9775 | 10 | Local | [13 empty] | 5 |  |  |  | 44784.36 |  |  | Public Works | [16 empty] | 1027.09 | 31 | 24880.2 | 0.40378
| Hall |  |  | FY 23 |  |  |  | Ellison Ave | Barret Ave | Spratt Ave | 35.6822 | 10 | Local | [13 empty] | 15 |  |  |  | 166187.376 |  |  | Public Works | [16 empty] | 2429.64 | 38 | 92326.32 | 1.4984
| Hall |  |  | FY 23 |  |  |  | Grantswood Ct | Audubon Ridge Ct | Dead End |  | 10 | Local | [13 empty] | 2 |  |  |  | 16264.8 |  |  | Public Works | [16 empty] | 502 | 18 | 9036 | 0.14665
| Hall |  |  | FY 23 |  |  |  | Reutlinger Ave | E Oak St | Ellison Ave | 23.3308 | 10 | Local | [13 empty] | 6 |  |  |  | 67047.624 |  |  | Public Works | [16 empty] | 1330.31 | 28 | 37248.68 | 0.60451
| LP |  | 366368-16 | FY 23 |  |  |  | Robards Ln | Gardiner Ln | Bishop Ln | 42.3597 | 10 | Pri Coll | [13 empty] | 2 |  |  |  | 147273 |  |  | Public Works | [16 empty] | 3717.62 | 20 | 75524.68 | 1.2257
| Hall |  |  | FY 23 |  |  |  | Spratt St | Goss Ave | St Michael St | 35.9444 | 10 | Local | [13 empty] | 16 |  |  |  | 74506.176 |  |  | Public Works | [16 empty] | 1171.43 | 35.3333 | 41392.32 | 0.67176
| Hall |  |  | FY 23 |  |  |  | St Michael St | Ellison Ave | Dead End | 41 | 10 | Local | [13 empty] | 0 |  |  |  | 35897.4 |  |  | Public Works | [16 empty] | 712.25 | 28 | 19943 | 0.32366
| LP |  | 388368-27 | FY 23 |  |  |  | E Rehl Ct | Rehl Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | 0 | 60541 | See Rehl Rd | August | Public Works | [18 empty] | 33634 | 0.54585
| Hall |  | 350002-631 | FY 23 |  |  |  | Bircham Rd | Shelbyville Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 110000 |  | September | Council | 8102-410-8210-148628-899998 | 110000 | [16 empty] | 66212 | 1.0746
| Hall |  | 350002-631 | FY 23 |  |  |  | Burleigh Ct | Burcham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 31000 |  | September | Council | 8102-410-8210-148628-899998 | 31000 | [16 empty] | 17407 | 0.2825
| Hall |  | 350002-631 | FY 23 |  |  |  | Burleigh Pl | Burleigh Ct | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 8500 |  | September | Council | 8102-410-8210-148628-899998 | 8500 | [16 empty] | 4726 | 0.076699
| LP |  | 350002-631 | FY 23 |  |  |  | Chenoweth Run Rd | Blankenbaker Pkwy | Taylorsville Rd | 36.517 | 11 | Pri Coll | [13 empty] | 0 |  |  |  | 196876 |  | September | Public Works | [16 empty] | 4135.4154 | 24 | 100961.8158 | 1.6385
| Hall |  | 350002-631 | FY 23 |  |  |  | Dorshire Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 20000 |  | September | Council | 8102-410-8210-148628-899998 | 20000 | [16 empty] | 11350 | 0.1842
| Hall |  | 350002-613 | FY 23 |  |  |  | Landis Lakes Dr | S English Station Rd | Landis Lakes Ct | 32.9592 | 11 | Local | [13 empty] | 10 |  |  |  | 66457.368 | 25967.35 | September | Public Works | [16 empty] | 1682.32 | 25.3333 | 41128.06 | 0.66747
| Hall |  | 350002-631 | FY 23 |  |  |  | Willoughby Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  |  | 26000 |  | September | Council | 8102-410-8210-148628-899998 | 26000 | [16 empty] | 14983 | 0.24316
| Hall |  |  | FY 23 |  |  |  | Constant Comment Pl | From J-Town R/W north of Electron | Dead End (south) | 22.3743 | 11 | Local | [13 empty] | 1 |  |  |  | 76709.25 |  |  | Public Works | [16 empty] | 987 | 35 | 42616.25 | 0.69162
| Hall |  |  | FY 23 |  |  |  | Electron Dr | Blankenbaker Pkwy | Constant Comment Pl | 19 | 11 | Local | [13 empty] | 1 |  |  |  | 51249.132 |  |  | Public Works | [16 empty] | 862.78 | 33 | 28471.74 | 0.46207
| Hall |  |  | FY 23 |  |  |  | Hurstbourne Park Blvd | Hurstbourne Pkwy | Dead End |  | 11 | Local | [17 empty] | 48685 |  |  | Public Works | [18 empty] | 27047 | 0.43895
| Hall |  |  | FY 23 |  |  |  | Summerfield Dr | Six Mile Ln | Weather Way |  | 11 | Local | [13 empty] | 17 |  |  |  | 75000 |  |  | Council | 8102-410-8210-148628-899998 | 28500 |  | 8150-410-8210-148628-899998 | 44500 |  | 8133-410-8210-148628-899998 | 2000 | [10 empty] | 112833 | 1.8312
| Hall |  | 350002-601 | FY 23 |  |  |  | Lynn Myra Ct | Vista John Dr | Dead End | 40 | 12 | Local | [13 empty] | 0 |  |  |  | 9422.424 | See Vista John Dr | September | Public Works | [16 empty] | 237.94 | 22 | 5234.68 | 0.084954
| Hall |  | 350002-601 | FY 23 |  |  |  | Stephan Rd | Vista John Dr | Oswego Cir | 25.3696 | 12 | Local | [13 empty] | 0 |  |  |  | 37562.1531 | See Vista John Dr | September | Public Works | [16 empty] | 1043.3931 | 20 | 20867.8628 | 0.33867
| Hall |  | 350002-601 | FY 23 |  |  |  | Terudon Dr | Manslick Rd | Vista John Dr | 28 | 12 | Local | [13 empty] | 0 |  |  |  | 31798.656 | See Vista John Dr | September | Public Works | [16 empty] | 736.08 | 24 | 17665.92 | 0.2867
| Hall |  | 350002-601 | FY 23 |  |  |  | Vista John Dr | Manslick Rd | Stephan Dr | 36.6481 | 12 | Local | [13 empty] | 0 |  |  |  | 59112.684 | 2151.17 | September | Public Works | [16 empty] | 1411.04 | 23.3333 | 32840.38 | 0.53297
| LP |  |  | FY 23 |  |  |  | Blanton Ln | St Andrews Church Rd | Dixie Hwy | 35.5419 | 12 | Pri Coll | [13 empty] | 0 |  |  |  | 226546 |  |  | Public Works | [16 empty] | 5256.12 | 22.5714 | 116177.36 | 1.8855
| Hall |  |  | FY 23 |  |  |  | De Mel Ave | Manslick Rd | Dead End | 23.8808 | 12 | Local | [13 empty] | 0 |  |  |  | 73224.6988 |  |  | Public Works | [16 empty] | 1904.3118 | 21.6667 | 40680.3882 | 0.66021
| Hall |  |  | FY 23 |  |  |  | Frank Lee Ave | Terry Rd | Dead End | 41.2207 | 12 | Local | [13 empty] | 5 |  |  |  | 29502 |  |  | Public Works | [16 empty] | 819.5 | 20 | 16390 | 0.266
| Hall |  | 350002-470 | FY 22 |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-600 | FY 23 |  |  |  | Maryview Dr | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 79947 |  |  | Pw/Council | 8676-410-8106-048212-822702 | 0.55 |  | 8102-410-8105-148230-822702 | 3441.57 |  | 8144-410-8205-148230-822702 | 19000 |  | 8642-410-8105-148230-822702 | 2389.77 | [7 empty] | 45684
| Hall |  | 350002-518 | FY 22 |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [18 empty] | LWC Project | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-614 | FY 23 |  |  |  | Mount Marcy Rd | Mount Holyoke Dr | Alps Rd | 25 | 12 | Local | [13 empty] | 6 |  |  |  | 57474.144 | 14650.75 |  | Public Works | [16 empty] | 1330.42 | 24 | 31930.08 | 0.5182
| Hall |  | 350002-600 | FY 23 |  |  |  | Nancy Ave | Dawn Dr | Dead End | 22 | 12 | Local | [13 empty] | 0 |  |  |  | 34899.984 |  |  | Public Works | [16 empty] | 807.87 | 24 | 19388.88 | 0.31466
| Hall |  | 350002-600 | FY 23 |  |  |  | Princewood Pl | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 18314 |  |  | PW/Council | See Maryview | [17 empty] | 10465 | 0.16984
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 9956.96 | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 581 | 32 | 18592 | 0.30173
| Hall |  |  | FY 23 |  |  |  | Wade Lee Ct | Wilke Farm Ave | Dead End | 37 | 12 | Local | [13 empty] | 0 |  |  |  | 7507.08 |  |  | Public Works | [16 empty] | 208.53 | 20 | 4170.6 | 0.067685
| Hall |  |  | FY 23 |  |  |  | Wilke Farm Ave | Frank Lee Ave | Ree Dr | 48.9395 | 12 | Local | [13 empty] | 5 |  |  |  | 50846.004 |  |  | Public Works | [16 empty] | 1283.99 | 22 | 28247.78 | 0.45844
| Hall |  | 350002-592 | FY 23 |  |  |  | Clay Ave | Minor Ln | Preston Hwy | 25.2005 | 13 | Local | [13 empty] | 0 |  |  |  | 102532.608 |  |  | Public Works | [16 empty] | 3415.39 | 16.8 | 56962.56 | 0.92445
|  |  |  | FY 22 |  |  |  | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
| Hall |  | 350002-560 | FY 22 |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| LP |  |  | FY 23 |  |  |  | Jefferson Hill Rd | Keys Ferry Rd | Snawder Ln | 37.0674 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 444131 |  |  | Public Works | [15 empty] | LWC has a project to complete on this roadway, to be complete in 2024. | 12300.93 | 18.6667 | 227759.57 | 3.6963
| LP |  | 388368-34 | FY 23 |  |  |  | Joyner Hill Rd | Lonesome Hollow Rd | Dead End | 33 | 13 | Local | [13 empty] | 0 |  |  |  | 22761.882 |  |  | Public Works | [16 empty] | 1149.59 | 11 | 12645.49 | 0.20523
| LP |  | 388368-34 | FY 23 |  |  |  | Lonesome Hollow Rd | Blevins Gap Rd | Dead End | 23.6259 | 13 | Local | [13 empty] | 0 |  |  |  | 93498.0588 |  |  | Public Works | [16 empty] | 2990.1966 | 18 | 51943.366 | 0.843
| LP |  | 388368-34 | FY 23 |  |  |  | Lonesome Hollow Rd | Jefferson Hill Rd | Dead End | 37 | 13 | Local | [13 empty] | 0 |  |  |  | 16334.784 |  |  | Public Works | [16 empty] | 756.24 | 12 | 9074.88 | 0.14728
| Hall |  | 350002-592 | FY 23 |  |  |  | Meadow Hill Rd | Minyard Dr | Dead End | 9 | 13 | Local | [13 empty] | 2 |  |  |  | 8903.2847 |  |  | Public Works | [15 empty] | Metro ROW is small, only 4 houses, rest private | 206.0946 | 24 | 4946.2693 | 0.080274
| Hall |  | 350002-592 | FY 23 |  |  |  | Minyard Dr | Clay Ave | Minor Ln | 28.853 | 13 | Local | [13 empty] | 0 |  |  |  | 91895.328 |  |  | Public Works | [16 empty] | 1930.73 | 26.25 | 51052.96 | 0.82855
| LP |  | 388368-35 | FY 23 |  |  |  | Snawder Ln | Jefferson Hill Rd | Dead End | 21 | 13 | Local | [13 empty] | 0 |  |  |  | 22803.48 |  |  | Public Works | [16 empty] | 1266.86 | 10 | 12668.6 | 0.2056
| Hall |  | 350002-592 | FY 23 |  |  |  | Sunset Dr | Minor Ln | Clay Ave | 39 | 13 | Local | [13 empty] | 0 |  |  |  | 36200.52 |  |  | Public Works | [16 empty] | 1117.3 | 18 | 20111.4 | 0.32639
| LP |  | 388368-34 | FY 23 |  |  |  | Tidwell Rd | Lonesome Hollow Rd | Dead End | 35 | 13 | Local | [13 empty] | 0 |  |  |  | 16525.8 |  |  | Public Works | [16 empty] | 765 | 12 | 9181 | 0.149
| LP |  | 388368-35 | FY 23 |  |  |  | Top Hill Rd | Snawder Ln | Mitchell Hill Rd | 45.371 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 377132 |  |  | Public Works | [16 empty] | 9913.74 | 19 | 193400.8 | 3.1387
| Hall |  | 350002-552 | FY 22 |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| Hall |  | 350002-599 | FY 23 |  |  |  | Chase Rd | W Pages Ln | Stephan Dr | 43 | 14 | Local | [13 empty] | 2 |  |  |  | 41561.28 | See Stephan Dr |  | Public Works | [16 empty] | 1154.48 | 20 | 23089.6 | 0.37472
| Hall |  | 350002-594 | FY 23 |  |  |  | Dixie Garden Dr | Dixie Hwy | Blaze Way | 51.9782 | 14 | Local | [13 empty] | 4 |  |  |  | 123696.396 | 32366.42 |  | Public Works | [16 empty] | 2734.59 | 27.3333 | 68720.22 | 1.1153
| Hall |  | 350002-594 | FY 23 |  |  |  | Fashion Way | Bethany Ln | Nocturne Dr | 17.6755 | 14 | Local | [13 empty] | 11 |  |  |  | 68407.524 | See dixie Garden Dr |  | Public Works | [16 empty] | 1659.78 | 22.8 | 38004.18 | 0.61677
| Hall |  | 350002-598 | FY 23 |  |  |  | Johnsontown Rd | Dixie Hwy | Trade Port Dr | 47.0122 | 14 | Min Art | [13 empty] | 22 |  |  |  | 568391 |  |  | Public Works | [15 empty] | Applied for rubber aspahlt grant on this roadway | 7412.9412 | 36.1429 | 270662.5039 | 4.3926
| Hall |  | 350002-599 | FY 23 |  |  |  | Mark Dr | Vicki Ln | Robbins Rd | 21 | 14 | Local | [13 empty] | 0 |  |  |  | 17582.832 | See Stephan Dr |  | Public Works | [16 empty] | 407.01 | 24 | 9768.24 | 0.15853
| LP |  | 388368-36 | FY 23 |  |  |  | Medora Rd | Blevins Gap Rd | Pendleton Rd | 30 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 201498 |  |  | Public Works | [16 empty] | 5166.62 | 20 | 103332.4 | 1.677
| Hall |  | 350002-599 | FY 23 |  |  |  | Minette Ct | Stephan Dr | public dead end | 13 | 14 | Local | [13 empty] | 0 |  |  |  | 12123.108 | See Stephan Dr |  | Public Works | [15 empty] | Likely has base failures, ROW ends half way and turns private | 374.17 | 18 | 6735.06 | 0.1093
| Hall |  | 350002-594 | FY 23 |  |  |  | Nocturne Dr | Fashion Way | Blaze Way | 59 | 14 | Local | [13 empty] | 4 |  |  |  | 50247.216 | See dixie Garden Dr |  | Public Works | [16 empty] | 1163.13 | 24 | 27915.12 | 0.45304
| LP |  | 388368-36 | FY 23 |  |  |  | Pendleton Rd | Deixie Hwy | County Line |  | 14 | Collector | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works
| Hall |  | 350002-599 | FY 23 |  |  |  | Sally Dr | W Pages Ln | Stephan Dr | 36 | 14 | Local | [13 empty] | 2 |  |  |  | 46032.84 | See Stephan Dr |  | Public Works | [16 empty] | 1217.8 | 21 | 25573.8 | 0.41504
| LP |  | 388368-37 | FY 23 |  |  |  | Schooler Ln | Stonestreet Rd | Dead End | 17 | 14 | Local | [13 empty] | 0 |  |  |  | 25697 |  |  | Public Works | [16 empty] | 1190 | 12 | 14276 | 0.23169
| Hall |  | 350002-599 | FY 23 |  |  |  | Stephan Dr | Dixie Hwy | Vicki Ln | 29.4396 | 14 | Local | [13 empty] | 0 |  |  |  | 100447.704 | 6375.48 |  | Public Works | [16 empty] | 2218.41 | 24.8 | 55804.28 | 0.90565
| Hall |  | 350002-599 | FY 23 |  |  |  | Vicki Ln | W Pages Ln | Stephan Dr | 30.6944 | 14 | Local | [13 empty] | 2 |  |  |  | 50143.5 | See Stephan Dr |  | Public Works | [16 empty] | 1266.25 | 22 | 27857.5 | 0.4521
| LP |  | 388368-14 | FY 22 |  |  |  | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [14 empty] | 0 |  |  | 0 | 40000 | 33834.75 | August | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Locust Ave | 35 | 15 | Local | [13 empty] | 0 |  |  |  | 6959.304 |  |  | Public Works | [16 empty] | 322.19 | 12 | 3866.28 | 0.062746
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Hazelwood Ave | 35.5932 | 15 | Local | [13 empty] | 15 |  |  |  | 49112.784 |  |  | Public Works | [16 empty] | 1269.19 | 21.5 | 27284.88 | 0.44281
| Hall |  | 350002-622 | FY 23 |  |  |  | Bicknell Ave | Taylor Blvd | Parthenia Ave | 25.5625 | 15 | Local | [13 empty] | 30 |  |  |  | 146000.0686 |  |  | Public Works | [16 empty] | 2752.4779 | 28.2857 | 81111.1492 | 1.3164
| Hall |  | 350002-622 | FY 23 |  |  |  | Churchman Ave | Cayuga St | Bluegrass Ave | 22.1273 | 15 | Local | [13 empty] | 6 |  |  |  | 111811.392 |  |  | Public Works | [16 empty] | 2384.91 | 26.4 | 62117.44 | 1.0081
| Hall |  | 350002-624 | FY 23 |  |  |  | Delmar Ct | Sadie Ln | Dead End | 27 | 15 | Local | [13 empty] | 0 |  |  |  | 22756.536 | See Estate Dr |  | Public Works | [16 empty] | 574.66 | 22 | 12642.52 | 0.20518
| Hall |  | 350002-624 | FY 23 |  |  |  | Delmar Ln | Naneen Dr | Sadie Ln | 32.8435 | 15 | Local | [13 empty] | 5 |  |  |  | 56828.736 | See Estate Dr |  | Public Works | [16 empty] | 1315.48 | 24 | 31571.52 | 0.51238
| Hall |  | 350002-624 | FY 23 |  |  |  | Estate Dr | Delmar Ln | Dead End | 19.2977 | 15 | Local | [13 empty] | 11 |  |  |  | 37388.052 | 62381.13 |  | Public Works | [16 empty] | 907.18 | 22.6667 | 20771.14 | 0.3371
| Hall |  |  | FY 23 |  |  |  | Friden Way | Manslick Rd | Tracy Way | 35.1576 | 15 | Local | [13 empty] | 0 |  |  |  | 41825.052 |  |  | Public Works | [16 empty] | 1010.87 | 23 | 23236.14 | 0.3771
| Hall |  | 350002-624 | FY 23 |  |  |  | Garvey Ct | Garvey Dr | Dead End | 50 | 15 | Local | [13 empty] | 0 |  |  |  | 9785.664 | See Estate Dr |  | Public Works | [16 empty] | 226.52 | 24 | 5436.48 | 0.088229
| Hall |  | 350002-624 | FY 23 |  |  |  | Garvey Dr | Estate Dr | Dead End | 19.068 | 15 | Local | [13 empty] | 3 |  |  |  | 48994.416 | See Estate Dr |  | Public Works | [16 empty] | 1223.68 | 22.6667 | 27219.12 | 0.44174
| Hall |  | 350002-622 | FY 23 |  |  |  | Hazelwood Ave | Bicknell Ave | Bluegrass Ave | 23.8773 | 15 | Local | [13 empty] | 10 |  |  |  | 65304.3784 |  |  | Public Works | [16 empty] | 1511.6754 | 24 | 36280.2102 | 0.5888
| Hall |  |  | FY 23 |  |  |  | Joetta Ct | Rhonda Way | Dead End | 37 | 15 | Local | [13 empty] | 0 |  |  |  | 7142.256 |  |  | Public Works | [16 empty] | 165.33 | 24 | 3967.92 | 0.064396
| Hall |  | 350002-623 | FY 23 |  |  |  | Knight Rd | Tracy Way | Manslick Rd | 21 | 15 | Local | [13 empty] | 1 |  |  |  | 21031.2 |  |  | Public Works | [16 empty] | 531 | 22 | 11684 | 0.18962
| Hall |  | 350002-622 | FY 23 |  |  |  | La Salle Ave | Cayuga St | Bluegrass Ave | 34.3206 | 15 | Local | [13 empty] | 10 |  |  |  | 98051.346 |  |  | Public Works | [16 empty] | 2151.96 | 25 | 54472.97 | 0.88405
| Hall |  |  | FY 23 |  |  |  | Locust Ave | Alma Ave | Old Bluegrass Ave | 43 | 15 | Local | [13 empty] | 0 |  |  |  | 9529.56 |  |  | Public Works | [16 empty] | 529.42 | 10 | 5294.2 | 0.08592
| Hall |  |  | FY 23 |  |  |  | Old Bluegrass Ave | Churchman Ave | Dead end near Locust Ave | 63.3936 | 15 | Local | [13 empty] | 0 |  |  |  | 17200.0653 |  |  | Public Works | [15 empty] | ROW ends just past Locust | 434.3451 | 22 | 9555.5918 | 0.15508
| Hall |  | 350002-624 | FY 23 |  |  |  | Rhonda Way | Naneen Dr | Garvey Dr | 45.2191 | 15 | Local | [13 empty] | 4 |  |  |  | 57205.44 |  |  | Public Works | [16 empty] | 1324.2 | 24 | 31780.8 | 0.51577
| Hall |  |  | FY 23 |  |  |  | Rolling Ridge Rd | Friden Way | Dead End | 39 | 15 | Local | [13 empty] | 0 |  |  |  | 20820.6 |  |  | Public Works | [16 empty] | 482 | 24 | 11567 | 0.18772
| Hall |  | 350002-624 | FY 23 |  |  |  | Sadie Ln | Bryce Dr | Dead End (north) | 54.408 | 15 | Local | [13 empty] | 1 |  |  |  | 24534.756 |  |  | Public Works | [16 empty] | 878.21 | 14.6667 | 13630.42 | 0.22121
| Hall |  | 350002-623 | FY 23 |  |  |  | Tracy Way | Knight Rd | Hazelwood Ave | 62.5221 | 15 | Local | [13 empty] | 1 |  |  |  | 38359.008 |  |  | Public Works | [16 empty] | 887.94 | 24 | 21310.56 | 0.34585
| LP |  | 388368-20 | FY 23 |  |  |  | Hitt Rd | Ballardsville Rd | County Line | 46 | 16 | Sec Coll | [13 empty] | 5 |  |  | 0 | 18747 | 92359.62 | August | Public Works | [14 empty] | 92359.62 |  | 4369.7222 | 21.9936 | 96106 | 1.5597
| Hall |  | 350002-619 | FY 23 |  |  |  | Barbour Manor Ct | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7000 |  |  | Council | 8150-410-8210-148628-899998 | 7000 | [16 empty] | 4681 | 0.075969
| Hall |  | 350002-619 | FY 23 |  |  |  | Barbour Manor Dr | Barbour Ln | Dead End |  | 16 | Local | [13 empty] | 6 |  |  |  | 200000 |  |  | Council | 8150-410-8210-148628-899998 | 200000 | [16 empty] | 117151 | 1.9013
| Hall |  |  | FY 23 |  |  |  | Branning Rd | Brownsboro Rd | end of Metro R/W | 15 | 16 | Local | [13 empty] | 0 |  |  |  | 27000 |  |  | Public Works | [16 empty] | 596.7397 | 18 | 15000 | 0.24344
| Hall |  | 350002-619 | FY 23 |  |  |  | Brentler Rd | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 9000 |  |  | Council | 8150-410-8210-148628-899998 | 9000 | [16 empty] | 7123 | 0.1156
| Hall |  | 350002-620 | FY 23 |  |  |  | Cronin Dr | Halifax Dr | Halifax Dr | 47.1575 | 16 | Local | [13 empty] | 8 |  |  |  | 84968.496 |  |  | Public Works | [16 empty] | 1988.68 | 23.5 | 47204.72 | 0.76609
| Hall |  | 350002-619 | FY 23 |  |  |  | Debsom Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7500 |  |  | Council | 8150-410-8210-148628-899998 | 7500 | [16 empty] | 6759 | 0.10969
| Hall |  | 350002-619 | FY 23 |  |  |  | Jenica Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 25000 |  |  | Council | 8150-410-8210-148628-899998 | 25000 | [16 empty] | 16165 | 0.26234
| Hall |  | 350002-619 | FY 23 |  |  |  | Machupe Ct | Machupe Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 4920 | 0.079847
| Hall |  | 350002-619 | FY 23 |  |  |  | Machupe Dr | Barbour Manor Dr | Machupe Ct |  | 16 | Local | [13 empty] | 3 |  |  |  | 6000 |  |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 5388 | 0.087443
| Hall |  | 350002-620 | FY 23 |  |  |  | Oak Pointe Dr (south) | Halifax Dr | Halifax Dr | 27 | 16 | Local | [13 empty] | 2 |  |  |  | 60335.712 |  |  | Public Works | [16 empty] | 1396.66 | 24 | 33519.84 | 0.544
| Hall |  |  | FY 23 |  |  |  | Spring Farm Rd | Wolf Pen Branch Rd | 4945 Spring Farm Rd | 33.8399 | 16 | Local | [13 empty] | 0 |  |  |  | 140331.8097 |  |  | Public Works | [16 empty] | 3543.7326 | 22 | 77962.1165 | 1.2653
| Hall |  |  | FY 23 |  |  |  | Tamerlane Ct | Tamerlane Rd | Dead End | 27 | 16 | Local | [13 empty] | 0 |  |  |  | 9991.8 |  |  | Public Works | [16 empty] | 278 | 20 | 5551 | 0.090088
| Hall |  |  | FY 23 |  |  |  | Tamerlane Rd | Woodside Rd | Tuckaho Rd | 32.5001 | 16 | Local | [13 empty] | 0 |  |  |  | 41516.496 |  |  | Public Works | [16 empty] | 961.03 | 24 | 23064.72 | 0.37432
| Hall |  | 350002-619 | FY 23 |  |  |  | Therina Ct | Therina Way | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 |  |  | Council | 8133-410-8210-148628-899998 | 6000 | [16 empty] | 3399 | 0.055163
| Hall |  | 350002-619 | FY 23 |  |  |  | Therina Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 3 |  |  |  | 20000 |  |  | Council | 8133-410-8210-148628-899998 | 20000 | [16 empty] | 14191 | 0.23031
| Hall |  |  | FY 23 |  |  |  | Tuckaho Rd | Tamerlane Rd | 2510 Tuckaho Rd | 38 | 16 | Local | [13 empty] | 0 |  |  |  | 15400.8644 |  |  | Public Works | [16 empty] | 388.9107 | 22 | 8556.0358 | 0.13886
| Hall |  | 350002-618 | FY 22 |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 |  | September | [16 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-618 | FY 22 |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 |  | September | [16 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-618 | FY 22 |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 |  | September | [16 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-618 | FY 22 |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 |  | September | [16 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-620 | FY 23 |  |  |  | Glen Meadow Rd | Brownsboro Glen Rd | Spring Gate Dr | 16 | 17 | Local | [13 empty] | 4 |  |  |  | 10759.716 |  |  | Public Works | [16 empty] | 271.71 | 22 | 5977.62 | 0.097012
| Hall |  |  | FY 23 |  |  |  | Murphy Ln | Halifax Dr | Ballardsville Rd | 37 | 17 | Pri Coll | [13 empty] | 0 |  |  |  | 115825 |  |  | Public Works | [16 empty] | 2969.88 | 20 | 59397.6 | 0.96397
| LP |  | 388368-19 | FY 23 |  |  |  | N English Station Rd | Aiken Rd | Old Henry Rd | 31 | 17 | Min Art | [13 empty] | 0 |  |  |  | 122122 |  |  | Public Works | [16 empty] | 2423.0596 | 24 | 58153.4298 | 0.94378
| Hall |  |  | FY 23 |  |  |  | Oakland Forest Ct | Spring Mill Rd | Dead End | 47 | 17 | Local | [13 empty] | 0 |  |  |  | 11897.28 |  |  | Public Works | [16 empty] | 275.4 | 24 | 6609.6 | 0.10727
| LP |  | 388368-23 | FY 23 |  |  |  | Old Harrods Creek Rd | LaGrange Rd | End of Metro R/W | 32.4157 | 17 | Sec Coll | [13 empty] | 0 |  |  |  | 38914 |  |  | Public Works | [16 empty] | 1085.356 | 19 | 19956.0265 | 0.32387
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Ct | Rock Bay Dr | Dead End | 27.7903 | 17 | Local | [13 empty] | 3 |  |  |  | 28799.712 |  |  | Public Works | [16 empty] | 666.66 | 24 | 15999.84 | 0.25966
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Pl | Rolling Springs Ct | Dead End | 53 | 17 | Local | [13 empty] | 0 |  |  |  | 12216.528 |  |  | Public Works | [16 empty] | 282.79 | 24 | 6786.96 | 0.11015
| Hall |  |  | FY 23 |  |  |  | Spring Forest Ct | Spring Forest Dr | Dead End | 36 | 17 | Local | [13 empty] | 0 |  |  |  | 8882.352 |  |  | Public Works | [16 empty] | 205.61 | 24 | 4934.64 | 0.080085
| Hall |  |  | FY 23 |  |  |  | Spring Forest Dr | Spring Mill Rd | Dead End | 31.2435 | 17 | Local | [13 empty] | 2 |  |  |  | 20158.848 |  |  | Public Works | [16 empty] | 466.64 | 24 | 11199.36 | 0.18176
| Hall |  |  | FY 23 |  |  |  | Spring Gate Dr | Chamberlain Ln | Stone Glen Rd | 20.3691 | 17 | Local | [13 empty] | 8 |  |  |  | 35943.264 |  |  | Public Works | [16 empty] | 832.02 | 24 | 19968.48 | 0.32407
| Hall |  |  | FY 23 |  |  |  | Spring Mill Pl | Spring Mill Rd | Dead End | 25 | 17 | Local | [13 empty] | 0 |  |  |  | 22846.32 |  |  | Public Works | [16 empty] | 528.85 | 24 | 12692.4 | 0.20599
| Hall |  |  | FY 23 |  |  |  | Spring Mill Rd | Rock Bay Dr | Rock Bay Dr | 33.8903 | 17 | Local | [13 empty] | 14 |  |  |  | 140905.008 |  |  | Public Works | [16 empty] | 3261.69 | 24 | 78280.56 | 1.2704
| Hall |  |  | FY 23 |  |  |  | Woods View Pl | Spring Mill Rd | Dead End | 21 | 17 | Local | [13 empty] | 0 |  |  |  | 31692.384 |  |  | Public Works | [16 empty] | 733.62 | 24 | 17606.88 | 0.28574
| Hall |  | 350002-559 | FY 22 |  |  |  | Dorsey Ln | N Hurstbourne | Nearest Joint |  | 18 | Pri Coll | [17 empty] | 41000 |  |  | Council | 8133-410-8210-148628-899998 | 41000
| Hall |  |  | FY 23 |  |  |  | Dorsey Way | Elsmete Cir | Dead End |  | 18 | Local | [13 empty] | 0 |  |  |  | 126000 |  |  | Council | 8133-410-8210-148628-899998 | 90000 |  | 8102-410-8210-148922-899998 | 36000 | [13 empty] | 67992 | 1.1035
| Hall |  |  | FY 23 |  |  |  | Hobbs Station Rd | Lodge Hill Rd (south) | Sable Wing Cir (south) | 34.5421 | 18 | Local | [13 empty] | 14 |  |  |  | 343037 |  |  | Public Works | [16 empty] | 4051.56 | 51.2857 | 190575.9 | 3.0929
| Hall |  |  | FY 23 |  |  |  | Talon Way | Dead End | Dead End | 30.4359 | 18 | Local | [13 empty] | 0 |  |  |  | 39874 |  |  | Public Works | [16 empty] | 1006.93 | 22 | 22152.46 | 0.35952
| Hall |  |  | FY 23 |  |  |  | UPS Dr | Whipps Mill Rd | Ormsby Station Rd | 34 | 18 | Pri Coll | [13 empty] | 2 |  |  |  | 86968 |  |  | Public Works | [16 empty] | 1238.86 | 36 | 44598.96 | 0.7238
| LP |  | 388368-26 | FY 23 |  |  |  | Aiken Rd | Bush Farm Rd | N Beckley Station Rd | 22.1639 | 19 | Sec Coll | [13 empty] | 0 |  |  | 0 | 102472 | 62992.17 | August | Public Works | [16 empty] | 2201.95 | 23.5 | 52549.75 | 0.85284
| Hall |  | 350002-559 | FY 22 |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  |  | FY 23 |  |  |  | Forest Oaks Dr | Arnold Palmer Blvd | N Beckley Station Rd | 32.0199 | 19 | Local | [13 empty] | 2 |  |  |  | 133678.548 |  |  | Public Works | [16 empty] | 3064.06 | 24 | 74265.86 | 1.2053
| Hall |  |  | FY 23 |  |  |  | Forest Trace Ct | Spring Mill Rd | Dead End | 79 | 19 | Local | [17 empty] | 7902 |  |  | Public Works | [18 empty] | 4390 | 0.071246
| Hall |  |  | FY 23 |  |  |  | Garden Hill Pl | N Beckley Station Rd | Dead End | 67 | 19 | Local | [13 empty] | 0 |  |  |  | 38556.54 |  |  | Public Works | [16 empty] | 973.65 | 22 | 21420.3 | 0.34763
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Pl | Golden Leaf Way | Dead End | 24.4599 | 19 | Local | [13 empty] | 4 |  |  |  | 37940.652 |  |  | Public Works | [16 empty] | 921.38 | 23 | 21078.14 | 0.34208
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Way (all) | Forest Oaks Dr | Golden Leaf Way | 24.4823 | 19 | Local | [13 empty] | 6 |  |  |  | 80431.938 |  |  | Public Works | [16 empty] | 1933.05 | 23 | 44684.41 | 0.72519
| Hall |  |  | FY 23 |  |  |  | Greensbrook Pl | Forest Oaks Dr | Dead End | 40 | 19 | Local | [13 empty] | 2 |  |  |  | 24575.184 |  |  | Public Works | [16 empty] | 568.87 | 24 | 13652.88 | 0.22157
| Hall |  |  | FY 23 |  |  |  | Hiawatha Ave | Heafer Rd | N English Station Rd | 26.069 | 19 | Local | [13 empty] | 5 |  |  |  | 53858.2262 |  |  | Public Works | [16 empty] | 1789.2936 | 22.25 | 29921.2368 | 0.4856
| Hall |  |  | FY 23 |  |  |  | Hines Ct | Heafer Rd | Dead End | 34 | 19 | Local | [13 empty] | 2 |  |  |  | 14106.816 |  |  | Public Works | [16 empty] | 489.82 | 16 | 7837.12 | 0.12719
| Hall |  |  | FY 23 |  |  |  | Hines Rd | Berrytown Rd | Dead End | 36.953 | 19 | Local | [13 empty] | 0 |  |  |  | 24453.3305 |  |  | Public Works | [16 empty] | 930.572 | 14 | 13585.1836 | 0.22048
| Hall |  |  | FY 23 |  |  |  | Lilly Ln | LaGrange Rd | Dead End | 40 | 19 | Local | [13 empty] | 0 |  |  |  | 48427.92 |  |  | Public Works | [16 empty] | 672.61 | 20 | 13452.2 | 0.21832
| Hall |  |  | FY 23 |  |  |  | Majestic Woods Pl | Forest Oaks Dr | Dead End | 68 | 19 | Local | [13 empty] | 2 |  |  |  | 15169.572 |  |  | Public Works | [16 empty] | 383.07 | 22 | 8427.54 | 0.13677
| Hall |  |  | FY 23 |  |  |  | Treeline Ct | Winding Creek Pl | Dead End | 23 | 19 | Local | [13 empty] | 0 |  |  |  | 11213.856 |  |  | Public Works | [16 empty] | 129.79 | 48 | 6229.92 | 0.10111
| LP |  | 388368-24 | FY 23 |  |  |  | Urton Ln | N English Station Rd | Rockbridge Rd | 51.4001 | 19 | Pri Coll | [13 empty] | 0 |  |  |  | 389882 |  |  | Public Works | [16 empty] | 9449.3838 | 24.7143 | 199939.2989 | 3.2448
| Hall |  |  | FY 23 |  |  |  | Whisperwood Trace | Forest Oaks Dr | Dead End | 54 | 19 | Local | [13 empty] | 2 |  |  |  | 13030.38 |  |  | Public Works | [16 empty] | 329.05 | 22 | 7239.1 | 0.11748
| Hall |  |  | FY 23 |  |  |  | Winding Creek Ct | Winding Creek Pl | Dead End | 24 | 19 | Local | [13 empty] | 0 |  |  |  | 8396.784 |  |  | Public Works | [16 empty] | 194.37 | 24 | 4664.88 | 0.075707
| Hall |  |  | FY 23 |  |  |  | Winding Creek Pl | Oakhurst Rd | Dead End | 32.4998 | 19 | Local | [13 empty] | 4 |  |  |  | 47345.904 |  |  | Public Works | [16 empty] | 1095.97 | 24 | 26303.28 | 0.42688
| Hall |  |  | FY 23 |  |  |  | Winterbranch Way | Forest Oaks Dr | Dead End | 72 | 19 | Local | [13 empty] | 2 |  |  |  | 33957 |  |  | Public Works | [16 empty] | 857.5 | 22 | 18865 | 0.30616
| Hall |  |  | FY 23 |  |  |  | Wood Thrush Trace | Golden Leaf Pl | Dead End | 18 | 19 | Local | [13 empty] | 0 |  |  |  | 10616.4 |  |  | Public Works | [16 empty] | 245.75 | 24 | 5898 | 0.095719
| LP |  | 388368-27 | FY 23 |  |  |  | Rehl Rd | S Pope Lick Rd | S English Station Rd | 41 | 20 | Sec Coll | [13 empty] | 0 |  |  | 0 | 76297 | 79319.14 | August | Public Works | [16 empty] | 1956.3229 | 20 | 39126.4576 | 0.63499
| Hall |  |  | FY 23 |  |  |  | Burkett Ct | Mary Dell Ln | Dead End | 52 | 20 | Local | [13 empty] | 0 |  |  |  | 24655.752 |  |  | Public Works | [16 empty] | 257.85 | 18 | 4641.3 | 0.075324
| Hall |  |  | FY 23 |  |  |  | Chenoweth Park Ln | Mary Dell Ln | Dead End (south) | 22.4943 | 20 | Local | [13 empty] | 0 |  |  |  | 55485.936 |  |  | Public Works | [16 empty] | 622.62 | 22 | 13697.64 | 0.2223
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Rd | Taylorsville Rd | Old Heady Rd |  | 20 | Collector | [13 empty] | 0 |  |  |  | 600000 |  |  | Council/PW | 8133-410-8210-148628-899998 | 20171.81 |  | 8131-410-8210-148628-899998 | 111849.75 |  | 8125-410-8210-148628-899998 | 30910.5 |  | 8108-410-8210-148628-899998 | 55476.24 |  | 8115-410-8210-148628-899998 | 34084.92 |  |  |  |  | 321828 | 5.223
| LP |  |  | FY 23 |  |  |  | Chenoweth Run Service Rd | Off Chenoweth Run Rd |  |  | 20 | Local | [13 empty] | 0 |  |  |  | 35000 |  |  | Council/PW | 8133-410-8210-148619-899998 | 12572.06 |  | 8123-410-8210-148619-899998 | 5273.67 |  | 8102-410-8210-148619-899998 | 17154.27
| LP |  |  | FY 23 |  |  |  | Dawson Hill Rd | Brush Run Rd | End of Metro R/W | 42.6283 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 568462 |  |  | Public Works | [16 empty] | 16893.8891 | 18.1111 | 291518.9848 | 4.7311
| Hall |  |  | FY 23 |  |  |  | Dry Ridge Ln | Dry Ridge Rd | Dead End | 18 | 20 | Local | [13 empty] | 0 |  |  |  | 7328.232 |  |  | Public Works | [16 empty] | 3076.73 | 12 | 36920.76 | 0.59919
| Hall |  |  | FY 23 |  |  |  | Hopewell Rd | Taylorsville Rd | Dead End | 23.2664 | 20 | Local | [13 empty] | 0 |  |  |  | 94449.744 |  |  | Public Works | [16 empty] | 2707.72 | 20.5 | 52472.08 | 0.85158
| Hall |  |  | FY 23 |  |  |  | Mary Dell Ln | Billtown Rd | Cynthia Dr | 26.1581 | 20 | Local | [13 empty] | 7 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 1401.16 | 22 | 30825.52 | 0.50027
| LP |  |  | FY 22 |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  | 388368-31 | FY 23 |  |  |  | Old Heady Rd | Dead End | Dead End | 18.0252 | 20 | Local | [13 empty] | 0 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 669.4406 | 20 | 13388.8119 | 0.21729
| LP |  | 388368-31 | FY 23 |  |  |  | Old Heady Rd | Taylorsville Rd | Hopewell Rd | 42.6384 | 20 | Sec Coll | [13 empty] | 10 |  |  |  | 50671 |  |  | Public Works | [16 empty] | 12887.1089 | 19.7273 | 256754.4486 | 4.1669
| Hall |  |  | FY 23 |  |  |  | Sloane Ct | Mary Dell Ln | Dead End | 61 | 20 | Local | [13 empty] | 0 |  |  |  | 8354.34 |  |  | Public Works | [16 empty] | 226.18 | 18 | 4071.24 | 0.066073
| Hall |  | 350002-505 | FY 22 |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | 208260.52 | July | [16 empty] | Asphalt done on forum/school Need to make concrete repairs | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-609 | FY 23 |  |  |  | Campobello St | Howard St | Zeta Ct | 79 | 21 | Local | [17 empty] | 30106.944 | See Howard St |  | Public Works | [18 empty] | 16726 | 0.27145
| Hall |  | 350002-609 | FY 23 |  |  |  | Carroll Ave | Durrett Ln | Scholar St | 27.7446 | 21 | Local | [13 empty] | 0 |  |  |  | 63563.112 | See Howard St |  | Public Works | [16 empty] | 1773.87 | 20 | 35312.84 | 0.5731
| Hall |  | 350002-609 | FY 23 |  |  |  | Cavelle Ave | Durrett Ln | Dead End | 26.7981 | 21 | Local | [13 empty] | 0 |  |  |  | 58023.216 | See Howard St |  | Public Works | [16 empty] | 1790.84 | 18 | 32235.12 | 0.52315
| Hall |  |  | FY23 |  |  |  | Crittenden Dr | Grade Lane | Dead End |  | 21 | Local | [17 empty] | 790710 |  |  | Public Works | [18 empty] | 395355 | 6.4163
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [13 empty] | LWC Project in area | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-603 | FY 23 |  |  |  | E Kenwood Dr | Southside Dr | Tecumseh Ave | 22.2323 | 21 | Pri Coll | [13 empty] | 6 |  |  |  | 90116 |  |  | Public Works | [16 empty] | 1992.2543 | 23.2 | 46213.3095 | 0.75
| Hall |  | 350002-610 | FY 23 |  |  |  | Greenleaf Rd | Rosemary Dr | Fern Dr | 25.4686 | 21 | Local | [13 empty] | 6 |  |  |  | 51594.948 | 21680.6 |  | Public Works | [16 empty] | 1691.27 | 17 | 28663.86 | 0.46519
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-609 | FY 23 |  |  |  | Howard St | Carroll Ave | Dead End | 35.3777 | 21 | Local | [13 empty] | 0 |  |  |  | 47118.96 | 5437 |  | Public Works | [16 empty] | 1583.17 | 16.25 | 26177.2 | 0.42483
| Hall |  | 350002-609 | FY 23 |  |  |  | Lacona Ln | Carroll Ave | Campobello St | 20 | 21 | Local | [13 empty] | 0 |  |  |  | 43749.504 | See Howard St |  | Public Works | [16 empty] | 1012.72 | 24 | 24305.28 | 0.39445
| Hall |  | 350002-622 | FY 23 |  |  |  | Meridale Ave | W Southern Heights Ave | S 2nd St | 59 | 21 | Local | [13 empty] | 2 |  |  |  | 47460.15 |  |  | Public Works | [16 empty] | 1054.67 | 25 | 26366.75 | 0.42791
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [13 empty] | LWC Project in area | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [13 empty] | LWC Project in area | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-622 | FY 23 |  |  |  | S 2nd St | W Southern Heights Ave | W Wellington Ave | 30.9927 | 21 | Local | [13 empty] | 10 |  |  |  | 107083.08 |  |  | Public Works | [16 empty] | 2074.1 | 29.75 | 59490.6 | 0.96548
| Hall |  | 350002-609 | FY 23 |  |  |  | Scholar St | Carroll Ave | Campobello St | 14 | 21 | Local | [13 empty] | 0 |  |  |  | 43307.298 | See Howard St |  | Public Works | [16 empty] | 1046.07 | 23 | 24059.61 | 0.39047
| Hall |  | 350002-603 | FY 23 |  |  |  | W Kenwood Dr | Tecumseh Ave | New Cut Rd | 45.879 | 21 | Pri Coll | [13 empty] | 7 |  |  |  | 130320 |  |  | Public Works | [16 empty] | 2906.21 | 22.8 | 66830.86 | 1.0846
| Hall |  | 350002-622 | FY 23 |  |  |  | W Wampum Ave | S 3rd St | S 1st St | 27.4999 | 21 | Local | [13 empty] | 2 |  |  |  | 45249.516 |  |  | Public Works | [16 empty] | 966.87 | 26 | 25138.62 | 0.40798
| Hall |  | 350002-622 | FY 23 |  |  |  | W Wellington Ave | Southern Pkwy | S 1st St | 31.391 | 21 | Local | [13 empty] | 4 |  |  |  | 80171.1 |  |  | Public Works | [16 empty] | 1484.65 | 30 | 44539.5 | 0.72284
| Hall |  | 350002-596 | FY 23 |  |  |  | Woodmore Ave | New Cut Rd | Southside Dr | 45.5274 | 21 | Local | [13 empty] | 0 |  |  |  | 116415.36 | 1711.66 |  | Public Works | [16 empty] | 2694.8 | 24 | 64675.2 | 1.0496
| Hall |  |  | FY 23 |  |  |  | Zeta Ct | Campobello St | Dead End | 52 | 21 | Local | [13 empty] | 0 |  |  |  | 3236.76 |  |  | Public Works | [16 empty] | 89.91 | 20 | 1798.2 | 0.029183
| Hall |  | 350002-621 | FY 23 |  |  |  | Artis Pl | Artis Way | Dead End | 39 | 22 | Local | [13 empty] | 2 |  |  |  | 7681.212 |  |  | Public Works | [16 empty] | 193.97 | 22 | 4267.34 | 0.069255
| Hall |  | 350002-621 | FY 23 |  |  |  | Artis Way | Beulah Church Rd | Dead End | 39.0264 | 22 | Local | [13 empty] | 10 |  |  |  | 133542.432 |  |  | Public Works | [16 empty] | 3091.26 | 24 | 74190.24 | 1.204
| LP |  | 388368-33 | FY 23 |  |  |  | Brentlinger Ln (Old Alignment) | Dobson Ln | Dead End | 30 | 22 | Local | [13 empty] | 0 |  |  |  | 8915 |  |  | Public Works | [18 empty] | 4953 | 0.080383
| LP |  | 388368-33 | FY 23 |  |  |  | Dobson Ln | Brentlinger Ln | Dead End | 17.6261 | 22 | Local | [13 empty] | 0 |  |  |  | 49091 |  |  | Public Works | [16 empty] | 2400.0313 | 10.6667 | 27272.787 | 0.44261
| Hall |  | 350002-621 | FY 23 |  |  |  | Fox Ledge Ct | Artis Way | Dead End | 50 | 22 | Local | [13 empty] | 0 |  |  |  | 12031.56 |  |  | Public Works | [16 empty] | 334.21 | 20 | 6684.2 | 0.10848
| Hall |  | 391627 | FY 23 |  |  |  | Gainsborough Dr | Johnson School Rd | Annalisa Dr | 32.3999 | 22 | Local | [13 empty] | 6 |  |  |  | 87744.284 | 13412.04 |  | Public Works | [16 empty] | 2076.5444 | 23.4286 | 48746.8245 | 0.79112
| LP |  | 388368-30 | FY 23 |  |  |  | Johnson School Rd | Beulah Church Rd | Cedar Creek Rd | 50.9745 | 22 | Sec Coll | [13 empty] | 0 |  |  |  | 291737 |  |  | Public Works | [16 empty] | 7438.24 | 20 | 149608.76 | 2.428
| Hall |  | 350002-621 | FY 23 |  |  |  | Ledge Pointe Ct | Artis Way | Dead End | 63 | 22 | Local | [13 empty] | 0 |  |  |  | 11113.56 |  |  | Public Works | [16 empty] | 308.71 | 20 | 6174.2 | 0.1002
| LP |  | 366368-18 | FY 23 |  |  |  | S Watterson Trl | Bardstown Rd | S Hurstbourne Pkwy | 53.8655 | 22 | Pri Coll | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works | [16 empty] | 7830.1598 | 21.3333 | 177103.3586 | 2.8742
| Hall |  | 350002-621 | FY 23 |  |  |  | Stone Ledge Ct | Stone Ledge Rd | Dead End | 71 | 22 | Local | [13 empty] | 0 |  |  |  | 11923.848 |  |  | Public Works | [16 empty] | 368.02 | 18 | 6624.36 | 0.10751
| Hall |  | 350002-621 | FY 23 |  |  |  | Stone Ledge Rd | Artis Way | Dead End | 54.5897 | 22 | Local | [13 empty] | 2 |  |  |  | 46839.96 |  |  | Public Works | [16 empty] | 1301.11 | 20 | 26022.2 | 0.42232
| Hall |  | 350002-621 | FY 23 |  |  |  | Warrenton Hill Ct | Artis Way | Dead End | 38.1799 | 22 | Local | [13 empty] | 0 |  |  |  | 35755.2 |  |  | Public Works | [16 empty] | 993.2 | 20 | 19864 | 0.32238
| Hall |  | 350002-621 | FY 23 |  |  |  | Wellington Hill Ct | Warrenton Hill Ct | Dead End | 31 | 22 | Local | [13 empty] | 0 |  |  |  | 29155.32 |  |  | Public Works | [16 empty] | 809.87 | 20 | 16197.4 | 0.26287
| Hall |  | 350002-555 | FY 22 |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 | 118962.35 | July | PW/CIF/Local Contribution
| Hall |  | 350002-597 | FY 23 |  |  |  | Adkins Rd | Honor Ave | Dead End | 44.5373 | 23 | Local | [13 empty] | 0 |  |  |  | 43504.956 |  |  | Public Works | [16 empty] | 1098.61 | 22 | 24169.42 | 0.39225
| Hall |  | 350002-597 | FY 23 |  |  |  | Amalfi Ave | Dead End | Honor Ave | 58.5583 | 23 | Local | [13 empty] | 0 |  |  |  | 38727.108 |  |  | Public Works | [16 empty] | 940.89 | 22.6667 | 21515.06 | 0.34917
| Hall |  | 350002-597 | FY 23 |  |  |  | Beth Rd | Denise Dr | Dead End | 45.0781 | 23 | Local | [13 empty] | 0 |  |  |  | 80040.96 |  |  | Public Works | [16 empty] | 1927.18 | 23.3333 | 44467.2 | 0.72166
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherita Rd | Denise Dr | Dead End | 52.2629 | 23 | Local | [13 empty] | 0 |  |  |  | 41878.98 |  |  | Public Works | [16 empty] | 1057.55 | 22 | 23266.1 | 0.37759
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherriville Rd | Manslick Rd | Amalfi Ave | 67 | 23 | Local | [13 empty] | 0 |  |  |  | 26279.856 |  |  | Public Works | [16 empty] | 608.33 | 24 | 14599.92 | 0.23694
| Hall |  | 350002-597 | FY 23 |  |  |  | Denise Dr | Lois Ave | Dead End | 33.26 | 23 | Local | [13 empty] | 0 |  |  |  | 189163.728 |  |  | Public Works | [16 empty] | 4378.79 | 24 | 105090.96 | 1.7055
| Hall |  | 350002-597 | FY23 |  |  |  | Elise Way | Shepherdsville Rd | Dead End |  | 23 | Local | [13 empty] | 0 |  |  |  | 5000
| Hall |  | 350002-597 | FY 23 |  |  |  | Honor Ave | Adkins Rd | Dead End | 50.0632 | 23 | Local | [13 empty] | 0 |  |  |  | 68010.732 |  |  | Public Works | [16 empty] | 1652.42 | 22.8 | 37783.74 | 0.6132
| Hall |  | 350002-597 | FY 23 |  |  |  | Lois Ave | Beth Rd | Dead End | 58.3886 | 23 | Local | [13 empty] | 0 |  |  |  | 87275.016 |  |  | Public Works | [16 empty] | 2033.95 | 23.3333 | 48486.12 | 0.78689
| Hall |  | 350002-597 | FY 23 |  |  |  | Senator Ln | Denise Dr | Honor Ave | 19 | 23 | Local | [13 empty] | 0 |  |  |  | 38432.016 |  |  | Public Works | [16 empty] | 889.63 | 24 | 21351.12 | 0.34651
| Hall |  | 350002-591 | FY 23 |  |  |  | Bellflower Dr | Blue Lick Rd | Dead End | 36.645 | 24 | Local | [13 empty] | 0 |  |  |  | 24800.76 | See Bluebell Dr | September | Public Works | [16 empty] | 607.95 | 23 | 13778.2 | 0.22361
| Hall |  | 350002-591 | FY 23 |  |  |  | Bluebell Dr | Blue Lick Rd | Narcissus Dr | 48.3834 | 24 | Local | [13 empty] | 2 |  |  |  | 113040.576 | 24274.75 | September | Public Works | [16 empty] | 2616.68 | 24 | 62800.32 | 1.0192
| Hall |  |  | FY 23 |  |  |  | Burnt Cedar Ln | Dead End | Dead End | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 39631 |  | September | Council | 8102-410-8210-148386-899998 | 3342.34 |  | 8672-410-8210-148385-899998 | 3342.34 |  | 8101-410-8210-148386-899998 | 48420.4 |  | 8137-410-8210-148385-899998 | 19301.47 |  | 8131-410-8210-148385-899998 | 1520.9 |  |  |  |  | 24019 | 0.38981
| Hall |  |  | FY 23 |  |  |  | Cameo Ct | Pebblebrook Ln | Dead End | 33 | 24 | Local | [13 empty] | 0 |  |  |  | 7625 |  | September | Council | See Burnt cedar | [17 empty] | 4621 | 0.074995
| Hall |  |  | FY 23 |  |  |  | Cathay Ct | Linda Rd | Dead End | 35 | 24 | Local | [13 empty] | 0 |  |  |  | 17416 |  | September | Council | See Burnt cedar | [17 empty] | 10555 | 0.1713
| Hall |  | 350002-591 | FY 23 |  |  |  | Delee Way | Narcissus Dr | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 15685.056 | See Bluebell Dr | September | Public Works | [16 empty] | 363.08 | 24 | 8713.92 | 0.14142
| Hall |  | 350002-591 | FY 23 |  |  |  | Narcissus Dr | Bluebell Dr | Dead End | 19.0231 | 24 | Local | [13 empty] | 2 |  |  |  | 51919.488 | See Bluebell Dr | September | Public Works | [16 empty] | 1201.84 | 24 | 28844.16 | 0.46812
| Hall |  |  | FY 23 |  |  |  | Pebblebrook Ln | Burnt Cedar Ln | Santa Paula Ln |  | 24 | Local | [17 empty] | 5000 |  | September | Council Funded | See Burnt cedar
| Hall |  | 350002-591 | FY 23 |  |  |  | Tulip Cir | Bluebell Dr | Dead End | 56 | 24 | Local | [13 empty] | 0 |  |  |  | 8485.488 | See Bluebell Dr | September | Public Works | [16 empty] | 214.28 | 22 | 4714.16 | 0.076507
| Hall |  | 350002-591 | FY 23 |  |  |  | Weigela Dr | Blue Lick Rd | Bluebell Dr | 45 | 24 | Local | [13 empty] | 0 |  |  |  | 23762.592 | See Bluebell Dr | September | Public Works | [16 empty] | 550.06 | 24 | 13201.44 | 0.21425
| Hall |  | 350002-593 | FY 23 |  |  |  | Abbydale Ct | Wood Hollow Rd | Dead End | 36 | 24 | Local | [13 empty] | 0 |  |  |  | 19077.12 | See Woodsend Rd |  | Public Works | [16 empty] | 588.8 | 18 | 10598.4 | 0.172
| Hall |  | 350002-617 | FY 22 |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| LP |  | 388368-32 | FY 23 |  |  |  | Smyrna Rd | Briscoe Ln | Outer Loop | 26 | 24 | Sec Coll | [13 empty] | 0 |  |  |  | 97192 |  |  | Public Works | [16 empty] | 2265.55 | 22 | 49842.1 | 0.80889
| Hall |  | 350002-593 | FY 23 |  |  |  | Tolkien Ct | Wood Hollow Rd | Dead End | 16 | 24 | Local | [13 empty] | 0 |  |  |  | 19069.02 | See Woodsend Rd |  | Public Works | [16 empty] | 588.55 | 18 | 10593.9 | 0.17193
| Hall |  | 350002-593 | FY 23 |  |  |  | Wood Hollow Rd | Oldshire Rd | Woodsend Rd | 37.445 | 24 | Local | [13 empty] | 6 |  |  |  | 34705.152 | See Woodsend Rd |  | Public Works | [16 empty] | 803.36 | 24 | 19280.64 | 0.31291
| Hall |  | 350002-593 | FY 23 |  |  |  | Woodsend Rd | Dead End | Dead End | 26.2616 | 24 | Local | [13 empty] | 2 |  |  |  | 34921.368 | 14281.9 |  | Public Works | [16 empty] | 1077.82 | 18 | 19400.76 | 0.31486
| LP |  | 388368-1 | FY 23 |  |  |  | Fordhaven Rd | St Anthony Church Rd | public road end | 37 | 25 | Local | [13 empty] | 0 |  |  | 0 | 70953 | See St Anthony Church Rd | August | Public Works | [16 empty] | 1359.2584 | 29 | 39418.4924 | 0.63973
| LP |  | 388368-1 | FY 23 |  |  |  | Manslick Rd | St Anthony Church Rd | Palatka Rd | 41.9559 | 25 | Pri Coll | [13 empty] | 0 |  |  | 2 | 357026 | See St Anthony Church Rd | August | Public Works | [16 empty] | 8143.41 | 22.6 | 183090.48 | 2.9714
| LP |  | 388368-1 | FY 23 |  |  |  | Springfield Dr | St Anthony Church Rd | public road end | 14 | 25 | Local | [13 empty] | 0 |  |  | 0 | 38326 | See St Anthony Church Rd | August | Public Works | [16 empty] | 887.1779 | 24 | 21292.2706 | 0.34556
| LP |  | 388368-1 | FY 22 |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [13 empty] | 0 |  |  | 0 | 390484.05 | 1025274.42 | August | [17 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-602 | FY 23 |  |  |  | Bamberrie Cross Rd | Chet Ln | 3rd Street Rd | 46.757 | 25 | Local | [13 empty] | 0 |  |  |  | 41704 |  | September | Public Works | [16 empty] | 1053.13 | 22 | 23168.86 | 0.37601
| Hall |  | 350002-602 | FY 23 |  |  |  | Burr Ln | Carol Way | Dead End | 28 | 25 | Local | [13 empty] | 0 |  |  |  | 35239 |  | September | Public Works | [16 empty] | 815.71 | 24 | 19577.04 | 0.31772
| Hall |  | 350002-602 | FY 23 |  |  |  | Carol Way | Manslick Rd | Chet Ln | 20.8911 | 25 | Local | [13 empty] | 0 |  |  |  | 56753 |  | September | Public Works | [16 empty] | 1433.15 | 22 | 31529.3 | 0.51169
| Hall |  | 350002-602 | FY 23 |  |  |  | Cartledge Ct | Chet Ln | 3rd Street Rd | 45 | 25 | Local | [13 empty] | 0 |  |  |  | 33549 |  |  | Public Works | [16 empty] | 1164.91 | 16 | 18638.56 | 0.30249
| Hall |  | 350002-602 | FY 23 |  |  |  | Chet Ln | Carol Way | Cartledge Ct | 26.9408 | 25 | Local | [13 empty] | 0 |  |  |  | 32341 |  | September | Public Works | [16 empty] | 816.69 | 22 | 17967.18 | 0.29159
| Hall |  | 350002-595 | FY 23 |  |  |  | Constitution Dr | Manslick Rd | Dead End | 45.4192 | 25 | Local | [13 empty] | 0 |  |  |  | 49339 |  | September | Public Works | [16 empty] | 1105.27 | 25 | 27410.36 | 0.44485
| Hall |  | 350002-595 | FY 23 |  |  |  | Heritage Pl | Manslick Rd | Dead End | 26 | 25 | Local | [13 empty] | 0 |  |  |  | 32230 |  | September | Public Works | [16 empty] | 596.85 | 30 | 17905.5 | 0.29059
| Hall |  | 350002-595 | FY 23 |  |  |  | Potomac Pl | Manslick Rd | Dead End | 30 | 25 | Local | [13 empty] | 0 |  |  |  | 28850 |  | September | Public Works | [16 empty] | 616.45 | 26 | 16027.7 | 0.26012
| Hall |  | 350002-595 | FY 23 |  |  |  | Quaker Ct | Constitution Dr | Dead End | 17 | 25 | Local | [13 empty] | 0 |  |  |  | 14012 |  | September | Public Works | [16 empty] | 389.22 | 20 | 7784.4 | 0.12633
| LP |  | 388368-4 | FY 22 |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded | 8138-410-8107-148547-82134 | 83369.78 |  | 8146-410-8107-148547-822705 | 88630.22 |  | 8138-410-8210-148386-822702 | 19000
| Hall |  | 350002-544 | FY 22 |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  |  | FY 23 |  |  |  | Brockton Ln | Hendon Rd | Commander Dr | 41.8604 | 26 | Local | [13 empty] | 0 |  |  |  | 92931.3659 |  |  | Public Works | [16 empty] | 2239.9299 | 23 | 51628.5366 | 0.83789
| Hall |  |  | FY 23 |  |  |  | Bryan Way | Dogwood Dr | Deibel Way | 37 | 26 | Local | [13 empty] | 6 |  |  |  | 47250 |  |  | Council | 8102-410-8210-148626-899998 | 112284.06 |  | 8672-410-8210-148626-899998 | 50492.42 |  | 8131-410-8210-148626-899998 | 17653.65 |  | 8133-410-8210-148626-899998 | 28163.58 | [7 empty] | 27008 | 0.43832
| Hall |  |  | FY 23 |  |  |  | Commander Dr | Brockton Ln | Herb Ln | 35 | 26 | Local | [13 empty] | 1 |  |  |  | 39974.22 |  |  | Public Works | [16 empty] | 854.15 | 26 | 22207.9 | 0.36041
|  |  |  | FY 23 |  |  |  | D26 Paving |  |  |  | 26 | [18 empty] | 122844 |  |  | Council | [19 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doreen Way | Brockton Ln | Dead End | 32 | 26 | Local | [13 empty] | 4 |  |  |  | 69295.464 |  |  | Public Works | [18 empty] | 38497 | 0.62477
| Hall |  |  | FY 23 |  |  |  | Eastside Ct | Eastside Dr | Dead End | 69 | 26 | Local | [13 empty] | 0 |  |  |  | 3877.2 |  |  | Public Works | [16 empty] | 89.75 | 24 | 2154 | 0.034958
| Hall |  |  | FY 23 |  |  |  | Eastside Dr | Manner Gate Dr | Hunsinger Ln | 18.5457 | 26 | Local | [13 empty] | 24 |  |  |  | 38431.584 |  |  | Public Works | [16 empty] | 889.62 | 24 | 21350.88 | 0.34651
| Hall |  |  | FY 23 |  |  |  | Enridge Dr | Manner Dale Dr | Landside Dr | 42 | 26 | Local | [13 empty] | 5 |  |  |  | 38500 |  |  | Council | See Bryan Way | [17 empty] | 21891 | 0.35527
| Hall |  |  | FY 23 |  |  |  | Garden View Ct | Westwood Farms Dr | Dead End | 58 | 26 | Local | [13 empty] | 0 |  |  |  | 17266.788 |  |  | Public Works | [16 empty] | 436.03 | 22 | 9592.66 | 0.15568
| Hall |  |  | FY 23 |  |  |  | Kings Hwy | Rosedale Blvd | Talisman Rd | 34.4907 | 26 | Local | [13 empty] | 0 |  |  |  | 31081.536 |  |  | Public Works | [16 empty] | 719.48 | 24 | 17267.52 | 0.28024
| Hall |  |  | FY 23 |  |  |  | Nadina Dr | Wedgewood Way | Herb Ln | 39 | 26 | Local | [13 empty] | 6 |  |  |  | 36193.95 |  |  | Public Works | [16 empty] | 874.25 | 23 | 20107.75 | 0.32633
| Hall |  |  | FY 23 |  |  |  | Plain Field Ct | Shaker Mill Rd | Dead End | 33 | 26 | Local | [13 empty] | 0 |  |  |  | 12043.548 |  |  | Public Works | [16 empty] | 304.13 | 22 | 6690.86 | 0.10859
| Hall |  |  | FY 23 |  |  |  | Rosedale Blvd | Brockton Ln | Radiance Rd | 41 | 26 | Local | [13 empty] | 6 |  |  |  | 10746.432 |  |  | Public Works | [16 empty] | 248.76 | 24 | 5970.24 | 0.096892
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Ct | Shaker Mill Rd | Dead End | 28 | 26 | Local | [13 empty] | 0 |  |  |  | 10504.692 |  |  | Public Works | [16 empty] | 265.27 | 22 | 5835.94 | 0.094712
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Rd | Westwood Farms Dr | Plain Field Ct | 50.7877 | 26 | Local | [13 empty] | 8 |  |  |  | 85603.392 |  |  | Public Works | [16 empty] | 1981.56 | 24 | 47557.44 | 0.77182
| Hall |  |  | FY 23 |  |  |  | Taylorsville Rd | Brockton Ln | Dead End | 64 | 26 | Local | [13 empty] | 1 |  |  |  | 21875.328 |  |  | Public Works | [16 empty] | 759.56 | 16 | 12152.96 | 0.19723
| Hall |  |  | FY 23 |  |  |  | Wedgewood Way (north) | Brockton Ln | Herb Ln | 26.4861 | 26 | Local | [13 empty] | 4 |  |  |  | 38181.924 |  |  | Public Works | [16 empty] | 936.5 | 23 | 21212.18 | 0.34426
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Ct | Westwood Farms Dr | Dead End | 80 | 26 | Local | [13 empty] | 0 |  |  |  | 12974.94 |  |  | Public Works | [16 empty] | 327.65 | 22 | 7208.3 | 0.11698
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Dr | Six Mile Ln | Plain Field Ct | 50.7893 | 26 | Local | [13 empty] | 13 |  |  |  | 117732.096 |  |  | Public Works | [16 empty] | 2395.29 | 30 | 65406.72 | 1.0615
|  |  | 350002-618 |  |  |  |  | Bay Pointe Cir |  |  |  | 17 | [20 empty] | September
| Strand |  | 373479-43 | FY 23 |  |  |  | Alley paving administration | [23 empty] | 4675.92
| Strand |  | 373479-47 | FY23 |  |  |  | Crittenden Dr Striping | [23 empty] | 5650
| Strand |  | 373479-38 |  |  |  |  | Red Stone Hill study | [23 empty] | 29740
| Michael Baker |  | 387658-1 | FY 23 |  |  |  | Supplemental Inspections | [22 empty] | 71609 | 112063.14

## Oct 22
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-608 | FY 23 |  |  |  | S 32nd St | Grand Ave | Greenwood Ave | 50 | 1 | Local | [17 empty] | 13598.63 | 13598.63 | August | Public Works | [18 empty] | 14567 | 0.23641
| Hall |  | 350002-628 | FY 23 |  |  |  | Bridwell Dr | Kaufman Ln | Dead End | 30.6881 | 1 | Local | [13 empty] | 1 |  |  |  | 100503 | 5448.79 |  | Public Works | [16 empty] | 2965.84 | 19 | 55835.26 | 0.90616
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Virginia Ave | Wilson Ave | 30.1848 | 1 | Local | [13 empty] | 14 |  |  |  | 155020 |  |  | Public Works | [15 empty] | Speed Humps and rail crossing | 2421.8757 | 35.25 | 86122.4396 | 1.3977
| Hall |  |  | FY 23 |  |  |  | Catalpa St | Wilson Ave | Dead End (south) | 29.2907 | 1 | Local | [13 empty] | 6 |  |  |  | 54951.192 |  |  | Public Works | [16 empty] | 984.82 | 30.6667 | 30528.44 | 0.49545
|  |  |  | FY 23 |  |  |  | Challis Cir | Regatta Way | Dead End |  | 1 | Local | [17 empty] | 6549 |  |  | Council | See S 36th
|  |  |  | FY 23 |  |  |  | D1 Paving |  |  |  | 1 | [18 empty] | 40000 |  |  | Council | 8102-410-8210-148991-899998 | 40000 | [17 empty] | 0
| Hall |  | 350002-629 | FY 23 |  |  |  | Farnsley Rd (west) | Cane Run Rd | Dead End | 37.2527 | 1 | Local | [13 empty] | 2 |  |  |  | 41202 |  |  | Public Works | [15 empty] | Narrows at dead end. Look to possibly add Zoeller and Van Winkle to Paving | 1321.12 | 17 | 22889.77 | 0.37148
| Hall |  |  | FY 23 |  |  |  | Frank Lee Ave | Terry Rd | Dead End | 41.2207 | 1 | Local | [13 empty] | 5 |  |  |  | 29502 |  |  | Public Works | [16 empty] | 819.5 | 20 | 16390 | 0.266
|  |  |  | FY 23 |  |  |  | Gregg Ave | Vorster Ave | Dead End (Alley) |  | 1 | Local | [17 empty] | 20000 |  |  | Council | 8676-410-8106-048201-822702 | 20000
| Hall |  |  | FY 23 |  |  |  | Hemlock Ct | W Gaulbert Ave | Dead End | 56 | 1 | Local | [13 empty] | 0 |  |  |  | 9432 |  |  | Public Works | [16 empty] | 187 | 28 | 5240 | 0.085041
|  |  |  | FY 23 |  |  |  | Kirby Ave | Louis Coleman Jr Dr | Rosewell Ave |  | 1 | Local | [17 empty] | 18250 |  |  | Council | See S 36th
| Hall |  | 350002-628 | FY 23 |  |  |  | Mary Rose Dr | Bridwell Dr | Lencott Dr | 51.4364 | 1 | Local | [13 empty] | 0 |  |  |  | 27007 | See Bridwell |  | Public Works | [15 empty] | Likely illegal driveway at Wilkie, but leave it alone | 759.69 | 20 | 15003.7 | 0.2435
| Hall |  |  | FY 23 |  |  |  | Olive St | W Gaulbert Ave | Dead End | 55 | 1 | Local | [13 empty] | 0 |  |  |  | 16247.52 |  |  | Public Works | [16 empty] | 300.88 | 30 | 9026.4 | 0.14649
| Hall |  | 350002-629 | FY 23 |  |  |  | Ronald Ct | Cane Run Rd | Dead End | 37 | 1 | Local | [13 empty] | 2 |  |  |  | 12907 |  |  | Public Works | [15 empty] | Possible base failure | 358.54 | 20 | 7170.8 | 0.11638
| Hall |  |  | FY 23 |  |  |  | S 28th ST | W Gaulbert Ave | Dead End | 51 | 1 | Local | [13 empty] | 0 |  |  |  | 10071.828 |  |  | Public Works | [16 empty] | 215.21 | 26 | 5595.46 | 0.090809
| Hall |  |  | FY 23 |  |  |  | S 31st St | Southern Ave | Dr William G Weathers Dr | 30.9738 | 1 | Local | [13 empty] | 12 |  |  |  | 62558 |  |  | Public Works | [15 empty] | do not repalce east sidewalk median on weathers where bump out is | 1579.74 | 22 | 34754.28 | 0.56403
|  |  |  | FY23 |  |  |  | S 36th St | Dumesnil St | Colmar Dr |  | 1 | Local | [17 empty] | 43747 |  |  | Council | 8101-410-8105-148391-822702 | 10754.93 |  | 8102-410-8105-148371-822702 | 48791.07 |  | 8133-410-8107-148911-822702 | 9000
| Hall |  |  | FY 22 |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  | FY 22 |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  | FY 22 |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-629 | FY 23 |  |  |  | Van Winkle Dr | Cane Run Rd | Dead End | 90 | 1 | Local | [13 empty] | 0 |  |  |  | 48286 |  |  | Public Works | [15 empty] | Check to see if this needs to be paved |  |  | 26825 | 0.43535
| Hall |  |  | FY 23 |  |  |  | W Gaulbert Ave | Cypress St | Wilson Ave | 35.2883 | 1 | Local | [13 empty] | 9 |  |  |  | 79050.6 |  |  | Public Works | [16 empty] | 1631.47 | 26.8 | 43917 | 0.71273
| Hall |  |  | FY 23 |  |  |  | Wade Lee Ct | Wilke Farm Ave | Dead End | 37 | 1 | Local | [13 empty] | 0 |  |  |  | 7507.08 |  |  | Public Works | [16 empty] | 208.53 | 20 | 4170.6 | 0.067685
| Hall |  |  | FY 23 |  |  |  | Wilke Farm Ave | Frank Lee Ave | Ree Dr | 48.9395 | 1 | Local | [13 empty] | 5 |  |  |  | 50846.004 |  |  | Public Works | [16 empty] | 1283.99 | 22 | 28247.78 | 0.45844
| Hall |  |  | FY 23 |  |  |  | Woodland Ave | Olive St | S 32nd St | 19.9396 | 1 | Local | [13 empty] | 21 |  |  |  | 144319 |  |  | Public Works | [16 empty] | 2380.0935 | 33.4286 | 80177.1976 | 1.3012
[8 empty] | Young Ave | S 32nd St | Louis Coleman Ave |  | 1 | Local | [17 empty] | 55000 |  |  | Council | 8133-410-8107-148911-822702 | 4951.02 |  | 8133-410-8210-148911-822702 | 13951.02 |  | 8102-410-8105-148911-831532 | 629.71 |  | CIF Account needed | 35468.25
| Hall |  | 350002-629 | FY 23 |  |  |  | Zoeller Ave | Farnsley Rd | Van Winkle Dr | 48 | 1 | Local | [13 empty] | 0 |  |  |  | 11885 |  |  | Public Works | [18 empty] | 6603 | 0.10716
| LP |  |  | FY 23 |  |  |  | Fegenbush Ln | Bardstown Rd | Fern Valley Rd | 55.6081 | 2 | Min Art | [13 empty] | 16 |  |  |  | 938271.8611 | 810127.57 | October | Public Works | [16 empty] | 9572.4106 | 47.8182 | 481165.057 | 7.8089
| Hall |  | 350002-536 | FY 22 |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 88144.05 | [17 empty] | LWC main replacement, LPA project | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  |  | FY 23 |  |  |  | Ayars Ct | Lambert Ave | Dead End | 11 | 2 | Local | [13 empty] | 0 |  |  |  | 12440.52 |  |  | Public Works | [16 empty] | 345.57 | 20 | 6911.4 | 0.11217
| Hall |  |  | FY 23 |  |  |  | Bartholomew Dr | Lambert Ave | Dead End | 62 | 2 | Local | [13 empty] | 0 |  |  |  | 16778.949 |  |  | Public Works | [15 empty] | Don’t update ramps at end of roaday | 462.23 | 22 | 10169.06 | 0.16503
| Hall |  |  | FY 23 |  |  |  | Beechbrook Rd | Kranet Way | Norfolk Dr | 38.6177 | 2 | Local | [13 empty] | 0 |  |  |  | 26909.712 |  |  | Public Works | [16 empty] | 622.91 | 24 | 14949.84 | 0.24262
| Hall |  | 350002-536 | FY 22 |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [17 empty] | LWC main replacement, LPA project | 674 | 24 | 14370 | 0.23321
| Hall |  |  | FY 23 |  |  |  | Bunche Ct | Ellington Ave | Dead End | 64 | 2 | Local | [13 empty] | 0 |  |  |  | 7492.176 |  |  | Public Works | [16 empty] | 173.43 | 24 | 4162.32 | 0.067551
| Hall |  |  | FY 23 |  |  |  | Ellington Ave | Stokes Ct | Petersburg Rd | 46.0801 | 2 | Local | [13 empty] | 8 |  |  |  | 93178.512 |  |  | Public Works | [16 empty] | 1437.94 | 36 | 51765.84 | 0.84011
| Hall |  |  | FY 23 |  |  |  | Exeter Ave | E Indian Trl | Stokes Ct | 19.8519 | 2 | Local | [13 empty] | 12 |  |  |  | 92320.56 |  |  | Public Works | [15 empty] | 2 bar walks at school which should go back. Do not add ramp at shared use path | 1424.7 | 36 | 51289.2 | 0.83238
| Hall |  |  | FY 23 |  |  |  | Heller St | Buechel Bank Rd | Dead End | 20 | 2 | Local | [13 empty] | 0 |  |  |  | 94402.764 |  |  | Public Works | [16 empty] | 2280.26 | 23 | 52445.98 | 0.85115
| Hall |  |  | FY 23 |  |  |  | Kilgore Ct | Exeter Ave | Dead End | 39 | 2 | Local | [13 empty] | 0 |  |  |  | 15129.504 |  |  | Public Works | [16 empty] | 350.22 | 24 | 8405.28 | 0.13641
| Hall |  |  | FY 23 |  |  |  | Lambert Ave | Buechel Bank Rd | Beechbrook Rd | 25.1893 | 2 | Local | [13 empty] | 9 |  |  |  | 79433 |  |  | Public Works | [15 empty] | Speed Humps | 1922.24 | 23 | 44129.26 | 0.71618
| Hall |  |  | FY 23 |  |  |  | Lambert Ct | Lambert Ave | Dead End | 54 | 2 | Local | [13 empty] | 0 |  |  |  | 14204 |  |  | Public Works | [16 empty] | 438.4 | 18 | 7891.2 | 0.12807
| Hall |  |  | FY 23 |  |  |  | Landing Dr | Lambert Ave | Norfolk Dr | 55 | 2 | Local | [13 empty] | 0 |  |  |  | 20582.208 |  |  | Public Works | [15 empty] | Include little dead end seciton just northof norfolk | 476.44 | 24 | 11434.56 | 0.18557
| Hall |  |  | FY 23 |  |  |  | Norbrook Dr | Fegenbush Ln | Dead End | 54.7966 | 2 | Local | [13 empty] | 2 |  |  |  | 56620.872 |  |  | Public Works | [16 empty] | 1123.43 | 28 | 31456.04 | 0.5105
| Hall |  |  | FY 23 |  |  |  | Norfolk Dr | Fegenbush Ln | Landing Dr | 18.9326 | 2 | Local | [13 empty] | 1 |  |  |  | 67012.92 |  |  | Public Works | [15 empty] | Believe this section of roadway includes base failures | 1431.9 | 26 | 37229.4 | 0.6042
| Hall |  |  | FY 23 |  |  |  | Sanford Ave | Buechel Bank Rd | Lambert Ave | 53 | 2 | Local | [13 empty] | 4 |  |  |  | 59871.798 |  |  | Public Works | [16 empty] | 1583.91 | 21 | 33262.11 | 0.53982
| Hall |  |  | FY 23 |  |  |  | Stokes Ct | Ellington Ave | Dead End | 46 | 2 | Local | [13 empty] | 0 |  |  |  | 15148.08 |  |  | Public Works | [16 empty] | 350.65 | 24 | 8415.6 | 0.13658
| Hall |  |  | FY 23 |  |  |  | Tubman Ct | Ellington Ave | Dead End | 25 | 2 | Local | [13 empty] | 0 |  |  |  | 7706.88 |  |  | Public Works | [16 empty] | 178.4 | 24 | 4281.6 | 0.069487
| Hall |  |  | FY 23 |  |  |  | Wheatley Ct | Exeter Ave | Dead End | 66 | 2 | Local | [13 empty] | 0 |  |  |  | 19063.2829 |  |  | Public Works | [16 empty] | 441.2797 | 24 | 10590.7127 | 0.17188
| Hall |  |  | FY 23 |  |  |  | Hardesty Ave | Dixie Hwy | S 23rd St | 23 | 3 | Local | [13 empty] | 0 |  |  |  | 42265.4 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1514.8574 | 18.0004 | 27268 | 0.44254
| Hall |  |  | FY 23 |  |  |  | Plantation Dr | Wingfield Ln | Millers Ln | 42.7091 | 3 | Local | [13 empty] | 0 |  |  |  | 42614.15 |  |  | Public Works | [15 empty] | Put on hold. Same as 23rd and Becker | 1527.3899 | 18 | 27493 | 0.44619
| Hall |  |  | FY 22 |  |  |  | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [18 empty] | On Hold |  |  |  | 0
| Hall |  |  | FY 22 |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [18 empty] | On Hold | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-571 | FY 22 |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | 141383.01 | July | [17 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-571 | FY 22 |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | See Barrett | July | [17 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  |  | FY 23 |  |  |  | Guthrie St | S 2nd St | S 3rd St | 17 | 4 | Local | [13 empty] | Done |  |  |  | 31156.488 | Cost in FY 22 | June | Public Works | [16 empty] | 480.81 | 36 | 17309.16 | 0.28091
| Hall |  | 350002-590 | FY23 |  |  |  | Bus Pad at 6th & Jefferson |  |  |  | 4 | [18 empty] | 50000 | 29557.09 | September | Public Works
| Hall |  | 350002-472 | FY 22 |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | 116336.29 | September | [17 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-472 | FY 22 |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | 248959.71 | September | [17 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 | FY 22 |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | 184983.4 | September | [17 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  | 350002-472 | FY 22 |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | See E Madison | September | [17 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-399 | FY 22 |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 72050.98 | September | [17 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  | FY 23 |  |  |  | Cedar St | S 19th St | S 15th St | 38.9167 | 4 | Local | [13 empty] | 15 |  |  |  | 128110.8343 |  |  | Public Works | [16 empty] | 1923.464 | 37 | 71172.6857 | 1.1551
| Hall |  | 350002-400 | FY 22 |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  |  | FY 23 |  |  |  | E Washington St | N 1st St | N Preston St | 54.508 | 4 | Pri Coll | [13 empty] | 11 |  |  |  | 95355 |  |  | Public Works | [16 empty] | 1654.55 | 29.3333 | 48899.86 | 0.7936
| Hall |  |  | FY 23 |  |  |  | Lake Ave | Mellwood Ave | Dead End | 19 | 4 | Local | [13 empty] | 1 |  |  |  | 82170.72 |  |  | Public Works | [16 empty] | 1984.8 | 23 | 45650.4 | 0.74087
| Hall |  |  | FY 23 |  |  |  | Magazine St | S 10th St | S 11th St | 34 | 4 | Local | [13 empty] | 1? |  |  |  | 35643.132 |  |  | Public Works | [15 empty] | Maybe make a new ramp where Magazine hits 10th st | 471.47 | 42 | 19801.74 | 0.32136
| Hall |  |  | FY 23 |  |  |  | Mount Holly Ave | Brownsboro Rd | Lindsay Ave | 19.4575 | 4 | Local | [13 empty] | 2 |  |  |  | 49280.832 |  |  | Public Works | [15 empty] | Base fialure by Lindsay | 1215.32 | 24 | 27378.24 | 0.44432
| Hall |  |  | FY 23 |  |  |  | N 2nd St | River Rd | W Main St | 55.2249 | 4 | Pri Coll | [13 empty] | 6 |  |  |  | 35953 |  |  | Public Works | [16 empty] | 904.75 | 20 | 18437.4 | 0.29922
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 |  |  | See Roy Wilkins Ave | [16 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 | FY 22 |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  | 350002-590 | FY 22 |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 |  |  | 7849.84 | [16 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  | FY 23 |  |  |  | S 10th St | Magazine St | Read Alley | 34 | 4 | Local | [13 empty] | 2 |  |  |  | 16551.5921 |  |  | Public Works | [16 empty] | 218.9364 | 42 | 9195.3289 | 0.14923
| Hall |  |  | FY 23 |  |  |  | S 11th St | W Chestnut St | W Broadway | 33.1751 | 4 | Local | [13 empty] | 11 |  |  |  | 79179.012 |  |  | Public Works | [16 empty] | 1063.09 | 41.3333 | 43988.34 | 0.71389
| Hall |  |  | FY 23 |  |  |  | S 16th St | W Breckinridge St | W Oak St | 29.2853 | 4 | Local | [13 empty] | 47 |  |  |  | 150568.704 |  |  | Public Works | [16 empty] | 2614.04 | 32 | 83649.28 | 1.3576
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Broadway | Cedar St | 17.6734 | 4 | Local | [13 empty] | 33 |  |  |  | 145131.84 |  |  | Public Works | [18 empty] | 142801 | 2.3175
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Kentucky St | W Oak St | 28.3593 | 4 | Local | [13 empty] | 37 |  |  |  | 104515.344 |  |  | Public Works | [16 empty] | 1746.26 | 33.2 | 58064.08 | 0.94233
| Hall |  |  | FY 23 |  |  |  | S 18th St | Green Alley | Eddy St | 47.405 | 4 | Local | [13 empty] | 2 |  |  |  | 30136.104 |  |  | Public Works | [16 empty] | 492.42 | 34 | 16742.28 | 0.27171
| Hall |  | 350002-630 | FY 23 |  |  |  | S 4th St | Muhammad Ali | Chestnut St |  | 4 | Local | [13 empty] | 0 |  |  |  | 25000 |  |  | Public Works
| Hall |  | 350002-472 | FY 22 |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  |  | FY 23 |  |  |  | W Oak St | Dixie Hwy | S 26th St | 20.437 | 4 | Min Art | [13 empty] | 22 |  |  |  | 224089 |  |  | Public Works, Council | 8126-410-8105-148946-822806 | 11405.87 |  | 8102-410-8105-148406-831532 | 940 | [11 empty] | 2754.22 | 38.8 | 106709.2 | 1.7318
| Hall |  |  | FY 23 |  |  |  | W St Catherine St | S 15th St | S 16th St | 21 | 4 | Local | [13 empty] | 4 |  |  |  | 40212.18 |  |  | Public Works | [16 empty] | 744.67 | 30 | 22340.1 | 0.36256
| Hall |  | 350002-590 | FY 22 |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 |  |  | See Roy Wilkins Ave | [16 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  |  | FY 23 |  |  |  | W Washington St | N 1st St | N 2nd St | 29 | 4 | Pri Coll | [13 empty] | 4 |  |  |  | 21168 |  |  | Public Works | [16 empty] | 493.42 | 22 | 10855.24 | 0.17617
| Hall |  |  | FY 23 |  |  |  | Walter Barnes Way | W Chestnut St | Read Alley | 37 | 4 | Local | [13 empty] | 0 |  |  |  | 18051.3374 |  |  | Public Works | [16 empty] | 250.713 | 40 | 10028.5208 | 0.16275
| Hall |  | 350002-583 | FY 22 |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | See S 32nd St | July | [17 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | See S 32nd St | July | [17 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  | 350002-583 | FY 22 |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | See S 32nd St | July | [17 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  | 350002-583 | FY 22 |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | See S 32nd St | July | [17 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  | 350002-583 | FY 22 |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | 598239.34 | July | [17 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall |  | 350002-582 | FY 22 |  |  |  | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | 183786.63 | July | [17 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall |  | 350002-583 | FY 22 |  |  |  | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | 68387.89 | July | [16 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  | 350002-583 | FY 22 |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | See S 32nd St | July | [17 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall |  | 350002-583 | FY 22 |  |  |  | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | See S 32nd St | July | [17 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  | 350002-583 | FY 22 |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | See S 32nd St | July | [17 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  | 350002-583 | FY 22 |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | See S 32nd St | July | [17 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  | 350002-626 | FY 23 |  |  |  | Carter St | Portland Ave | Northwestern Pkwy | 25 | 5 | Local | [13 empty] | 3 |  |  |  | 38924.712 |  |  | Public Works | [15 empty] | Concrete Roadway, look to Overlay if possible. Otehrwise select panel replacement | 600.69 | 36 | 21624.84 | 0.35095
| Hall |  | 388368-9 | FY 22 |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  | FY 23 |  |  |  | Cedar Grove Ter | Northwestern Pkwy | Dead End | 20.0333 | 5 | Local | [13 empty] | 6 |  |  |  | 75938.472 |  |  | Public Works | [16 empty] | 781.26 | 54 | 42188.04 | 0.68468
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | Dead End (east) | 22.533 | 5 | Local | [13 empty] | 6 |  |  |  | 23711 |  |  | Public Works | [15 empty] | Looks like an alley. Base Failures likely | 1061.01 | 12.6667 | 13172.86 | 0.21378
| Hall |  |  | FY 23 |  |  |  | Doerhoefer Ave | S 44th St | S 45th St | 25.4062 | 5 | Local | [13 empty] | 6 |  |  |  | 16091.928 |  |  | Public Works | [16 empty] | 599.49 | 15 | 8939.96 | 0.14509
| Hall |  | 350002-625 | FY 23 |  |  |  | Duncan St | N 22nd St | N 24th St | 14.0205 | 5 | Local | [13 empty] | 12 |  |  |  | 62193.096 | See W Main |  | Public Works | [16 empty] | 959.77 | 36 | 34551.72 | 0.56074
| Hall |  | 350002-626 | FY 23 |  |  |  | Griffiths Ave | N 22nd St | Bank St | 18.0951 | 5 | Local | [13 empty] | 25 |  |  |  | 107352.144 | 44745.15 |  | Public Works | [16 empty] | 1754.12 | 34 | 59640.08 | 0.96791
| Hall |  |  | FY 23 |  |  |  | Lytle St | N 20th St | N 22nd St | 23 | 5 | Local | [13 empty] | 0 |  |  |  | 46251 |  |  | Public Works | [16 empty] | 713.75 | 36 | 25695 | 0.41701
| Hall |  | 350002-626 | FY 23 |  |  |  | N 20th St | Rowan St | Bank St | 15.4973 | 5 | Local | [13 empty] | 28 |  |  |  | 98944.488 | 97825.91 |  | Public Works | [16 empty] | 1616.74 | 34 | 54969.16 | 0.8921
| Hall |  | 350002-626 | FY 23 |  |  |  | N 20th St | Bank St | Portland Ave | 14.9549 | 5 | Local | [13 empty] | See N 20th |  |  |  | 43443.432 | See N 20th |  | Public Works | [16 empty] | 709.86 | 34 | 24135.24 | 0.39169
| Hall |  | 350002-626 | FY 23 |  |  |  | N 21st St | Bank St | Rowan St | 18.5511 | 5 | Local | [13 empty] | 30 |  |  |  | 80968.464 | 86153.4 |  | Public Works | [16 empty] | 1874.27 | 24 | 44982.48 | 0.73003
| Hall |  | 350002-626 | FY 23 |  |  |  | N 23rd St | Portland Ave | Northwestern Pkwy | 20.4356 | 5 | Local | [13 empty] | 10 |  |  |  | 56586.996 |  |  | Public Works | [16 empty] | 911.12 | 34.5 | 31437.22 | 0.5102
| Hall |  | 350002-626 | FY 23 |  |  |  | N 25th St | Portland Ave | Northwestern Pkwy | 27.0214 | 5 | Local | [13 empty] | 15 |  |  |  | 64663.6283 |  |  | Public Works | [15 empty] | Brick paver ramp to replace with concrete. Need to check if histroic preservation dist. | 1025.8987 | 35 | 35924.2379 | 0.58302
| Hall |  | 350002-626 | FY 23 |  |  |  | N 27th St | Portland Ave | Northwestern Pkwy | 17.9248 | 5 | Local | [13 empty] | 11 |  |  |  | 64603.008 |  |  | Public Works | [16 empty] | 996.96 | 36 | 35890.56 | 0.58247
| Hall |  |  | FY 23 |  |  |  | N 33rd St | Northwestern Pkwy | Pflanz St | 20 | 5 | Local | [13 empty] | 8 |  |  |  | 89696.592 |  |  | Public Works | [18 empty] | 49831 | 0.80871
| Hall |  |  | FY 23 |  |  |  | N 34th St | Northwestern Pkwy | Pflanz Ave | 35 | 5 | Local | [13 empty] | 5 |  |  |  | 17153.856 |  |  | Public Works | [16 empty] | 264.72 | 36 | 9529.92 | 0.15466
| Hall |  |  | FY 23 |  |  |  | N 35th St | Northwestern Pkwy | Parker Ave | 17.674 | 5 | Local | [13 empty] | 10 |  |  |  | 159050.88 |  |  | Public Works | [16 empty] | 2209.04 | 40 | 88361.6 | 1.434
| Hall |  |  | FY 23 |  |  |  | N 36th St | Northwestern Pkwy | Pflanz Ave | 38 | 5 | Local | [13 empty] | 4 |  |  |  | 11527.488 |  |  | Public Works | [16 empty] | 266.84 | 24 | 6404.16 | 0.10393
| Hall |  | 350002-625 | FY 23 |  |  |  | Rowan St | N 22nd St | N 24th St | 15.9641 | 5 | Local | [13 empty] | 8 |  |  |  | 62099.136 | See W Main |  | Public Works | [16 empty] | 958.32 | 36 | 34499.52 | 0.5599
| Hall |  |  | FY 23 |  |  |  | S 45th St | W Broadway | Garland Ave | 32.9625 | 5 | Local | [13 empty] | 7 |  |  |  | 58936.86 |  |  | Public Works | [16 empty] | 1117.9 | 29.3333 | 32742.7 | 0.53139
| Hall |  |  | FY 23 |  |  |  | Short St | Griffiths Ave | Owen St | 16 | 5 | Local | [13 empty] | 5 |  |  |  | 16947.684 |  |  | Public Works | [16 empty] | 362.13 | 26 | 9415.38 | 0.1528
| Hall |  | 350002-625 | FY 23 |  |  |  | W Main St | N 22nd St | N 25th St | 39.6711 | 5 | Local | [13 empty] | 17 |  |  |  | 155392.56 | 50805.43 |  | Public Works | [16 empty] | 1438.82 | 60 | 86329.2 | 1.401
| Hall |  | 350002-588 | FY 22 |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | see S Floyd | July | [17 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  | 350002-588 | FY 22 |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | 222661.02 | July | [17 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  | 350002-579 | FY 22 |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | 94995.62 | July | [17 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  | 350002-587 | FY 22 |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | 186252.09 | July | [17 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  |  | FY 23 |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 6 | Local | [13 empty] | Done |  |  |  | 67784.6 | Cost in FY 22 | June | Public Works | [16 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  |  | FY 23 |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 6 | Local | [13 empty] | Done |  |  |  | 31238.7 | Cost in FY 22 | june | Public Works | [16 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  |  | FY 23 |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 6 | Local | [13 empty] | Done |  |  |  | 28873.4 | Cost in FY 22 | June | Public Works | [16 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall |  |  | FY 23 |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 6 | Local | [13 empty] | Done |  |  |  | 50573.4 | Cost in FY 22 | June | Public Works | [16 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-627 | FY 23 |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | 52685.98 | October | [16 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  | 350002-615 | FY 22 |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 |  | October | [17 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  | 350002-606 | FY 23 |  |  |  | Dixie Hwy | Hale Ave | W Burnett Ave | 55.4031 | 6 | Min Art | [13 empty] | 29 |  |  |  | 236607 | 207213.06 | September | Public Works | [16 empty] | 3120.29 | 35.5455 | 112669.83 | 1.8285
| Hall |  |  | FY 23 |  |  |  | Lillian Ave | 7th Street Rd | Colorado Ave | 31.3741 | 6 | Local | [13 empty] | 11 |  |  |  | 92745.72 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 2015.69 | 25.3333 | 51525.4 | 0.83621
| Hall |  |  | FY 23 |  |  |  | Lincoln Ave | 7th Street Rd | Taylor Blvd | 24.899 | 6 | Local | [13 empty] | 18 |  |  |  | 183027.456 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 3815.61 | 26.7143 | 101681.92 | 1.6502
| Hall |  |  | FY 23 |  |  |  | Lindbergh Dr | Algonquin Pkwy | Dead End (Homeview) | 45.5354 | 6 | Local | [13 empty] | 35 |  |  |  | 166826.304 |  |  | Public Works | [15 empty] | Some ramps may be technically infeasible. Dead end at homeview is strange | 3138.68 | 29 | 94313.98 | 1.5306
| Hall |  |  | FY 23 |  |  |  | Reutlinger Ave | E Oak St | Ellison Ave | 23.3308 | 6 | Local | [13 empty] | 6 |  |  |  | 67047.624 |  |  | Public Works | [16 empty] | 1330.31 | 28 | 37248.68 | 0.60451
| Hall |  |  | FY 23 |  |  |  | S Preston St | E Hill St | I 65 Ramp | 52.6318 | 6 | Min Art | [13 empty] | 9 |  |  |  | 66983 |  |  | Public Works | [16 empty] | 911.2283 | 34.6667 | 31896.4441 | 0.51765
| Hall |  |  | FY 23 |  |  |  | Tennessee Ave | 7th Street Rd | Lindbergh Dr | 33 | 6 | Local | [13 empty] | 4 |  |  |  | 62034.264 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1380.5 | 25 | 34463.48 | 0.55931
| Hall |  |  | FY 23 |  |  |  | Weller Ave | 7th Street Rd | Dead End | 28.6273 | 6 | Local | [13 empty] | 4 |  |  |  | 64972.44 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1388.3 | 26 | 36095.8 | 0.5858
| Hall |  |  | FY 23 |  |  |  | Wurtele Ave | 7th Street Rd | Colorado Ave | 32.2659 | 6 | Local | [13 empty] | 3 |  |  |  | 109582.272 |  |  | Public Works | [15 empty] | Replace ramps where sidewalks exist only | 1902.47 | 32 | 60879.04 | 0.98801
| Hall |  |  | FY 23 |  |  |  | Branning Rd | Brownsboro Rd | end of Metro R/W | 15 | 7 | Local | [13 empty] | 0 |  |  |  | 27000 |  |  | Public Works | [16 empty] | 596.7397 | 18 | 15000 | 0.24344
| LP |  | 388368-7 | FY 22 |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [13 empty] | 0 |  |  | 0 | 44635.35 | 31523.81 | August | [17 empty] | 800 | 36 | 28797 | 0.46735
| LP |  | 366368-17 | FY 23 |  |  |  | Trevilian Way | Newburg Rd | Dundee Rd | 68.6911 | 8 | Min Art | [13 empty] | 0 |  |  | 0 | 192812 | 136694.4 | August | Google Funds | [16 empty] | 3604.72 | 26 | 91815.32 | 1.4901
| Hall |  |  | FY 23 |  |  |  | Alta Ave | Bardstown Rd | Cherokee Rd | 25.0798 | 8 | Local | [13 empty] | 29 |  |  |  | 169299.18 |  |  | Public Works | [16 empty] | 3135.17 | 30 | 94055.1 | 1.5264
| Hall |  |  | FY 23 |  |  |  | Benton Ave | St Anthony Pl | Rubel Ave | 23 | 8 | Local | [13 empty] | 4 |  |  |  | 15710.688 |  |  | Public Works | [16 empty] | 311.72 | 28 | 8728.16 | 0.14165
| Hall |  |  | FY 23 |  |  |  | Bonnycastle Ave | Bardstown Rd | Cherokee Rd | 37.5047 | 8 | Local | [13 empty] | 29 |  |  |  | 149154.516 |  |  | Public Works | [16 empty] | 2858.8 | 29 | 82863.62 | 1.3448
| Hall |  |  | FY 23 |  |  |  | Debarr St | Rubel Ave | Barret Ave | 32.4769 | 8 | Local | [13 empty] | 11 |  |  |  | 60853.68 |  |  | Public Works | [16 empty] | 1126.92 | 30 | 33807.6 | 0.54867
| Hall |  |  | FY 23 |  |  |  | Edward St | St Anthony Pl | Morton Ave | 24.8631 | 8 | Local | [13 empty] | 34 |  |  |  | 80043.228 |  |  | Public Works | [16 empty] | 1234.23 | 36 | 44468.46 | 0.72168
| Hall |  |  | FY 23 |  |  |  | Edward St | Morton Ave | Rufer Ave | 18.7033 | 8 | Local | [13 empty] | 39 |  |  |  | 116619.264 |  |  | Public Works | [16 empty] | 1799.68 | 36 | 64788.48 | 1.0515
| Hall |  |  | FY 23 |  |  |  | Grasmere Ter | Grasmere Dr | Dead End | 10.6363 | 8 | Local | [13 empty] | 0 |  |  |  | 6760.584 |  |  | Public Works | [15 empty] | Small alley, could be a nightmare | 312.99 | 12 | 3755.88 | 0.060955
| Hall |  |  | FY 23 |  |  |  | Parsons Pl | Alta Ave | Bonnycastle Ave | 30 | 8 | Local | [13 empty] | 0 |  |  |  | 14329.548 |  |  | Public Works | [16 empty] | 442.27 | 18 | 7960.86 | 0.1292
| Hall |  |  | FY 23 |  |  |  | Ray Ave | Grinstead Dr | Longest Ave | 22.8729 | 8 | Local | [13 empty] | 7 |  |  |  | 71597.52 |  |  | Public Works | [16 empty] | 1325.88 | 30 | 39776.4 | 0.64554
| Hall |  |  | FY 23 |  |  |  | Ridgeway Ave | Willow Ave | Dead End | 10 | 8 | Local | [13 empty] | 2 |  |  |  | 44804.52 |  |  | Public Works | [15 empty] | Looks like an alley | 1244.57 | 20 | 24891.4 | 0.40397
| Hall |  |  | FY 23 |  |  |  | Rubel Ave | E Broadway | Morton Ave | 30.1586 | 8 | Local | [13 empty] | 33 |  |  |  | 84858.9042 |  |  | Public Works | [16 empty] | 1341.3399 | 35.2 | 47143.8357 | 0.7651
| Hall |  |  | FY 23 |  |  |  | Spring Dr | Speed Ave | Woodford Pl | 18.0204 | 8 | Local | [13 empty] | 2 |  |  |  | 111570.696 |  |  | Public Works | [16 empty] | 1721.77 | 36 | 61983.72 | 1.0059
| Hall |  |  | FY 23 |  |  |  | St Anthony Pl | E Broadway | Barret Ave | 33.4304 | 8 | Local | [13 empty] | 5 |  |  |  | 63780.804 |  |  | Public Works | [16 empty] | 1161.78 | 31.3333 | 35433.78 | 0.57506
| Hall |  | 350002-584 | FY 22 |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 9 | Local | [17 empty] | 42573.85 | See Alta Vista Rd | August | [16 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  | 350002-612 | FY 23 |  |  |  | Bauer Ave | Lexington Rd | Wilmington Ave | 21 | 9 | Local | [13 empty] | 0 |  |  |  | 20857.32 | 29889.06 | October | Public Works | [16 empty] | 526.7 | 22 | 11587.4 | 0.18805
| Hall |  |  | FY 23 |  |  |  | Chamberry Cir (All) | Old Cannons Ln | Old Cannons Ln | 28.3517 | 9 | Local | [13 empty] | 0 |  |  |  | 86199.228 |  | October | Public Works | [16 empty] | 1958.4 | 25 | 47888.46 | 0.77719
| Hall |  |  | FY 23 |  |  |  | Circle Hill Rd | Rock Creek Dr | Old Cannons Ln | 28.8803 | 9 | Local | [13 empty] | 0 |  |  |  | 120190.7284 |  | October | Public Works | [16 empty] | 2587.9703 | 23 | 60702.3881 | 0.98515
| Hall |  |  | FY 23 |  |  |  | Homestead Blvd | Rock Creek Dr | Circle Hill Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 48453.688 |  | October | Public Works | [16 empty] | 1121.6131 | 24 | 26918.7155 | 0.43687
| Hall |  |  | FY 23 |  |  |  | Huntington Rd | Rock Creek Dr | Old Cannons Ln | 18.7864 | 9 | Local | [13 empty] | 0 |  |  |  | 67794.408 |  | October | Public Works | [16 empty] | 1711.98 | 22 | 37663.56 | 0.61125
| Hall |  |  | FY 23 |  |  |  | Rock Creek Dr | Cannons Ln | Pee Wee Reese Rd | 32.2104 | 9 | Local | [13 empty] | 0 |  |  |  | 114983.244 |  | October | Public Works | [15 empty] | Base failures | 3260.83 | 19.6 | 63879.58 | 1.0367
| Hall |  | 350002-612 | FY 23 |  |  |  | Willis Ave | Wiltshire Ave | Breckenridge Ln | 76 | 9 | Collector | [17 empty] | 14626.8 | See Bauer Ave | October | [19 empty] | 8126 | 0.13188
| Hall |  | 350002-612 | FY 23 |  |  |  | Wilmington Ave | Wallace Ave | Frankfort Ave | 28.1016 | 9 | Local | [13 empty] | 3 |  |  |  | 24518.88 | See Bauer Ave | October | Public Works | [16 empty] | 536.86 | 25 | 13621.6 | 0.22107
| Hall |  | 350002-612 | FY 23 |  |  |  | Wiltshire Ave | Wilmington Ave | Willis Ave | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 22864.644 | See Bauer Ave | October | Public Works | [16 empty] | 577.39 | 22 | 12702.58 | 0.20615
| Hall |  | 350002-611 | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Dead End |  | 9 | Local | [17 empty] | 23706.8246 | See Winchester Rd | October | [19 empty] | 13170 | 0.21374
| Hall |  | 350002-611 | FY 23 |  |  |  | Winchester Rd | Cannons Ln | Thompson Ave | 44.4846 | 9 | Pri Coll | [13 empty] | 6 |  |  |  | 118575 | 13643.27 | October | Public Works | [16 empty] | 2147.8793 | 29.3333 | 60807.4923 | 0.98685
| Hall |  |  | FY 23 |  |  |  | Avon Ct | Kennedy Ave | Kennedy Ct | 14 | 9 | Local | [13 empty] | 0 |  |  |  | 6826.644 |  |  | Public Works | [16 empty] | 172.39 | 22 | 3792.58 | 0.06155
| Hall |  |  | FY 23 |  |  |  | Crescent Ct | Frankfort Ave | Grinstead Dr | 27.5652 | 9 | Local | [13 empty] | 2 |  |  |  | 49072.7871 |  |  | Public Works | [15 empty] | Base failures? | 1239.2118 | 22 | 27262.6595 | 0.44245
| Hall |  | 35002-616 | FY 22 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  |  | FY 23 |  |  |  | Kennedy Ave | Frankfort Ave | Grinstead Dr | 31.0011 | 9 | Local | [13 empty] | 2 |  |  |  | 45585.036 |  |  | Public Works | [16 empty] | 1384.26 | 18 | 25325.02 | 0.411
| Hall |  |  | FY 23 |  |  |  | Kennedy Ct | Kennedy Ave | Dead End | 41.1453 | 9 | Local | [13 empty] | 2 |  |  |  | 20407.788 |  |  | Public Works | [16 empty] | 586.15 | 20 | 11337.66 | 0.184
| Hall |  | 350002-612 | FY 23 |  |  |  | Macon Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 20824.128 | See Bauer Ave |  | Public Works | [16 empty] | 482.04 | 24 | 11568.96 | 0.18775
| Hall |  |  | FY 23 |  |  |  | Meadowlark Ave | Seminary Rd | Stilz Ave | 15.5126 | 9 | Local | [13 empty] | 11 |  |  |  | 24502.176 |  |  | Public Works | [16 empty] | 850.77 | 16 | 13612.32 | 0.22092
| Hall |  |  | FY 23 |  |  |  | Napanee Rd | Chippewa Rd | St Matthews Ave | 19 | 9 | Local | [13 empty] | 0 |  |  |  | 25394.256 |  |  | Public Works | [16 empty] | 587.83 | 24 | 14107.92 | 0.22896
| Hall |  |  | FY 23 |  |  |  | Pleasantview Ave | Grinstead Dr | Lexington Rd | 18.075 | 9 | Local | [13 empty] | 10 |  |  |  | 98573.688 |  |  | Public Works | [16 empty] | 1878.18 | 29 | 54763.16 | 0.88876
| Hall |  | 350002-612 | FY 23 |  |  |  | S Hubbards Ln | Bowling Blvd | Shelbyville Rd | 27 | 9 | Min Art | [17 empty] | 253130 |  |  | Public Works | [18 empty] | 120538 | 1.9562
| Hall |  |  | FY 23 |  |  |  | Springdale Rd | Grinstead Dr | Pleasantview Ave | 20 | 9 | Local | [13 empty] | 3 |  |  |  | 29623.104 |  |  | Public Works | [16 empty] | 685.72 | 24 | 16457.28 | 0.26709
| Hall |  |  | FY 23 |  |  |  | St Matthews Ave | Napanee Rd | Ormond Rd | 31 | 9 | Local | [13 empty] | 0 |  |  |  | 14326.884 |  |  | Public Works | [16 empty] | 361.79 | 22 | 7959.38 | 0.12917
| Hall |  |  | FY 23 |  |  |  | Stilz Ave | Lexington Rd | Frankfort Ave | 53.6459 | 9 | Pri Coll | [13 empty] | 13 |  |  |  | 114290 |  |  | Public Works | [16 empty] | 2574.69 | 34.3333 | 87915.6 | 1.4268
| Hall |  | 350002-612 | FY 23 |  |  |  | Wallace Ave | Lexington Rd | Wilmington Ave | 18 | 9 | Local | [13 empty] | 0 |  |  |  | 18104.112 | See Bauer Ave |  | Public Works | [16 empty] | 386.84 | 26 | 10057.84 | 0.16323
| Hall |  | 350002-612 | FY 23 |  |  |  | Wendover Ave | Lexington Rd | Wilmington Ave | 26 | 9 | Local | [13 empty] | 0 |  |  |  | 17264.808 | See Bauer Ave |  | Public Works | [16 empty] | 435.98 | 22 | 9591.56 | 0.15566
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Ct | Audubon Ridge Dr | Dead End | 19.8104 | 10 | Local | [13 empty] | 0 |  |  |  | 33929.676 |  |  | Public Works | [16 empty] | 856.81 | 22 | 18849.82 | 0.30592
| Hall |  |  | FY 23 |  |  |  | Audubon Ridge Dr | Illinois Ave | Dead End | 48.9775 | 10 | Local | [13 empty] | 5 |  |  |  | 44784.36 |  |  | Public Works | [16 empty] | 1027.09 | 31 | 24880.2 | 0.40378
| Hall |  |  | FY 23 |  |  |  | Grantswood Ct | Audubon Ridge Ct | Dead End |  | 10 | Local | [13 empty] | 2 |  |  |  | 16264.8 |  |  | Public Works | [16 empty] | 502 | 18 | 9036 | 0.14665
| Hall |  | 350002-610 | FY 23 |  |  |  | Greenleaf Rd | Rosemary Dr | Fern Dr | 25.4686 | 10 | Local | [13 empty] | 6 |  |  |  | 51594.948 | 21680.6 |  | Public Works | [16 empty] | 1691.27 | 17 | 28663.86 | 0.46519
| LP |  | 366368-16 | FY 23 |  |  |  | Robards Ln | Gardiner Ln | Bishop Ln | 42.3597 | 10 | Pri Coll | [13 empty] | 2 |  |  |  | 147273 |  |  | Public Works | [16 empty] | 3717.62 | 20 | 75524.68 | 1.2257
| LP |  | 388368-27 | FY 23 |  |  |  | E Rehl Ct | Rehl Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | 0 | 60541 | See Rehl Rd | August | Public Works | [18 empty] | 33634 | 0.54585
| Hall |  | 350002-631 | FY 23 |  |  |  | Bircham Rd | Shelbyville Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | 140437.38 | 110000 |  | September | Council | 8102-410-8210-148628-899998 | 110000 | [16 empty] | 66212 | 1.0746
| Hall |  | 350002-631 | FY 23 |  |  |  | Burleigh Ct | Burcham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | See Bircham Rd | 31000 |  | September | Council | 8102-410-8210-148628-899998 | 31000 | [16 empty] | 17407 | 0.2825
| Hall |  | 350002-631 | FY 23 |  |  |  | Burleigh Pl | Burleigh Ct | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | See Bircham Rd | 8500 |  | September | Council | 8102-410-8210-148628-899998 | 8500 | [16 empty] | 4726 | 0.076699
| Hall |  | 350002-631 | FY 23 |  |  |  | Dorshire Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | See Bircham Rd | 20000 |  | September | Council | 8102-410-8210-148628-899998 | 20000 | [16 empty] | 11350 | 0.1842
| Hall |  | 350002-613 | FY 23 |  |  |  | Landis Lakes Dr | S English Station Rd | Landis Lakes Ct | 32.9592 | 11 | Local | [13 empty] | 10 |  |  | 76434.79 | 66457.368 | 78140.77 | September | Public Works | [16 empty] | 1682.32 | 25.3333 | 41128.06 | 0.66747
| Hall |  | 350002-631 | FY 23 |  |  |  | Willoughby Ct | Bircham Rd | Dead End |  | 11 | Local | [13 empty] | 0 |  |  | See Bircham Rd | 26000 |  | September | Council | 8102-410-8210-148628-899998 | 26000 | [16 empty] | 14983 | 0.24316
| Hall |  |  | FY 23 |  |  |  | Constant Comment Pl | From J-Town R/W north of Electron | Dead End (south) | 22.3743 | 11 | Local | [13 empty] | 1 |  |  |  | 76709.25 |  |  | Public Works | [16 empty] | 987 | 35 | 42616.25 | 0.69162
| Hall |  |  | FY 23 |  |  |  | Electron Dr | Blankenbaker Pkwy | Constant Comment Pl | 19 | 11 | Local | [13 empty] | 1 |  |  |  | 51249.132 |  |  | Public Works | [16 empty] | 862.78 | 33 | 28471.74 | 0.46207
| Hall |  |  | FY 23 |  |  |  | Hurstbourne Park Blvd | Hurstbourne Pkwy | Dead End |  | 11 | Local | [17 empty] | 48685 |  |  | Public Works | [18 empty] | 27047 | 0.43895
| Hall |  | 350002-601 | FY 23 |  |  |  | Lynn Myra Ct | Vista John Dr | Dead End | 40 | 12 | Local | [13 empty] | 0 |  |  |  | 9422.424 | See Vista John Dr | September | Public Works | [16 empty] | 237.94 | 22 | 5234.68 | 0.084954
| Hall |  | 350002-601 | FY 23 |  |  |  | Stephan Rd | Vista John Dr | Oswego Cir | 25.3696 | 12 | Local | [13 empty] | 0 |  |  |  | 37562.1531 | See Vista John Dr | September | Public Works | [16 empty] | 1043.3931 | 20 | 20867.8628 | 0.33867
| Hall |  | 350002-601 | FY 23 |  |  |  | Terudon Dr | Manslick Rd | Vista John Dr | 28 | 12 | Local | [13 empty] | 0 |  |  |  | 31798.656 | See Vista John Dr | September | Public Works | [16 empty] | 736.08 | 24 | 17665.92 | 0.2867
| Hall |  | 350002-601 | FY 23 |  |  |  | Vista John Dr | Manslick Rd | Stephan Dr | 36.6481 | 12 | Local | [13 empty] | 0 |  |  |  | 59112.684 | 108071.34 | September | Public Works | [16 empty] | 1411.04 | 23.3333 | 32840.38 | 0.53297
| LP |  |  | FY 23 |  |  |  | Blanton Ln | St Andrews Church Rd | Dixie Hwy | 35.5419 | 12 | Pri Coll | [13 empty] | 0 |  |  |  | 226546 |  |  | Public Works | [16 empty] | 5256.12 | 22.5714 | 116177.36 | 1.8855
| Hall |  |  | FY 23 |  |  |  | De Mel Ave | Manslick Rd | Dead End | 23.8808 | 12 | Local | [13 empty] | 0 |  |  |  | 73224.6988 |  |  | Public Works | [16 empty] | 1904.3118 | 21.6667 | 40680.3882 | 0.66021
| Hall |  | 350002-600 | FY 23 |  |  |  | Maryview Dr | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 79947 |  |  | Pw/Council | 8676-410-8106-048212-822702 | 0.55 |  | 8102-410-8105-148230-822702 | 3441.57 |  | 8144-410-8205-148230-822702 | 19000 |  | 8642-410-8105-148230-822702 | 2389.77 | [7 empty] | 45684
| Hall |  | 350002-518 | FY 22 |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [18 empty] | LWC Project | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-614 | FY 23 |  |  |  | Mount Marcy Rd | Mount Holyoke Dr | Alps Rd | 25 | 12 | Local | [13 empty] | 6 |  |  |  | 57474.144 | 14650.75 |  | Public Works | [16 empty] | 1330.42 | 24 | 31930.08 | 0.5182
| Hall |  | 350002-600 | FY 23 |  |  |  | Nancy Ave | Dawn Dr | Dead End | 22 | 12 | Local | [13 empty] | 0 |  |  |  | 34899.984 |  |  | Public Works | [16 empty] | 807.87 | 24 | 19388.88 | 0.31466
| Hall |  | 350002-600 | FY 23 |  |  |  | Princewood Pl | Dawn Dr | Dead End |  | 12 | Local | [17 empty] | 18314 |  |  | PW/Council | See Maryview | [17 empty] | 10465 | 0.16984
| Hall |  | 350002-552 | FY 22 |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | 18148.98 | September | [17 empty] | 1364 | 12 | 16372 | 0.2657
|  |  |  | FY 23 |  |  |  | Brookley Dr | Arroyo Trl | County Line |  | 13 | Local | [17 empty] | 59398 |  |  | Council | 8672-410-8105-148231-822702 | 5153.3 |  | 8133-410-8107-148413-822702 | 5557.21 |  | 8133-410-8210-148413-822702 | 3915 |  | 8148-410-8107-148574-822702 | 15500 |  | 8101-410-8105-148231-822702 | 29272.49
|  |  |  | FY 23 |  |  |  | Calm Ct | Calm Ln | Dead End |  | 13 | Local | [17 empty] | 6370 |  |  | Council | 8133-410-8107-148413-822702 | 6370
|  |  |  | FY 23 |  |  |  | Calm Ln | Endeavor Way | Dead End |  | 13 | Local | [17 empty] | 21773 |  |  | Council | 8133-410-8210-148413-822702 | 21773
| Hall |  | 350002-592 | FY 23 |  |  |  | Clay Ave | Minor Ln | Preston Hwy | 25.2005 | 13 | Local | [13 empty] | 0 |  |  |  | 102532.608 |  |  | Public Works | [16 empty] | 3415.39 | 16.8 | 56962.56 | 0.92445
| Hall |  | 350002-560 | FY 22 |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
|  |  |  | FY 23 |  |  |  | Jan Way | Bonaventure Blvd | Endeavor Way |  | 13 | Local | [17 empty] | 99799 |  |  | Council | 8101-410-8105-148231-822702 | 99799
| LP |  |  | FY 23 |  |  |  | Jefferson Hill Rd | Keys Ferry Rd | Snawder Ln | 37.0674 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 444131 |  |  | Public Works | [15 empty] | LWC has a project to complete on this roadway, to be complete in 2024. | 12300.93 | 18.6667 | 227759.57 | 3.6963
| LP |  | 388368-34 | FY 23 |  |  |  | Joyner Hill Rd | Lonesome Hollow Rd | Dead End | 33 | 13 | Local | [13 empty] | 0 |  |  |  | 22761.882 |  |  | Public Works | [16 empty] | 1149.59 | 11 | 12645.49 | 0.20523
| LP |  | 388368-34 | FY 23 |  |  |  | Lonesome Hollow Rd | Blevins Gap Rd | Dead End | 23.6259 | 13 | Local | [13 empty] | 0 |  |  |  | 93498.0588 |  |  | Public Works | [16 empty] | 2990.1966 | 18 | 51943.366 | 0.843
| LP |  | 388368-34 | FY 23 |  |  |  | Lonesome Hollow Rd | Jefferson Hill Rd | Dead End | 37 | 13 | Local | [13 empty] | 0 |  |  |  | 16334.784 |  |  | Public Works | [16 empty] | 756.24 | 12 | 9074.88 | 0.14728
| Hall |  | 350002-592 | FY 23 |  |  |  | Meadow Hill Rd | Minyard Dr | Dead End | 9 | 13 | Local | [13 empty] | 2 |  |  |  | 8903.2847 |  |  | Public Works | [15 empty] | Metro ROW is small, only 4 houses, rest private | 206.0946 | 24 | 4946.2693 | 0.080274
| Hall |  | 350002-592 | FY 23 |  |  |  | Minyard Dr | Clay Ave | Minor Ln | 28.853 | 13 | Local | [13 empty] | 0 |  |  |  | 91895.328 |  |  | Public Works | [16 empty] | 1930.73 | 26.25 | 51052.96 | 0.82855
| LP |  | 388368-37 | FY 23 |  |  |  | Schooler Ln | Stonestreet Rd | Dead End | 17 | 13 | Local | [13 empty] | 0 |  |  |  | 25697 |  |  | Public Works | [16 empty] | 1190 | 12 | 14276 | 0.23169
|  |  |  | FY 23 |  |  |  | Skyline Dr | Brookley Dr | County Line |  | 13 | Local | [17 empty] | 24312 |  |  | Council | 8133-410-8210-148413-822702 | 24312
| LP |  | 388368-35 | FY 23 |  |  |  | Snawder Ln | Jefferson Hill Rd | Dead End | 21 | 13 | Local | [13 empty] | 0 |  |  |  | 22803.48 |  |  | Public Works | [16 empty] | 1266.86 | 10 | 12668.6 | 0.2056
| Hall |  | 350002-592 | FY 23 |  |  |  | Sunset Dr | Minor Ln | Clay Ave | 39 | 13 | Local | [13 empty] | 0 |  |  |  | 36200.52 |  |  | Public Works | [16 empty] | 1117.3 | 18 | 20111.4 | 0.32639
| LP |  | 388368-34 | FY 23 |  |  |  | Tidwell Rd | Lonesome Hollow Rd | Dead End | 35 | 13 | Local | [13 empty] | 0 |  |  |  | 16525.8 |  |  | Public Works | [16 empty] | 765 | 12 | 9181 | 0.149
| LP |  | 388368-35 | FY 23 |  |  |  | Top Hill Rd | Snawder Ln | Mitchell Hill Rd | 45.371 | 13 | Sec Coll | [13 empty] | 0 |  |  |  | 377132 |  |  | Public Works | [16 empty] | 9913.74 | 19 | 193400.8 | 3.1387
|  |  |  | FY 23 |  |  |  | Tumbleweed Rd | Skyline Dr | County Line |  | 13 | Local | [17 empty] | 16046 |  |  | Council | 8133-410-8107-148413-822702 | 16046
| Hall |  | 350002-599 | FY 23 |  |  |  | Chase Rd | W Pages Ln | Stephan Dr | 43 | 14 | Local | [13 empty] | 2 |  |  |  | 41561.28 | See Stephan Dr |  | Public Works | [16 empty] | 1154.48 | 20 | 23089.6 | 0.37472
| Hall |  | 350002-594 | FY 23 |  |  |  | Dixie Garden Dr | Dixie Hwy | Blaze Way | 51.9782 | 14 | Local | [13 empty] | 4 |  |  |  | 123696.396 | 32366.42 |  | Public Works | [16 empty] | 2734.59 | 27.3333 | 68720.22 | 1.1153
| Hall |  | 350002-594 | FY 23 |  |  |  | Fashion Way | Bethany Ln | Nocturne Dr | 17.6755 | 14 | Local | [13 empty] | 11 |  |  |  | 68407.524 | See dixie Garden Dr |  | Public Works | [16 empty] | 1659.78 | 22.8 | 38004.18 | 0.61677
| Hall |  | 350002-470 | FY 22 |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 14 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-598 | FY 23 |  |  |  | Johnsontown Rd | Dixie Hwy | Trade Port Dr | 47.0122 | 14 | Min Art | [13 empty] | 22 |  |  |  | 568391 | 133030.75 |  | Public Works | [15 empty] | Applied for rubber aspahlt grant on this roadway | 7412.9412 | 36.1429 | 270662.5039 | 4.3926
| Hall |  | 350002-599 | FY 23 |  |  |  | Mark Dr | Vicki Ln | Robbins Rd | 21 | 14 | Local | [13 empty] | 0 |  |  |  | 17582.832 | See Stephan Dr |  | Public Works | [16 empty] | 407.01 | 24 | 9768.24 | 0.15853
| LP |  | 388368-36 | FY 23 |  |  |  | Medora Rd | Blevins Gap Rd | Pendleton Rd | 30 | 14 | Sec Coll | [13 empty] | 0 |  |  |  | 201498 |  |  | Public Works | [16 empty] | 5166.62 | 20 | 103332.4 | 1.677
| Hall |  | 350002-599 | FY 23 |  |  |  | Minette Ct | Stephan Dr | public dead end | 13 | 14 | Local | [13 empty] | 0 |  |  |  | 12123.108 | See Stephan Dr |  | Public Works | [15 empty] | Likely has base failures, ROW ends half way and turns private | 374.17 | 18 | 6735.06 | 0.1093
| Hall |  | 350002-594 | FY 23 |  |  |  | Nocturne Dr | Fashion Way | Blaze Way | 59 | 14 | Local | [13 empty] | 4 |  |  |  | 50247.216 | See dixie Garden Dr |  | Public Works | [16 empty] | 1163.13 | 24 | 27915.12 | 0.45304
| LP |  | 388368-36 | FY 23 |  |  |  | Pendleton Rd | Deixie Hwy | County Line |  | 14 | Collector | [13 empty] | 0 |  |  |  | 500000 |  |  | Public Works
| Hall |  | 350002-599 | FY 23 |  |  |  | Sally Dr | W Pages Ln | Stephan Dr | 36 | 14 | Local | [13 empty] | 2 |  |  |  | 46032.84 | See Stephan Dr |  | Public Works | [16 empty] | 1217.8 | 21 | 25573.8 | 0.41504
| Hall |  | 350002-599 | FY 23 |  |  |  | Stephan Dr | Dixie Hwy | Vicki Ln | 29.4396 | 14 | Local | [13 empty] | 0 |  |  |  | 100447.704 | 6375.48 |  | Public Works | [16 empty] | 2218.41 | 24.8 | 55804.28 | 0.90565
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 14 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [17 empty] | On-hold, looking to see if any state or fed funding avail | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-599 | FY 23 |  |  |  | Vicki Ln | W Pages Ln | Stephan Dr | 30.6944 | 14 | Local | [13 empty] | 2 |  |  |  | 50143.5 | See Stephan Dr |  | Public Works | [16 empty] | 1266.25 | 22 | 27857.5 | 0.4521
| LP |  | 388368-14 | FY 22 |  |  |  | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [14 empty] | 0 |  |  | 0 | 40000 | 33834.75 | August | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Locust Ave | 35 | 15 | Local | [13 empty] | 0 |  |  |  | 6959.304 |  |  | Public Works | [16 empty] | 322.19 | 12 | 3866.28 | 0.062746
| Hall |  |  | FY 23 |  |  |  | Alma Ave | Churchman Ave | Hazelwood Ave | 35.5932 | 15 | Local | [13 empty] | 15 |  |  |  | 49112.784 |  |  | Public Works | [16 empty] | 1269.19 | 21.5 | 27284.88 | 0.44281
| Hall |  | 350002-622 | FY 23 |  |  |  | Bicknell Ave | Taylor Blvd | Parthenia Ave | 25.5625 | 15 | Local | [13 empty] | 30 |  |  |  | 146000.0686 | See Chruchman |  | Public Works | [16 empty] | 2752.4779 | 28.2857 | 81111.1492 | 1.3164
| Hall |  | 350002-622 | FY 23 |  |  |  | Churchman Ave | Cayuga St | Bluegrass Ave | 22.1273 | 15 | Local | [13 empty] | 6 |  |  |  | 111811.392 | 70691.35 |  | Public Works | [16 empty] | 2384.91 | 26.4 | 62117.44 | 1.0081
| Hall |  | 350002-624 | FY 23 |  |  |  | Delmar Ct | Sadie Ln | Dead End | 27 | 15 | Local | [13 empty] | 0 |  |  |  | 22756.536 | See Estate Dr |  | Public Works | [16 empty] | 574.66 | 22 | 12642.52 | 0.20518
| Hall |  | 350002-624 | FY 23 |  |  |  | Delmar Ln | Naneen Dr | Sadie Ln | 32.8435 | 15 | Local | [13 empty] | 5 |  |  |  | 56828.736 | See Estate Dr |  | Public Works | [16 empty] | 1315.48 | 24 | 31571.52 | 0.51238
| Hall |  | 350002-624 | FY 23 |  |  |  | Estate Dr | Delmar Ln | Dead End | 19.2977 | 15 | Local | [13 empty] | 11 |  |  |  | 37388.052 | 62381.13 |  | Public Works | [16 empty] | 907.18 | 22.6667 | 20771.14 | 0.3371
| Hall |  |  | FY 23 |  |  |  | Friden Way | Manslick Rd | Tracy Way | 35.1576 | 15 | Local | [13 empty] | 0 |  |  |  | 41825.052 |  |  | Public Works | [16 empty] | 1010.87 | 23 | 23236.14 | 0.3771
| Hall |  | 350002-624 | FY 23 |  |  |  | Garvey Ct | Garvey Dr | Dead End | 50 | 15 | Local | [13 empty] | 0 |  |  |  | 9785.664 | See Estate Dr |  | Public Works | [16 empty] | 226.52 | 24 | 5436.48 | 0.088229
| Hall |  | 350002-624 | FY 23 |  |  |  | Garvey Dr | Estate Dr | Dead End | 19.068 | 15 | Local | [13 empty] | 3 |  |  |  | 48994.416 | See Estate Dr |  | Public Works | [16 empty] | 1223.68 | 22.6667 | 27219.12 | 0.44174
| Hall |  | 350002-622 | FY 23 |  |  |  | Hazelwood Ave | Bicknell Ave | Bluegrass Ave | 23.8773 | 15 | Local | [13 empty] | 10 |  |  |  | 65304.3784 | See Churchman |  | Public Works | [16 empty] | 1511.6754 | 24 | 36280.2102 | 0.5888
| Hall |  |  | FY 23 |  |  |  | Joetta Ct | Rhonda Way | Dead End | 37 | 15 | Local | [13 empty] | 0 |  |  |  | 7142.256 |  |  | Public Works | [16 empty] | 165.33 | 24 | 3967.92 | 0.064396
| Hall |  | 350002-623 | FY 23 |  |  |  | Knight Rd | Tracy Way | Manslick Rd | 21 | 15 | Local | [13 empty] | 1 |  |  |  | 21031.2 | 1881.67 |  | Public Works | [16 empty] | 531 | 22 | 11684 | 0.18962
| Hall |  | 350002-622 | FY 23 |  |  |  | La Salle Ave | Cayuga St | Bluegrass Ave | 34.3206 | 15 | Local | [13 empty] | 10 |  |  |  | 98051.346 | See Chruchman |  | Public Works | [16 empty] | 2151.96 | 25 | 54472.97 | 0.88405
| Hall |  |  | FY 23 |  |  |  | Locust Ave | Alma Ave | Old Bluegrass Ave | 43 | 15 | Local | [13 empty] | 0 |  |  |  | 9529.56 |  |  | Public Works | [16 empty] | 529.42 | 10 | 5294.2 | 0.08592
| Hall |  |  | FY 23 |  |  |  | Old Bluegrass Ave | Churchman Ave | Dead end near Locust Ave | 63.3936 | 15 | Local | [13 empty] | 0 |  |  |  | 17200.0653 |  |  | Public Works | [15 empty] | ROW ends just past Locust | 434.3451 | 22 | 9555.5918 | 0.15508
| Hall |  | 350002-624 | FY 23 |  |  |  | Rhonda Way | Naneen Dr | Garvey Dr | 45.2191 | 15 | Local | [13 empty] | 4 |  |  |  | 57205.44 |  |  | Public Works | [16 empty] | 1324.2 | 24 | 31780.8 | 0.51577
| Hall |  |  | FY 23 |  |  |  | Rolling Ridge Rd | Friden Way | Dead End | 39 | 15 | Local | [13 empty] | 0 |  |  |  | 20820.6 |  |  | Public Works | [16 empty] | 482 | 24 | 11567 | 0.18772
| Hall |  | 350002-624 | FY 23 |  |  |  | Sadie Ln | Bryce Dr | Dead End (north) | 54.408 | 15 | Local | [13 empty] | 1 |  |  |  | 24534.756 |  |  | Public Works | [16 empty] | 878.21 | 14.6667 | 13630.42 | 0.22121
| Hall |  |  | FY 23 |  |  |  | St Michael St | Ellison Ave | Dead End | 41 | 15 | Local | [13 empty] | 0 |  |  |  | 35897.4 |  |  | Public Works | [16 empty] | 712.25 | 28 | 19943 | 0.32366
| Hall |  | 350002-623 | FY 23 |  |  |  | Tracy Way | Knight Rd | Hazelwood Ave | 62.5221 | 15 | Local | [13 empty] | 1 |  |  |  | 38359.008 | See Knight Rd |  | Public Works | [16 empty] | 887.94 | 24 | 21310.56 | 0.34585
| Hall |  | 350002-619 | FY 23 |  |  |  | Barbour Manor Ct | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7000 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 7000 | [16 empty] | 4681 | 0.075969
| Hall |  | 350002-619 | FY 23 |  |  |  | Barbour Manor Dr | Barbour Ln | Dead End |  | 16 | Local | [13 empty] | 6 |  |  |  | 200000 | 88017.28 |  | Council | 8150-410-8210-148628-899998 | 200000 | [16 empty] | 117151 | 1.9013
| Hall |  | 350002-619 | FY 23 |  |  |  | Brentler Rd | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 9000 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 9000 | [16 empty] | 7123 | 0.1156
| Hall |  | 350002-619 | FY 23 |  |  |  | Debsom Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 7500 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 7500 | [16 empty] | 6759 | 0.10969
| Hall |  | 350002-619 | FY 23 |  |  |  | Jenica Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 25000 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 25000 | [16 empty] | 16165 | 0.26234
| Hall |  | 350002-619 | FY 23 |  |  |  | Machupe Ct | Machupe Dr | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 4920 | 0.079847
| Hall |  | 350002-619 | FY 23 |  |  |  | Machupe Dr | Barbour Manor Dr | Machupe Ct |  | 16 | Local | [13 empty] | 3 |  |  |  | 6000 | see Barbour Manor Dr |  | Council | 8150-410-8210-148628-899998 | 6000 | [16 empty] | 5388 | 0.087443
| Hall |  |  | FY 23 |  |  |  | Spring Farm Rd | Wolf Pen Branch Rd | 4945 Spring Farm Rd | 33.8399 | 16 | Local | [13 empty] | 0 |  |  |  | 140331.8097 |  |  | Public Works | [16 empty] | 3543.7326 | 22 | 77962.1165 | 1.2653
| Hall |  |  | FY 23 |  |  |  | Tamerlane Ct | Tamerlane Rd | Dead End | 27 | 16 | Local | [13 empty] | 0 |  |  |  | 9991.8 |  |  | Public Works | [16 empty] | 278 | 20 | 5551 | 0.090088
| Hall |  |  | FY 23 |  |  |  | Tamerlane Rd | Woodside Rd | Tuckaho Rd | 32.5001 | 16 | Local | [13 empty] | 0 |  |  |  | 41516.496 |  |  | Public Works | [16 empty] | 961.03 | 24 | 23064.72 | 0.37432
| Hall |  | 350002-619 | FY 23 |  |  |  | Therina Ct | Therina Way | Dead End |  | 16 | Local | [13 empty] | 2 |  |  |  | 6000 | see Barbour Manor Dr |  | Council | 8133-410-8210-148628-899998 | 6000 | [16 empty] | 3399 | 0.055163
| Hall |  | 350002-619 | FY 23 |  |  |  | Therina Way | Barbour Manor Dr | Dead End |  | 16 | Local | [13 empty] | 3 |  |  |  | 20000 | see Barbour Manor Dr |  | Council | 8133-410-8210-148628-899998 | 20000 | [16 empty] | 14191 | 0.23031
| Hall |  |  | FY 23 |  |  |  | Tuckaho Rd | Tamerlane Rd | 2510 Tuckaho Rd | 38 | 16 | Local | [13 empty] | 0 |  |  |  | 15400.8644 |  |  | Public Works | [16 empty] | 388.9107 | 22 | 8556.0358 | 0.13886
|  |  | 350002-618 |  |  |  |  | Bay Pointe Cir |  |  |  | 17 | Local | [18 empty] | See Bay Pointe Ct | September | Public Works
| Hall |  | 350002-618 | FY 22 |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | 111064.04 | September | [16 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-618 | FY 22 |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Bay Pointe Ct | September | [16 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-618 | FY 22 |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Bay Pointe Ct | September | [16 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-618 | FY 22 |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Bay Pointe Ct | September | [16 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-620 | FY 23 |  |  |  | Cronin Dr | Halifax Dr | Halifax Dr | 47.1575 | 17 | Local | [13 empty] | 8 |  |  |  | 84968.496 | 29227.76 |  | Public Works | [16 empty] | 1988.68 | 23.5 | 47204.72 | 0.76609
| Hall |  | 350002-620 | FY 23 |  |  |  | Glen Meadow Rd | Brownsboro Glen Rd | Spring Gate Dr | 16 | 17 | Local | [13 empty] | 4 |  |  |  | 10759.716 | See Spring Gate Dr |  | Public Works | [16 empty] | 271.71 | 22 | 5977.62 | 0.097012
| Hall |  |  | FY 23 |  |  |  | Hiawatha Ave | Heafer Rd | N English Station Rd | 26.069 | 17 | Local | [13 empty] | 5 |  |  |  | 53858.2262 |  |  | Public Works | [16 empty] | 1789.2936 | 22.25 | 29921.2368 | 0.4856
| Hall |  |  | FY 23 |  |  |  | Hines Ct | Heafer Rd | Dead End | 34 | 17 | Local | [13 empty] | 2 |  |  |  | 14106.816 |  |  | Public Works | [16 empty] | 489.82 | 16 | 7837.12 | 0.12719
| Hall |  |  | FY 23 |  |  |  | Hines Rd | Berrytown Rd | Dead End | 36.953 | 17 | Local | [13 empty] | 0 |  |  |  | 24453.3305 |  |  | Public Works | [16 empty] | 930.572 | 14 | 13585.1836 | 0.22048
| Hall |  |  | FY 23 |  |  |  | Lilly Ln | LaGrange Rd | Dead End | 40 | 17 | Local | [13 empty] | 0 |  |  |  | 48427.92 |  |  | Public Works | [16 empty] | 672.61 | 20 | 13452.2 | 0.21832
| Hall |  |  | FY 23 |  |  |  | Murphy Ln | Halifax Dr | Ballardsville Rd | 37 | 17 | Pri Coll | [13 empty] | 0 |  |  |  | 115825 |  |  | Public Works | [16 empty] | 2969.88 | 20 | 59397.6 | 0.96397
| LP |  | 388368-19 | FY 23 |  |  |  | N English Station Rd | Aiken Rd | Old Henry Rd | 31 | 17 | Min Art | [13 empty] | 0 |  |  |  | 122122 |  |  | Public Works | [16 empty] | 2423.0596 | 24 | 58153.4298 | 0.94378
| Hall |  | 350002-620 | FY 23 |  |  |  | Oak Pointe Dr (south) | Halifax Dr | Halifax Dr | 27 | 17 | Local | [13 empty] | 2 |  |  |  | 60335.712 | See Cronin Dr |  | Public Works | [16 empty] | 1396.66 | 24 | 33519.84 | 0.544
| Hall |  | 350002-620 | FY 23 |  |  |  | Spring Gate Dr | Chamberlain Ln | Stone Glen Rd | 20.3691 | 17 | Local | [13 empty] | 8 |  |  |  | 35943.264 | 47952.22 |  | Public Works | [16 empty] | 832.02 | 24 | 19968.48 | 0.32407
| Hall |  | 350002-559 | FY 22 |  |  |  | Dorsey Ln | N Hurstbourne | Nearest Joint |  | 18 | Pri Coll | [17 empty] | 41000 |  | October | Council | 8133-410-8210-148628-899998 | 41000
| LP |  | 388368-23 | FY 23 |  |  |  | Old Harrods Creek Rd | LaGrange Rd | End of Metro R/W | 32.4157 | 18 | Sec Coll | [13 empty] | 0 |  |  |  | 38914 | 61514.83 | September | Public Works | [16 empty] | 1085.356 | 19 | 19956.0265 | 0.32387
| Hall |  | 350002-559 | FY 22 |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 18 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  |  | FY 23 |  |  |  | Dorsey Way | Elsmete Cir | Dead End |  | 18 | Local | [13 empty] | 0 |  |  |  | 126000 |  |  | Council | 8133-410-8210-148628-899998 | 90000 |  | 8102-410-8210-148922-899998 | 36000 | [13 empty] | 67992 | 1.1035
| Hall |  |  | FY 23 |  |  |  | Hobbs Station Rd | Lodge Hill Rd (south) | Sable Wing Cir (south) | 34.5421 | 18 | Local | [13 empty] | 14 |  |  |  | 343037 |  |  | Public Works | [16 empty] | 4051.56 | 51.2857 | 190575.9 | 3.0929
| Hall |  |  | FY 23 |  |  |  | Talon Way | Dead End | Dead End | 30.4359 | 18 | Local | [13 empty] | 0 |  |  |  | 39874 |  |  | Public Works | [16 empty] | 1006.93 | 22 | 22152.46 | 0.35952
| Hall |  |  | FY 23 |  |  |  | UPS Dr | Whipps Mill Rd | Ormsby Station Rd | 34 | 18 | Pri Coll | [13 empty] | 2 |  |  |  | 86968 |  |  | Public Works | [16 empty] | 1238.86 | 36 | 44598.96 | 0.7238
| LP |  | 388368-26 | FY 23 |  |  |  | Aiken Rd | Bush Farm Rd | N Beckley Station Rd | 22.1639 | 19 | Sec Coll | [13 empty] | 0 |  |  | 0 | 102472 | 66225.02 | August | Public Works | [16 empty] | 2201.95 | 23.5 | 52549.75 | 0.85284
| LP |  | 388368-24 | FY 23 |  |  |  | Urton Ln | N English Station Rd | Rockbridge Rd | 51.4001 | 19 | Pri Coll | [13 empty] | 0 |  |  |  | 389882 | 354408.47 | September | Public Works | [16 empty] | 9449.3838 | 24.7143 | 199939.2989 | 3.2448
| Hall |  |  | FY 23 |  |  |  | Forest Oaks Dr | Arnold Palmer Blvd | N Beckley Station Rd | 32.0199 | 19 | Local | [13 empty] | 2 |  |  |  | 133678.548 |  |  | Public Works | [16 empty] | 3064.06 | 24 | 74265.86 | 1.2053
| Hall |  |  | FY 23 |  |  |  | Forest Trace Ct | Spring Mill Rd | Dead End | 79 | 19 | Local | [17 empty] | 7902 |  |  | Public Works | [18 empty] | 4390 | 0.071246
| Hall |  |  | FY 23 |  |  |  | Garden Hill Pl | N Beckley Station Rd | Dead End | 67 | 19 | Local | [13 empty] | 0 |  |  |  | 38556.54 |  |  | Public Works | [16 empty] | 973.65 | 22 | 21420.3 | 0.34763
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Pl | Golden Leaf Way | Dead End | 24.4599 | 19 | Local | [13 empty] | 4 |  |  |  | 37940.652 |  |  | Public Works | [16 empty] | 921.38 | 23 | 21078.14 | 0.34208
| Hall |  |  | FY 23 |  |  |  | Golden Leaf Way (all) | Forest Oaks Dr | Golden Leaf Way | 24.4823 | 19 | Local | [13 empty] | 6 |  |  |  | 80431.938 |  |  | Public Works | [16 empty] | 1933.05 | 23 | 44684.41 | 0.72519
| Hall |  |  | FY 23 |  |  |  | Greensbrook Pl | Forest Oaks Dr | Dead End | 40 | 19 | Local | [13 empty] | 2 |  |  |  | 24575.184 |  |  | Public Works | [16 empty] | 568.87 | 24 | 13652.88 | 0.22157
| Hall |  |  | FY 23 |  |  |  | Majestic Woods Pl | Forest Oaks Dr | Dead End | 68 | 19 | Local | [13 empty] | 2 |  |  |  | 15169.572 |  |  | Public Works | [16 empty] | 383.07 | 22 | 8427.54 | 0.13677
| Hall |  |  | FY 23 |  |  |  | Oakland Forest Ct | Spring Mill Rd | Dead End | 47 | 19 | Local | [13 empty] | 0 |  |  |  | 11897.28 |  |  | Public Works | [16 empty] | 275.4 | 24 | 6609.6 | 0.10727
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Ct | Rock Bay Dr | Dead End | 27.7903 | 19 | Local | [13 empty] | 3 |  |  |  | 28799.712 |  |  | Public Works | [16 empty] | 666.66 | 24 | 15999.84 | 0.25966
| Hall |  |  | FY 23 |  |  |  | Rolling Springs Pl | Rolling Springs Ct | Dead End | 53 | 19 | Local | [13 empty] | 0 |  |  |  | 12216.528 |  |  | Public Works | [16 empty] | 282.79 | 24 | 6786.96 | 0.11015
| Hall |  |  | FY 23 |  |  |  | Spring Forest Ct | Spring Forest Dr | Dead End | 36 | 19 | Local | [13 empty] | 0 |  |  |  | 8882.352 |  |  | Public Works | [16 empty] | 205.61 | 24 | 4934.64 | 0.080085
| Hall |  |  | FY 23 |  |  |  | Spring Forest Dr | Spring Mill Rd | Dead End | 31.2435 | 19 | Local | [13 empty] | 2 |  |  |  | 20158.848 |  |  | Public Works | [16 empty] | 466.64 | 24 | 11199.36 | 0.18176
| Hall |  |  | FY 23 |  |  |  | Spring Mill Pl | Spring Mill Rd | Dead End | 25 | 19 | Local | [13 empty] | 0 |  |  |  | 22846.32 |  |  | Public Works | [16 empty] | 528.85 | 24 | 12692.4 | 0.20599
| Hall |  |  | FY 23 |  |  |  | Spring Mill Rd | Rock Bay Dr | Rock Bay Dr | 33.8903 | 19 | Local | [13 empty] | 14 |  |  |  | 140905.008 |  |  | Public Works | [16 empty] | 3261.69 | 24 | 78280.56 | 1.2704
| Hall |  |  | FY 23 |  |  |  | Treeline Ct | Winding Creek Pl | Dead End | 23 | 19 | Local | [13 empty] | 0 |  |  |  | 11213.856 |  |  | Public Works | [16 empty] | 129.79 | 48 | 6229.92 | 0.10111
| Hall |  |  | FY 23 |  |  |  | Whisperwood Trace | Forest Oaks Dr | Dead End | 54 | 19 | Local | [13 empty] | 2 |  |  |  | 13030.38 |  |  | Public Works | [16 empty] | 329.05 | 22 | 7239.1 | 0.11748
| Hall |  |  | FY 23 |  |  |  | Winding Creek Ct | Winding Creek Pl | Dead End | 24 | 19 | Local | [13 empty] | 0 |  |  |  | 8396.784 |  |  | Public Works | [16 empty] | 194.37 | 24 | 4664.88 | 0.075707
| Hall |  |  | FY 23 |  |  |  | Winding Creek Pl | Oakhurst Rd | Dead End | 32.4998 | 19 | Local | [13 empty] | 4 |  |  |  | 47345.904 |  |  | Public Works | [16 empty] | 1095.97 | 24 | 26303.28 | 0.42688
| Hall |  |  | FY 23 |  |  |  | Winterbranch Way | Forest Oaks Dr | Dead End | 72 | 19 | Local | [13 empty] | 2 |  |  |  | 33957 |  |  | Public Works | [16 empty] | 857.5 | 22 | 18865 | 0.30616
| Hall |  |  | FY 23 |  |  |  | Wood Thrush Trace | Golden Leaf Pl | Dead End | 18 | 19 | Local | [13 empty] | 0 |  |  |  | 10616.4 |  |  | Public Works | [16 empty] | 245.75 | 24 | 5898 | 0.095719
| Hall |  |  | FY 23 |  |  |  | Woods View Pl | Spring Mill Rd | Dead End | 21 | 19 | Local | [13 empty] | 0 |  |  |  | 31692.384 |  |  | Public Works | [16 empty] | 733.62 | 24 | 17606.88 | 0.28574
| LP |  | 388368-31 | FY 23 |  |  |  | Chenoweth Run Rd | Taylorsville Rd | Old Heady Rd |  | 20 | Collector | [13 empty] | 0 |  |  |  | 600000 | See Old Heady Rd | October | Council/PW | 8133-410-8210-148628-899998 | 20171.81 |  | 8131-410-8210-148628-899998 | 111849.75 |  | 8125-410-8210-148628-899998 | 30910.5 |  | 8108-410-8210-148628-899998 | 55476.24 |  | 8115-410-8210-148628-899998 | 34084.92 |  |  |  |  | 321828 | 5.223
| LP |  | 388368-31 | FY 23 |  |  |  | Chenoweth Run Service Rd | Off Chenoweth Run Rd |  |  | 20 | Local | [13 empty] | 0 |  |  |  | 35000 | See Old Heady Rd | October | Council/PW | 8133-410-8210-148619-899998 | 12572.06 |  | 8123-410-8210-148619-899998 | 5273.67 |  | 8102-410-8210-148619-899998 | 17154.27
| LP |  | 388368-31 | FY 23 |  |  |  | Old Heady Rd | Taylorsville Rd | Hopewell Rd | 42.6384 | 20 | Sec Coll | [13 empty] | 10 |  |  |  | 50671 |  | October | Public Works | [16 empty] | 12887.1089 | 19.7273 | 256754.4486 | 4.1669
| Hall |  |  | FY 23 |  |  |  | Burkett Ct | Mary Dell Ln | Dead End | 52 | 20 | Local | [13 empty] | 0 |  |  |  | 24655.752 |  |  | Public Works | [16 empty] | 257.85 | 18 | 4641.3 | 0.075324
| Hall |  |  | FY 23 |  |  |  | Chenoweth Park Ln | Mary Dell Ln | Dead End (south) | 22.4943 | 20 | Local | [13 empty] | 0 |  |  |  | 55485.936 |  |  | Public Works | [16 empty] | 622.62 | 22 | 13697.64 | 0.2223
| LP |  |  | FY 23 |  |  |  | Dawson Hill Rd | Brush Run Rd | End of Metro R/W | 42.6283 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 568462 |  |  | Public Works | [16 empty] | 16893.8891 | 18.1111 | 291518.9848 | 4.7311
| Hall |  |  | FY 23 |  |  |  | Dry Ridge Ln | Dry Ridge Rd | Dead End | 18 | 20 | Local | [13 empty] | 0 |  |  |  | 7328.232 |  |  | Public Works | [16 empty] | 3076.73 | 12 | 36920.76 | 0.59919
| Hall |  |  | FY 23 |  |  |  | Hopewell Rd | Taylorsville Rd | Dead End | 23.2664 | 20 | Local | [13 empty] | 0 |  |  |  | 94449.744 |  |  | Public Works | [16 empty] | 2707.72 | 20.5 | 52472.08 | 0.85158
| Hall |  |  | FY 23 |  |  |  | Mary Dell Ln | Billtown Rd | Cynthia Dr | 26.1581 | 20 | Local | [13 empty] | 7 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 1401.16 | 22 | 30825.52 | 0.50027
| LP |  |  | FY 22 |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| LP |  | 388368-31 | FY 23 |  |  |  | Old Heady Rd | Dead End | Dead End | 18.0252 | 20 | Local | [13 empty] | 0 |  |  |  | 30000 |  |  | Public Works | [16 empty] | 669.4406 | 20 | 13388.8119 | 0.21729
| Hall |  |  | FY 23 |  |  |  | Sloane Ct | Mary Dell Ln | Dead End | 61 | 20 | Local | [13 empty] | 0 |  |  |  | 8354.34 |  |  | Public Works | [16 empty] | 226.18 | 18 | 4071.24 | 0.066073
| Hall |  | 350002-505 | FY 22 |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | 208260.52 | July | [16 empty] | Asphalt done on forum/school Need to make concrete repairs | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-609 | FY 23 |  |  |  | Campobello St | Howard St | Zeta Ct | 79 | 21 | Local | [17 empty] | 30106.944 | See Howard St |  | Public Works | [18 empty] | 16726 | 0.27145
| Hall |  | 350002-609 | FY 23 |  |  |  | Carroll Ave | Durrett Ln | Scholar St | 27.7446 | 21 | Local | [13 empty] | 0 |  |  |  | 63563.112 | See Howard St |  | Public Works | [16 empty] | 1773.87 | 20 | 35312.84 | 0.5731
| Hall |  | 350002-609 | FY 23 |  |  |  | Cavelle Ave | Durrett Ln | Dead End | 26.7981 | 21 | Local | [13 empty] | 0 |  |  |  | 58023.216 | See Howard St |  | Public Works | [16 empty] | 1790.84 | 18 | 32235.12 | 0.52315
| Hall |  |  | FY23 |  |  |  | Crittenden Dr | Grade Lane | Dead End |  | 21 | Local | [17 empty] | 790710 |  |  | Public Works | [18 empty] | 395355 | 6.4163
| Hall |  | 350002-603 | FY 23 |  |  |  | E Kenwood Dr | Southside Dr | Tecumseh Ave | 22.2323 | 21 | Pri Coll | [13 empty] | 6 |  |  |  | 90116 | 47667.64 |  | Public Works | [16 empty] | 1992.2543 | 23.2 | 46213.3095 | 0.75
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-609 | FY 23 |  |  |  | Howard St | Carroll Ave | Dead End | 35.3777 | 21 | Local | [13 empty] | 0 |  |  |  | 47118.96 | 5437 |  | Public Works | [16 empty] | 1583.17 | 16.25 | 26177.2 | 0.42483
| Hall |  | 350002-609 | FY 23 |  |  |  | Lacona Ln | Carroll Ave | Campobello St | 20 | 21 | Local | [13 empty] | 0 |  |  |  | 43749.504 | See Howard St |  | Public Works | [16 empty] | 1012.72 | 24 | 24305.28 | 0.39445
| Hall |  | 350002-622 | FY 23 |  |  |  | Meridale Ave | W Southern Heights Ave | S 2nd St | 59 | 21 | Local | [13 empty] | 2 |  |  |  | 47460.15 | See W Wellington |  | Public Works | [16 empty] | 1054.67 | 25 | 26366.75 | 0.42791
| Hall |  | 350002-622 | FY 23 |  |  |  | S 2nd St | W Southern Heights Ave | W Wellington Ave | 30.9927 | 21 | Local | [13 empty] | 10 |  |  |  | 107083.08 | See W Wellington |  | Public Works | [16 empty] | 2074.1 | 29.75 | 59490.6 | 0.96548
| Hall |  | 350002-609 | FY 23 |  |  |  | Scholar St | Carroll Ave | Campobello St | 14 | 21 | Local | [13 empty] | 0 |  |  |  | 43307.298 | See Howard St |  | Public Works | [16 empty] | 1046.07 | 23 | 24059.61 | 0.39047
| Hall |  | 350002-603 | FY 23 |  |  |  | W Kenwood Dr | Tecumseh Ave | New Cut Rd | 45.879 | 21 | Pri Coll | [13 empty] | 7 |  |  |  | 130320 | See E Kenwood |  | Public Works | [16 empty] | 2906.21 | 22.8 | 66830.86 | 1.0846
| Hall |  | 350002-622 | FY 23 |  |  |  | W Wampum Ave | S 3rd St | S 1st St | 27.4999 | 21 | Local | [13 empty] | 2 |  |  |  | 45249.516 | See W Wellington |  | Public Works | [16 empty] | 966.87 | 26 | 25138.62 | 0.40798
| Hall |  | 350002-622 | FY 23 |  |  |  | W Wellington Ave | Southern Pkwy | S 1st St | 31.391 | 21 | Local | [13 empty] | 4 |  |  |  | 80171.1 | 97498.02 |  | Public Works | [16 empty] | 1484.65 | 30 | 44539.5 | 0.72284
| Hall |  | 350002-596 | FY 23 |  |  |  | Woodmore Ave | New Cut Rd | Southside Dr | 45.5274 | 21 | Local | [13 empty] | 0 |  |  |  | 116415.36 | 1711.66 |  | Public Works | [16 empty] | 2694.8 | 24 | 64675.2 | 1.0496
| Hall |  |  | FY 23 |  |  |  | Zeta Ct | Campobello St | Dead End | 52 | 21 | Local | [13 empty] | 0 |  |  |  | 3236.76 |  |  | Public Works | [16 empty] | 89.91 | 20 | 1798.2 | 0.029183
| Hall |  | 350002-621 | FY 23 |  |  |  | Artis Pl | Artis Way | Dead End | 39 | 22 | Local | [13 empty] | 2 |  |  |  | 7681.212 |  | October | Public Works | [16 empty] | 193.97 | 22 | 4267.34 | 0.069255
| Hall |  | 350002-621 | FY 23 |  |  |  | Artis Way | Beulah Church Rd | Dead End | 39.0264 | 22 | Local | [13 empty] | 10 |  |  |  | 133542.432 |  | October | Public Works | [16 empty] | 3091.26 | 24 | 74190.24 | 1.204
| Hall |  | 350002-621 | FY 23 |  |  |  | Fox Ledge Ct | Artis Way | Dead End | 50 | 22 | Local | [13 empty] | 0 |  |  |  | 12031.56 |  | October | Public Works | [16 empty] | 334.21 | 20 | 6684.2 | 0.10848
| LP |  | 388368-30 | FY 23 |  |  |  | Johnson School Rd | Beulah Church Rd | Cedar Creek Rd | 50.9745 | 22 | Sec Coll | [13 empty] | 0 |  |  |  | 291737 |  | October | Public Works | [16 empty] | 7438.24 | 20 | 149608.76 | 2.428
| Hall |  | 350002-621 | FY 23 |  |  |  | Ledge Pointe Ct | Artis Way | Dead End | 63 | 22 | Local | [13 empty] | 0 |  |  |  | 11113.56 |  | October | Public Works | [16 empty] | 308.71 | 20 | 6174.2 | 0.1002
| Hall |  | 350002-621 | FY 23 |  |  |  | Stone Ledge Ct | Stone Ledge Rd | Dead End | 71 | 22 | Local | [13 empty] | 0 |  |  |  | 11923.848 |  | October | Public Works | [16 empty] | 368.02 | 18 | 6624.36 | 0.10751
| Hall |  | 350002-621 | FY 23 |  |  |  | Stone Ledge Rd | Artis Way | Dead End | 54.5897 | 22 | Local | [13 empty] | 2 |  |  |  | 46839.96 |  | October | Public Works | [16 empty] | 1301.11 | 20 | 26022.2 | 0.42232
| Hall |  | 350002-621 | FY 23 |  |  |  | Warrenton Hill Ct | Artis Way | Dead End | 38.1799 | 22 | Local | [13 empty] | 0 |  |  |  | 35755.2 |  | October | Public Works | [16 empty] | 993.2 | 20 | 19864 | 0.32238
| Hall |  | 350002-621 | FY 23 |  |  |  | Wellington Hill Ct | Warrenton Hill Ct | Dead End | 31 | 22 | Local | [13 empty] | 0 |  |  |  | 29155.32 |  | October | Public Works | [16 empty] | 809.87 | 20 | 16197.4 | 0.26287
| LP |  | 388368-33 | FY 23 |  |  |  | Brentlinger Ln (Old Alignment) | Dobson Ln | Dead End | 30 | 22 | Local | [13 empty] | 0 |  |  |  | 8915 | See Dobson Ln | September | Public Works | [18 empty] | 4953 | 0.080383
| LP |  | 388368-33 | FY 23 |  |  |  | Dobson Ln | Brentlinger Ln | Dead End | 17.6261 | 22 | Local | [13 empty] | 0 |  |  |  | 49091 | 52893.41 | September | Public Works | [16 empty] | 2400.0313 | 10.6667 | 27272.787 | 0.44261
| Hall |  | 391627 | FY 23 |  |  |  | Gainsborough Dr | Johnson School Rd | Annalisa Dr | 32.3999 | 22 | Local | [13 empty] | 6 |  |  |  | 87744.284 | 13412.04 |  | Public Works | [16 empty] | 2076.5444 | 23.4286 | 48746.8245 | 0.79112
| Hall |  | 350002-555 | FY 22 |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 | 118962.35 | July | PW/CIF/Local Contribution
| Hall |  | 350002-597 | FY 23 |  |  |  | Adkins Rd | Honor Ave | Dead End | 44.5373 | 23 | Local | [13 empty] | 0 |  |  |  | 43504.956 | 444366.36 | October | Public Works | [16 empty] | 1098.61 | 22 | 24169.42 | 0.39225
| Hall |  | 350002-597 | FY 23 |  |  |  | Amalfi Ave | Dead End | Honor Ave | 58.5583 | 23 | Local | [13 empty] | 0 |  |  |  | 38727.108 | See Adkins Rd | October | Public Works | [16 empty] | 940.89 | 22.6667 | 21515.06 | 0.34917
| Hall |  | 350002-597 | FY 23 |  |  |  | Beth Rd | Denise Dr | Dead End | 45.0781 | 23 | Local | [13 empty] | 0 |  |  |  | 80040.96 | See Adkins Rd | October | Public Works | [16 empty] | 1927.18 | 23.3333 | 44467.2 | 0.72166
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherita Rd | Denise Dr | Dead End | 52.2629 | 23 | Local | [13 empty] | 0 |  |  |  | 41878.98 | See Adkins Rd | October | Public Works | [16 empty] | 1057.55 | 22 | 23266.1 | 0.37759
| Hall |  | 350002-597 | FY 23 |  |  |  | Cherriville Rd | Manslick Rd | Amalfi Ave | 67 | 23 | Local | [13 empty] | 0 |  |  |  | 26279.856 | See Adkins Rd | October | Public Works | [16 empty] | 608.33 | 24 | 14599.92 | 0.23694
| Hall |  | 350002-597 | FY 23 |  |  |  | Denise Dr | Lois Ave | Dead End | 33.26 | 23 | Local | [13 empty] | 0 |  |  |  | 189163.728 | See Adkins Rd | October | Public Works | [16 empty] | 4378.79 | 24 | 105090.96 | 1.7055
| Hall |  | 350002-597 | FY23 |  |  |  | Elise Way | Shepherdsville Rd | Dead End |  | 23 | Local | [13 empty] | 0 |  |  |  | 5000 | See Adkins Rd | October
| Hall |  | 350002-597 | FY 23 |  |  |  | Honor Ave | Adkins Rd | Dead End | 50.0632 | 23 | Local | [13 empty] | 0 |  |  |  | 68010.732 | See Adkins Rd | October | Public Works | [16 empty] | 1652.42 | 22.8 | 37783.74 | 0.6132
| Hall |  | 350002-597 | FY 23 |  |  |  | Lois Ave | Beth Rd | Dead End | 58.3886 | 23 | Local | [13 empty] | 0 |  |  |  | 87275.016 | See Adkins Rd | October | Public Works | [16 empty] | 2033.95 | 23.3333 | 48486.12 | 0.78689
| Hall |  | 350002-597 | FY 23 |  |  |  | Senator Ln | Denise Dr | Honor Ave | 19 | 23 | Local | [13 empty] | 0 |  |  |  | 38432.016 | See Adkins Rd | October | Public Works | [16 empty] | 889.63 | 24 | 21351.12 | 0.34651
| Hall |  | 350002-591 | FY 23 |  |  |  | Bellflower Dr | Blue Lick Rd | Dead End | 36.645 | 24 | Local | [13 empty] | 0 |  |  |  | 24800.76 | See Bluebell Dr | September | Public Works | [16 empty] | 607.95 | 23 | 13778.2 | 0.22361
| Hall |  | 350002-591 | FY 23 |  |  |  | Bluebell Dr | Blue Lick Rd | Narcissus Dr | 48.3834 | 24 | Local | [13 empty] | 2 |  |  |  | 113040.576 | 178159.03 | September | Public Works | [16 empty] | 2616.68 | 24 | 62800.32 | 1.0192
| Hall |  | 350002-591 | FY 23 |  |  |  | Burnt Cedar Ln | Dead End | Dead End | 42 | 24 | Local | [13 empty] | 0 |  |  |  | 39631 | 68022.16 | September | Council | 8102-410-8210-148386-899998 | 3342.34 |  | 8672-410-8210-148385-899998 | 3342.34 |  | 8101-410-8210-148385-899998 | 48420.4 |  | 8137-410-8210-148385-899998 | 19301.47 |  | 8131-410-8210-148385-899998 | 1520.9 |  |  |  |  | 24019 | 0.38981
| Hall |  | 350002-591 | FY 23 |  |  |  | Cameo Ct | Pebblebrook Ln | Dead End | 33 | 24 | Local | [13 empty] | 0 |  |  |  | 7625 | See Burnt Cedar Ln | September | Council | See Burnt cedar | [17 empty] | 4621 | 0.074995
| Hall |  | 350002-591 | FY 23 |  |  |  | Cathay Ct | Linda Rd | Dead End | 35 | 24 | Local | [13 empty] | 0 |  |  |  | 17416 | See Burnt Cedar Ln | September | Council | See Burnt cedar | [17 empty] | 10555 | 0.1713
| Hall |  | 350002-591 | FY 23 |  |  |  | Delee Way | Narcissus Dr | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 15685.056 | See Bluebell Dr | September | Public Works | [16 empty] | 363.08 | 24 | 8713.92 | 0.14142
| Hall |  | 350002-591 | FY 23 |  |  |  | Narcissus Dr | Bluebell Dr | Dead End | 19.0231 | 24 | Local | [13 empty] | 2 |  |  |  | 51919.488 | See Bluebell Dr | September | Public Works | [16 empty] | 1201.84 | 24 | 28844.16 | 0.46812
| Hall |  | 350002-591 | FY 23 |  |  |  | Pebblebrook Ln | Burnt Cedar Ln | Santa Paula Ln |  | 24 | Local | [17 empty] | 5000 | See Burnt Cedar Ln | September | Council Funded | See Burnt cedar
| Hall |  | 350002-591 | FY 23 |  |  |  | Tulip Cir | Bluebell Dr | Dead End | 56 | 24 | Local | [13 empty] | 0 |  |  |  | 8485.488 | See Bluebell Dr | September | Public Works | [16 empty] | 214.28 | 22 | 4714.16 | 0.076507
| Hall |  | 350002-591 | FY 23 |  |  |  | Weigela Dr | Blue Lick Rd | Bluebell Dr | 45 | 24 | Local | [13 empty] | 0 |  |  |  | 23762.592 | See Bluebell Dr | September | Public Works | [16 empty] | 550.06 | 24 | 13201.44 | 0.21425
| Hall |  | 350002-593 | FY 23 |  |  |  | Abbydale Ct | Wood Hollow Rd | Dead End | 36 | 24 | Local | [13 empty] | 0 |  |  |  | 19077.12 | See Woodsend Rd |  | Public Works | [16 empty] | 588.8 | 18 | 10598.4 | 0.172
| Hall |  | 350002-593 | FY 23 |  |  |  | Tolkien Ct | Wood Hollow Rd | Dead End | 16 | 24 | Local | [13 empty] | 0 |  |  |  | 19069.02 | See Woodsend Rd |  | Public Works | [16 empty] | 588.55 | 18 | 10593.9 | 0.17193
| Hall |  | 350002-593 | FY 23 |  |  |  | Wood Hollow Rd | Oldshire Rd | Woodsend Rd | 37.445 | 24 | Local | [13 empty] | 6 |  |  |  | 34705.152 | See Woodsend Rd |  | Public Works | [16 empty] | 803.36 | 24 | 19280.64 | 0.31291
| Hall |  | 350002-593 | FY 23 |  |  |  | Woodsend Rd | Dead End | Dead End | 26.2616 | 24 | Local | [13 empty] | 2 |  |  |  | 34921.368 | 14281.9 |  | Public Works | [16 empty] | 1077.82 | 18 | 19400.76 | 0.31486
| LP |  | 388368-1 | FY 23 |  |  |  | Fordhaven Rd | St Anthony Church Rd | public road end | 37 | 25 | Local | [13 empty] | 0 |  |  | 0 | 70953 | See St Anthony Church Rd | August | Public Works | [16 empty] | 1359.2584 | 29 | 39418.4924 | 0.63973
| LP |  | 388368-1 | FY 23 |  |  |  | Manslick Rd | St Anthony Church Rd | Palatka Rd | 41.9559 | 25 | Pri Coll | [13 empty] | 0 |  |  | 2 | 357026 | See St Anthony Church Rd | August | Public Works | [16 empty] | 8143.41 | 22.6 | 183090.48 | 2.9714
| LP |  | 388368-1 | FY 23 |  |  |  | Springfield Dr | St Anthony Church Rd | public road end | 14 | 25 | Local | [13 empty] | 0 |  |  | 0 | 38326 | See St Anthony Church Rd | August | Public Works | [16 empty] | 887.1779 | 24 | 21292.2706 | 0.34556
| LP |  | 388368-1 | FY 22 |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [13 empty] | 0 |  |  | 0 | 390484.05 | 1025274.42 | August | [17 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-602 | FY 23 |  |  |  | Bamberrie Cross Rd | Chet Ln | 3rd Street Rd | 46.757 | 25 | Local | [13 empty] | 0 |  |  |  | 41704 | 107100.46 | September | Public Works | [16 empty] | 1053.13 | 22 | 23168.86 | 0.37601
| Hall |  | 350002-602 | FY 23 |  |  |  | Burr Ln | Carol Way | Dead End | 28 | 25 | Local | [13 empty] | 0 |  |  |  | 35239 | See Bamberrie Cross | September | Public Works | [16 empty] | 815.71 | 24 | 19577.04 | 0.31772
| Hall |  | 350002-602 | FY 23 |  |  |  | Carol Way | Manslick Rd | Chet Ln | 20.8911 | 25 | Local | [13 empty] | 0 |  |  |  | 56753 | See Bamberrie Cross | September | Public Works | [16 empty] | 1433.15 | 22 | 31529.3 | 0.51169
| Hall |  | 350002-602 | FY 23 |  |  |  | Cartledge Ct | Chet Ln | 3rd Street Rd | 45 | 25 | Local | [13 empty] | 0 |  |  |  | 33549 | See Bamberrie Cross | September | Public Works | [16 empty] | 1164.91 | 16 | 18638.56 | 0.30249
| Hall |  | 350002-602 | FY 23 |  |  |  | Chet Ln | Carol Way | Cartledge Ct | 26.9408 | 25 | Local | [13 empty] | 0 |  |  |  | 32341 | See Bamberrie Cross | September | Public Works | [16 empty] | 816.69 | 22 | 17967.18 | 0.29159
| Hall |  | 350002-595 | FY 23 |  |  |  | Constitution Dr | Manslick Rd | Dead End | 45.4192 | 25 | Local | [13 empty] | 0 |  |  |  | 49339 | See Heritage Pl | September | Public Works | [16 empty] | 1105.27 | 25 | 27410.36 | 0.44485
| Hall |  | 350002-595 | FY 23 |  |  |  | Heritage Pl | Manslick Rd | Dead End | 26 | 25 | Local | [13 empty] | 0 |  |  |  | 32230 | 105480.93 | September | Public Works | [16 empty] | 596.85 | 30 | 17905.5 | 0.29059
| Hall |  | 350002-595 | FY 23 |  |  |  | Potomac Pl | Manslick Rd | Dead End | 30 | 25 | Local | [13 empty] | 0 |  |  |  | 28850 | See Heritage Pl | September | Public Works | [16 empty] | 616.45 | 26 | 16027.7 | 0.26012
| Hall |  | 350002-595 | FY 23 |  |  |  | Quaker Ct | Constitution Dr | Dead End | 17 | 25 | Local | [13 empty] | 0 |  |  |  | 14012 | See Heritage Pl | September | Public Works | [16 empty] | 389.22 | 20 | 7784.4 | 0.12633
| LP |  | 388368-4 | FY 22 |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded | 8138-410-8107-148547-82134 | 83369.78 |  | 8146-410-8107-148547-822705 | 88630.22 |  | 8138-410-8210-148386-822702 | 19000
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 25 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 25 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [13 empty] | LWC Project in area | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 25 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [13 empty] | LWC Project in area | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 25 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [13 empty] | LWC Project in area | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-544 | FY 22 |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| Hall |  |  | FY 23 |  |  |  | Brockton Ln | Hendon Rd | Commander Dr | 41.8604 | 26 | Local | [13 empty] | 0 |  |  |  | 92931.3659 |  |  | Public Works | [16 empty] | 2239.9299 | 23 | 51628.5366 | 0.83789
| Hall |  |  | FY 23 |  |  |  | Bryan Way | Dogwood Dr | Deibel Way | 37 | 26 | Local | [13 empty] | 6 |  |  |  | 47250 |  |  | Council | 8102-410-8210-148626-899998 | 112284.06 |  | 8672-410-8210-148626-899998 | 50492.42 |  | 8131-410-8210-148626-899998 | 17653.65 |  | 8133-410-8210-148626-899998 | 28163.58 | [7 empty] | 27008 | 0.43832
|  |  |  | FY 23 |  |  |  | D26 Paving |  |  |  | 26 | [18 empty] | 122844 |  |  | Council | [19 empty] | 0
| Hall |  |  | FY 23 |  |  |  | Doreen Way | Brockton Ln | Dead End | 32 | 26 | Local | [13 empty] | 4 |  |  |  | 69295.464 |  |  | Public Works | [18 empty] | 38497 | 0.62477
| Hall |  |  | FY 23 |  |  |  | Eastside Ct | Eastside Dr | Dead End | 69 | 26 | Local | [13 empty] | 0 |  |  |  | 3877.2 |  |  | Public Works | [16 empty] | 89.75 | 24 | 2154 | 0.034958
| Hall |  |  | FY 23 |  |  |  | Eastside Dr | Manner Gate Dr | Hunsinger Ln | 18.5457 | 26 | Local | [13 empty] | 24 |  |  |  | 38431.584 |  |  | Public Works | [16 empty] | 889.62 | 24 | 21350.88 | 0.34651
| Hall |  |  | FY 23 |  |  |  | Enridge Dr | Manner Dale Dr | Landside Dr | 42 | 26 | Local | [13 empty] | 5 |  |  |  | 38500 |  |  | Council | See Bryan Way | [17 empty] | 21891 | 0.35527
| Hall |  |  | FY 23 |  |  |  | Garden View Ct | Westwood Farms Dr | Dead End | 58 | 26 | Local | [13 empty] | 0 |  |  |  | 17266.788 |  |  | Public Works | [16 empty] | 436.03 | 22 | 9592.66 | 0.15568
| Hall |  |  | FY 23 |  |  |  | Kings Hwy | Rosedale Blvd | Talisman Rd | 34.4907 | 26 | Local | [13 empty] | 0 |  |  |  | 31081.536 |  |  | Public Works | [16 empty] | 719.48 | 24 | 17267.52 | 0.28024
| Hall |  |  | FY 23 |  |  |  | Nadina Dr | Wedgewood Way | Herb Ln | 39 | 26 | Local | [13 empty] | 6 |  |  |  | 36193.95 |  |  | Public Works | [16 empty] | 874.25 | 23 | 20107.75 | 0.32633
| Hall |  |  | FY 23 |  |  |  | Plain Field Ct | Shaker Mill Rd | Dead End | 33 | 26 | Local | [13 empty] | 0 |  |  |  | 12043.548 |  |  | Public Works | [16 empty] | 304.13 | 22 | 6690.86 | 0.10859
| Hall |  |  | FY 23 |  |  |  | Rosedale Blvd | Brockton Ln | Radiance Rd | 41 | 26 | Local | [13 empty] | 6 |  |  |  | 10746.432 |  |  | Public Works | [16 empty] | 248.76 | 24 | 5970.24 | 0.096892
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Ct | Shaker Mill Rd | Dead End | 28 | 26 | Local | [13 empty] | 0 |  |  |  | 10504.692 |  |  | Public Works | [16 empty] | 265.27 | 22 | 5835.94 | 0.094712
| Hall |  |  | FY 23 |  |  |  | Shaker Mill Rd | Westwood Farms Dr | Plain Field Ct | 50.7877 | 26 | Local | [13 empty] | 8 |  |  |  | 85603.392 |  |  | Public Works | [16 empty] | 1981.56 | 24 | 47557.44 | 0.77182
| Hall |  |  | FY 23 |  |  |  | Taylorsville Rd | Brockton Ln | Dead End | 64 | 26 | Local | [13 empty] | 1 |  |  |  | 21875.328 |  |  | Public Works | [16 empty] | 759.56 | 16 | 12152.96 | 0.19723
| Hall |  |  | FY 23 |  |  |  | Wedgewood Way (north) | Brockton Ln | Herb Ln | 26.4861 | 26 | Local | [13 empty] | 4 |  |  |  | 38181.924 |  |  | Public Works | [16 empty] | 936.5 | 23 | 21212.18 | 0.34426
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Ct | Westwood Farms Dr | Dead End | 80 | 26 | Local | [13 empty] | 0 |  |  |  | 12974.94 |  |  | Public Works | [16 empty] | 327.65 | 22 | 7208.3 | 0.11698
| Hall |  |  | FY 23 |  |  |  | Westwood Farms Dr | Six Mile Ln | Plain Field Ct | 50.7893 | 26 | Local | [13 empty] | 13 |  |  |  | 117732.096 |  |  | Public Works | [16 empty] | 2395.29 | 30 | 65406.72 | 1.0615
| Hall |  |  | FY 23 |  |  |  | Greenwood Ave | S 26th St | S 29th St | 29.2162 | 1 & 4 | Local | [13 empty] | 8 |  |  |  | 100582 |  |  | Public Works | [15 empty] | alley just west of S 28th | 1582.87 | 35.5 | 55879.08 | 0.90687
| LP |  | 388368-27 | FY 23 |  |  |  | Rehl Rd | S Pope Lick Rd | S English Station Rd | 41 | 11 & 20 | Sec Coll | [13 empty] | 0 |  |  | 0 | 76297 | 79319.14 | August | Public Works | [16 empty] | 1956.3229 | 20 | 39126.4576 | 0.63499
| LP |  | 350002-631 | FY 23 |  |  |  | Chenoweth Run Rd | Blankenbaker Pkwy | Taylorsville Rd | 36.517 | 11 & 20 | Pri Coll | [13 empty] | 0 |  |  | See Bircham Rd | 196876 |  | September | Public Works | [16 empty] | 4135.4154 | 24 | 100961.8158 | 1.6385
| Hall |  |  | FY 23 |  |  |  | Summerfield Dr | Six Mile Ln | Weather Way |  | 11 & 26 | Local | [13 empty] | 17 |  |  |  | 75000 |  |  | Council | 8102-410-8210-148628-899998 | 28500 |  | 8150-410-8210-148628-899998 | 44500 |  | 8133-410-8210-148628-899998 | 2000 | [10 empty] | 112833 | 1.8312
| Hall |  | 350002-470 | FY 22 |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 & 14 | Min Art | [17 empty] | 225680 | 9956.96 | [17 empty] | On-hold, looking to see if any state or fed funding avail | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-617 | FY 22 |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 13 & 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| LP |  | 388368-20 | FY 23 |  |  |  | Hitt Rd | Ballardsville Rd | County Line | 46 | 16 & 17 | Sec Coll | [13 empty] | 5 |  |  | 0 | 18747 | 96889.36 | August | Public Works | [14 empty] | 92359.62 |  | 4369.7222 | 21.9936 | 96106 | 1.5597
| LP |  | 366368-18 | FY 23 |  |  |  | S Watterson Trl | Bardstown Rd | S Hurstbourne Pkwy | 53.8655 | 2 & 24 | Pri Coll | [13 empty] | 0 |  |  |  | 500000 | 328511.1 | September | Public Works | [16 empty] | 7830.1598 | 21.3333 | 177103.3586 | 2.8742
| LP |  | 388368-32 | FY 23 |  |  |  | Smyrna Rd | Briscoe Ln | Outer Loop | 26 | 23 & 24 | Sec Coll | [13 empty] | 0 |  |  |  | 97192 | 74662.88 | September | Public Works | [16 empty] | 2265.55 | 22 | 49842.1 | 0.80889
| Hall |  |  | FY 23 |  |  |  | Colorado Ave | Central Ave | Algonquin Pkwy | 20.2796 | 3 & 6 | Local | [13 empty] | 14 |  |  |  | 105470.388 |  |  | Public Works | [16 empty] | 2259.89 | 27.2 | 58594.66 | 0.95094
|  |  |  | FY 23 |  |  |  | W Oak St | S 13th St | S 15th St |  | 4 & 6 | Min Art | [17 empty] | 100000 | [18 empty] | Will likely need specialty equipment
| Hall |  | 350002-400 | FY 22 |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 & 9 | Min Art | [17 empty] | 88352.55 | 33402.02 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  |  | FY 23 |  |  |  | Spratt St | Goss Ave | St Michael St | 35.9444 | 6 & 15 | Local | [13 empty] | 16 |  |  |  | 74506.176 |  |  | Public Works | [16 empty] | 1171.43 | 35.3333 | 41392.32 | 0.67176
| Hall |  |  | FY 23 |  |  |  | Ellison Ave | Barret Ave | Spratt Ave | 35.6822 | 6, 10 & 15 | Local | [13 empty] | 15 |  |  |  | 166187.376 |  |  | Public Works | [16 empty] | 2429.64 | 38 | 92326.32 | 1.4984
| Hall |  |  | FY 23 |  |  |  | Chippewa Rd | Elfin Ave | Napanee Rd | 42 | 7 & 9 | Local | [13 empty] | 0 |  |  |  | 12590.424 |  |  | Public Works | [15 empty] | Big base failure north of Elfin need to complete with this work. | 317.94 | 22 | 6994.68 | 0.11352
| Hall |  |  | FY 23 |  |  |  | Commander Dr | Brockton Ln | Herb Ln | 35 | 8 & 26 | Local | [13 empty] | 1 |  |  |  | 39974.22 |  |  | Public Works | [16 empty] | 854.15 | 26 | 22207.9 | 0.36041
| Hall |  | 350002-584 | FY 22 |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 & 9 | Local | [17 empty] | 56092.95 | 121935.01 | August | [17 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Strand |  | 373479-43 | FY 23 |  |  |  | Alley paving administration | [23 empty] | 4675.92
| Strand |  | 373479-47 | FY23 |  |  |  | Crittenden Dr Striping | [23 empty] | 5650
| Strand |  | 373479-38 |  |  |  |  | Red Stone Hill study | [23 empty] | 29740
| Michael Baker |  | 387658-1 | FY 23 |  |  |  | Supplemental Inspections | [22 empty] | 71609 | 112063.14

## March 23
[22 empty] | 75 | 1 | 0.2 |  |  | 2500 | [21 empty] | LWC work done in area
Pre- Pave | Contract | SW | PO# | Date received | Est Sidewalk Start Date | From | To | Road | From | To | Rating | District | Classification | Length (ft) | Width (ft) | Surface Area (sqft) | Surface Area (SY) | Depth (in) | Volume (cf) | lbs | tons + 15% | Asphalt | Milling | Striping | MH | Historic | Estimated Ramps | Ramps/ other | Total | ADA Ramps Installed | Estimate | Actual | Actual End Date | Funding Source | Account Code #1 | Amount | Spent | Account Code #2 | Amount | Spent | Account Code #3 | Amount | Spent | Account Code #4 | Amount | Spent | Account Code #5 | Amount | Spent | Notes: | Length (ft) | Width (ft) | Area (SqFt) | Lane Miles
| Hall |  | 350002-554 |  |  | 1117 | 1499 | Cecil Ave | Hale Ave | Dead End | 47 | 1 | Local | [17 empty] | 106322.25 | 53022.19 | [18 empty] | 1429.0491 | 47.9998 | 68595 | 1.1132
| Hall |  |  |  |  | 4600 | 4799 | Clarion Ct | Lees Ln | Dead End | 45 | 1 | Local | [17 empty] | 56234 | [19 empty] | 1473.9232 | 24.6146 | 36280 | 0.58879
| Hall |  | 350002-554 |  |  | 1100 | 1199 | Ellerholt Ct | Virginia Ave | Dead End | 32 | 1 | Local | [17 empty] | 13061.85 | See Cecil Ave | [18 empty] | 324 | 26 | 8427 | 0.13676
| Hall |  | 350002-554 |  |  | 4000 | 4299 | Fordson Way | S 43rd St | S 41st St | 26.706 | 1 | Local | [17 empty] | 58683.4185 | See Cecil Ave | [18 empty] | 1316.89 | 28.5 | 37860.27 | 0.61444
| Hall |  | 350002-441 |  |  | 2600 | 4427 | Greenwood Ave | S 29th St | Cecil Ave | 40.0694 | 1 | Local | [17 empty] | 311221.4 | 245434.81 | [17 empty] | All paved but 2 blocks where LWC conflict is | 5697.0895 | 35.244 | 200788 | 3.2586
| Hall |  | 350002-535 |  |  |  |  | Mae Ave | Crums Ln | S Crums Ln | 27 | 1 | Sec Coll | [17 empty] | 23741.652 | See S Crums Ln | [18 empty] | 654.04 | 22 | 14388.88 | 0.23352
| Hall |  |  |  |  | 1032 | 1299 | S 28th St | Dumesnil St | Greenwood Ave | 35.034 | 1 | Local | [17 empty] | 109708.752 | [19 empty] | 2022.34 | 35 | 70779.84 | 1.1487
| Hall |  |  |  |  | 2100 | 2136 | S 39th St | Algonquin Pky | I264 Ramp | 33 | 1 | Local | [17 empty] | 110276 | [18 empty] | Concrete LWC Main replacement area | 862 | 32 | 27569 | 0.44742
| Hall |  |  |  |  | 1800 | 2125 | S 40th St | Dead End | I 264 Ramp | 36.1451 | 1 | Local | [13 empty] | 3 |  |  |  | 52188.5 | [18 empty] | Concrete by I264, asphalt on other side of Algonquin, LWC Main replacement Area | 1342.9409 | 25.0718 | 33670 | 0.54643
| Hall |  |  |  |  | 2000 | 2199 | S 41st St | Dead End | Bells Ln | 41.1041 | 1 | Local | [13 empty] | 1 |  |  |  | 64010.35 | [18 empty] | SW connection should be made in SE corner @ Algonquin extending sidewalk to intersection. Concrete Rd next to Ernst. , LWC Main replacement Area | 1717.4638 | 24.0453 | 41297 | 0.67021
| Hall |  | 350002-554 |  |  | 1100 | 1401 | S 41st St | Hale Ave | Dead End | 48 | 1 | Local | [17 empty] | 58766.7 | See Cecil Ave | [18 empty] | 1354.0409 | 28.0006 | 37914 | 0.61531
| Hall |  | 350002-554 |  |  | 1140 | 1199 | S 42nd St | Hale Ave | Virginia Ave | 62 | 1 | Local | [17 empty] | 23591 | See Cecil Ave | [18 empty] | 507 | 30 | 15220 | 0.24701
| Hall |  | 350002-535 |  |  | 2958 | 3299 | S Crums Ln | Mae Ave | Cane Run Red | 51 | 1 | Pri Coll | [17 empty] | 155675.85 | 29122.48 | [18 empty] | 4193.0788 | 22.5011 | 94349 | 1.5312
| Hall |  | 350002-554 |  |  | 4100 | 4299 | Winnrose Way | S 43rd St | Cecil Ave | 27 | 1 | Local | [17 empty] | 37463.5 | See Cecil Ave | [18 empty] | 1007 | 24 | 24170 | 0.39226
| LP |  | 339051-94 |  |  | 1200 | 1399 | Dahl Rd | Guest Ave | Poplar Level Rd | 39 | 2 | Sec Coll | [17 empty] | 93299.25 | 82228.33 | August | [17 empty] | 3141.3701 | 18.0001 | 56545 | 0.91768
| Hall |  | 350002-532 |  |  | 5200 | 7399 | Jefferson Blvd | Fern Valley Rd | McCawley Rd | 41.2016 | 2 | Min Art | [17 empty] | 682945.8463 | 367774.58 | November | [17 empty] | 6319.7901 | 64.25 | 390254.7693 | 6.3335
| Hall |  | 350002-536 |  |  | 1915 | 2135 | ***Buechel Bank Rd *** | Barley Ave | Bruce Ave | 27 | 2 | Pri Coll | [17 empty] | 139301.25 | 73605.48 | [17 empty] | Need to confirm when time gets closer if this roadway should be paved or if it will be widened as part of the planned LPA project. | 4105.8567 | 20.5621 | 84425 | 1.3701
| Hall |  | 350002-567 |  |  | 4900 | 4999 | Applegrove Ln | Newport Rd | Newport Rd | 65 | 2 | Local | [17 empty] | 30403.25 | [19 empty] | 980.7477 | 20 | 19615 | 0.31833
| Hall |  | 350002-567 |  |  | 4600 | 4699 | Beechbrook Rd | Kranet Wat | Belrad Dr | 14 | 2 | Local | [17 empty] | 23000.45 | [19 empty] | 618 | 24 | 14839 | 0.24082
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Belrad Dr | Beechbrook Rd | Fegenbush Ln | 15.0981 | 2 | Local | [17 empty] | 53955.5089 | [19 empty] | 1453.7355 | 24 | 34810.0057 | 0.56494
| Hall |  | 350002-536 |  |  | 2136 | 2199 | Buechel Bank Rd | Bruce Ave | Bardstown Rd | 26 | 2 | Local | [17 empty] | 22273.5 | See Buechel Bank Rd | [18 empty] | 674 | 24 | 14370 | 0.23321
| Hall |  | 350002-567 |  |  |  |  | Cawood Dr | Newport Rd | Belrad Dr | 30 | 2 | Local | [17 empty] | 30914.037 | [19 empty] | 906.57 | 22 | 19944.54 | 0.32368
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Coram Way | Dead End | Sebree Ln | 26 | 2 | Local | [17 empty] | 16947.7 | [19 empty] | 421 | 26 | 10934 | 0.17745
| Hall |  | 350002-536 |  |  | 3800 | 4099 | Handley Ave (West) | Dead End | Buechel Bank Rd | 19 | 2 | Local | [17 empty] | 56035.6 | [19 empty] | 1291 | 28 | 36152 | 0.58672
| Hall |  | 350002-567 |  |  | 4400 | 4499 | Kern Ct | Dead End | Fegenbush Ln | 54 | 2 | Local | [17 empty] | 16209.9 | [19 empty] | 349 | 30 | 10458 | 0.16972
| Hall |  | 350002-567 |  |  | 4300 | 4499 | Kranet Way | Beechbrook Rd | Sebree Ln | 34 | 2 | Local | [17 empty] | 24753.5 | [19 empty] | 614 | 26 | 15970 | 0.25918
| Hall |  | 350002-567 |  |  | 4200 | 4499 | Newport Rd | Fegenbush Ln | Dead End | 20 | 2 | Local | [17 empty] | 77431.8 | [19 empty] | 1561.1217 | 32.0001 | 49956 | 0.81074
| Hall |  | 350002-567 |  |  | 4700 | 4899 | Sebree Ln | Kranet Way | Belrad Dr | 23 | 2 | Local | [17 empty] | 29803.4 | [19 empty] | 740 | 26 | 19228 | 0.31205
| LP |  | 339051-104 |  |  | 100 | 13399 | Ralph Ave | Dixie Hwy | Gerald Dr | 42.0628 | 3 | Pri Coll | [16 empty] | 3 | 323726.898 | 333341.38 | December | [17 empty] | 8488.84 | 24.375 | 196198.12 | 3.1841
| Hall |  | 350002-471 |  |  | 2930 | 3499 | Wilson Ave | W Hill St | Algonquin Pky | 42 | 3 | Min Art | [17 empty] | 198968 | 162565.9 | November | [17 empty] | 2879.4147 | 39.4858 | 113696 | 1.8452
| Hall |  | 350002-568 |  |  |  |  | Bolling Ave | Dixie Hwy | S 17th St | 20 | 3 | Local | [17 empty] | 67784.6 | [19 empty] | 1566.7757 | 27.9121 | 43732 | 0.70973
| Hall |  | 350002-568 |  |  |  |  | McCloskey Ave | W Hill St | W Burnett Ave | 56 | 3 | Local | [17 empty] | 31238.7 | [19 empty] | 629.7976 | 32.0008 | 20154 | 0.32708
| Hall |  | 350002-568 |  |  |  |  | S 17th St | W Hill St | W Burnett Ave | 34 | 3 | Local | [17 empty] | 28873.4 | [19 empty] | 620.9462 | 29.9994 | 18628 | 0.30232
| Hall | [6 empty] | S 23rd & Becker Ct intersection |  |  |  | 3 | Local | [17 empty] | 50000 | [22 empty] | 0
| Hall |  |  |  |  | 2200 | 2299 | S 23rd St | Wingfield Ln | Hardesty Ave | 61.3757 | 3 | Local | [17 empty] | 21154.4 | [19 empty] | 758.2057 | 18.0004 | 13648 | 0.2215
| Hall |  | 350002-568 |  |  |  |  | W Burnett Ave | Dixie Hwy | S 17th St | 47 | 3 | Local | [17 empty] | 50573.4 | [19 empty] | 1483.122 | 21.9995 | 32628 | 0.52952
| Hall |  | 350002-401 |  |  | 100 | 199 | Cabel St | Story Ave | Franklin St | 40.443 | 4 | Local | [17 empty] | 45134.45 | 39763.92 | August | [17 empty] | 798.6543 | 36.4601 | 29119 | 0.47258
| Hall |  | 350002-401 |  |  | 600 | 1299 | E Washington St | N Hancock St | Cabel St | 57.3852 | 4 | Local | [17 empty] | 203087.2 | See Cabel St | August | [17 empty] | 3881.86 | 33.7529 | 131024 | 2.1264
| Hall |  | 350002-455 |  |  |  |  | Woodbine St | 521 Woodbine St | Dead End |  | 4 | Local | [17 empty] | 12500 | 17509.02 | August | Council | 8102-410-8105-148223-822702 | 3432.86 |  | 8138-410-8107-148223-822702 | 9067.14 | [13 empty] | 7841 | 0.12725
| Hall |  | 350002-454 |  |  | 2200 | 2399 | W Jefferson St | S 22nd St | S 24th St | 34.2662 | 4 | Local | [17 empty] | 113532.85 | 271075.53 | July | [17 empty] | 1220.7901 | 59.9997 | 73247 | 1.1887
| Hall |  | 350002-467 |  |  |  |  | YUM Center Ramps | On Main St |  |  | 4 | [18 empty] | 35000 | 36083.36 | July | [16 empty] | $1400 charged against PO 350002-549 |  |  |  | 0
| Hall |  |  |  |  | 500 | 699 | Barrett Ave | E Broadway | Baxter Ave | 25 | 4 | Local | [17 empty] | 98990.75 | [19 empty] | 1691 | 39 | 63865 | 1.0365
| Hall |  | 350002-472 |  |  | 100 | 899 | E Chestnut St | S 1st St | S Campbell St | 58 | 4 | Min Art | [17 empty] | 326676 | [19 empty] | 4583.8785 | 40.7236 | 186672 | 3.0295
| Hall |  | 350002-400 |  |  | 1100 | 1199 | E Liberty St | Baxter Ave | Cooper St | 46 | 4 | Min Art | [17 empty] | 88352.55 | 21852.98 | [18 empty] | 764.9525 | 70.0004 | 53547 | 0.86902
| Hall |  | 350002-400 |  |  | 100 | 399 | E Liberty St | S 1st St | S Preston St | 57.286 | 4 | Min Art | [17 empty] | 145539.9 | See E Liberty above | [18 empty] | 1709.9099 | 51.5852 | 88206 | 1.4315
| Hall |  | 350002-472 |  |  | 800 | 999 | E Madison St | S Shelby St | Dead End | 29 | 4 | Local | [17 empty] | 63942.15 | [19 empty] | 1114.5147 | 37.0152 | 41253 | 0.6695
| Hall |  | 350002-472 |  |  | 100 | 1099 | E Muhammad Ali Blvd | S 1st St | E Chestnut St | 53 | 4 | Min Art | [17 empty] | 374336.9175 | [19 empty] | 5484.79 | 39 | 213906.81 | 3.4715
| Hall |  | 350002-565 |  |  |  |  | Guthrie St | S 2nd St | S 4th St |  | 4 | Local | [17 empty] | 50000 | [18 empty] | Pave only that which had not been paved previously. No ramps
| Hall |  |  |  |  | 100 | 199 | N 9th St | W Main St | W Washington St | 37 | 4 | Local | [17 empty] | 14171.65 | [19 empty] | 254 | 36 | 9143 | 0.14838
| Hall |  | 350002-472 |  |  | 136 | 299 | N Shelby St | Franklin St | E Witherspoon St | 35 | 4 | Pri Coll | [17 empty] | 54247.05 | [19 empty] | 966.9876 | 33.9994 | 32877 | 0.53357
| Hall |  |  |  |  | 100 | 199 | Roy Wilkins Ave | I 64 Ramp | W Market St | 20 | 4 | Local | [17 empty] | 28657.95 | [19 empty] | 514 | 36 | 18489 | 0.30006
| Hall |  |  |  |  | 616 | 699 | Rubel Ave | Payne St | E Broadway | 19 | 4 | Local | [17 empty] | 34380.55 | [19 empty] | 619.8365 | 36 | 22181 | 0.35998
| Hall |  | 350002-472 |  |  | 100 | 629 | S Campbell St | E Main St | Dead End | 21 | 4 | Local | [17 empty] | 184008.25 | [19 empty] | 3063.1175 | 38.7563 | 118715 | 1.9266
| Hall |  | 350002-472 |  |  |  |  | S Clay St | E Jefferson | E Muhammad Ali | ? | 4 | Local | [17 empty] | 150444 | [18 empty] | complete rebuild | 995 | 36 | 35820 | 0.58133
| Hall |  | 350002-399 |  |  | 600 | 699 | S Floyd St | E Chestnut St | E Broadway | 66.7115 | 4 | Pri Coll | [17 empty] | 62261.1 | 30131.58 | [18 empty] | 943.3255 | 40.001 | 37734 | 0.61239
| Hall |  |  |  |  | 800 | 899 | W Washington St | N 8th St | N 9th St | 26 | 4 | Local | [17 empty] | 14680.05 | [19 empty] | 474 | 20 | 9471 | 0.15371
| Hall |  | 350002-459 |  |  | 4400 | 4699 | Jewell Ave | S 44th St | Northwestern Pky | 42.7378 | 5 | Local | [17 empty] | 51884.7 | 47172.62 | July | [17 empty] | 1142.4877 | 29.2992 | 33474 | 0.54325
| Hall |  | 350002-363 |  |  | 4500 | 4530 | Southwestern Pky | S Shawnee Ter | Shawnee Park Dr | 44.1611 | 5 | Min Art | [17 empty] | 42518.85 | See Southwestern Pkwy | July | [17 empty] | 1073.6733 | 24.0008 | 25769 | 0.41821
| Hall |  | 350002-363 |  |  | 1900-04-09 | 1900-07-17 | Southwestern Pky | Northwestern Pky | W Market St | 57 | 5 | Min Art | [17 empty] | 18273.75 | 294173.52 | July | [17 empty] | 425.9801 | 25.9989 | 11075 | 0.17974
| Hall |  | 350002-454 |  |  | 2400 | 2999 | W Jefferson St | S 24th St | S 30th St | 34.3089 | 5 | Local | [17 empty] | 183603.7 | See W Jefferson | July | [17 empty] | 2634.7773 | 44.9579 | 118454 | 1.9224
| Hall |  | 350002-312 |  |  | 700 | 799 | Cedar Grove Ct | Northwestern Pky | Rudd Ave | 45 | 5 | Local | [17 empty] | 16371.1 | [18 empty] | This is a private Roadway | 528 | 20 | 10562 | 0.17141
| Hall |  |  |  |  | 2600 | 2999 | Cedar St | S 26th St | S 30th St | 26 | 5 | Local | [17 empty] | 83166.8 | [19 empty] | 1794.7087 | 29.8968 | 53656 | 0.87079
| Hall |  |  |  |  | 3100 | 3199 | Larkwood Ave | S 32nd St | Dead End | 25 | 5 | Local | [17 empty] | 13483.45 | [19 empty] | 362 | 24 | 8699 | 0.14118
| Hall |  |  |  |  | 200 | 549 | S 30th St | W Market St | W Madison St | 19 | 5 | Local | [17 empty] | 109563.3 | [19 empty] | 1963.5 | 36 | 70686 | 1.1472
| Hall |  |  |  |  | 500 | 619 | S 31st St | W Madison St | Dead End | 17 | 5 | Local | [17 empty] | 33046 | [19 empty] | 710.6708 | 29.9998 | 21320 | 0.34601
| Hall |  |  |  |  | 200 | 599 | S 32nd St | River Park Dr | W Market St | 41 | 5 | Local | [17 empty] | 120216.45 | [19 empty] | 2370.8763 | 32.7132 | 77559 | 1.2587
| Hall | [6 empty] | S/N 34th St | W Market St | N 35th St | 18.3722 | 5 | Local | [17 empty] | 123495.785 | [19 empty] | 2951.4 | 27 | 79674.7 | 1.2931
| Hall | [6 empty] | S/N Shawnee Ter | W Market St | Duncan St | 29.667 | 5 | Local | [17 empty] | 46620.6675 | [18 empty] | check for MSD project | 1262.51 | 19 | 24062.28 | 0.39051
| Hall |  |  |  |  | 3000 | 3223 | Vermont Ave | S 31st St | I 264 Ramp | 15 | 5 | Local | [17 empty] | 61666.75 | [19 empty] | 1105.1174 | 36.0007 | 39785 | 0.64568
| Hall | [6 empty] | Vermont Ave | S 40th St | Southwestern Pkwy | 17.7965 | 5 | Local | [17 empty] | 189887.4 | [19 empty] | 3403 | 36 | 122508 | 1.9882
| Hall |  |  |  |  | 3100 | 3199 | W Jefferson St | S 32nd St | Dead End | 79 | 5 | Local | [17 empty] | 13567.15 | [19 empty] | 337 | 26 | 8753 | 0.14205
| Hall |  |  |  |  | 2600 | 3099 | W Madison St | S 26th St | S 31st St | 29 | 5 | Local | [17 empty] | 129361.45 | [19 empty] | 2318.2741 | 36.0005 | 83459 | 1.3545
| Hall |  |  |  |  | 1800 | 2599 | Hale Ave | Dixie Hwy | S 26th St | 28 | 6 | Local | [17 empty] | 129173.9 | [19 empty] | 2777.934 | 30 | 83338 | 1.3525
| Hall |  |  |  |  | 700 | 1299 | S 6th St | W Broadway | W Ormsby Ave | 73 | 6 | Min Art | [17 empty] | 532328.0725 | [18 empty] | Possibly moving this project into FY 23 to account for bridge project | 4840.05 | 62.848 | 304187.47 | 4.9367
| Hall |  |  |  |  | 1370 | 1999 | S 7th St | S 9th St | Algonquin Pky | 46 | 6 | Maj Art | [17 empty] | 280871.5 | [19 empty] | 4905.1876 | 32.7201 | 160498 | 2.6047
| Hall |  |  |  |  | 1472 | 1499 | S Floyd St | E Burnett Ave | Dead End | 25 | 6 | Local | [17 empty] | 23454.6 | [19 empty] | 378 | 40 | 15132 | 0.24558
| Hall |  |  |  |  | 1100 | 1471 | S Floyd St | E St Catherine St | E Burnett Ave | 44 | 6 | Pri Coll | [17 empty] | 226619.25 | [19 empty] | 3710.4254 | 37.016 | 137345 | 2.229
| Hall |  |  |  |  | 1400 | 1499 | St James Ct | W Magnolia Ave | W Hill St | 18.1042 | 6 | Local | [17 empty] | 289513.6774 | [19 empty] | 2169.8398 | 71.3333 | 186783.0177 | 3.0313
| Hall |  |  |  |  | 1800 | 2399 | St Louis Ave | Dixie Hwy | Wilson Ave | 52 | 6 | Local | [17 empty] | 85482.5 | [19 empty] | 1969.6265 | 28 | 55150 | 0.89504
| Hall |  |  |  |  | 100 | 699 | W Oak St | S 1st St | S 7th St | 38 | 6 | Min Art | [17 empty] | 183590.75 | [19 empty] | 2820.555 | 37.1945 | 104909 | 1.7026
| Hall |  | 350002-394 |  |  | 1400 | 1499 | Lancaster Essex Ct | Greenlawn Rd | Dead End | 53 | 7 | Local | [17 empty] | 14213.5 | 18123.68 | July | [17 empty] | 458.5225 | 20 | 9170 | 0.14882
| Hall |  | 350002-394 |  |  | 7100 | 7299 | Wesboro Rd | Herr Ln | Hayward Rd | 66.1274 | 7 | Local | [17 empty] | 92609.4 | 105317.36 | July | [17 empty] | 2489.4842 | 24.0002 | 59748 | 0.96966
| Hall |  | 350002-564 |  |  | 9500 | 9599 | Erin Way | Millgate Rd | Meadowgate Ln | 50 | 7 | Local | [17 empty] | 21726.35 | 7746.71 | [17 empty] | portion may be in Lyndon | 584 | 24 | 14017 | 0.22748
| Hall |  | 350002-564 |  |  | 1700 | 1899 | Flagstaff Ct | Dead End | Dead End | 32 | 7 | Local | [17 empty] | 25137.9 | 12122.47 | [18 empty] | 900.9905 | 18.0002 | 16218 | 0.2632
| Hall |  | 350002-541 |  |  | 1000 | 1499 | Lyndon Ln | Herr Ln | Westport Rd | 30 | 7 | Pri Coll | [17 empty] | 99389.4 | 13421.2 | [18 empty] | 2502 | 24 | 60236 | 0.97758
| Hall |  | 350002-564 |  |  | 1900 | 1999 | Maricopa Ct | Dead End | Farnham Dr | 61 | 7 | Local | [17 empty] | 13979.45 | 4892.93 | [18 empty] | 501.0822 | 18 | 9019 | 0.14637
| Hall |  | 350002-564 |  |  | 2000 | 2099 | Maricopa Dr | Farnham Dr | Creekwood Rd | 42 | 7 | Local | [17 empty] | 11945.85 | See Maricopa Ct | [17 empty] | portion may be in Meadowbrook Farm | 428.1743 | 18 | 7707 | 0.12508
| Hall |  | 350002-486 |  |  |  |  | Dudley Ave | Highland Ave | Dead End | 15 | 8 | Local | [17 empty] | 12000 | See Highland Ave | October | [17 empty] | 209.31 | 12 | 2511.72 | 0.040763
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Ellwood Ave | Baxter Ave | Bardstown Rd | 29 | 8 | Local | [17 empty] | 32746.85 | 25669.75 | October | [17 empty] | 621 | 34.0209 | 21127 | 0.34287
| Hall |  | 350002-486 |  |  |  |  | Highland Ave | Baxter Ave | Dudley Ave | 21.2016 | 8 | Local | [17 empty] | 61295.37 | 52409.65 | October | [17 empty] | 1445.54 | 27.5 | 39545.4 | 0.64179
| Hall |  | 350002-474 |  |  | 1600 | 1699 | Bonnycastle Ter | Bonnycastle Ave | Bonnycastle Ave | 24 | 8 | Local | [17 empty] | 45000 | 26315.86 | September | [17 empty] | 1265.37 | 18 | 22776.66 | 0.36965
| Hall |  | 350002-482 |  |  | 1 | 2699 | Denham Rd | Valletta Rd | Pee Wee Reese Rd | 49 | 8 | Local | [17 empty] | 53611.4 | 155192.24 | September | [17 empty] | 1631.927 | 21.1946 | 34588 | 0.56133
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Drayton Dr | Denham Rd | Taylorsville Rd | 21 | 8 | Local | [17 empty] | 56725.35 | See Denham Rd | September | [17 empty] | 1743 | 20.9966 | 36597 | 0.59394
| Hall |  | 350002-482 |  |  | 2500 | 2599 | Gladstone Ave | Taylorsville Rd | Dead End | 12 | 8 | Local | [17 empty] | 13528.4 | See Denham Rd | September | [17 empty] | 423.4543 | 20.6114 | 8728 | 0.14165
| Hall |  | 350002-482 |  |  | 2600 | 2699 | Landor Ave | Denham Rd | Taylorsville Rd | 24 | 8 | Local | [17 empty] | 45160.8 | See Denham Rd | September | [17 empty] | 1457 | 19.9973 | 29136 | 0.47285
| Hall |  | 350002-482 |  |  | 2600 | 2699 | McCoy Way | Trevilian Way | Gladstone Ave | 56 | 8 | Local | [17 empty] | 56283.6 | See Denham Rd | September | [17 empty] | 1512.9948 | 24.0001 | 36312 | 0.58931
| Hall |  |  |  |  | 2800 | 2899 | Alta Vista Ct | Alta Vista Rd | Dead End | 34 | 8 | Local | [17 empty] | 42573.85 | [18 empty] | LG&E conflict | 1525.9359 | 18.0001 | 27467 | 0.44577
| Hall |  |  |  |  | 700 | 999 | Alta Vista Rd | Lexington Rd | Maple Rd | 47 | 8 | Local | [17 empty] | 56092.95 | [19 empty] | 1644.9194 | 22.0005 | 36189 | 0.58732
| Hall |  | 350002-473 |  |  | 1600 | 1699 | Lucia Ave | Baxter Ave | Bardstown Rd | 10 | 8 | Local | [17 empty] | 44635.35 | [19 empty] | 800 | 36 | 28797 | 0.46735
| Hall |  | 350002-506 | 43 | 20 | Local | 2999 | Cleveland Blvd | N Birchwood Ave | University Rd | 12 | 9 | Local | [17 empty] | 19898.9 | See Riedling Dr | December | [17 empty] | 642 | 20 | 12838 | 0.20835
| Hall |  | 350002-506 | 63 | 20 | Local | 2899 | Fleming Ave | N Hite Ave | N Birchwood Ave | 46 | 9 | Local | [17 empty] | 44207.55 | See Riedling Dr | December | [17 empty] | 1426.064 | 19.9998 | 28521 | 0.46287
| Hall |  | 350002-506 | 68 | 20 | Local | 2699 | Le Blanc Ct | N Hite Ave | Dead End | 37 | 9 | Local | [17 empty] | 7230.75 | See Riedling Dr | December | [17 empty] | 212 | 22 | 4665 | 0.075709
| Hall |  | 350002-506 | 67 | 20 | Local | 2999 | Moran Pl | Ridgedale Rd | Dead End | 11 | 9 | Local | [17 empty] | 8277 | See Riedling Dr | December | [17 empty] | 243 | 22 | 5340 | 0.086664
| Hall |  | 350002-506 | 68 | 20 | Local | 499 | N Birchwood Ave | Brownsboro Rd | Cleveland Blvd | 23 | 9 | Local | [17 empty] | 77242.7 | See Riedling Dr | December | [17 empty] | 1916.6368 | 26.0008 | 49834 | 0.80876
| Hall |  | 350002-506 | 43 | 20 | Local | 399 | Ridgedale Rd | Brownsboro Rd | Dead End | 12 | 9 | Local | [17 empty] | 27047.5 | See Riedling Dr | December | [17 empty] | 754.6547 | 23.1232 | 17450 | 0.2832
| Hall |  | 350002-506 | 28 | 20 | Local | 2999 | Riedling Dr | Thistlewood Dr | Zorn Ave | 44 | 9 | Local | [17 empty] | 102264.35 | 277953.26 | December | [17 empty] | 3068.9028 | 21.4986 | 65977 | 1.0707
| Hall |  | 350002-506 | 54 | 20 | Local | 499 | University Ave | Brownsboro Rd | Regan Ave | 34 | 9 | Local | [17 empty] | 44973.25 | See Riedling Dr | December | [17 empty] | 1390.1485 | 20.8719 | 29015 | 0.47089
| Hall |  | 350002-506 |  |  |  |  | Cornell and Iola | Lexington Rd | St Mathew boundry (North) |  | 9 | Local | [18 empty] | 3986.35 | October | [16 empty] | Hall was paving the remainder of these blocks for St Mathews
| Hall |  |  | 39 | 20 | Local |  | S Peterson Dr Brick Repair |  |  |  | 9 | Local | [17 empty] | 4950 | 650 | September | CIF | 8138-410-8107-148818-821344 | 4950 | [13 empty] | Completed by roads. Contractor showed up, have to pay for mobilization. PW will cover these costs. |  |  |  | 0
| Hall |  |  | 67 | 20 | Local | 2527 | Grinstead Dr | Lexington Rd | S Petterson Ave | 54 | 9 | Min Art | [17 empty] | 185858.75 | [19 empty] | 1938.5246 | 54.7865 | 106205 | 1.7236
| Hall |  | 350002-475 | 45 | 20 | Local | 3099 | Ashview Ter | English Ave | Dead End | 33 | 10 | Local | [17 empty] | 14115.85 | See Clarks Ln | September | [17 empty] | 350 | 26 | 9107 | 0.1478
| Hall |  | 350002-475 | 38 | 20 | Local | 1099 | Clarks Ln | Preston Hwy | Poplar Level Rd | 55 | 10 | Pri Coll | [17 empty] | 157900.05 | 621992.76 | September | [17 empty] | 4433.884 | 21.5831 | 95697 | 1.5531
| Hall |  | 350002-475 | 26 | 20 | Local | 2599 | E Burnett Ave | Clarks Ln | French Ave | 57 | 10 | Local | [17 empty] | 49660.45 | See Clarks Ln | September | [17 empty] | 1662.8415 | 19.2676 | 32039 | 0.51997
| Hall |  | 350002-475 | 58 | 20 | Local | 1199 | English Ave | Meade Ave | Harrison Ave | 47 | 10 | Local | [17 empty] | 17392.55 | See Clarks Ln | September | [17 empty] | 527.1789 | 21.285 | 11221 | 0.18211
| Hall |  | 350002-475 |  |  | 1500 | 2599 | Filson Ave | Clarks Ln | French Ave | 67 | 10 | Local | [17 empty] | 47177.35 | See Clarks Ln | September | [17 empty] | 1690.9463 | 18.0006 | 30437 | 0.49397
| Hall |  | 350002-475 |  |  | 800 | 999 | French Ave | Colin Ave | Filson Ave | 67 | 10 | Local | [17 empty] | 41256.35 | See Clarks Ln | September | [17 empty] | 1377.761 | 19.319 | 26617 | 0.43197
| Hall |  | 350002-475 |  |  | 3000 | 3099 | Greenup Rd | McKinley Ave | Hess Ln | 46 | 10 | Local | [17 empty] | 31426.25 | See Clarks Ln | September | [17 empty] | 1128.8777 | 17.9603 | 20275 | 0.32905
| Hall |  | 350002-475 |  |  | 2500 | 2999 | Greenup Rd | Thruston Ave | Dead End | 57 | 10 | Local | [17 empty] | 30784.55 | See Clarks Ln | September | [17 empty] | 1139.5186 | 17.4302 | 19861 | 0.32233
| Hall |  | 350002-475 |  |  | 2900 | 3099 | Meade Ave | McKinley Ave | Hess Ln | 28 | 10 | Local | [17 empty] | 31987.35 | See Clarks Ln | September | [17 empty] | 1146.4449 | 18.0009 | 20637 | 0.33492
| Hall |  | 350002-475 |  |  |  |  | Parkway Dr | Alexander Ave | Poplar Level Rd |  | 10 | Local | [18 empty] | See Clarks Ln | September | [19 empty] | 66603 | 1.0809
| Hall |  | 350002-475 |  |  | 800 | 1099 | Thruston Ave | Parklawn Dr | Poplar Level Rd | 38 | 10 | Local | [17 empty] | 91984.75 | See Clarks Ln | September | [17 empty] | 3297.0021 | 17.9997 | 59345 | 0.96312
| Hall |  | 350002-485 |  |  | 3000 | 3199 | Debra Way | McMahan Blvd | Sunrise Way | 44 | 11 | Local | [17 empty] | 68713.05 | 51940.01 | August | [17 empty] | 1847.1254 | 24 | 44331 | 0.71945
| Hall |  | 350002-485 |  |  | 4000 | 4099 | Hope Ct | Hunsinger Ln | Dead End | 38 | 11 | Local | [17 empty] | 7475.65 | Dee Debra Way | August | [17 empty] | 185 | 26 | 4823 | 0.078273
| Hall |  | 350002-463 |  |  |  |  | Hunsinger Gardens Road Repairs |  |  |  | 11 | [18 empty] | 20000 | 10500 | July | Council Funds | 8123-410-8107-148411-822702 | 15774.47 |  | 8133-410-8107-148411-822702 | 1560.37 |  | 8102-410-8105-148411-822702 | 2665.16 | [11 empty] | 0
| Hall |  | 350002-556 |  |  |  |  | Briarglen Ln | Dead End | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 15513 | 0.25176
| Hall |  | 350002-556 |  |  |  |  | Brody Ln | Ridgehurst Pl | Dead End |  | 11 | [21 empty] | CIF | 8148-410-8107-148573-822702 | 117000 | [16 empty] | 15086 | 0.24483
| Hall |  | 350002-556 |  |  |  |  | Brookglen Ct | Stonydale Ln | Dead End |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 11656 | 0.18917
| Hall | [6 empty] | Coverbrook Ct | Stonyrun Dr | Dead End |  | 11 | Local
| Hall |  |  |  |  | 3800 | 3999 | Fieldside Cir | Ridgehurst Pl | Ridgehurst Pl | 40 | 11 | Local | [17 empty] | 59166.6 | [19 empty] | 1654.3968 | 23.0725 | 38172 | 0.6195
| Hall |  | 350002-557 |  |  |  |  | Greenbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 6221 | 0.10096
| Hall |  |  |  |  | 3800 | 3899 | Ridgehurst Ct | Ridgehurst Pl | Dead End | 61 | 11 | Local | [17 empty] | 19182.8 | [19 empty] | 563 | 21.9822 | 12376 | 0.20085
| Hall |  |  |  |  | 2500 | 2699 | Six Mile Ln | Taylorsville Rd | Old Six Mile Ln | 40.3583 | 11 | Pri Coll | [17 empty] | 81156.5193 | [19 empty] | 2050.0975 | 25.6667 | 49185.7693 | 0.79824
| Hall |  |  |  |  | 2900 | 2999 | Six Mile Ln | Green Garden Ct | Stony Brook Dr | 41.775 | 11 | Pri Coll | [17 empty] | 56927.9566 | [19 empty] | 1277.8164 | 27.5 | 34501.7919 | 0.55993
| Hall |  |  |  |  | 3900 | 3999 | Stone Hollow Dr | Ridgehurst Pl | Fieldside Cir | 41 | 11 | Local | [17 empty] | 23192.65 | [19 empty] | 623 | 24.0177 | 14963 | 0.24284
| Hall |  |  |  |  | 3800 | 3899 | Stone River Ct | Ridgehurst Pl | Dead End | 28 | 11 | Local | [17 empty] | 19295.95 | [19 empty] | 566 | 21.9947 | 12449 | 0.20204
| Hall |  | 350002-556 |  |  |  |  | Stonydale Ln | Brookhollow Dr | Brookhollow Dr |  | 11 | [21 empty] | CIF |  | See Brody Ln | [16 empty] | 35998 | 0.58422
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Cir | Stonyrun Dr | Stonyrun Dr (All) |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 33728 | 0.54738
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Ct | Stonyrun Cir | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4627 | 0.075092
| Hall |  | 350002-557 |  |  |  |  | Stonyrun Dr | Stonygale Ln | Stonyrun Dr (All) |  | 11 | Local | [20 empty] | CIF | 8148-410-8210-148572-822702 | 207000 | [16 empty] | 73246 | 1.1887
| Hall |  | 350002-566 |  |  | 8300 | 8599 | Watterson Trl | S Hurstbourne Pkwy | Stony Brook Dr | 40 | 11 | Pri Coll | [17 empty] | 168567.3 | [19 empty] | 3083.1003 | 33.1361 | 102162 | 1.658
| Hall |  | 350002-557 |  |  |  |  | Windbrook Ct | Stonyrun Dr | Dead End |  | 11 | [21 empty] | CIF |  | See Stonyrun Dr | [16 empty] | 4172 | 0.067708
| Hall | [6 empty] | Kosene Ct |  |  |  | 12 | Local | [17 empty] | 5000 | See Westmeadow | August | CIF | [18 empty] | 3508 | 0.056932
| Hall |  | 350002-434 |  |  | 3600 | 3699 | Westmeadow Ct | Birnamwood Dr | Dead End | 27 | 12 | Local | [17 empty] | 5800.1 | 13978.4 | August | [17 empty] | 208 | 18 | 3742 | 0.060729
| Hall |  | 350002-518 |  |  | 6600 | 7099 | Capella Ln | Sylvania Rd | Wood Rd | 55 | 12 | Local | [17 empty] | 74429.45 | 196212.95 | October | [17 empty] | 2527 | 19 | 48019 | 0.77931
| Hall |  | 350002-518 |  |  | 6600 | 6999 | Sylvania #4 Rd | Sylvania Rd | Rutledge Rd | 37 | 12 | Local | [17 empty] | 57568.55 | See Capella Ln | October | [17 empty] | 2063 | 18 | 37141 | 0.60277
| Hall |  | 350002-470 |  |  | 10500 | 10699 | Freeport Dr | Trade Port Dr | Dead End | 29 | 12 | Local | [17 empty] | 190025.35 | See Trade Port Dr | [18 empty] | 3831.1765 | 32.0001 | 122597 | 1.9896
| Hall |  | 350002-518 |  |  | 6500 | 7199 | Memory Ln | Terry Rd | Wood Rd | 26 | 12 | Local | [17 empty] | 80646.5 | [19 empty] | 2863.2501 | 18.1717 | 52030 | 0.8444
| Hall |  | 350002-470 |  |  | 7000 | 7499 | Trade Port Dr | Johnsontown Rd | Greenbelt Hwy | 29 | 12 | Min Art | [17 empty] | 225680 | 7236.52 | [18 empty] | 3792.9346 | 34.0001 | 128960 | 2.0929
| Hall |  | 350002-470 |  |  | 7000 | 7099 | Transport Ct | Freeport Dr | Dead End | 41 | 12 | Local | [17 empty] | 28817.6 | See Trade Port Dr | [18 empty] | 581 | 32 | 18592 | 0.30173
| Hall |  | 350002-468 |  |  | 4204 | 4299 | Carbine Ln | Commerce Crossings Dr | Dead End | 34 | 13 | Local | [17 empty] | 16487.35 | See Commerce Crossing Dr | August | [17 empty] | 443 | 24 | 10637 | 0.17263
| Hall |  | 350002-468 |  |  | 4400 | 5199 | Commerce Crossings Dr | Cooper Chruch Rd | Dead End | 30 | 13 | Local | [17 empty] | 286088.15 | 485380.19 | August | [17 empty] | 5127.0331 | 36 | 184573 | 2.9955
| Hall |  | 350002-468 |  |  | 11300 | 11899 | Interchange Dr | Preston Hwy | Commerce Crossings Dr | 43 | 13 | Local | [17 empty] | 227805.05 | See Commerce Crossing Dr | August | [16 empty] | includes RWCOMPKEY 31714 Old Preston | 4052.874 | 36.2634 | 146971 | 2.3852
| Hall |  | 350002-468 |  |  | 5100 | 5299 | Interchange Way | Interchange Dr | Dead End | 22 | 13 | Local | [17 empty] | 33018.1 | See Commerce Crossing Dr | August | [17 empty] | 592 | 36 | 21302 | 0.34571
| LP |  | 339051-100 |  |  | 9500 | 10699 | Keys Ferry Rd | W Manslick Rd | Mitchell Hill Rd | 40 | 13 | Sec Coll | [17 empty] | 275416.35 | 370380.86 | December | [17 empty] | 8596.7384 | 19.4165 | 166919 | 2.709
| LP |  | 339051-99 |  |  | 2300 | 2508 | Blevins Gap Rd | Greyling Dr | Lonsome Hollow Rd | 24 | 13 | Pri Coll | [17 empty] | 72616.5 | See Blevins Gap | November | [17 empty] | 2200.5175 | 19.9998 | 44010 | 0.71424
| LP |  | 339051-99 |  |  | 1600 | 2299 | Greyling Dr | W Manslick Rd | Blevins Gap Rd | 28.1291 | 13 | Sec Coll | [17 empty] | 200510.7648 | See Blevins Gap | November | [16 empty] | portion in D 14 | 5964.4188 | 20.5 | 121521.6756 | 1.9722
[8 empty] | D13 Paving Projects | TBD |  |  | 13 | [18 empty] | 15500 |  |  | CIF | 8148-410-8107-148574-822702 | 15500 | [17 empty] | 0
|  |  | 350002-560 |  |  |  |  | Entrance at Scottsdale Blvd |  |  |  | 13 | [21 empty] | CIF | 8148-410-8107-148574-822702 | 9500
| Hall |  | 350002-553 |  |  | 5500 | 5699 | Garrow Ave | Clay Ave | Southacres Dr | 45 | 13 | Local | [17 empty] | 40177.55 | See Southacres Dr | [18 empty] | 1224.0017 | 21.1781 | 25921 | 0.42068
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Garrow Ct | Garrow Ave | Dead End | 61 | 13 | Local | [17 empty] | 5869.85 | See Southacres Dr | [18 empty] | 237 | 16 | 3787 | 0.06146
| Hall |  | 350002-553 |  |  | 1148 | 1149 | Lone Oak Ave (North) | Outer Loop | Dead End | 17 | 13 | Local | [17 empty] | 9761.9 | See Southacres Dr | [18 empty] | 262 | 24 | 6298 | 0.10221
| Hall |  | 350002-553 |  |  | 1100 | 1199 | Markwell Ln | Preston Hwy | Obrecht Way | 45 | 13 | Local | [17 empty] | 69550.3135 | See Southacres Dr | [18 empty] | 2292.58 | 20.6667 | 44871.17 | 0.72822
| Hall |  | 350002-553 |  |  | 5608 | 5699 | Obrecht Way | Markwell Ln | Dead End | 26 | 13 | Local | [17 empty] | 16296.7 | See Southacres Dr | [18 empty] | 451.1452 | 23.3051 | 10514 | 0.17063
| Hall |  | 350002-553 |  |  | 1000 | 1099 | Southacres Dr | Obrecht Way | Minyard Dr | 40 | 13 | Local | [17 empty] | 32582.55 | 101911.72 | [18 empty] | 955.5177 | 21.9996 | 21021 | 0.34115
| Hall |  | 350002-552 |  |  | 700 | 999 | Whites Ln | Gerald Way | Dead End | 10 | 13 | Local | [17 empty] | 25376.6 | [19 empty] | 1364 | 12 | 16372 | 0.2657
| LP |  | 339051-95 |  |  | 12000 | 12799 | E Orell Rd | Dixie Hwy | Blevins Gap Rd | 45 | 14 | Sec Coll | [17 empty] | 178785.75 | 152634.79 | August | [17 empty] | 4819.9565 | 22.4809 | 108355 | 1.7585
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ct | Appollo Ln | Dead End | 64 | 14 | Local | [17 empty] | 27546.6 | See Appollo Ln | December | [17 empty] | 740.5 | 24 | 17772 | 0.28842
| Hall |  | 350002-502 |  |  | 9900 | 9999 | Appollo Ln | Ponder Ln | Appollo Ct | 66.3769 | 14 | Local | [17 empty] | 51557.712 | 339120.82 | December | [17 empty] | 1385.96 | 24 | 33263.04 | 0.53983
| LP |  | 339051-102 |  |  | 5800 | 7399 | Ashby Ln | Dixie Hwy | Greenbelt | 48.6358 | 14 | Pri Coll | [16 empty] | 6 | 270507.3349 | 264966.36 | December | [17 empty] | 7713.7136 | 21.6364 | 163943.8394 | 2.6607
| Hall |  | 350002-502 |  |  | 5900 | 6199 | Count Turf Dr | Donerail Way | Plaudit Way | 45 | 14 | Local | [17 empty] | 75560.95 | See Appollo Ln | December | [17 empty] | 2151.3634 | 22.6596 | 48749 | 0.79115
| Hall |  | 350002-502 |  |  | 10000 | 10199 | Donau Ln | Reigh Count Dr | Plaudit Way | 41 | 14 | Local | [17 empty] | 49395.4 | See Appollo Ln | December | [17 empty] | 1327.8536 | 24.0004 | 31868 | 0.51719
| Hall |  | 350002-502 |  |  | 9413 | 9999 | Donerail Way | Halma Dr | Count Fleet Dr | 43 | 14 | Local | [17 empty] | 53543.2 | See Appollo Ln | December | [17 empty] | 1439.3365 | 24.0006 | 34544 | 0.56062
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Halma Dr | Donerail Way | Omar Khayyam Blvd | 54 | 14 | Local | [17 empty] | 37764.2 | See Appollo Ln | December | [17 empty] | 1015.1661 | 24 | 24364 | 0.39541
| Hall |  | 350002-502 |  |  | 5900 | 6099 | Middleground Dr | Donerail Way | Omar Khayyam Blvd | 52 | 14 | Local | [17 empty] | 49198.55 | See Appollo Ln | December | [17 empty] | 1322.5463 | 24 | 31741 | 0.51513
| Hall |  | 350002-502 |  |  | 9900 | 10199 | Plaudit Way | Count Turf Dr | Dead End | 42 | 14 | Local | [17 empty] | 85848.3 | See Appollo Ln | December | [17 empty] | 2307.7144 | 24.0004 | 55386 | 0.89887
| Hall |  | 350002-502 |  |  | 6000 | 6199 | Reigh Count Dr | Donau Ln | Plaudit Way | 60 | 14 | Local | [17 empty] | 29284.15 | See Appollo Ln | December | [17 empty] | 787.2275 | 23.9994 | 18893 | 0.30662
| LP |  | 339051-99 |  |  | 5100 | 5699 | Blevins Gap Rd | Stonestreet Rd | Bearcamp Rd | 18.5373 | 14 | Sec Coll | [17 empty] | 117573.9938 | 374884.01 | November | [17 empty] | 3562.8483 | 20 | 71256.9659 | 1.1564
| Hall |  | 350002-480 | 2017-07-01 |  |  |  | University Blvd | Crittenden Dr | Arthur St |  | 15 | Min Art | [13 empty] | 0 |  |  | See Crittenden | 33872.85 | 27832.66 | July | PW FUNDS 18 | [15 empty] | LWC LSR Work, added $2,271.50 to this PO from striping on Barbee Ln | 567 | 36 | 20412 | 0.33127
| Hall |  | 350002-504 |  |  | 1400 | 1599 | Anna Ln | Manslick Rd | Yolanda Dr | 27.5844 | 15 | Local | [17 empty] | 113000.704 | 55722.96 | [18 empty] | 3015.23 | 24.3333 | 72903.68 | 1.1832
| Hall |  | 350002-546 |  |  | 3800 | 4049 | Bellevue Ave | Longfield Ave | Brentwood Ave | 58 | 15 | Local | [17 empty] | 55149 | See Brentwood | [18 empty] | 1397.4473 | 25.4607 | 35580 | 0.57743
| Hall |  | 350002-546 |  |  | 500 | 999 | Brentwood Ave | Warren Ave | S 5th St | 34 | 15 | Local | [17 empty] | 116383.3 | 54743.76 | [18 empty] | 2502.8675 | 30 | 75086 | 1.2186
| Hall |  | 350002-545 |  |  | 1100 | 1199 | Calhoun Ave | Taylor Ave | Bohannon Ave | 17 | 15 | Local | [17 empty] | 14503.35 | See Homeview | [18 empty] | 390 | 24 | 9357 | 0.15186
| Hall |  | 350002-546 |  |  | 3400 | 3533 | Cliff Ave | Longfield Ave | Brentwood Ave | 73 | 15 | Local | [17 empty] | 54260.85 | See Brentwood | [18 empty] | 1398.7601 | 25.0272 | 35007 | 0.56813
| Hall |  | 350002-545 |  |  | 1000 | 1099 | Homeview Dr | Taylor Blvd | Bohannon Ave | 30 | 15 | Local | [17 empty] | 19530 | 59095.34 | [18 empty] | 394 | 32 | 12600 | 0.20449
[8 empty] | Oakdale Ave | S 3rd St | S 4th St (only locations not paved with utility paving) |  | 15 | [18 empty] | 40000 |  |  | CIF | 8125-410-8105-048215-822702 | 9331.24 |  | 8102-410-8105-148376-822702 | 1736.45 |  | 8672-410-8105-148376-822702 | 589.2 |  | 8133-410-8107-148962-822702 | 16513.81 |  | 8133-410-8210-148962-822702 | 977.81 |  | Acct 6: 8101-410-8105-148962-822702 for $10,851.49
| Hall |  | 350002-545 |  |  | 1000 | 1399 | Queen Ave | Taylor Ave | Dead End | 61 | 15 | Local | [17 empty] | 77876.65 | See Homeview | [18 empty] | 1606.292 | 31.2789 | 50243 | 0.8154
| Hall |  | 350002-546 |  |  | 500 | 999 | W Evelyn Ave | Warren Ave | S 5th St | 23 | 15 | Local | [17 empty] | 114844.15 | See Brentwood | [18 empty] | 2469.7566 | 30.0001 | 74093 | 1.2025
| Hall |  | 350002-449 |  |  |  |  | Albrecht Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 9500 | 51982.72 | August | Council | 8133 410 8210 048101 822702 | 9500 | [16 empty] | 5775 | 0.093723
| Hall |  | 350002-449 |  |  |  |  | Doe Spring Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 13250 | See Albrecht Ct | August | Council | 8676-410-8106-048101-822702 | 13250 | [16 empty] | 8026 | 0.13025
| Hall |  | 350002-449 |  |  |  |  | Falls Ridge Ct | Trail Ridge Rd | Dead end |  | 16 | Local | [17 empty] | 41000 | 35887.9 | August | Council | 8133 410 8210 048101 822702 | 41000 | [16 empty] | 24788 | 0.40229
| Hall |  | 350002-449 |  |  |  |  | Fawn Meadow Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 4500 | See Albrecht Ct | August | Council | 8133 410 8107 048101 822702 | 4500 | [16 empty] | 2632 | 0.042715
| Hall |  | 350002-449 |  |  |  |  | Spring Branch Ct | Albrecht Cir | Dead End |  | 16 | Local | [17 empty] | 6750 | See Albrecht Ct | August | Council | 8133 410 8210 048101 822702 | 6750 | [16 empty] | 4104 | 0.066604
| Hall |  | 350002-449 |  |  |  |  | Trail Crest Ct | Trail Ridge Rd | Dead End |  | 16 | Local | [17 empty] | 7000 | See Falls Ridge Ct | August | Council | 8133 410 8210 048101 822702 | 7000 | [16 empty] | 4218 | 0.068454
| Hall |  | 350002-448 |  |  | 5000 | 5199 | Dunvegan Rd | Lime Kiln Ln | Dead End | 73.5636 | 16 | Local | [17 empty] | 71290.7 | 93228.54 | July | [17 empty] | 2299.6811 | 20.0002 | 45994 | 0.74644
| Hall |  | 350002-448 |  |  | 6600 | 6703 | Regal Rd | Dunvegan Rd | Bates View Ct | 58.453 | 16 | Local | [17 empty] | 26745.25 | See Dunvegan | July | [17 empty] | 915.0719 | 18.8564 | 17255 | 0.28003
| LP |  | 339051-98 |  |  | 4300 | 5238 | River Rd | Blankenbaker Ln | Lime Kiln Ln | 35 | 16 | Min Art | [17 empty] | 412647.6497 | 376932.69 | November | [17 empty] | 10499.6325 | 23.1 | 235798.657 | 3.8268
| LP |  | 339051-101 |  |  |  |  | Springdale Rd | I-71 Overpass | KY 22 |  | 16 | [18 empty] | 110000 | 306149.9 | November | CIF | 8148-410-8107-148576-822702 | 110000 | [17 empty] | 0
| Hall |  | 350002-476 |  |  | 6700 | 6999 | Aspenwood Ave | Seminary Dr | Chickering Woods Dr | 42 | 16 | Local | [17 empty] | 123324.2 | See Aspenwood Way | September | [17 empty] | 2453.0901 | 32.4342 | 79564 | 1.2913
| Hall |  | 350002-476 |  |  | 3000 | 3099 | Aspenwood Way | Aspenwood Ave | Wooded Meadow Rd | 35 | 16 | Local | [17 empty] | 14859.85 | 191892.52 | September | [17 empty] | 436 | 22 | 9587 | 0.15559
| Hall |  | 350002-476 |  |  |  |  | Wooded Meadow Ct | Wooded Meadow Rd | Dead End |  | 16 | Local | [18 empty] | See Aspenwood Way | September | [19 empty] | 3828 | 0.062125
| Hall |  | 350002-476 |  |  | 7000 | 7099 | Wooded Meadow Rd | Woods Club Rd | Dead End | 53 | 16 | Local | [17 empty] | 40575.9 | See Aspenwood Way | September | [17 empty] | 1120.6118 | 23.3605 | 26178 | 0.42485
| Hall |  | 350002-307 |  |  |  |  | Chamberlain Ln | Brownsboro Rd | Mint Spring Branch Rd | 73 | 16 | Pri Coll | [17 empty] | 297233 | [18 empty] | Moved to FY 23 |  |  |  | 0
| Hall |  | 350002-392 |  |  | 10500 | 10599 | Bay Pointe Ct | Dead End | Bay Pointe Dr | 59 | 17 | Local | [13 empty] | 0 |  |  |  | 30665.2 | See Eagles Cove Dr | [17 empty] | MSD project in area | 581.8693 | 34 | 19784 | 0.32108
| Hall |  | 350002-392 |  |  | 4100 | 4399 | Bay Pointe Dr | Dead End | Chamberlain Ln | 58.9157 | 17 | Local | [13 empty] | 2 |  |  |  | 43331.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1188.8878 | 23.5144 | 27956 | 0.4537
| Hall |  | 350002-543 |  |  | 4800 | 4899 | Cedar Forest Pl | Willow Forest Dr | Dead End | 70 | 17 | Local | [17 empty] | 31486.7 | [19 empty] | 923.3805 | 21.9996 | 20314 | 0.32968
| Hall |  | 350002-543 |  |  | 13000 | 13004 | Cedar Forest Way | Cedar Forest Pl | Dead End | 56 | 17 | Local | [17 empty] | 8129.75 | [19 empty] | 238 | 22 | 5245 | 0.085122
| Hall |  | 350002-392 |  |  | 3700 | 3799 | Chamberlain Ct | Chamberlain Ln | Chamberlain Ln | 51 | 17 | Local | [13 empty] | 4 |  |  |  | 47671.8 | See Eagles Cove Dr | [17 empty] | MSD project in area | 1281.5067 | 24 | 30756 | 0.49914
| Hall |  | 350002-543 |  |  | 4500 | 4699 | Cherry Forest Cir (all) | Willow Forest Dr | Cherry Forest Cir | 61 | 17 | Local | [17 empty] | 75001.4 | [19 empty] | 2199.4496 | 22 | 48388 | 0.7853
| Hall |  | 350002-529 |  |  | 3206 | 4099 | Collins Ln | Chamberlain Ln | Westport Rd | 23 | 17 | Sec Coll | [17 empty] | 208043.55 | 208168.14 | [18 empty] | 5810 | 24 | 126087 | 2.0463
| Hall |  | 350002-543 |  |  | 4300 | 4399 | Juniper Forest Pl | Willow Forest Dr | Dead End | 47 | 17 | Local | [16 empty] | 29 | 29443.8 | 67209.73 | [18 empty] | 863 | 22 | 18996 | 0.30829
| Hall |  | 350002-551 |  |  | 2599 | 2405 | Lakeland Rd | Freys Hill Rd | Evergreen Wynde | 23 | 17 | Pri Coll | [17 empty] | 14701.5 | See Southlake Dr | [18 empty] | 445.4749 | 20.0011 | 8910 | 0.1446
| Hall |  | 350002-543 |  |  | 4400 | 4499 | Maple Forest Dr | Westport Rd | Willow Forest Dr | 43 | 17 | Local | [17 empty] | 9896.75 | [19 empty] | 290 | 22 | 6385 | 0.10362
| Hall |  | 350002-392 |  |  |  |  | Pointe Bay Blvd | Chamberlain Ln | Bay Pointe Dr |  | 17 | Local | [17 empty] | 5000 | See Eagles Cove Dr | [17 empty] | MSD project in area |  |  |  | 0
| Hall |  | 350002-543 |  |  | 4700 | 4799 | Redbud Forest Pl | Willow Forest Dr | Dead End | 58 | 17 | Local | [17 empty] | 20179.45 | [19 empty] | 592 | 22 | 13019 | 0.21129
| Hall |  | 350002-543 |  |  | 3900 | 4399 | Rollington Rd | Westport Rd | County Line | 40 | 17 | Sec Coll | [17 empty] | 94883.25 | [18 empty] | potential developer widening project | 3064.6157 | 18.7642 | 57505 | 0.93326
| Hall |  | 350002-551 |  |  | 1700 | 1799 | Southlake Dr | LaGrange Rd | Dead End | 46 | 17 | Local | [17 empty] | 33267.65 | 16840.92 | [18 empty] | 940.008 | 22.8328 | 21463 | 0.34833
| Hall |  | 350002-543 |  |  | 12900 | 13099 | Willow Forest Dr (west loop) | Cedar Forest Pl | Willow Forest Dr | 44.6057 | 17 | Local | [17 empty] | 85590.659 | [19 empty] | 2509.99 | 22 | 55219.78 | 0.89617
| Hall |  | 350002-551 |  |  | 10800 | 10899 | Willow Lake Ct | Southlake Dr | Dead End | 39 | 17 | Local | [17 empty] | 7779.45 | See Southlake Dr | [18 empty] | 251 | 20 | 5019 | 0.081454
| Hall |  | 350002-477 |  |  | 4000 | 4299 | Blossomwood Dr | Woodsdale Ave | Laurelwood Ave | 27.1347 | 18 | Local | [17 empty] | 95575.728 | 88021.98 | December | [17 empty] | 2569.24 | 24 | 61661.76 | 1.0007
| Hall |  | 350002-477 |  |  | 4300 | 4499 | Rockwood Dr | Brookhaven Ave | Brookhaven Ave | 39 | 18 | Local | [17 empty] | 86682.2 | 95837.23 | December | [17 empty] | 2330.1716 | 23.9999 | 55924 | 0.9076
| Hall |  | 350002-477 |  |  | 2600 | 2699 | Woodsdale Ave | Blossomwood Dr | Lynnbrook Dr | 24 | 18 | Local | [17 empty] | 26379.45 | See Blossomwood Dr | December | [17 empty] | 740 | 23 | 17019 | 0.2762
|  |  | 350002-559 |  |  |  |  | Foxboro Dr | Vannah Ave | Dorsey Way |  | 18 | Local | [17 empty] | 128000 |  |  | Council | 8148-410-8107-148580-822702 | 128000
| LP |  | 339051-90 |  |  | 100 | 2599 | Flat Rock Rd | Shelbyville Rd | Aiken Rd | 40 | 19 | Sec Coll | [17 empty] | 738432.75 | 707823.65 | August | [17 empty] | 20311 | 23 | 447535 | 7.2631
| Hall |  | 350002-389 |  |  | 2100 | 2199 | Arnold Palmer Blvd | Landmark Dr | Aiken Rd | 28 | 19 | Local | [17 empty] | 205271.15 | 3585.12 | July | [16 empty] | Asphalt quantities shown in PO 350002-450. | 1488.0063 | 89 | 132433 | 2.1493
| Hall |  | 350002-450 |  |  |  |  | Arnold Palmer Blvd | Old Henry Rd | Aiken Rd |  | 19 | Local | [17 empty] | 250000 | 307881.71 | July | Council | 8133 410 8210 048101 822702 | 86472.74 | [17 empty] | 0
| LP |  | 339051-89 |  |  | 1700 | 2500 | Eastpoint Pkwy | middle section not paved in FY 20 |  | 39 | 19 | Local | [17 empty] | 239290.1625 | 242678.62 | July | [17 empty] | 4421 | 44.4627 | 205841 | 3.3406
| LP |  | 339051-91 |  |  | 100 | 1999 | Clark Station Rd | Shelbyville Rd | Spotswood Ln | 39 | 19 | Sec Coll | [17 empty] | 357432.9 | 362956.32 | September | [17 empty] | 10927.1148 | 19.8246 | 216626 | 3.5157
| Hall |  | 350002-559 |  |  | 510 | 609 | Dorsey Ln | McMeekin Ln | Ward Ave | 42.1893 | 19 | Pri Coll | [17 empty] | 39174.7772 | [19 empty] | 840.7605 | 28 | 23742.2892 | 0.38532
| Hall |  | 350002-537 |  |  | 9400 | 9599 | Candywood Ln | Dead End | Dead End | 43 | 20 | Local | [17 empty] | 13398.2 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8644 | 0.14028
| Hall |  | 350002-534 |  |  | 4700 | 4799 | Carolina Springs Ct | Saratoga Ridge Dr | Dead End | 63 | 20 | Local | [17 empty] | 18905.35 | See Saratoga Woods Dr | [18 empty] | 554 | 22 | 12197 | 0.19795
| Hall |  | 350002-534 |  |  | 11700 | 11799 | Coventry Hill Rd | Easum Rd | Saratoga Woods Dr | 67 | 20 | Local | [17 empty] | 20523.55 | See Saratoga Woods Dr | [18 empty] | 552 | 24 | 13241 | 0.21489
| Hall |  | 350002-537 |  |  | 9700 | 9799 | Fairwood Ct | Fairwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4154 | See Michael Edward Dr | [18 empty] | 168 | 16 | 2680 | 0.043494
| Hall |  | 350002-537 |  |  | 5000 | 5199 | Fairwood Ln | Fairground Rd | Dead End | 67 | 20 | Local | [17 empty] | 37351.9 | See Michael Edward Dr | [18 empty] | 1064 | 23 | 24098 | 0.39109
| Hall |  | 350002-537 |  |  | 9600 | 9699 | Firwood Ct | Firwood Ln | Dead End | 68 | 20 | Local | [17 empty] | 4388.05 | See Michael Edward Dr | [18 empty] | 157 | 18 | 2831 | 0.045945
| Hall |  | 350002-537 |  |  | 9806 | 10099 | Michael Edward Dr | Billtown Rd | Sprucewood Dr | 43 | 20 | Local | [17 empty] | 48642.1 | 39104.27 | [18 empty] | 923 | 34 | 31382 | 0.5093
| Hall |  | 350002-534 |  |  | 12300 | 12399 | Newport Trace Ct | Saratoga Woods Dr | Dead End | 28 | 20 | Local | [17 empty] | 8188.65 | See Saratoga Woods Dr | [18 empty] | 240 | 22 | 5283 | 0.085738
| Hall |  | 350002-537 |  |  | 5100 | 5299 | Old Billtown Rd | Michael Edward Dr | Dead End | 39 | 20 | Local | [17 empty] | 13399.75 | See Michael Edward Dr | [18 empty] | 480 | 18 | 8645 | 0.1403
| LP |  |  |  |  | 2000 | 4000 | Old Clark Station Rd | Hwy 148 | Hwy 148 | 62 | 20 | Sec Coll | [13 empty] | 0 |  |  |  | 245286.3105 | [18 empty] | Bridge proejct and new development coming into area. Need to hold on work until we get more clarification on those projects. | 8744.61 | 17 | 148658.37 | 2.4126
| Hall |  | 350002-534 |  |  | 11400 | 11799 | Saratoga Ridge Dr | Saratoga Woods Dr | Pleasant Lawn Ct | 54 | 20 | Local | [17 empty] | 62271.25 | See Saratoga Woods Dr | [18 empty] | 1674 | 24 | 40175 | 0.65201
| Hall |  | 350002-534 |  |  | 4400 | 4599 | Saratoga Woods Dr | Saratoga Club Rd | Pleasant Lawn Ct | 45 | 20 | Local | [17 empty] | 84561.8 | 41474.37 | [18 empty] | 2273 | 24 | 54556 | 0.8854
| Hall |  | 350002-537 |  |  | 5400 | 5499 | Sprucewood Ct | Sprucewood Dr | Dead End | 38 | 20 | Local | [17 empty] | 4149.35 | See Michael Edward Dr | [18 empty] | 149 | 18 | 2677 | 0.043445
| Hall |  | 350002-537 |  |  | 5000 | 5399 | Sprucewood Dr | Michael Edward Dr | Sprigwood Ln | 26 | 20 | Local | [17 empty] | 68736.3 | See Michael Edward Dr | [18 empty] | 1958 | 23 | 44346 | 0.7197
| Hall |  | 350002-537 |  |  | 4600 | 4699 | Steep Ridge Ct | Saratoga Ridge Dr | Dead End | 58 | 20 | Local | [17 empty] | 10583.4 | See Michael Edward Dr | [18 empty] | 310 | 22 | 6828 | 0.11081
| LP |  | 388368-3 |  |  |  |  | Tucker Station and Rehl Rd |  |  |  | 20 | [18 empty] | 50000
| Hall |  | 350002-505 |  |  | 4700 | 4799 | Burkley Ave | W Kenwood Way | Southern Pky | 20 | 21 | Local | [17 empty] | 50263.4 | See W Kingston Ave | [18 empty] | 1158 | 28 | 32428 | 0.52628
| Hall |  | 350002-505 |  |  | 400 | 599 | Christopher Pl | W Kingston Ave | S 4th St | 14 | 21 | Local | [17 empty] | 27952.7 | See W Kingston Ave | [18 empty] | 897 | 20 | 18034 | 0.29268
| Hall |  | 350002-507 |  |  | 6900 | 6999 | Coon Trl | Kenwood Hill Rd | Possum Path | 41 | 21 | Local | [17 empty] | 8712.55 | [18 empty] | See Possum Path | 312.2615 | 18 | 5621 | 0.091224
| Hall |  | 350002-190 | 2018-07-01 |  | 200 | 499 | Downes Ln | Strawberry Ln | Rob Roy St | 51.0008 | 21 | Local | [13 empty] | 6 |  |  |  | 91627.5 |  |  | PW Funds |  | 91627.5 | [13 empty] | Section from Stawberry to macalester may have been repaved | 2545.2553 | 23.9996 | 61085 | 0.99136
| Hall |  | 350002-190 | 2018-07-01 |  | 400 | 599 | Downes Ter | Downes Ln | Dead End | 29.2418 | 21 | Local | [13 empty] | 0 |  |  |  | 71077.68 |  |  | PW Funds |  | 71077.68 | [14 empty] | 1974.38 | 24 | 47385.12 | 0.76902
| Hall |  | 350002-505 |  |  | 500 | 599 | Forum Ave | School Way | Southern Pky | 25 | 21 | Local | [17 empty] | 52331.1 | See W Kingston Ave | [18 empty] | 1407 | 24 | 33762 | 0.54793
|  |  |  | 2017-07-01 |  |  |  | High Rise Dr | Holiday Towers Dr | Dead End |  | 21 | Local | [17 empty] | 27956 |  |  | PW FUNDS 18 | [15 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 16943 | 0.27497
|  |  |  | 2017-07-01 |  |  |  | Holiday Towers Blvd | Fern Valley Rd | Bermuda Ln |  | 21 | Local | [17 empty] | 57107 |  |  | CD Capital, PW Bond | 8102-410-8105-148323-822702 | 50000 | [13 empty] | Heritage green work complete. Will schedule for spring 2019 |  |  | 34610 | 0.56169
| Hall |  | 350002-190 | 2018-07-01 |  | 6700 | 6799 | New Way | Downes Ln | Downes Ter | 2 | 21 | Local | [13 empty] | 0 |  |  |  | 14709.6 |  |  | PW Funds |  | 14709.6 | [14 empty] | 408.6 | 24 | 9806.4 | 0.15915
| Hall |  | 350002-190 | 2018-07-01 |  | 6500 | 6699 | New Way | Downes Ln | E Southside Ct | 53.9777 | 21 | Local | [13 empty] | 4 |  |  |  | 45316.5 |  |  | PW Funds |  | 45316.5 | [14 empty] | 1316.566 | 22.9468 | 30211 | 0.4903
| Hall |  | 350002-507 |  |  | 200 | 399 | Possum Path | Kenwood Hill Rd | Dead End (All) | 52.759 | 21 | Local | [17 empty] | 38633.75 | [18 empty] | MSD to help with work. | 1704.5485 | 14.6226 | 24925 | 0.40451
| Hall |  | 350002-505 |  |  | 4800 | 5099 | S 4th St | Burkley Ave | W Kingston Ave | 55 | 21 | Local | [17 empty] | 103527.6 | See W Kingston Ave | [18 empty] | 2450 | 27 | 66792 | 1.084
| Hall |  | 350002-505 |  |  | 4800 | 4999 | S 5th St | Burkley Ave | Christopher Pl | 51 | 21 | Local | [17 empty] | 66095.1 | See W Kingston Ave | [18 empty] | 1653 | 26 | 42642 | 0.69204
| Hall |  | 350002-505 |  |  | 500 | 599 | School Way | Forum Ave | Southern Pky | 24 | 21 | Local | [17 empty] | 41704.3 | See W Kingston Ave | [18 empty] | 1121 | 24 | 26906 | 0.43666
| Hall |  | 350002-505 |  |  | 115 | 499 | W Amherst Ave | Southside Dr | Dead End (west) | 44.1914 | 21 | Local | [17 empty] | 48178.619 | See W Kingston Ave | [18 empty] | 1422.3 | 22 | 31082.98 | 0.50445
| Hall |  | 350002-505 |  |  | 300 | 599 | W Kingston Ave | Southern Pky | S 3rd St | 45 | 21 | Local | [17 empty] | 89424.15 | 115529.16 | [18 empty] | 1950 | 30 | 57693 | 0.93631
| LP |  | 339051-96 |  |  | 7500 | 9849 | Cedar Creek Rd | Bardstown Rd | Cooper Chapel Rd | 40 | 22 | Sec Coll | [17 empty] | 638144.1 | 683469.75 | October | [16 empty] | may require road widening | 20702.2291 | 18.6818 | 386754 | 6.2767
| LP |  | 339051-97 |  |  | 9900 | 10499 | Oak Grove Rd | Independence School Rd | Thixton Ln | 20 | 22 | Sec Coll | [17 empty] | 102677.85 | 87814.62 | October | [17 empty] | 3889.3639 | 15.9998 | 62229 | 1.0099
| LP |  | 339051-93 |  |  | 1927-02-07 | 1932-01-11 | Brentlinger Ln | Bardstown Rd | Seatonville Rd | 72.774 | 22 | Sec Coll | [17 empty] | 100000 | 312964.8 | September | [16 empty] | Waiting on MOU with KYTC | 9967.8721 | 19.298 | 192360 | 3.1218
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Cris Dr | Dead End | Dead End | 52 | 22 | Local | [17 empty] | 24711.65 | [19 empty] | 688.772 | 23.147 | 15943 | 0.25874
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Dart Dr | Edsel Ln | Cris Dr | 28 | 22 | Local | [17 empty] | 22909 | 79426.35 | [18 empty] | 641.1239 | 23.0533 | 14780 | 0.23987
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Eagles Crest Ct | Mercury Dr | Dead End | 46 | 22 | Local | [17 empty] | 28117 | [19 empty] | 907.0072 | 20 | 18140 | 0.2944
| Hall |  | 350002-548 |  |  | 7800 | 8299 | Edsel Ln | Ferndale Rd | Dead End | 38 | 22 | Local | [17 empty] | 99939.35 | [19 empty] | 2782.6886 | 23.1708 | 64477 | 1.0464
| Hall |  | 350002-548 |  |  | 7800 | 7899 | Fair Ln | S Watterson Trl | Edsel Ln | 28 | 22 | Local | [17 empty] | 20301.9 | [19 empty] | 467.7745 | 28 | 13098 | 0.21257
| Hall |  | 350002-548 |  |  | 6300 | 6399 | Ferncliff Ln | Cris Dr | Ferndale Rd | 33 | 22 | Local | [17 empty] | 17727.35 | [19 empty] | 476.5244 | 24 | 11437 | 0.18561
| Hall |  | 350002-548 |  |  | 8100 | 8199 | Keira Ridge Ct | Mercury Dr | Dead End | 50 | 22 | Local | [17 empty] | 14196.45 | [19 empty] | 457.963 | 20 | 9159 | 0.14864
| Hall |  | 350002-548 |  |  | 5900 | 6599 | Mercury Dr | Dead End | Edsel Ln | 42 | 22 | Local | [17 empty] | 97240.8 | [19 empty] | 2873.3706 | 21.8336 | 62736 | 1.0182
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Meter Ct | Mercury Dr | Dead End | 42 | 22 | Local | [17 empty] | 5651.3 | [19 empty] | 165.7105 | 22 | 3646 | 0.059171
| Hall |  | 350002-548 |  |  | 8100 | 8299 | Sprint Ct | Dart Dr | Dead End | 53 | 22 | Local | [17 empty] | 14872.25 | [19 empty] | 399.7845 | 24 | 9595 | 0.15572
| Hall |  | 350002-548 |  |  | 6200 | 6299 | Van Ct | Dead End | Mercury Dr | 81 | 22 | Local | [17 empty] | 5707.1 | [19 empty] | 167.3467 | 22 | 3682 | 0.059756
| Hall |  | 350002-519 |  |  |  |  | Acme Way | Smyrna Pl | Michael Ray Dr |  | 23 | Local | [17 empty] | 28700 | See Michael Ray Dr | November | CIF | [15 empty] | Public Works funding initially, will JV money when appropriation complete
| Hall |  | 350002-519 |  |  |  |  | Boca Chica Ct | Gregory Way | Dead End | 48 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4682 | 0.075985
| Hall |  | 350002-519 |  |  |  |  | Diablo Ct | Gregory Way | Dead End | 56 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4626 | 0.075076
| Hall |  | 350002-519 |  |  | 8500 | 8699 | Gregory Way | Michael Ray Dr | Dead End | 34.9695 | 23 | Local | [17 empty] | 43259.508 | See Michael Ray Dr | November | [17 empty] | 1162.89 | 24 | 27909.36 | 0.45294
| Hall |  | 350002-519 |  |  |  |  | La Cima Ct | Michael Ray Dr | Dead End | 84 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4000 | 0.064917
| Hall |  | 350002-519 |  |  |  |  | Malibu Dr | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 9510 | 0.15434
| Hall |  | 350002-519 |  |  |  |  | Mar Vista Ct | Michael Ray Dr | Dead End | 65 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 4707 | 0.076391
| Hall |  | 350002-519 |  |  | 8000 | 8799 | Michael Ray Dr | Joyce Dr | Smyrna Pky | 44 | 23 | Local | [17 empty] | 199410.6 | 343331.24 | November | [17 empty] | 5482.3638 | 23.4665 | 128652 | 2.0879
| Hall |  | 350002-519 |  |  |  |  | Petra Ct | Michael Ray Dr | Dead end | 37 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6819 | 0.11067
| Hall |  | 350002-519 |  |  | 6100 | 6299 | Richiewayne Dr | Dead End | Smyrna Pky | 50 | 23 | Local | [17 empty] | 43984.35 | See Michael Ray Dr | November | [17 empty] | 1218.9502 | 23.2799 | 28377 | 0.46053
| Hall |  | 350002-519 |  |  |  |  | Rodney Cir | Michael Ray Dr | Dead End | 60 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 11970 | 0.19426
| Hall |  | 350002-519 |  |  | 6200 | 6299 | Timmy Ct | Timmy Ln | Dead End | 81 | 23 | Local | [17 empty] | 14365.4 | See Michael Ray Dr | November | [17 empty] | 463 | 20 | 9268 | 0.15041
| Hall |  | 350002-519 |  |  | 8100 | 8199 | Timmy Ln | Applegate Ln | Richiewayne Dr | 32 | 23 | Local | [17 empty] | 25040.25 | See Michael Ray Dr | November | [17 empty] | 621.3517 | 25.9998 | 16155 | 0.26218
| Hall |  | 350002-519 |  |  |  |  | Trakia Ct | Michael Ray Dr | Dead End | 34 | 23 | Local | [18 empty] | See Michael Ray Dr | November | [19 empty] | 6309 | 0.10239
|  |  | 350002-555 |  |  |  |  | Damascus Ct |  |  |  | 23 | Local | [17 empty] | 60000 |  |  | PW/CIF/Local Contribution
| Hall |  | 350002-562 |  |  | 6900 | 7299 | Woodrow Way | Briscoe Ln | Moorhaven Dr | 21 | 23 | Local | [17 empty] | 66363.25 | 18931.95 | [18 empty] | 2100.9802 | 20.3786 | 42815 | 0.69485
| Hall |  |  |  |  | 5900 | 5999 | Bluestone Rd | Yellowsands Dr | Dead End | 54 | 24 | Local | [17 empty] | 26512.75 | [19 empty] | 713 | 24 | 17105 | 0.2776
| Hall |  | 350002-563 |  |  | 7614 | 7699 | Buena Vista Ct | Outer Loop | Monaco Dr | 61 | 24 | Local | [17 empty] | 23570.85 | See Monaco Dr | [18 empty] | 634 | 24 | 15207 | 0.2468
[8 empty] | D24 TBD |  |  |  | 24 | Local | [17 empty] | 75927.45 |  |  | Council | 8672-410-8105-148236-822702 | 3342.34 |  | 8102-410-8105-148236-822702 | 3342.34 |  | 8125-410-8207-148385-822702 | 20822.37 |  | 8101-410-8210-148385-822702 | 48420.4 |  |  |  |  | Use accounts in order |  |  |  | 0
| Hall |  |  |  |  | 7200 | 7499 | Egypt Ln | McCawley Rd | Dead End | 34 | 24 | Local | [13 empty] | 0 |  |  |  | 36798.55 | [18 empty] | Stop paving just past last entrance to the apartments, LWC main replacement project | 1032.2135 | 23 | 23741 | 0.3853
| Hall |  |  |  |  | 5800 | 5899 | Flagstone Ct | Rock Hollow Dr | Dead End | 30 | 24 | Local | [17 empty] | 4358.6 | [19 empty] | 117 | 24 | 2812 | 0.045636
| Hall |  | 350002-563 |  |  | 5200 | 5599 | Monaco Dr/Layne Rd | Shepherdsville Rd | Morningside Way | 39 | 24 | Local | [17 empty] | 80906.9 | 9275.65 | [18 empty] | 2211.0709 | 23.6076 | 52198 | 0.84713
| Hall |  | 350002-561 |  |  | 550 | 5599 | Pattie Ln | Shepherdsville Rd | Seebolt Dr | 52 | 24 | Local | [17 empty] | 21520.2 | See Seebolt Dr | [18 empty] | 694 | 20 | 13884 | 0.22533
| Hall |  |  |  |  | 6000 | 6099 | Red Rock Ct | Sandstone Blvd | Dead End | 46 | 24 | Local | [17 empty] | 14797.85 | [19 empty] | 398 | 24 | 9547 | 0.15494
| Hall |  |  |  |  | 6800 | 6999 | Rock Forest Dr | Whispering Hills Blvd | Rock Hollow Dr | 28 | 24 | Local | [17 empty] | 30826.4 | [19 empty] | 828.6582 | 24.0002 | 19888 | 0.32276
| Hall |  |  |  |  | 6800 | 7099 | Rock Hollow Dr | Rock Forest Dr | Whispering Hills Blvd | 36.7789 | 24 | Local | [17 empty] | 49972.992 | [19 empty] | 1343.36 | 24 | 32240.64 | 0.52324
| Hall |  |  |  |  | 6800 | 6999 | Sandstone Blvd | Whispering Hills Blvd | Yellowsands Dr | 24 | 24 | Local | [17 empty] | 68093.05 | [19 empty] | 1830.4282 | 24.0004 | 43931 | 0.71296
| Hall |  | 350002-561 |  |  | 7400 | 7699 | Seebolt Dr | Briscoe Ln | Dead End | 68 | 24 | Local | [17 empty] | 27816.3 | [19 empty] | 897.2826 | 20.0004 | 17946 | 0.29125
| Hall |  |  |  |  | 6000 | 6199 | Yellowsands Dr | Sandstone Blvd | Moorhaven Dr | 38 | 24 | Local | [17 empty] | 35073.4 | [19 empty] | 942.8513 | 23.9995 | 22628 | 0.36723
| LP |  | 339051-92 |  |  | 9303 | 9799 | Stonestreet Rd | Valley College Dr | 3rd Street Rd | 22 | 25 | Min Art | [17 empty] | 274825.25 | 285503.59 | July | [17 empty] | 2814.6936 | 55.794 | 157043 | 2.5487
| Hall |  | 350002-544 |  |  | 1800 | 1899 | Allanwood Rd | Red Stone Hill Rd | Dead End | 39 | 25 | Local | [17 empty] | 45475.45 | See Cristland | March | [17 empty] | 1128.4374 | 25.9997 | 29339 | 0.47615
| Hall |  | 350002-544 |  |  | 1000 | 1699 | Cristland Rd | 3rd Street Rd | Dead End | 30 | 25 | Local | [17 empty] | 153572.45 | 59691.83 | March | [17 empty] | 4254 | 23.2972 | 99079 | 1.608
| Hall |  | 350002-544 |  |  | 1900 | 1999 | Roycewood Ct | Dead End | Roycewood Rd | 62 | 25 | Local | [17 empty] | 8098.75 | See Cristland | March | [17 empty] | 237.4801 | 22 | 5225 | 0.084797
| Hall |  | 350002-544 |  |  | 7900 | 7999 | Roycewood Rd | Dead End | Allanwood Rd | 52 | 25 | Local | [17 empty] | 18855.75 | See Cristland | March | [17 empty] | 552.9736 | 21.9992 | 12165 | 0.19743
| Hall |  | 350002-508 |  |  |  |  | Bentford Dr | 3rd St Rd | Dead End (intersects Prarie Dr) |  | 25 | [19 empty] | 297.065.74 | September | CIF | See Sunlight Ln | [17 empty] | 16436 | 0.26674
| Hall |  | 350002-508 |  |  |  |  | Heavenly Way | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 11639 | 0.18889
| Hall |  | 350002-508 |  |  |  |  | Iron Horse Way | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 58190 | 0.94437
| Hall |  | 350002-508 |  |  |  |  | Moonlight Way | Heavenly Way | Valley Station Rd |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 53784 | 0.87287
| Hall |  | 350002-508 |  |  |  |  | Sedalia Ct | Sedalia Trail | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 9827 | 0.15948
| Hall |  | 350002-508 |  |  |  |  | Sedalia Trail | Moonlight Way | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 32604 | 0.52913
| Hall |  | 350002-508 |  |  |  |  | Starlight Way | Moonlight Way | Moonlight Way |  | 25 | [19 empty] | See Bentford Dr | September | CIF | See Sunlight Ln | [17 empty] | 57023 | 0.92543
| Hall |  | 350002-508 |  |  |  |  | Sunlight Lane | Goldstein Ln | Dead End |  | 25 | [19 empty] | See Bentford Dr | September | CIF | 8102-410-8105-148586-822702 | 225809.78 |  | 8138-410-8107-148586-822702 | 103190.22 |  | 8148-410-8107-148586-822702 | 100000 | [10 empty] | 39914 | 0.64777
|  |  | 388368-4 |  |  |  |  | Barrett Ln Reconstruction | Dixie Hwy | dead end |  | 25 | [18 empty] | 210000 |  |  | Council Funded
| Hall |  | 350002-544 |  |  | 7900 | 8399 | Red Stone Hill Rd | Manslick Rd | Dead End (All) | 26 | 25 | Local | [17 empty] | 70776.1 | See Cristland | [17 empty] | Will complete an engineering study to review stability of roadway. | 3055.0091 | 14.9466 | 45662 | 0.74105
| LP |  | 388368-1 |  |  | 7100 | 8299 | St Anthony Church Rd | St Andrews Church Rd | Manslick Rd | 22 | 25 | Pri Coll | [17 empty] | 390484.05 | [19 empty] | 11697.7997 | 20.2309 | 236657 | 3.8407
| Hall |  | 350002-484 |  |  | 3400 | 3499 | Clingstone Way | Hikes Ln | Orchard Manor Cir | 45 | 26 | Local | [17 empty] | 13049.45 | 49914.82 | August | [17 empty] | 351 | 24 | 8419 | 0.13663
| Hall |  | 350002-478 |  |  | 3800 | 4299 | Manner Dale Dr | Cabinwood Dr | Pomeroy Dr | 33 | 26 | Local | [17 empty] | 115834.6 | 310918.9 | August | [17 empty] | 3135.2059 | 23.8364 | 74732 | 1.2128
| Hall |  | 350002-484 |  |  | 3100 | 3399 | Orchard Manor Cir | Whitehall Ter | Dead End | 40 | 26 | Local | [17 empty] | 52848.8 | See Clingstone Way | August | [17 empty] | 1433.545 | 23.7844 | 34096 | 0.55335
| Hall |  | 350002-478 |  |  | 3000 | 3099 | Roselawn Blvd (west) | Manner Dale Dr | Vogue Ave | 51 | 26 | Local | [17 empty] | 45653.7 | See Manner Dale Dr | August | [17 empty] | 1339 | 22 | 29454 | 0.47801
| Hall |  | 350002-478 |  |  | 3000 | 3199 | Vogue Ave (all) | Klondike Ln | Roselawn Blvd | 44 | 26 | Local | [17 empty] | 77986.7 | See Manner Dale Dr | August | [17 empty] | 2287.0094 | 21.9999 | 50314 | 0.81655
| Hall |  | 350002-533 |  |  |  |  | Alvarado Way | Woodluck Way | Dead End |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 4864 | 0.078938
| Hall |  | 350002-533 |  |  |  |  | Garden Way | Almara Cir | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 7520 | 0.12204
| Hall |  | 350002-533 |  |  |  |  | Vivian Ln | Dutchmans Ln | Dead End |  | 26 | [19 empty] | 87152 | December | CIF | 8138-410-8107-148587-822702 | 30362 |  | 8146-410-8107-148587-822702 | 79500 |  | 8102-410-8105-148587-822702 | 39638 | [10 empty] | 41907 | 0.68011
| Hall |  | 350002-533 |  |  |  |  | Woodluck Ave | Vivian Ln | Vivian Ln |  | 26 | [19 empty] | See Vivian | December | CIF | See Vivian Ln | [17 empty] | 31457 | 0.51052
| Hall |  | 350002-469 |  |  | 100 | 1099 | Browns Ln | Shelbyville Rd | Kresge Way | 45 | 26 | Pri Coll | [17 empty] | 199070.85 | See Kresge Way | September | [16 empty] | check Capital project, portion in D 10 | 5308 | 23 | 120649 | 1.958
| Hall |  | 350002-469 |  |  | 3800 | 4299 | Kresge Way | Breckenridge Ln | S Hubbards Ln | 38 | 26 | Pri Coll | [17 empty] | 217118.55 | 415172.35 | september | [17 empty] | 2633.616 | 49.9644 | 131587 | 2.1355
| Seven Seas |  | 373766-40 |  |  |  |  | Hidden Creek Stream Mitigation | [22 empty] | 31058 | 31058 | November
| LP |  | 388368-5 |  |  |  |  | Aiken Rd Base Failure | [22 empty] | 500000
| Hall |  | 350002-520 |  |  |  |  | Jail Bollards | [22 empty] | 25100 | 37585.62 |  | Develop Louisville Funds | [15 empty] | Bollards requested by facilities. Using Develop Louisville Funds
|  |  | 350002-503 |  |  |  |  | Johnson Rd Catch Basin Repairs | [22 empty] | 8800 | 8800
| Michael Baker |  | 387658-1 |  |  |  |  | Supplemental Inspections | [22 empty] | 71609

## Alleys
PO # | Contractor | Alley Name | From | To | Parallel To | District | Ramps | Estimated Cost | Actual Cost | Completed | Funding Source | Alley Match |  | Council Funds |  | Council Funds |  | Other |  | Notes
388368-10 |  | Ward Alley | S 5th St | S 6th St | Garland and Kentucky | 4 |  | 25000 |  |  | Council | 25000 | 8146-410-8107-148793-822702
388368-13 |  | 2914 S 6th St Alley | Heywood Ave | Iowa Ave | Rodman St & S 6th St | 15 |  | 45000 |  |  | Council | 310.34 | 8137-410-8210-148962-822702 | 5239.79 | 8138-410-8205-148915-822702 | 17704.04 | 8138-410-8107-148962-822702 | 21745.83 | 8101-410-8105-148962-822702 | On leg closest to church, last 3 properties are non Metro
|  | Alley 1 | S 32nd St | Dead End (east) | Greenwood and Grand | 1 |  | 14080
|  | Alley 2 | S32nd St | Louis Coleman Ave | Kirby (South of Kirby) | 1 |  | 22582
5

## Key
Complete
Utility Conflict
Moved to FY 21 due to virus
Concrete Road
Metro Project Pending
Not completed yet
Distribute report to the following:
Daniel Frockt
Benjamin Tipton
Maxwell Bradley
Kellie Watson
Christy Tapp
Aaron Jackson
LaTonya Bell
CC:
Jeff Brown
Vanessa Burns
John Callihan
Ozzy Gibson
Metro Council Staff

## Rating
86-100 | Good
71-85 | Satisfactory
56-70 | Fair
41-55 | Poor
26-40 | Very Poor
11-25 | Serious
0-10 | Failed