## Metrics
Agreement | Section in 1043 | Fund | PRC | Eligible | Description | Period of Expenditure | Status | Goal | Metric | Totals as of August 31 | Notes
13-00 | HB1043 Section 3.3 (13) | 1 | 121 | LEA, Charter, ISD | to provide a supplemental summer learning program in response to negative effects of COVID-19 for K-4. | date of submission of Plan to DPI to 12/30/2020 | Policy and allotment approved and posted. PSU are required to submit plans to DPI prior to release of funds. Funds allotted. | Accelerate summer learning for students below proficiency. | Students served
12-00 | HB1043 Section 3.3 (12) | 1 | 122 | LEA, Charter, ISD | for contracted school health support personnel for physical and mental health support services for students until December 30,2020. school counselors, school nurses, school psychologists and school social workers. | expire 12/30/20 | Policy approved June 11th SBE meeting. Allotted 7/21/2020 | Students have adequate physical and mental health support in school settings. | Contractual hours/month
15-00 | HB1043 Section 3.3 (15) | 1 | 123 | LEAs, charters, regional schools, ISD | to provide nondigital remote instruction resources to students with limited connectivity | expire 12/30/20 | Policy approved July 9 SBE meeting. Allotted 7/21/2020 | All students have equitable access to non-digital resources needed for remote learning settings. | Students served
09-00 | HB1043 Section 3.3 (9) | 1 | 124 | LEAs, charters, regional schools, ISD | computers or other electronic devices for use by students in response to COVID-19. | expire 12/30/20 | Policy approved June 4th SBE meeting. Allotted 6/19/2020 | All students have equitable acceess to digital resources needed for remote learning | Student devices provided
06-00 | HB1043 Section 3.3 (6) | 1 | 125 | PSUs participating in the NSLP or School Breakfast | School nutrition services provided in response to COVID-19 | 3/16/2020 to 6/30/2020 HB 1035 extended period of use to 12/30/2020 | Allotted 5/29/2020 | Food insecure families have access to week-day meals for school age children. | Monthly meals served
10-00 | HB1043 Section 3.3 (10) | 1 | 126 | LEAs, charters, regional schools, ISD | to provide computers or other electronic devices for use by school personnel. | expire 12/30/20 | Policy approved June 4th SBE meeting. Allotted 6/19/2020 | All educators have equitable acceess to digital resources needed for remote learning | Staff devices provided
07-00 | HB1043 Section 3.3 (7) | 1 | 127 | LEAs, charters, regional schools, ISD | improving Internet connectivity by installing extended reach mobile wifi gateway router devices in school buses. Cost of devices only, not subscription. Believe intention is to provide funds, not DPI procurement | expire 12/30/20 | Policy approved June 11th SBE meeting. Allotted 7/27/2020 | All students have equitable acceess to digital resources needed for remote learning | Devices purchased
08-00 | HB1043 Section 3.3 (8) | 1 | 128 | LEAs, charters, regional schools, ISD | DPI for improving Internet connectivity for students through mobile Internet access points. Cost of devices, not subscription. Believe intention is to provide funds, not DPI procurement | expire 12/30/20 | Policy approved June 11th SBE meeting. Allotted 6/19/2020 | All students have equitable acceess to digital resources needed for remote learning | Hot spots purchased
14-00 | HB1043 Section 3.3 (14) | 1 | 129 | LEA, charter, regional ISD | To assist PSUs in providing remote instruction by expanding the learning management platform | expire 12/30/20 | Policy approved June 11th SBE meeting. Allotted 7/27/2020 | All educators and students have equitable acceess to digital resources needed for remote learning | Number of PSU's added to the LMS
16-00 | HB1043 Section 3.3 (16) & HB1023 section 1.1(d) (64) | 1 | 132 | PSU | grants to public school units for extraordinary costs of providing Extended School Year Services or future services for exceptional children. | expire 12/30/20 | Policy approved June 11th SBE meeting. $15.5m allotted 8/4/2020 | All students are provided equitable services; Missed services, ESY or Comp Ed is delivered as appropriate. | EC students served; types of services provided
18-00 | HB1043 Section 3.3 (18) | 1 | 133 | Non profits and non profits working with LEAs | The Extended Learning and Integrated Student Supports Competitive Grant Program. 3:1 Match requirement. Grants are for 2019-20 and 2020-21. | expire 12/30/20 | Policy approved July 9 SBE meeting. Grantees approved by SBE on August 6. | Families and students are supported in remote learning environments | Number of students participating in ELISS programming
11-00 | HB1043 Section 3.3 (11) | 1 | 135 | DPI and LEA | to establish a shared cybersecurity infrastructure and district cybersecurity monitoring and support. | expire 12/30/20 | 1) Policy approved August 6 SBE meeting. $3,452,400 allotted Aug 20. 2) Training procurement in process to be available in late September. 3) Contract amendment with MCNC for assessments in progress. | Improve PSU cybersecurity posture through employee awareness training, vulnerability assessments, implementing IT best-practices and establishing basic response plans by June, 2021 | (1) Percent of PSU employees completing assigned training (2) Number of PSU vulnerability assessments completed
CARES Act Coronavirus Relief Fund | SL 2020-27 | 1 | 134 | PSU | supplemental instructional services to low wealth counties | expire 12/30/20 | Funds available 07/09/2020. allotted in PRC 134 Aug 20. | Assist low wealth LEAs in effectively responding to the impacts of COVID-19 | Students served
63-00 | HB1023 section 1.1(d) (63) | 1 | pending | PSU | Personal protective equipment | expire 12/30/20 | Combining with additional appropriation. To be allotted at next SBE meeting. | Support in-person learning with funding for personal protective equipment for students and school personnel. | % of schools reporting adequate supply of PPE

## NOTES
INSTRUCTIONS
Fill in the yellow column with the appropriate metric. Use the most appropriate data available. If you are unable to identify just the students served, for example, with only this pot of money, just report total students served on this metric with all fund sources.
NC DPI has explained to OSBM that PSUs may not be able to isolate metrics to just this allotment. Please use the notes column to indicate the relevant population measured. For example, if you are unable to measure only the students who received devices via PRC 124, list the total number of students who have received devices from the PSU, and write "total number of students who have received devices" in the Notes box.