## Sheet1
FMMI Feb 2025 Cutover Communications - System by System Impacts
FMS-PSB will continue to audit relocation vouchers during the FMMI downtime, however, documents will be held for disbursement until the cutover period ends. Agencies should stamp Relocation Authorizations as “READY FOR FMMI (FMS)” during this period. Once FMMI is back online, agencies must revise the authorizations to “APPROVE AUTH/SEND TO FMMI”.
System Type | System Name | Impact to End Users (Y/N) | Cutoff Date/Time | Startup Date/Time | End User Impact Description
SAP | BW | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAP CRM | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | Solman Monitoring | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | ezFedGrants | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | FNS Grantor | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
CMS | Pega | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
Job Scheduler | Control-M | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | ECC | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAP Portal | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | Data Services | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | BOBJ | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | SAC | Yes | Thursday (2/13) @ 6 p.m. CT | Wednesday (2/19) | Users should not plan to access these systems from Thursday (2/13) @ 6 p.m. through Wednesday (2/19).
SAP | GRC | Yes | Thursday (1/30) | Wednesday (2/19) | Users should not plan to access GRC from Thursday (1/30) through Wednesday (2/19).
Interface | IAS | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | Concur | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | SmartPay | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | MLINQs | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | NRCS Protracts | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | HHS Grants Solutions | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | ASAP | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | ABCO | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | All Other Agency-Specific Systems | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
SAP | PI/PO | Yes | Wednesday (2/12) @ 6 a.m. CT | Wednesday (2/19) | End users can continue completing transactions in these systems during the cutover, but those transactions will not be reflected in FMMI until at least Wednesday (2/19). We ask end users to limit transactions during this time to only those that are critical.
Interface | IPAC/INTR | Yes | Tuesday (2/11) @ Midnight CT | Wednesday (2/19) | IPAC and INTR invoices must be posted within FMMI by midnight CT on Tuesday (2/11) to be processed on Wednesday (2/12). This will be the last IPAC and INTR runs prior to cutover.
N/A | Disbursements | Yes | Tuesday (2/11) @ Midnight CT | Wednesday (2/19) | Invoices must be posted within FMMI by midnight CT on Tuesday (2/11) to be disbursed on Thursday (2/13). This will be the last disbursement run prior to cutover.
SAP | EnableNow | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
SAP | saprouter | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | ACRWS | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | RITA | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | CPAIS | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
CMS | MINC | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
FSDW | FSDW | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Archiving | OpenText | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Secure FTP/Dropbox | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Web Proxy | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.
Infra/Sec | Nessus | No | N/A | N/A | N/A - The FMMI cutover will have no impact on these systems. End users can continue using these systems as normal. Note that during cutover, these systems will not receive up-to-date data from FMMI.